## Welcome!
Welcome to Statistical PERT® Normal Edition
Statistical PERT® (SPERT®) is a freely licensed, probabilistic, estimation technique. Use Statistical PERT | All models are wrong, but some are useful.
to estimate uncertainties that have bell-shaped risk properties, like: task duration, work effort, | George E. P. Box, British statistician (1919-2013)
revenue, expenses, agile story points, project portfolios, event attendance, and more.
Statistical PERT® Normal Edition uses Excel's two normal distribution functions, NORM.DIST and | Facts are stubborn things, but statistics are pliable.
NORM.INV to model mild-to-moderately skewed uncertainties. To model a wider range of | Mark Twain, American humorist (1835-1910)
bell-shaped uncertainties, try Statistical PERT® Beta Edition which uses Excel's two beta
distribution functions, BETA.DIST and BETA.INV. It's freely licensed, too!
This example workbook is intended to help you quickly get started. You can also download
a Quick Start guide for Statistical PERT® Normal Edition. The Quick Start guide explains the
essential things you need to know to use this Statistical PERT® Normal Edition spreadsheet.
All Statistical PERT downloads share the same three steps for making a probablistic estimate:
1) Create a 3-point estimate (minimum, most likely, maximum)
2) Render a subjective judgment about the most likely outcome
3) Select any probabilistic planning estimate, or make a risk-based forecast
If you have any questions, suggestions, or comments, I'd love to hear from you! | New with Version 3 -- Dynamic, tri-colored, bell-shaped curves!
Contact me!
Plus:
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP | - New! Super Simple SPERT worksheet
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com | - New! Line Sparklines to visualize the 3-point uncertainty of every row
Watch a Pluralsight course on Statistical PERT® Normal Edition | - Enhanced! Agile forecasting using up to three scenarios
Watch Statistical PERT videos on YouTube | - A link to a brand-new Pluralsight course on estimating using SPERT
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Practice Forecasting
Statistical PERT® (SPERT®) Normal Edition - Practice Forecasting
Practice forecasting! How many pennies are in this jar?
Use the "Super Simple SPERT®" worksheet to create your first forecast!
First, estimate the most likely number of pennies in the jar, and enter your estimate into cell C4. This is your anchor estimate.
Second, estimate the minimum possible number of pennies in the jar, and enter your estimate into cell C3.
Third, estimate the maximum possible number of pennies in the jar, and enter your estimate into cell C5.
Your most likely estimate should be approximately midway between your minimum and maximum estimates.
Fourth, choose a subjective judgment (in cell C9) about HOW LIKELY your "most likely" will be close to the actual count.
Fifth, enter a planning estimate in cell 12. Choose any number between your minimum and maximum estimates.
Now see if you can answer questions like these by forecasting:
- How probable is the actual number of pennies in the jar less than your planning estimate?
- How probable is the actual number of pennies in the jar greater than your planning estimate?
- If I sell the jar for $30 (change the planning estimate to 3000), what is the chance I'll make a profit? What if I sell for $40? $50? $60?
- What is the 50/50 estimate (that is, 50% likely the true value is less than the 50/50 estimate, and 50% likely it is more)?
- If I told you that the jar contains not less than 2000 pennies and not more than 8000 pennies, would your forecast change? How?
An estimate is somebody's idea about the true value of something unknown.
A prediction is somebody's single idea about the true value of something unknown.
A forecast is somebody's varied idea about the true value of something unknown.
A forecast creates a range of possibilities with associated probabilities of occurrence.
Want to know the actual number of pennies in this jar? Unhide rows 26-35 ↓↓↓
The short answer: The actual number is 4,532 pennies. Maybe.
The long answer: I only counted one-third of the jar's pennies, then I estimated the uncounted coins.
To do that, I began by taking 15 random samples of 100 pennies out of the jar and weighing each sample,
then finding the average weight of 100 pennies. Pennies weigh either 2.5g (1982-present) or 3.11g (pre-1982).
I used the average weight of 100 pennies to calculate, by weight, the remaining two-thirds of the pennies in the jar.
So, I never counted ALL the pennies! But I did use some real data to create my forecasted mode of 4,532 pennies.
It's highly improbable that there are fewer than 4,412 pennies or more than 4,652 pennies.
Don't worry if your penny count forecast was way off. Forecasting is easy to do but hard to master.
Good forecasting is an empirical process. Make a forecast, observe, learn, then re-forecast.
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Super Simple SPERT®
Statistical PERT® (SPERT®) Normal Edition Super Simple SPERT®
Think about an uncertain outcome. Then, fill-in the yellow cells, below:
Enter your uncertainty's minimum value → | 50 | What's the minimum possible value or outcome for your uncertainty?
HINT: DO THIS FIRST → → → Enter your uncertainty's most likely value → | 100 | What's the most-likely-to-occur value or outcome for your uncertainty? This is your anchor estimate.
Enter your uncertainty's maximum value → | 150 | What's the maximum possible value or outcome for your uncertainty?
Validate your values → | 1 | See a green checkmark? Keep going! See a yellow exclamation mark? Check your 3-point entry to see if it's correct.
Check if this is a bell-shaped uncertainty → | 1 | See a green or yellow light? Keep going! See a red light? SPERT won't work well for this estimate scenario.
100
How confident are you in the most likely outcome? → | Medium confidence | Render a subjective judgment (your opinion) about HOW LIKELY the Most Likely outcome really is
Here's your implied, bell-shaped curve → |  | Based upon your entries, this is how SPERT models your uncertainty using the normal distribution
20
Enter a planning estimate → | 75 | Your planning estimate is any interesting number between your minimum and maximum estimates
Choose either the left- or right-side area → | Show Left-Side Area | You can obtain SPERT estimates from either the left- or right-side area of the bell-curve
Your planning estimate of 75 is greater than 11% of all possible outcomes → | 0.10565 | 89% of all possible outcomes exceed your planning estimate of 75
Enter any percentage between 1% and 99% → | 0.5 | Below, SPERT will calculate an estimate for you
The SPERT estimate of 100 is greater than 50% of all possible outcomes → | 100 | 50% of all possible outcomes exceed the SPERT estimate of 100
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
X-axis increments | 1.6667 | This, along with the grayed-out table below, is only used to create a Sparkline
16.6667 | 3.3882e-06
18.3333 | 4.7781e-06
20 | 6.6915e-06
21.6667 | 9.3064e-06
23.3333 | 1.2854e-05
25 | 1.763e-05
26.6667 | 2.4014e-05
28.3333 | 3.2482e-05
30 | 4.3634e-05
31.6667 | 5.8209e-05
33.3333 | 7.7114e-05
35 | 0.00010145
36.6667 | 0.00013255
38.3333 | 0.00017198
40 | 0.00022159
41.6667 | 0.00028354
43.3333 | 0.0003603
45 | 0.00045468
46.6667 | 0.0005698
48.3333 | 0.00070913
50 | 0.00087642
51.6667 | 0.0010757
53.3333 | 0.0013111
55 | 0.001587
56.6667 | 0.0019076
58.3333 | 0.0022772
60 | 0.0026995
61.6667 | 0.0031781
63.3333 | 0.0037156
65 | 0.0043139
66.6667 | 0.0049739
68.3333 | 0.0056951
70 | 0.0064759
71.6667 | 0.0073127
73.3333 | 0.0082005
75 | 0.0091325
76.6667 | 0.0101
78.3333 | 0.011093
80 | 0.012099
81.6667 | 0.013104
83.3333 | 0.014096
85 | 0.015057
86.6667 | 0.015972
88.3333 | 0.016826
90 | 0.017603
91.6667 | 0.018289
93.3333 | 0.018869
95 | 0.019333
96.6667 | 0.019672
98.3333 | 0.019878
100 | 0.019947
101.6667 | 0.019878
103.3333 | 0.019672
105 | 0.019333
106.6667 | 0.018869
108.3333 | 0.018289
110 | 0.017603
111.6667 | 0.016826
113.3333 | 0.015972
115 | 0.015057
116.6667 | 0.014096
118.3333 | 0.013104
120 | 0.012099
121.6667 | 0.011093
123.3333 | 0.0101
125 | 0.0091325
126.6667 | 0.0082005
128.3333 | 0.0073127
130 | 0.0064759
131.6667 | 0.0056951
133.3333 | 0.0049739
135 | 0.0043139
136.6667 | 0.0037156
138.3333 | 0.0031781
140 | 0.0026995
141.6667 | 0.0022772
143.3333 | 0.0019076
145 | 0.001587
146.6667 | 0.0013111
148.3333 | 0.0010757
150 | 0.00087642
151.6667 | 0.00070913
153.3333 | 0.0005698
155 | 0.00045468
156.6667 | 0.0003603
158.3333 | 0.00028354
160 | 0.00022159
161.6667 | 0.00017198
163.3333 | 0.00013255
165 | 0.00010145
166.6667 | 7.7114e-05
168.3333 | 5.8209e-05
170 | 4.3634e-05
171.6667 | 3.2482e-05
173.3333 | 2.4014e-05
175 | 1.763e-05
176.6667 | 1.2854e-05
178.3333 | 9.3064e-06
180 | 6.6915e-06
181.6667 | 4.7781e-06
183.3333 | 3.3882e-06
↑ Rows 36 through 138 are hidden; they are used to create the bell-curve Sparkline

## SPERT® Normal for Beginners
Statistical PERT® (SPERT®) Normal Edition for Beginners
First, enter a three-point estimate for any uncertainty
| Minimum | Most Likely | Maximum | [6 empty] | SPERT Var
| 60 | 120 | 240 | Use SPERT to estimate task duration, work effort, agile story points, cost, revenue, event attendance, etc. | [5 empty] | 1296
|  |  | Validate your bell-shaped uncertainty | 1 | 0.5 | A green checkmark means you have correctly entered minimum, most likely and maximum point-estimates. A green or yellow light means you have a suitable, bell-shaped uncertainty. If it's red, try changing your three-point estimate.
[5 empty] | The PERT Mean is the average result | PERT Mean
[5 empty] | (It's also called the expected result) | 130 | The PERT Mean is calculated using the PERT formula: (Minimum + 4(Most Likely) + Maximum) / 6
[6 empty] | Render a subjective judgment about HOW LIKELY | Most Likely Confidence
[6 empty] | the Most Likely outcome really is | Medium confidence | This choice influences the implied bell-shaped curve for the uncertainty you are estimating
This normal distribution graph shows the bell-shaped curve for your uncertainty | [7 empty] | Curve | The bell-shaped curve will change depending on your 3-point estimate and your subjective judgment about the Most Likely outcome (above)
Note: Even if your 3-point estimate indicates skewing, SPERT Normal Edition fits your uncertainty into a normally-distributed, bell-shaped curve
This is the SPERT Standard Deviation for your uncertainty | [8 empty] | SPERT SD |  | You don't have to know this or do anything with this, but SPERT needs this
36
[9 empty] | Show probabilities from either the left-side area or right-side area |  | Show Left-Side Area |  | Read the red text below to see how this choice affects the SPERT estimates
[11 empty] | Planning Estimate | SPERT Probability | Note: This is a cumulative probability, so the SPERT Probability is the likelihood that
the Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty's actual outcome*
[9 empty] | Enter a Planning Estimate and see its likelihood of occurrence under SPERT Probability |  | 150 | 71.07% | * This is true if you choose Show Left-Side Area in the dropdown control above. If you choose Show Right-Side Area,
you'll see the SPERT Probability that your Planning Estimate will be EXCEEDED by the uncertainty's actual outcome.
Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[12 empty] | Here, you'll see several SPERT estimates with different probabilities of occurrence | SPERT Probabilistic Estimates
[12 empty] | You can change these cumulative probability choices (enter values between 1% and 99%) → | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7
[12 empty] | Find a SPERT Probablistic Estimate that best matches your risk propensity → | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 148.8784
Choose whether to show currency formatting
Do not show currency formatting
That's it! Now try using the (3-Point entry) worksheet!
Or, use the (1-Point entry) worksheet, where two heuristics automatically calculate the Minimum and Maximum point-estimates
| -0.5 | << Heuristics >> | 1 | (You can change the dropdown options on the Vlookups worksheet)
| Minimum | Most Likely | Maximum
| 60 | 120 | 240
Try selecting a different dropdown percentage by clicking above the Minimum and Maximum cell headings,
and see the value changes for the minimum and maximum point-estimates in the green-shaded cells.
The rest of the (1-Point entry) worksheet works exactly the same way as the (3-Point entry) worksheet.
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
| X-axis increments | 3 | This, along with the grayed-out table below, is only used to create a Sparkline
| 0 | 1.633e-05
| 3 | 2.1987e-05
| 6 | 2.9399e-05
| 9 | 3.9037e-05
| 12 | 5.1477e-05
| 15 | 6.7411e-05
| 18 | 8.7667e-05
| 21 | 0.00011322
| 24 | 0.00014521
| 27 | 0.00018495
| 30 | 0.00023393
| 33 | 0.00029384
| 36 | 0.00036654
| 39 | 0.00045406
| 42 | 0.00055858
| 45 | 0.00068241
| 48 | 0.00082792
| 51 | 0.00099751
| 54 | 0.0011935
| 57 | 0.0014182
| 60 | 0.0016734
| 63 | 0.001961
| 66 | 0.002282
| 69 | 0.0026372
| 72 | 0.0030267
| 75 | 0.0034496
| 78 | 0.0039043
| 81 | 0.0043885
| 84 | 0.0048986
| 87 | 0.0054301
| 90 | 0.0059776
| 93 | 0.0065348
| 96 | 0.0070944
| 99 | 0.0076487
| 102 | 0.0081893
| 105 | 0.0087074
| 108 | 0.0091942
| 111 | 0.009641
| 114 | 0.01004
| 117 | 0.010382
| 120 | 0.010662
| 123 | 0.010874
| 126 | 0.011014
| 129 | 0.011077
| 132 | 0.011065
| 135 | 0.010975
| 138 | 0.010811
| 141 | 0.010576
| 144 | 0.010275
| 147 | 0.0099125
| 150 | 0.009497
| 153 | 0.0090359
| 156 | 0.0085377
| 159 | 0.0080112
| 162 | 0.0074651
| 165 | 0.0069081
| 168 | 0.0063484
| 171 | 0.0057937
| 174 | 0.0052508
| 177 | 0.0047259
| 180 | 0.004224
| 183 | 0.0037493
| 186 | 0.0033049
| 189 | 0.0028931
| 192 | 0.002515
| 195 | 0.0021712
| 198 | 0.0018614
| 201 | 0.0015848
| 204 | 0.00134
| 207 | 0.0011251
| 210 | 0.00093816
| 213 | 0.00077686
| 216 | 0.00063884
| 219 | 0.00052171
| 222 | 0.00042311
| 225 | 0.00034076
| 228 | 0.00027255
| 231 | 0.00021648
| 234 | 0.00017075
| 237 | 0.00013375
| 240 | 0.00010405
| 243 | 8.0378e-05
| 246 | 6.1664e-05
| 249 | 4.6979e-05
| 252 | 3.5544e-05
| 255 | 2.6706e-05
| 258 | 1.9927e-05
| 261 | 1.4766e-05
| 264 | 1.0865e-05
| 267 | 7.9401e-06
| 270 | 5.7622e-06
| 273 | 4.1528e-06
| 276 | 2.9722e-06
| 279 | 2.1125e-06
| 282 | 1.491e-06
| 285 | 1.0451e-06
| 288 | 7.2752e-07
| 291 | 5.0292e-07
| 294 | 3.4525e-07
| 297 | 2.3537e-07
| 300 | 1.5935e-07
↑ Rows 62 through 164 are hidden; they are used to create the bell-curve Sparkline
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on G8: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H11: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I14: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on J17: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on L22: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on M22: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on N29: You can choose different probabilities by entering a value between 1% and 99%.
Note on B39: Use a simple heuristic to quickly create MINIMUM point-estimates. Do this by selecting a percentage in cell B2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and reducing it by the percentage value specified in cell B2. If you want, overwrite any cell formula in column B to manually enter a non-calculated, minimum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell B2, you can do that in the Vlookups worksheet).
Note on C39: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D39: Use a simple heuristic to quickly create MAXIMUM point-estimates. Do this by selecting a percentage in cell D2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and increasing it by the percentage value specified in cell D2. If you want, overwrite any cell formula in column D to manually enter a non-calculated, maximum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell D2, you can do that in the Vlookups worksheet).

## SPERT® Normal (1-Point entry)
| Statistical PERT® (SPERT®) Normal Edition | [10 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
| -0.5 | << Heuristics >> | 1 | [8 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.5 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 0.5 | 130 | Near certainty |  |  | 12.7279 | 162 | 150 | 94.19% | 113.6885 | 146.3115 | 143.1916 | 140.7121 | 138.5849 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 6.9685e-25 | 7.5266e-24 | 7.6901e-23 | 7.4325e-22 | 6.7954e-21 | 5.8771e-20 | 4.8082e-19 | 3.7212e-18 | 2.7243e-17 | 1.8866e-16 | 1.236e-15 | 7.6593e-15 | 4.49e-14 | 2.4899e-13 | 1.3061e-12 | 6.4812e-12 | 3.0423e-11 | 1.3509e-10 | 5.6743e-10 | 2.2547e-09 | 8.4746e-09 | 3.0132e-08 | 1.0135e-07 | 3.2245e-07 | 9.705e-07 | 2.7631e-06 | 7.4417e-06 | 1.8959e-05 | 4.5691e-05 | 0.00010417 | 0.00022464 | 0.00045827 | 0.00088437 | 0.0016144 | 0.0027878 | 0.004554 | 0.0070371 | 0.010286 | 0.014223 | 0.018605 | 0.02302 | 0.026945 | 0.029834 | 0.031247 | 0.030959 | 0.029016 | 0.025726 | 0.021576 | 0.017117 | 0.012846 | 0.0091198 | 0.0061245 | 0.0038907 | 0.0023381 | 0.0013291 | 0.00071473 | 0.00036357 | 0.00017495 | 7.9636e-05 | 3.4291e-05 | 1.3967e-05 | 5.3818e-06 | 1.9616e-06 | 6.7634e-07 | 2.206e-07 | 6.8061e-08 | 1.9864e-08 | 5.4843e-09 | 1.4323e-09 | 3.5386e-10 | 8.2698e-11 | 1.8282e-11 | 3.8233e-12 | 7.5635e-13 | 1.4154e-13 | 2.5056e-14 | 4.1957e-15 | 6.6463e-16 | 9.9592e-17 | 1.4117e-17 | 1.8929e-18 | 2.401e-19 | 2.8809e-20 | 3.2699e-21 | 3.5109e-22 | 3.5659e-23 | 3.426e-24 | 3.1138e-25 | 2.6771e-26 | 2.1772e-27 | 1.675e-28 | 1.219e-29 | 8.392e-31 | 5.4651e-32 | 3.3667e-33 | 1.9619e-34 | 1.0815e-35 | 5.6397e-37 | 2.7819e-38 | 1.2981e-39 | 5.73e-41
2 | 60 | 120 | 240 | 1 | 0.5 | 130 | High confidence |  |  | 20.4853 | 419.6468 | 150 | 83.55% | 103.7471 | 156.2529 | 151.2316 | 147.2408 | 143.8171 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5037e-11 | 8.7797e-11 | 2.1534e-10 | 5.1695e-10 | 1.2147e-09 | 2.7936e-09 | 6.2885e-09 | 1.3855e-08 | 2.9879e-08 | 6.3069e-08 | 1.303e-07 | 2.6349e-07 | 5.215e-07 | 1.0103e-06 | 1.9157e-06 | 3.5553e-06 | 6.4583e-06 | 1.1483e-05 | 1.9983e-05 | 3.4038e-05 | 5.6748e-05 | 9.2603e-05 | 0.00014791 | 0.00023122 | 0.0003538 | 0.00052988 | 0.00077674 | 0.0011145 | 0.0015651 | 0.0021513 | 0.0028943 | 0.0038113 | 0.0049124 | 0.0061972 | 0.0076522 | 0.0092483 | 0.01094 | 0.012667 | 0.014355 | 0.015923 | 0.017287 | 0.01837 | 0.019107 | 0.019451 | 0.019382 | 0.018903 | 0.018045 | 0.01686 | 0.015419 | 0.013801 | 0.012092 | 0.010369 | 0.008703 | 0.0071497 | 0.0057491 | 0.0045247 | 0.0034855 | 0.002628 | 0.0019395 | 0.0014009 | 0.00099046 | 0.0006854 | 0.00046423 | 0.00030776 | 0.0001997 | 0.00012683 | 7.8844e-05 | 4.7972e-05 | 2.8569e-05 | 1.6653e-05 | 9.5011e-06 | 5.3056e-06 | 2.8999e-06 | 1.5514e-06 | 8.1236e-07 | 4.1635e-07 | 2.0886e-07 | 1.0255e-07 | 4.9284e-08 | 2.3182e-08 | 1.0673e-08 | 4.8097e-09 | 2.1214e-09 | 9.1585e-10 | 3.87e-10 | 1.6006e-10 | 6.4793e-11 | 2.5672e-11 | 9.9562e-12 | 3.7792e-12 | 1.4041e-12 | 5.106e-13 | 1.8174e-13 | 6.3315e-14 | 2.159e-14 | 7.2056e-15 | 2.3539e-15 | 7.5263e-16 | 2.3554e-16 | 7.215e-17 | 2.1632e-17
3 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-high confidence |  |  | 28.2426 | 797.6468 | 150 | 76.06% | 93.8056 | 166.1944 | 159.2716 | 153.7696 | 149.0494 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5419e-07 | 5.7429e-07 | 9.2071e-07 | 1.4595e-06 | 2.2877e-06 | 3.5457e-06 | 5.4336e-06 | 8.2335e-06 | 1.2336e-05 | 1.8275e-05 | 2.677e-05 | 3.8775e-05 | 5.5531e-05 | 7.8637e-05 | 0.00011011 | 0.00015244 | 0.00020869 | 0.00028248 | 0.00037807 | 0.00050034 | 0.00065472 | 0.00084712 | 0.0010838 | 0.0013709 | 0.0017148 | 0.0021208 | 0.0025935 | 0.0031359 | 0.0037493 | 0.0044324 | 0.0051812 | 0.0059885 | 0.0068439 | 0.0077337 | 0.0086412 | 0.0095468 | 0.010429 | 0.011265 | 0.012031 | 0.012706 | 0.013267 | 0.013698 | 0.013985 | 0.014117 | 0.01409 | 0.013906 | 0.01357 | 0.013094 | 0.012492 | 0.011785 | 0.010993 | 0.010139 | 0.0092464 | 0.0083379 | 0.0074342 | 0.0065542 | 0.0057134 | 0.0049247 | 0.0041972 | 0.003537 | 0.0029473 | 0.0024283 | 0.0019782 | 0.0015935 | 0.0012692 | 0.00099957 | 0.00077838 | 0.00059933 | 0.0004563 | 0.0003435 | 0.00025568 | 0.00018818 | 0.00013695 | 9.8545e-05 | 7.0115e-05 | 4.9327e-05 | 3.4313e-05 | 2.3601e-05 | 1.6051e-05 | 1.0794e-05 | 7.1773e-06 | 4.7189e-06 | 3.0677e-06 | 1.9719e-06 | 1.2533e-06 | 7.8765e-07 | 4.8945e-07 | 3.0073e-07 | 1.8271e-07 | 1.0976e-07 | 6.5193e-08 | 3.8289e-08 | 2.2235e-08 | 1.2768e-08 | 7.2492e-09 | 4.0697e-09 | 2.2591e-09 | 1.24e-09 | 6.7294e-10 | 3.6112e-10 | 1.9161e-10
4 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium confidence |  |  | 36 | 1296 | 150 | 71.07% | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 1.633e-05 | 2.1987e-05 | 2.9399e-05 | 3.9037e-05 | 5.1477e-05 | 6.7411e-05 | 8.7667e-05 | 0.00011322 | 0.00014521 | 0.00018495 | 0.00023393 | 0.00029384 | 0.00036654 | 0.00045406 | 0.00055858 | 0.00068241 | 0.00082792 | 0.00099751 | 0.0011935 | 0.0014182 | 0.0016734 | 0.001961 | 0.002282 | 0.0026372 | 0.0030267 | 0.0034496 | 0.0039043 | 0.0043885 | 0.0048986 | 0.0054301 | 0.0059776 | 0.0065348 | 0.0070944 | 0.0076487 | 0.0081893 | 0.0087074 | 0.0091942 | 0.009641 | 0.01004 | 0.010382 | 0.010662 | 0.010874 | 0.011014 | 0.011077 | 0.011065 | 0.010975 | 0.010811 | 0.010576 | 0.010275 | 0.0099125 | 0.009497 | 0.0090359 | 0.0085377 | 0.0080112 | 0.0074651 | 0.0069081 | 0.0063484 | 0.0057937 | 0.0052508 | 0.0047259 | 0.004224 | 0.0037493 | 0.0033049 | 0.0028931 | 0.002515 | 0.0021712 | 0.0018614 | 0.0015848 | 0.00134 | 0.0011251 | 0.00093816 | 0.00077686 | 0.00063884 | 0.00052171 | 0.00042311 | 0.00034076 | 0.00027255 | 0.00021648 | 0.00017075 | 0.00013375 | 0.00010405 | 8.0378e-05 | 6.1664e-05 | 4.6979e-05 | 3.5544e-05 | 2.6706e-05 | 1.9927e-05 | 1.4766e-05 | 1.0865e-05 | 7.9401e-06 | 5.7622e-06 | 4.1528e-06 | 2.9722e-06 | 2.1125e-06 | 1.491e-06 | 1.0451e-06 | 7.2752e-07 | 5.0292e-07 | 3.4525e-07 | 2.3537e-07 | 1.5935e-07
5 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-low confidence |  |  | 48.3721 | 2339.8615 | 150 | 66.04% | 68.0086 | 191.9914 | 180.1345 | 170.711 | 162.6265 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00022281 | 0.00026272 | 0.00030858 | 0.00036106 | 0.00042084 | 0.00048864 | 0.00056518 | 0.0006512 | 0.00074744 | 0.0008546 | 0.00097338 | 0.0011044 | 0.0012483 | 0.0014054 | 0.0015763 | 0.0017612 | 0.0019602 | 0.0021733 | 0.0024004 | 0.002641 | 0.0028945 | 0.0031602 | 0.0034371 | 0.0037239 | 0.0040191 | 0.004321 | 0.0046278 | 0.0049373 | 0.0052474 | 0.0055555 | 0.0058591 | 0.0061556 | 0.0064422 | 0.0067163 | 0.0069752 | 0.0072163 | 0.007437 | 0.0076351 | 0.0078083 | 0.0079548 | 0.008073 | 0.0081615 | 0.0082192 | 0.0082456 | 0.0082403 | 0.0082034 | 0.0081353 | 0.0080368 | 0.0079091 | 0.0077534 | 0.0075717 | 0.0073658 | 0.0071381 | 0.0068908 | 0.0066265 | 0.0063479 | 0.0060577 | 0.0057585 | 0.0054532 | 0.0051441 | 0.004834 | 0.0045251 | 0.0042197 | 0.0039198 | 0.0036273 | 0.0033436 | 0.0030704 | 0.0028086 | 0.0025593 | 0.0023232 | 0.0021007 | 0.0018923 | 0.001698 | 0.0015178 | 0.0013515 | 0.0011988 | 0.0010593 | 0.00093245 | 0.00081762 | 0.00071418 | 0.00062143 | 0.00053865 | 0.00046511 | 0.00040006 | 0.00034279 | 0.00029259 | 0.00024878 | 0.00021072 | 0.0001778 | 0.00014945 | 0.00012513 | 0.00010437 | 8.6719e-05 | 7.1777e-05 | 5.9181e-05 | 4.8608e-05 | 3.9771e-05 | 3.2416e-05 | 2.6319e-05 | 2.1287e-05 | 1.7151e-05
6 | 60 | 120 | 240 | 1 | 0.5 | 130 | Low confidence |  |  | 60.7442 | 3689.8615 | 150 | 62.9% | 52.1531 | 207.8469 | 192.9573 | 181.1236 | 170.9714 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00066504 | 0.00073828 | 0.00081758 | 0.00090321 | 0.00099536 | 0.0010943 | 0.0012 | 0.0013128 | 0.0014327 | 0.0015598 | 0.001694 | 0.0018352 | 0.0019834 | 0.0021383 | 0.0022997 | 0.0024673 | 0.0026406 | 0.0028192 | 0.0030025 | 0.00319 | 0.003381 | 0.0035746 | 0.0037701 | 0.0039667 | 0.0041633 | 0.004359 | 0.0045528 | 0.0047436 | 0.0049304 | 0.005112 | 0.0052874 | 0.0054556 | 0.0056153 | 0.0057657 | 0.0059056 | 0.0060343 | 0.0061507 | 0.006254 | 0.0063437 | 0.0064189 | 0.0064792 | 0.0065241 | 0.0065534 | 0.0065667 | 0.006564 | 0.0065454 | 0.0065109 | 0.0064608 | 0.0063954 | 0.0063154 | 0.0062211 | 0.0061133 | 0.0059927 | 0.0058602 | 0.0057167 | 0.0055631 | 0.0054004 | 0.0052297 | 0.0050521 | 0.0048686 | 0.0046804 | 0.0044884 | 0.0042939 | 0.0040978 | 0.0039011 | 0.0037048 | 0.0035098 | 0.003317 | 0.0031271 | 0.0029409 | 0.0027591 | 0.0025822 | 0.0024108 | 0.0022452 | 0.0020859 | 0.0019332 | 0.0017874 | 0.0016485 | 0.0015167 | 0.001392 | 0.0012745 | 0.001164 | 0.0010605 | 0.00096391 | 0.00087395 | 0.00079046 | 0.0007132 | 0.00064193 | 0.00057637 | 0.00051624 | 0.00046127 | 0.00041114 | 0.00036557 | 0.00032425 | 0.00028691 | 0.00025325 | 0.00022299 | 0.00019587 | 0.00017163 | 0.00015002 | 0.00013081
7 | 60 | 120 | 240 | 1 | 0.5 | 130 | Guesstimate |  |  | 73.1163 | 5346 | 150 | 60.78% | 36.2976 | 223.7024 | 205.7802 | 191.5363 | 179.3162 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.0011232 | 0.0012071 | 0.0012952 | 0.0013874 | 0.0014836 | 0.0015839 | 0.001688 | 0.001796 | 0.0019077 | 0.0020229 | 0.0021415 | 0.0022632 | 0.0023878 | 0.002515 | 0.0026445 | 0.002776 | 0.0029092 | 0.0030436 | 0.0031789 | 0.0033147 | 0.0034504 | 0.0035856 | 0.0037198 | 0.0038526 | 0.0039834 | 0.0041117 | 0.004237 | 0.0043588 | 0.0044766 | 0.0045898 | 0.0046979 | 0.0048005 | 0.0048971 | 0.0049872 | 0.0050705 | 0.0051465 | 0.0052148 | 0.0052751 | 0.0053272 | 0.0053707 | 0.0054055 | 0.0054313 | 0.0054481 | 0.0054558 | 0.0054542 | 0.0054435 | 0.0054237 | 0.0053949 | 0.0053572 | 0.0053108 | 0.0052559 | 0.0051929 | 0.005122 | 0.0050435 | 0.0049579 | 0.0048656 | 0.004767 | 0.0046625 | 0.0045526 | 0.0044378 | 0.0043187 | 0.0041956 | 0.0040693 | 0.0039401 | 0.0038085 | 0.0036752 | 0.0035406 | 0.0034052 | 0.0032694 | 0.0031338 | 0.0029987 | 0.0028647 | 0.002732 | 0.0026011 | 0.0024723 | 0.0023459 | 0.0022223 | 0.0021016 | 0.0019841 | 0.00187 | 0.0017596 | 0.0016529 | 0.00155 | 0.0014511 | 0.0013562 | 0.0012654 | 0.0011787 | 0.0010961 | 0.0010175 | 0.00094303 | 0.00087251 | 0.00080591 | 0.00074314 | 0.0006841 | 0.0006287 | 0.00057681 | 0.00052831 | 0.00048308 | 0.00044098 | 0.00040187 | 0.00036561
8 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
11 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 420 | 840 | 1680 |  |  | 910 |  |  |  | 118.537 | 14051.0166 | 1050 | 88.12% | 551.5647 | 1268.4353 | 1199.8785 | 1145.3918 | 1098.6471 | 910 | 554.389 | 561.4308 | 568.4727 | 575.5145 | 582.5563 | 589.5981 | 596.6399 | 603.6817 | 610.7235 | 617.7653 | 624.8071 | 631.8489 | 638.8907 | 645.9325 | 652.9743 | 660.0161 | 667.0579 | 674.0997 | 681.1415 | 688.1833 | 695.2251 | 702.2669 | 709.3087 | 716.3505 | 723.3923 | 730.4341 | 737.4759 | 744.5177 | 751.5595 | 758.6013 | 765.6431 | 772.6849 | 779.7267 | 786.7685 | 793.8103 | 800.8521 | 807.8939 | 814.9357 | 821.9775 | 829.0193 | 836.0611 | 843.1029 | 850.1447 | 857.1865 | 864.2283 | 871.2701 | 878.3119 | 885.3537 | 892.3955 | 899.4373 | 906.4791 | 913.5209 | 920.5627 | 927.6045 | 934.6463 | 941.6881 | 948.7299 | 955.7717 | 962.8135 | 969.8553 | 976.8971 | 983.9389 | 990.9807 | 998.0225 | 1005.0643 | 1012.1061 | 1019.1479 | 1026.1897 | 1033.2315 | 1040.2733 | 1047.3151 | 1054.3569 | 1061.3987 | 1068.4405 | 1075.4823 | 1082.5241 | 1089.5659 | 1096.6077 | 1103.6495 | 1110.6913 | 1117.7331 | 1124.7749 | 1131.8167 | 1138.8585 | 1145.9003 | 1152.9421 | 1159.9839 | 1167.0257 | 1174.0675 | 1181.1093 | 1188.1511 | 1195.1929 | 1202.2347 | 1209.2765 | 1216.3183 | 1223.3601 | 1230.4019 | 1237.4437 | 1244.4855 | 1251.5273 | 1258.5692 | 1265.611 | 4.4603e-05 | 5.3023e-05 | 6.281e-05 | 7.4142e-05 | 8.721e-05 | 0.00010222 | 0.00011939 | 0.00013896 | 0.00016116 | 0.00018625 | 0.00021448 | 0.00024613 | 0.00028146 | 0.00032071 | 0.00036416 | 0.00041204 | 0.00046456 | 0.00052194 | 0.00058434 | 0.0006519 | 0.0007247 | 0.0008028 | 0.00088618 | 0.00097477 | 0.0010684 | 0.001167 | 0.0012701 | 0.0013775 | 0.0014887 | 0.0016033 | 0.0017205 | 0.0018398 | 0.0019605 | 0.0020817 | 0.0022027 | 0.0023224 | 0.00244 | 0.0025546 | 0.0026651 | 0.0027706 | 0.0028701 | 0.0029627 | 0.0030475 | 0.0031238 | 0.0031906 | 0.0032474 | 0.0032936 | 0.0033286 | 0.0033522 | 0.0033641 | 0.0033641 | 0.0033522 | 0.0033286 | 0.0032936 | 0.0032474 | 0.0031906 | 0.0031238 | 0.0030475 | 0.0029627 | 0.0028701 | 0.0027706 | 0.0026651 | 0.0025546 | 0.00244 | 0.0023224 | 0.0022027 | 0.0020817 | 0.0019605 | 0.0018398 | 0.0017205 | 0.0016033 | 0.0014887 | 0.0013775 | 0.0012701 | 0.001167 | 0.0010684 | 0.00097477 | 0.00088618 | 0.0008028 | 0.0007247 | 0.0006519 | 0.00058434 | 0.00052194 | 0.00046456 | 0.00041204 | 0.00036416 | 0.00032071 | 0.00028146 | 0.00024613 | 0.00021448 | 0.00018625 | 0.00016116 | 0.00013896 | 0.00011939 | 0.00010222 | 8.721e-05 | 7.4142e-05 | 6.281e-05 | 5.3023e-05 | 4.4603e-05 | 3.7388e-05
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 77.62% | 758.0887 | 1061.9113 | 1032.8557 | 1009.7632 | 989.952 | 910 | [102 empty] | 4.4603e-05 | 5.3023e-05 | 6.281e-05 | 7.4142e-05 | 8.721e-05 | 0.00010222 | 0.00011939 | 0.00013896 | 0.00016116 | 0.00018625 | 0.00021448 | 0.00024613 | 0.00028146 | 0.00032071 | 0.00036416 | 0.00041204 | 0.00046456 | 0.00052194 | 0.00058434 | 0.0006519 | 0.0007247 | 0.0008028 | 0.00088618 | 0.00097477 | 0.0010684 | 0.001167 | 0.0012701 | 0.0013775 | 0.0014887 | 0.0016033 | 0.0017205 | 0.0018398 | 0.0019605 | 0.0020817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0022027 | 0.0023224 | 0.00244 | 0.0025546 | 0.0026651 | 0.0027706 | 0.0028701 | 0.0029627 | 0.0030475 | 0.0031238 | 0.0031906 | 0.0032474 | 0.0032936 | 0.0033286 | 0.0033522 | 0.0033641 | 0.0033641 | 0.0033522 | 0.0033286 | 0.0032936 | 0.0032474 | 0.0031906 | 0.0031238 | 0.0030475 | 0.0029627 | 0.0028701 | 0.0027706 | 0.0026651 | 0.0025546 | 0.00244 | 0.0023224 | 0.0022027 | 0.0020817 | 0.0019605 | 0.0018398 | 0.0017205 | 0.0016033 | 0.0014887 | 0.0013775 | 0.0012701 | 0.001167 | 0.0010684 | 0.00097477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 0.8 | confidence | [117 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00088618 | 0.0008028 | 0.0007247 | 0.0006519 | 0.00058434 | 0.00052194 | 0.00046456 | 0.00041204 | 0.00036416 | 0.00032071 | 0.00028146 | 0.00024613 | 0.00021448 | 0.00018625 | 0.00016116 | 0.00013896 | 0.00011939 | 0.00010222 | 8.721e-05 | 7.4142e-05 | 6.281e-05 | 5.3023e-05 | 4.4603e-05 | 3.7388e-05
|  | The lowerbound threshold is | 758.0887 | [118 empty] | 4.4603e-05 | 5.3023e-05 | 6.281e-05 | 7.4142e-05 | 8.721e-05 | 0.00010222 | 0.00011939 | 0.00013896 | 0.00016116 | 0.00018625 | 0.00021448 | 0.00024613 | 0.00028146 | 0.00032071 | 0.00036416 | 0.00041204 | 0.00046456 | 0.00052194 | 0.00058434 | 0.0006519 | 0.0007247 | 0.0008028 | 0.00088618 | 0.00097477 | 0.0010684 | 0.001167 | 0.0012701 | 0.0013775 | 0.0014887 | 0.0016033 | 0.0017205 | 0.0018398 | 0.0019605 | 0.0020817 | 0.0022027 | 0.0023224 | 0.00244 | 0.0025546 | 0.0026651 | 0.0027706 | 0.0028701 | 0.0029627 | 0.0030475 | 0.0031238 | 0.0031906 | 0.0032474 | 0.0032936 | 0.0033286 | 0.0033522 | 0.0033641 | 0.0033641 | 0.0033522 | 0.0033286 | 0.0032936 | 0.0032474 | 0.0031906 | 0.0031238 | 0.0030475 | 0.0029627 | 0.0028701 | 0.0027706 | 0.0026651 | 0.0025546 | 0.00244 | 0.0023224 | 0.0022027 | 0.0020817 | 0.0019605 | 0.0018398 | 0.0017205 | 0.0016033 | 0.0014887 | 0.0013775 | 0.0012701 | 0.001167 | 0.0010684 | 0.00097477 | 0.00088618 | 0.0008028 | 0.0007247 | 0.0006519 | 0.00058434 | 0.00052194 | 0.00046456 | 0.00041204 | 0.00036416 | 0.00032071 | 0.00028146 | 0.00024613 | 0.00021448 | 0.00018625 | 0.00016116 | 0.00013896 | 0.00011939 | 0.00010222 | 8.721e-05 | 7.4142e-05 | 6.281e-05 | 5.3023e-05 | 4.4603e-05 | 3.7388e-05
|  | and the upperbound threshold is | 1061.9113
|  | Between a lowerbound value of | 800 |  | Miss the pie
|  | and an upperbound value of | 1100 |  | chart? Press
|  | the range probability is | 0.76881 |  | CTRL and 6
|  | The lowerbound area covers | 0.17671 |  | to show the
|  | and the upperbound area covers | 0.054481 |  | pie chart
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Note: NORM.DIST and NORM.INV functions use the mean (i.e., the PERT expected value) which impliies probabilistic symmetry.
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on M2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on N2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: Use a simple heuristic to quickly create MINIMUM point-estimates. Do this by selecting a percentage in cell B2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and reducing it by the percentage value specified in cell B2. If you want, overwrite any cell formula in column B to manually enter a non-calculated, minimum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell B2, you can do that in the Vlookups worksheet).
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: Use a simple heuristic to quickly create MAXIMUM point-estimates. Do this by selecting a percentage in cell D2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and increasing it by the percentage value specified in cell D2. If you want, overwrite any cell formula in column D to manually enter a non-calculated, maximum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell D2, you can do that in the Vlookups worksheet).
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on O3: You can choose different probabilities by entering a value between 1% and 99%.
Note on A13: Need more than just 10 rows to enter your estimates? Rows 14 through 103 are hidden. Unhide these rows to display 90 more rows like rows 4 through 13.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.

## SPERT® Normal (3-Point entry)
| Statistical PERT® (SPERT®) Normal Edition | [10 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[12 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium confidence |  |  | 36 | 1296 | 150 | 71.07% | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 148.8784 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 1.633e-05 | 2.1987e-05 | 2.9399e-05 | 3.9037e-05 | 5.1477e-05 | 6.7411e-05 | 8.7667e-05 | 0.00011322 | 0.00014521 | 0.00018495 | 0.00023393 | 0.00029384 | 0.00036654 | 0.00045406 | 0.00055858 | 0.00068241 | 0.00082792 | 0.00099751 | 0.0011935 | 0.0014182 | 0.0016734 | 0.001961 | 0.002282 | 0.0026372 | 0.0030267 | 0.0034496 | 0.0039043 | 0.0043885 | 0.0048986 | 0.0054301 | 0.0059776 | 0.0065348 | 0.0070944 | 0.0076487 | 0.0081893 | 0.0087074 | 0.0091942 | 0.009641 | 0.01004 | 0.010382 | 0.010662 | 0.010874 | 0.011014 | 0.011077 | 0.011065 | 0.010975 | 0.010811 | 0.010576 | 0.010275 | 0.0099125 | 0.009497 | 0.0090359 | 0.0085377 | 0.0080112 | 0.0074651 | 0.0069081 | 0.0063484 | 0.0057937 | 0.0052508 | 0.0047259 | 0.004224 | 0.0037493 | 0.0033049 | 0.0028931 | 0.002515 | 0.0021712 | 0.0018614 | 0.0015848 | 0.00134 | 0.0011251 | 0.00093816 | 0.00077686 | 0.00063884 | 0.00052171 | 0.00042311 | 0.00034076 | 0.00027255 | 0.00021648 | 0.00017075 | 0.00013375 | 0.00010405 | 8.0378e-05 | 6.1664e-05 | 4.6979e-05 | 3.5544e-05 | 2.6706e-05 | 1.9927e-05 | 1.4766e-05 | 1.0865e-05 | 7.9401e-06 | 5.7622e-06 | 4.1528e-06 | 2.9722e-06 | 2.1125e-06 | 1.491e-06 | 1.0451e-06 | 7.2752e-07 | 5.0292e-07 | 3.4525e-07 | 2.3537e-07 | 1.5935e-07
2 | 60 | 120 | 240 | 1 | 0.5 | 130 | High confidence |  |  | 20.4853 | 419.6468 | 150 | 83.55% | 103.7471 | 156.2529 | 151.2316 | 147.2408 | 143.8171 | 140.7425 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5037e-11 | 8.7797e-11 | 2.1534e-10 | 5.1695e-10 | 1.2147e-09 | 2.7936e-09 | 6.2885e-09 | 1.3855e-08 | 2.9879e-08 | 6.3069e-08 | 1.303e-07 | 2.6349e-07 | 5.215e-07 | 1.0103e-06 | 1.9157e-06 | 3.5553e-06 | 6.4583e-06 | 1.1483e-05 | 1.9983e-05 | 3.4038e-05 | 5.6748e-05 | 9.2603e-05 | 0.00014791 | 0.00023122 | 0.0003538 | 0.00052988 | 0.00077674 | 0.0011145 | 0.0015651 | 0.0021513 | 0.0028943 | 0.0038113 | 0.0049124 | 0.0061972 | 0.0076522 | 0.0092483 | 0.01094 | 0.012667 | 0.014355 | 0.015923 | 0.017287 | 0.01837 | 0.019107 | 0.019451 | 0.019382 | 0.018903 | 0.018045 | 0.01686 | 0.015419 | 0.013801 | 0.012092 | 0.010369 | 0.008703 | 0.0071497 | 0.0057491 | 0.0045247 | 0.0034855 | 0.002628 | 0.0019395 | 0.0014009 | 0.00099046 | 0.0006854 | 0.00046423 | 0.00030776 | 0.0001997 | 0.00012683 | 7.8844e-05 | 4.7972e-05 | 2.8569e-05 | 1.6653e-05 | 9.5011e-06 | 5.3056e-06 | 2.8999e-06 | 1.5514e-06 | 8.1236e-07 | 4.1635e-07 | 2.0886e-07 | 1.0255e-07 | 4.9284e-08 | 2.3182e-08 | 1.0673e-08 | 4.8097e-09 | 2.1214e-09 | 9.1585e-10 | 3.87e-10 | 1.6006e-10 | 6.4793e-11 | 2.5672e-11 | 9.9562e-12 | 3.7792e-12 | 1.4041e-12 | 5.106e-13 | 1.8174e-13 | 6.3315e-14 | 2.159e-14 | 7.2056e-15 | 2.3539e-15 | 7.5263e-16 | 2.3554e-16 | 7.215e-17 | 2.1632e-17
3 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-high confidence |  |  | 28.2426 | 797.6468 | 150 | 76.06% | 93.8056 | 166.1944 | 159.2716 | 153.7696 | 149.0494 | 144.8105 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5419e-07 | 5.7429e-07 | 9.2071e-07 | 1.4595e-06 | 2.2877e-06 | 3.5457e-06 | 5.4336e-06 | 8.2335e-06 | 1.2336e-05 | 1.8275e-05 | 2.677e-05 | 3.8775e-05 | 5.5531e-05 | 7.8637e-05 | 0.00011011 | 0.00015244 | 0.00020869 | 0.00028248 | 0.00037807 | 0.00050034 | 0.00065472 | 0.00084712 | 0.0010838 | 0.0013709 | 0.0017148 | 0.0021208 | 0.0025935 | 0.0031359 | 0.0037493 | 0.0044324 | 0.0051812 | 0.0059885 | 0.0068439 | 0.0077337 | 0.0086412 | 0.0095468 | 0.010429 | 0.011265 | 0.012031 | 0.012706 | 0.013267 | 0.013698 | 0.013985 | 0.014117 | 0.01409 | 0.013906 | 0.01357 | 0.013094 | 0.012492 | 0.011785 | 0.010993 | 0.010139 | 0.0092464 | 0.0083379 | 0.0074342 | 0.0065542 | 0.0057134 | 0.0049247 | 0.0041972 | 0.003537 | 0.0029473 | 0.0024283 | 0.0019782 | 0.0015935 | 0.0012692 | 0.00099957 | 0.00077838 | 0.00059933 | 0.0004563 | 0.0003435 | 0.00025568 | 0.00018818 | 0.00013695 | 9.8545e-05 | 7.0115e-05 | 4.9327e-05 | 3.4313e-05 | 2.3601e-05 | 1.6051e-05 | 1.0794e-05 | 7.1773e-06 | 4.7189e-06 | 3.0677e-06 | 1.9719e-06 | 1.2533e-06 | 7.8765e-07 | 4.8945e-07 | 3.0073e-07 | 1.8271e-07 | 1.0976e-07 | 6.5193e-08 | 3.8289e-08 | 2.2235e-08 | 1.2768e-08 | 7.2492e-09 | 4.0697e-09 | 2.2591e-09 | 1.24e-09 | 6.7294e-10 | 3.6112e-10 | 1.9161e-10
4 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium confidence |  |  | 36 | 1296 | 150 | 71.07% | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 148.8784 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 1.633e-05 | 2.1987e-05 | 2.9399e-05 | 3.9037e-05 | 5.1477e-05 | 6.7411e-05 | 8.7667e-05 | 0.00011322 | 0.00014521 | 0.00018495 | 0.00023393 | 0.00029384 | 0.00036654 | 0.00045406 | 0.00055858 | 0.00068241 | 0.00082792 | 0.00099751 | 0.0011935 | 0.0014182 | 0.0016734 | 0.001961 | 0.002282 | 0.0026372 | 0.0030267 | 0.0034496 | 0.0039043 | 0.0043885 | 0.0048986 | 0.0054301 | 0.0059776 | 0.0065348 | 0.0070944 | 0.0076487 | 0.0081893 | 0.0087074 | 0.0091942 | 0.009641 | 0.01004 | 0.010382 | 0.010662 | 0.010874 | 0.011014 | 0.011077 | 0.011065 | 0.010975 | 0.010811 | 0.010576 | 0.010275 | 0.0099125 | 0.009497 | 0.0090359 | 0.0085377 | 0.0080112 | 0.0074651 | 0.0069081 | 0.0063484 | 0.0057937 | 0.0052508 | 0.0047259 | 0.004224 | 0.0037493 | 0.0033049 | 0.0028931 | 0.002515 | 0.0021712 | 0.0018614 | 0.0015848 | 0.00134 | 0.0011251 | 0.00093816 | 0.00077686 | 0.00063884 | 0.00052171 | 0.00042311 | 0.00034076 | 0.00027255 | 0.00021648 | 0.00017075 | 0.00013375 | 0.00010405 | 8.0378e-05 | 6.1664e-05 | 4.6979e-05 | 3.5544e-05 | 2.6706e-05 | 1.9927e-05 | 1.4766e-05 | 1.0865e-05 | 7.9401e-06 | 5.7622e-06 | 4.1528e-06 | 2.9722e-06 | 2.1125e-06 | 1.491e-06 | 1.0451e-06 | 7.2752e-07 | 5.0292e-07 | 3.4525e-07 | 2.3537e-07 | 1.5935e-07
5 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-low confidence |  |  | 48.3721 | 2339.8615 | 150 | 66.04% | 68.0086 | 191.9914 | 180.1345 | 170.711 | 162.6265 | 155.3664 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00022281 | 0.00026272 | 0.00030858 | 0.00036106 | 0.00042084 | 0.00048864 | 0.00056518 | 0.0006512 | 0.00074744 | 0.0008546 | 0.00097338 | 0.0011044 | 0.0012483 | 0.0014054 | 0.0015763 | 0.0017612 | 0.0019602 | 0.0021733 | 0.0024004 | 0.002641 | 0.0028945 | 0.0031602 | 0.0034371 | 0.0037239 | 0.0040191 | 0.004321 | 0.0046278 | 0.0049373 | 0.0052474 | 0.0055555 | 0.0058591 | 0.0061556 | 0.0064422 | 0.0067163 | 0.0069752 | 0.0072163 | 0.007437 | 0.0076351 | 0.0078083 | 0.0079548 | 0.008073 | 0.0081615 | 0.0082192 | 0.0082456 | 0.0082403 | 0.0082034 | 0.0081353 | 0.0080368 | 0.0079091 | 0.0077534 | 0.0075717 | 0.0073658 | 0.0071381 | 0.0068908 | 0.0066265 | 0.0063479 | 0.0060577 | 0.0057585 | 0.0054532 | 0.0051441 | 0.004834 | 0.0045251 | 0.0042197 | 0.0039198 | 0.0036273 | 0.0033436 | 0.0030704 | 0.0028086 | 0.0025593 | 0.0023232 | 0.0021007 | 0.0018923 | 0.001698 | 0.0015178 | 0.0013515 | 0.0011988 | 0.0010593 | 0.00093245 | 0.00081762 | 0.00071418 | 0.00062143 | 0.00053865 | 0.00046511 | 0.00040006 | 0.00034279 | 0.00029259 | 0.00024878 | 0.00021072 | 0.0001778 | 0.00014945 | 0.00012513 | 0.00010437 | 8.6719e-05 | 7.1777e-05 | 5.9181e-05 | 4.8608e-05 | 3.9771e-05 | 3.2416e-05 | 2.6319e-05 | 2.1287e-05 | 1.7151e-05
6 | 60 | 120 | 240 | 1 | 0.5 | 130 | Low confidence |  |  | 60.7442 | 3689.8615 | 150 | 62.9% | 52.1531 | 207.8469 | 192.9573 | 181.1236 | 170.9714 | 161.8543 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00066504 | 0.00073828 | 0.00081758 | 0.00090321 | 0.00099536 | 0.0010943 | 0.0012 | 0.0013128 | 0.0014327 | 0.0015598 | 0.001694 | 0.0018352 | 0.0019834 | 0.0021383 | 0.0022997 | 0.0024673 | 0.0026406 | 0.0028192 | 0.0030025 | 0.00319 | 0.003381 | 0.0035746 | 0.0037701 | 0.0039667 | 0.0041633 | 0.004359 | 0.0045528 | 0.0047436 | 0.0049304 | 0.005112 | 0.0052874 | 0.0054556 | 0.0056153 | 0.0057657 | 0.0059056 | 0.0060343 | 0.0061507 | 0.006254 | 0.0063437 | 0.0064189 | 0.0064792 | 0.0065241 | 0.0065534 | 0.0065667 | 0.006564 | 0.0065454 | 0.0065109 | 0.0064608 | 0.0063954 | 0.0063154 | 0.0062211 | 0.0061133 | 0.0059927 | 0.0058602 | 0.0057167 | 0.0055631 | 0.0054004 | 0.0052297 | 0.0050521 | 0.0048686 | 0.0046804 | 0.0044884 | 0.0042939 | 0.0040978 | 0.0039011 | 0.0037048 | 0.0035098 | 0.003317 | 0.0031271 | 0.0029409 | 0.0027591 | 0.0025822 | 0.0024108 | 0.0022452 | 0.0020859 | 0.0019332 | 0.0017874 | 0.0016485 | 0.0015167 | 0.001392 | 0.0012745 | 0.001164 | 0.0010605 | 0.00096391 | 0.00087395 | 0.00079046 | 0.0007132 | 0.00064193 | 0.00057637 | 0.00051624 | 0.00046127 | 0.00041114 | 0.00036557 | 0.00032425 | 0.00028691 | 0.00025325 | 0.00022299 | 0.00019587 | 0.00017163 | 0.00015002 | 0.00013081
7 | 60 | 120 | 240 | 1 | 0.5 | 130 | Guesstimate |  |  | 73.1163 | 5346 | 150 | 60.78% | 36.2976 | 223.7024 | 205.7802 | 191.5363 | 179.3162 | 168.3422 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.0011232 | 0.0012071 | 0.0012952 | 0.0013874 | 0.0014836 | 0.0015839 | 0.001688 | 0.001796 | 0.0019077 | 0.0020229 | 0.0021415 | 0.0022632 | 0.0023878 | 0.002515 | 0.0026445 | 0.002776 | 0.0029092 | 0.0030436 | 0.0031789 | 0.0033147 | 0.0034504 | 0.0035856 | 0.0037198 | 0.0038526 | 0.0039834 | 0.0041117 | 0.004237 | 0.0043588 | 0.0044766 | 0.0045898 | 0.0046979 | 0.0048005 | 0.0048971 | 0.0049872 | 0.0050705 | 0.0051465 | 0.0052148 | 0.0052751 | 0.0053272 | 0.0053707 | 0.0054055 | 0.0054313 | 0.0054481 | 0.0054558 | 0.0054542 | 0.0054435 | 0.0054237 | 0.0053949 | 0.0053572 | 0.0053108 | 0.0052559 | 0.0051929 | 0.005122 | 0.0050435 | 0.0049579 | 0.0048656 | 0.004767 | 0.0046625 | 0.0045526 | 0.0044378 | 0.0043187 | 0.0041956 | 0.0040693 | 0.0039401 | 0.0038085 | 0.0036752 | 0.0035406 | 0.0034052 | 0.0032694 | 0.0031338 | 0.0029987 | 0.0028647 | 0.002732 | 0.0026011 | 0.0024723 | 0.0023459 | 0.0022223 | 0.0021016 | 0.0019841 | 0.00187 | 0.0017596 | 0.0016529 | 0.00155 | 0.0014511 | 0.0013562 | 0.0012654 | 0.0011787 | 0.0010961 | 0.0010175 | 0.00094303 | 0.00087251 | 0.00080591 | 0.00074314 | 0.0006841 | 0.0006287 | 0.00057681 | 0.00052831 | 0.00048308 | 0.00044098 | 0.00040187 | 0.00036561
8 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
11 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 420 | 840 | 1680 |  |  | 910 |  |  |  | 123.2275 | 15185.0166 | 1050 | 87.2% | 521.7404 | 1298.2596 | 1223.9985 | 1164.9781 | 1114.3438 | 1068.8727 | 540.3175 | 547.6379 | 554.9584 | 562.2788 | 569.5993 | 576.9197 | 584.2402 | 591.5606 | 598.8811 | 606.2015 | 613.522 | 620.8424 | 628.1628 | 635.4833 | 642.8037 | 650.1242 | 657.4446 | 664.7651 | 672.0855 | 679.406 | 686.7264 | 694.0469 | 701.3673 | 708.6877 | 716.0082 | 723.3286 | 730.6491 | 737.9695 | 745.29 | 752.6104 | 759.9309 | 767.2513 | 774.5718 | 781.8922 | 789.2126 | 796.5331 | 803.8535 | 811.174 | 818.4944 | 825.8149 | 833.1353 | 840.4558 | 847.7762 | 855.0967 | 862.4171 | 869.7375 | 877.058 | 884.3784 | 891.6989 | 899.0193 | 906.3398 | 913.6602 | 920.9807 | 928.3011 | 935.6216 | 942.942 | 950.2625 | 957.5829 | 964.9033 | 972.2238 | 979.5442 | 986.8647 | 994.1851 | 1001.5056 | 1008.826 | 1016.1465 | 1023.4669 | 1030.7874 | 1038.1078 | 1045.4282 | 1052.7487 | 1060.0691 | 1067.3896 | 1074.71 | 1082.0305 | 1089.3509 | 1096.6714 | 1103.9918 | 1111.3123 | 1118.6327 | 1125.9531 | 1133.2736 | 1140.594 | 1147.9145 | 1155.2349 | 1162.5554 | 1169.8758 | 1177.1963 | 1184.5167 | 1191.8372 | 1199.1576 | 1206.478 | 1213.7985 | 1221.1189 | 1228.4394 | 1235.7598 | 1243.0803 | 1250.4007 | 1257.7212 | 1265.0416 | 1272.3621 | 1279.6825 | 4.2905e-05 | 5.1005e-05 | 6.042e-05 | 7.132e-05 | 8.3891e-05 | 9.8329e-05 | 0.00011485 | 0.00013367 | 0.00015502 | 0.00017916 | 0.00020632 | 0.00023676 | 0.00027074 | 0.00030851 | 0.0003503 | 0.00039635 | 0.00044688 | 0.00050208 | 0.0005621 | 0.00062709 | 0.00069712 | 0.00077224 | 0.00085245 | 0.00093767 | 0.0010278 | 0.0011226 | 0.0012218 | 0.0013251 | 0.0014321 | 0.0015422 | 0.001655 | 0.0017698 | 0.0018859 | 0.0020025 | 0.0021188 | 0.002234 | 0.0023471 | 0.0024573 | 0.0025636 | 0.0026651 | 0.0027608 | 0.0028499 | 0.0029315 | 0.0030049 | 0.0030692 | 0.0031238 | 0.0031682 | 0.0032019 | 0.0032246 | 0.003236 | 0.003236 | 0.0032246 | 0.0032019 | 0.0031682 | 0.0031238 | 0.0030692 | 0.0030049 | 0.0029315 | 0.0028499 | 0.0027608 | 0.0026651 | 0.0025636 | 0.0024573 | 0.0023471 | 0.002234 | 0.0021188 | 0.0020025 | 0.0018859 | 0.0017698 | 0.001655 | 0.0015422 | 0.0014321 | 0.0013251 | 0.0012218 | 0.0011226 | 0.0010278 | 0.00093767 | 0.00085245 | 0.00077224 | 0.00069712 | 0.00062709 | 0.0005621 | 0.00050208 | 0.00044688 | 0.00039635 | 0.0003503 | 0.00030851 | 0.00027074 | 0.00023676 | 0.00020632 | 0.00017916 | 0.00015502 | 0.00013367 | 0.00011485 | 9.8329e-05 | 8.3891e-05 | 7.132e-05 | 6.042e-05 | 5.1005e-05 | 4.2905e-05 | 3.5965e-05
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 76.74% | 752.0776 | 1067.9224 | 1037.7171 | 1013.7109 | 993.1157 | 974.6206 | [102 empty] | 4.2905e-05 | 5.1005e-05 | 6.042e-05 | 7.132e-05 | 8.3891e-05 | 9.8329e-05 | 0.00011485 | 0.00013367 | 0.00015502 | 0.00017916 | 0.00020632 | 0.00023676 | 0.00027074 | 0.00030851 | 0.0003503 | 0.00039635 | 0.00044688 | 0.00050208 | 0.0005621 | 0.00062709 | 0.00069712 | 0.00077224 | 0.00085245 | 0.00093767 | 0.0010278 | 0.0011226 | 0.0012218 | 0.0013251 | 0.0014321 | 0.0015422 | 0.001655 | 0.0017698 | 0.0018859 | 0.0020025 | 0.0021188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002234 | 0.0023471 | 0.0024573 | 0.0025636 | 0.0026651 | 0.0027608 | 0.0028499 | 0.0029315 | 0.0030049 | 0.0030692 | 0.0031238 | 0.0031682 | 0.0032019 | 0.0032246 | 0.003236 | 0.003236 | 0.0032246 | 0.0032019 | 0.0031682 | 0.0031238 | 0.0030692 | 0.0030049 | 0.0029315 | 0.0028499 | 0.0027608 | 0.0026651 | 0.0025636 | 0.0024573 | 0.0023471 | 0.002234 | 0.0021188 | 0.0020025 | 0.0018859 | 0.0017698 | 0.001655 | 0.0015422 | 0.0014321 | 0.0013251 | 0.0012218 | 0.0011226 | 0.0010278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 0.8 | confidence | [117 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00093767 | 0.00085245 | 0.00077224 | 0.00069712 | 0.00062709 | 0.0005621 | 0.00050208 | 0.00044688 | 0.00039635 | 0.0003503 | 0.00030851 | 0.00027074 | 0.00023676 | 0.00020632 | 0.00017916 | 0.00015502 | 0.00013367 | 0.00011485 | 9.8329e-05 | 8.3891e-05 | 7.132e-05 | 6.042e-05 | 5.1005e-05 | 4.2905e-05 | 3.5965e-05
|  | The lowerbound threshold is | 752.0776 | [118 empty] | 4.2905e-05 | 5.1005e-05 | 6.042e-05 | 7.132e-05 | 8.3891e-05 | 9.8329e-05 | 0.00011485 | 0.00013367 | 0.00015502 | 0.00017916 | 0.00020632 | 0.00023676 | 0.00027074 | 0.00030851 | 0.0003503 | 0.00039635 | 0.00044688 | 0.00050208 | 0.0005621 | 0.00062709 | 0.00069712 | 0.00077224 | 0.00085245 | 0.00093767 | 0.0010278 | 0.0011226 | 0.0012218 | 0.0013251 | 0.0014321 | 0.0015422 | 0.001655 | 0.0017698 | 0.0018859 | 0.0020025 | 0.0021188 | 0.002234 | 0.0023471 | 0.0024573 | 0.0025636 | 0.0026651 | 0.0027608 | 0.0028499 | 0.0029315 | 0.0030049 | 0.0030692 | 0.0031238 | 0.0031682 | 0.0032019 | 0.0032246 | 0.003236 | 0.003236 | 0.0032246 | 0.0032019 | 0.0031682 | 0.0031238 | 0.0030692 | 0.0030049 | 0.0029315 | 0.0028499 | 0.0027608 | 0.0026651 | 0.0025636 | 0.0024573 | 0.0023471 | 0.002234 | 0.0021188 | 0.0020025 | 0.0018859 | 0.0017698 | 0.001655 | 0.0015422 | 0.0014321 | 0.0013251 | 0.0012218 | 0.0011226 | 0.0010278 | 0.00093767 | 0.00085245 | 0.00077224 | 0.00069712 | 0.00062709 | 0.0005621 | 0.00050208 | 0.00044688 | 0.00039635 | 0.0003503 | 0.00030851 | 0.00027074 | 0.00023676 | 0.00020632 | 0.00017916 | 0.00015502 | 0.00013367 | 0.00011485 | 9.8329e-05 | 8.3891e-05 | 7.132e-05 | 6.042e-05 | 5.1005e-05 | 4.2905e-05 | 3.5965e-05
|  | and the upperbound threshold is | 1067.9224
|  | Between a lowerbound value of | 800 |  | Miss the pie
|  | and an upperbound value of | 1100 |  | chart? Press
|  | the range probability is | 0.75243 |  | CTRL and 6
|  | The lowerbound area covers | 0.18602 |  | to show the
|  | and the upperbound area covers | 0.061553 |  | pie chart
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Note: NORM.DIST and NORM.INV functions use the mean (i.e., the PERT expected value) which impliies probabilistic symmetry.
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on M2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on N2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on O3: You can choose different probabilities by entering a value between 1% and 99%.
Note on A13: Need more than just 10 rows to enter your estimates? Rows 14 through 103 are hidden. Unhide these rows to display 90 more rows like rows 4 through 13.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.

## SPERT® Normal (Mixed entry)
| Statistical PERT® (SPERT®) Normal Edition | [14 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
|  |  | -0.5 | < Heuristics > | 1 | [10 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Min % | Min point | Minimum | Most Likely | Maximum | Max point | Max % |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns Y through HS are hidden; they are used to create Sparklines and the bell-curve ball chart
1 |  |  | 60 | 120 | 240 |  |  | 1 | 0.5 | 130 | Near certainty |  |  | 12.7279 | 162 | 150 | 94.19% | 113.6885 | 146.3115 | 143.1916 | 140.7121 | 138.5849 | 136.6745 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 6.9685e-25 | 7.5266e-24 | 7.6901e-23 | 7.4325e-22 | 6.7954e-21 | 5.8771e-20 | 4.8082e-19 | 3.7212e-18 | 2.7243e-17 | 1.8866e-16 | 1.236e-15 | 7.6593e-15 | 4.49e-14 | 2.4899e-13 | 1.3061e-12 | 6.4812e-12 | 3.0423e-11 | 1.3509e-10 | 5.6743e-10 | 2.2547e-09 | 8.4746e-09 | 3.0132e-08 | 1.0135e-07 | 3.2245e-07 | 9.705e-07 | 2.7631e-06 | 7.4417e-06 | 1.8959e-05 | 4.5691e-05 | 0.00010417 | 0.00022464 | 0.00045827 | 0.00088437 | 0.0016144 | 0.0027878 | 0.004554 | 0.0070371 | 0.010286 | 0.014223 | 0.018605 | 0.02302 | 0.026945 | 0.029834 | 0.031247 | 0.030959 | 0.029016 | 0.025726 | 0.021576 | 0.017117 | 0.012846 | 0.0091198 | 0.0061245 | 0.0038907 | 0.0023381 | 0.0013291 | 0.00071473 | 0.00036357 | 0.00017495 | 7.9636e-05 | 3.4291e-05 | 1.3967e-05 | 5.3818e-06 | 1.9616e-06 | 6.7634e-07 | 2.206e-07 | 6.8061e-08 | 1.9864e-08 | 5.4843e-09 | 1.4323e-09 | 3.5386e-10 | 8.2698e-11 | 1.8282e-11 | 3.8233e-12 | 7.5635e-13 | 1.4154e-13 | 2.5056e-14 | 4.1957e-15 | 6.6463e-16 | 9.9592e-17 | 1.4117e-17 | 1.8929e-18 | 2.401e-19 | 2.8809e-20 | 3.2699e-21 | 3.5109e-22 | 3.5659e-23 | 3.426e-24 | 3.1138e-25 | 2.6771e-26 | 2.1772e-27 | 1.675e-28 | 1.219e-29 | 8.392e-31 | 5.4651e-32 | 3.3667e-33 | 1.9619e-34 | 1.0815e-35 | 5.6397e-37 | 2.7819e-38 | 1.2981e-39 | 5.73e-41
2 |  |  | 60 | 120 | 240 |  |  | 1 | 0.5 | 130 | High confidence |  |  | 20.4853 | 419.6468 | 150 | 83.55% | 103.7471 | 156.2529 | 151.2316 | 147.2408 | 143.8171 | 140.7425 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5037e-11 | 8.7797e-11 | 2.1534e-10 | 5.1695e-10 | 1.2147e-09 | 2.7936e-09 | 6.2885e-09 | 1.3855e-08 | 2.9879e-08 | 6.3069e-08 | 1.303e-07 | 2.6349e-07 | 5.215e-07 | 1.0103e-06 | 1.9157e-06 | 3.5553e-06 | 6.4583e-06 | 1.1483e-05 | 1.9983e-05 | 3.4038e-05 | 5.6748e-05 | 9.2603e-05 | 0.00014791 | 0.00023122 | 0.0003538 | 0.00052988 | 0.00077674 | 0.0011145 | 0.0015651 | 0.0021513 | 0.0028943 | 0.0038113 | 0.0049124 | 0.0061972 | 0.0076522 | 0.0092483 | 0.01094 | 0.012667 | 0.014355 | 0.015923 | 0.017287 | 0.01837 | 0.019107 | 0.019451 | 0.019382 | 0.018903 | 0.018045 | 0.01686 | 0.015419 | 0.013801 | 0.012092 | 0.010369 | 0.008703 | 0.0071497 | 0.0057491 | 0.0045247 | 0.0034855 | 0.002628 | 0.0019395 | 0.0014009 | 0.00099046 | 0.0006854 | 0.00046423 | 0.00030776 | 0.0001997 | 0.00012683 | 7.8844e-05 | 4.7972e-05 | 2.8569e-05 | 1.6653e-05 | 9.5011e-06 | 5.3056e-06 | 2.8999e-06 | 1.5514e-06 | 8.1236e-07 | 4.1635e-07 | 2.0886e-07 | 1.0255e-07 | 4.9284e-08 | 2.3182e-08 | 1.0673e-08 | 4.8097e-09 | 2.1214e-09 | 9.1585e-10 | 3.87e-10 | 1.6006e-10 | 6.4793e-11 | 2.5672e-11 | 9.9562e-12 | 3.7792e-12 | 1.4041e-12 | 5.106e-13 | 1.8174e-13 | 6.3315e-14 | 2.159e-14 | 7.2056e-15 | 2.3539e-15 | 7.5263e-16 | 2.3554e-16 | 7.215e-17 | 2.1632e-17
3 |  |  | 60 | 120 | 240 |  |  | 1 | 0.5 | 130 | Medium-high confidence |  |  | 28.2426 | 797.6468 | 150 | 76.06% | 93.8056 | 166.1944 | 159.2716 | 153.7696 | 149.0494 | 144.8105 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5419e-07 | 5.7429e-07 | 9.2071e-07 | 1.4595e-06 | 2.2877e-06 | 3.5457e-06 | 5.4336e-06 | 8.2335e-06 | 1.2336e-05 | 1.8275e-05 | 2.677e-05 | 3.8775e-05 | 5.5531e-05 | 7.8637e-05 | 0.00011011 | 0.00015244 | 0.00020869 | 0.00028248 | 0.00037807 | 0.00050034 | 0.00065472 | 0.00084712 | 0.0010838 | 0.0013709 | 0.0017148 | 0.0021208 | 0.0025935 | 0.0031359 | 0.0037493 | 0.0044324 | 0.0051812 | 0.0059885 | 0.0068439 | 0.0077337 | 0.0086412 | 0.0095468 | 0.010429 | 0.011265 | 0.012031 | 0.012706 | 0.013267 | 0.013698 | 0.013985 | 0.014117 | 0.01409 | 0.013906 | 0.01357 | 0.013094 | 0.012492 | 0.011785 | 0.010993 | 0.010139 | 0.0092464 | 0.0083379 | 0.0074342 | 0.0065542 | 0.0057134 | 0.0049247 | 0.0041972 | 0.003537 | 0.0029473 | 0.0024283 | 0.0019782 | 0.0015935 | 0.0012692 | 0.00099957 | 0.00077838 | 0.00059933 | 0.0004563 | 0.0003435 | 0.00025568 | 0.00018818 | 0.00013695 | 9.8545e-05 | 7.0115e-05 | 4.9327e-05 | 3.4313e-05 | 2.3601e-05 | 1.6051e-05 | 1.0794e-05 | 7.1773e-06 | 4.7189e-06 | 3.0677e-06 | 1.9719e-06 | 1.2533e-06 | 7.8765e-07 | 4.8945e-07 | 3.0073e-07 | 1.8271e-07 | 1.0976e-07 | 6.5193e-08 | 3.8289e-08 | 2.2235e-08 | 1.2768e-08 | 7.2492e-09 | 4.0697e-09 | 2.2591e-09 | 1.24e-09 | 6.7294e-10 | 3.6112e-10 | 1.9161e-10
4 | -0.1 |  | 108 | 120 | 144 |  | 0.2 | 1 | 0.5 | 122 | Medium confidence |  |  | 7.2 | 51.84 | 150 | 99.99% | 112.7728 | 131.2272 | 129.4623 | 128.0597 | 126.8563 | 125.7757 | 0.6 | 96 | 96.6 | 97.2 | 97.8 | 98.4 | 99 | 99.6 | 100.2 | 100.8 | 101.4 | 102 | 102.6 | 103.2 | 103.8 | 104.4 | 105 | 105.6 | 106.2 | 106.8 | 107.4 | 108 | 108.6 | 109.2 | 109.8 | 110.4 | 111 | 111.6 | 112.2 | 112.8 | 113.4 | 114 | 114.6 | 115.2 | 115.8 | 116.4 | 117 | 117.6 | 118.2 | 118.8 | 119.4 | 120 | 120.6 | 121.2 | 121.8 | 122.4 | 123 | 123.6 | 124.2 | 124.8 | 125.4 | 126 | 126.6 | 127.2 | 127.8 | 128.4 | 129 | 129.6 | 130.2 | 130.8 | 131.4 | 132 | 132.6 | 133.2 | 133.8 | 134.4 | 135 | 135.6 | 136.2 | 136.8 | 137.4 | 138 | 138.6 | 139.2 | 139.8 | 140.4 | 141 | 141.6 | 142.2 | 142.8 | 143.4 | 144 | 144.6 | 145.2 | 145.8 | 146.4 | 147 | 147.6 | 148.2 | 148.8 | 149.4 | 150 | 150.6 | 151.2 | 151.8 | 152.4 | 153 | 153.6 | 154.2 | 154.8 | 155.4 | 156 | 8.1649e-05 | 0.00010993 | 0.00014699 | 0.00019519 | 0.00025739 | 0.00033706 | 0.00043834 | 0.0005661 | 0.00072605 | 0.00092474 | 0.0011697 | 0.0014692 | 0.0018327 | 0.0022703 | 0.0027929 | 0.003412 | 0.0041396 | 0.0049875 | 0.0059676 | 0.0070908 | 0.0083671 | 0.0098048 | 0.01141 | 0.013186 | 0.015133 | 0.017248 | 0.019522 | 0.021942 | 0.024493 | 0.02715 | 0.029888 | 0.032674 | 0.035472 | 0.038244 | 0.040947 | 0.043537 | 0.045971 | 0.048205 | 0.050198 | 0.051911 | 0.053312 | 0.054371 | 0.055068 | 0.055387 | 0.055323 | 0.054877 | 0.054057 | 0.052882 | 0.051373 | 0.049563 | 0.047485 | 0.04518 | 0.042689 | 0.040056 | 0.037325 | 0.03454 | 0.031742 | 0.028968 | 0.026254 | 0.02363 | 0.02112 | 0.018747 | 0.016525 | 0.014465 | 0.012575 | 0.010856 | 0.0093072 | 0.0079241 | 0.0066998 | 0.0056255 | 0.0046908 | 0.0038843 | 0.0031942 | 0.0026085 | 0.0021155 | 0.0017038 | 0.0013627 | 0.0010824 | 0.00085376 | 0.00066877 | 0.00052024 | 0.00040189 | 0.00030832 | 0.0002349 | 0.00017772 | 0.00013353 | 9.9634e-05 | 7.3828e-05 | 5.4327e-05 | 3.9701e-05 | 2.8811e-05 | 2.0764e-05 | 1.4861e-05 | 1.0562e-05 | 7.4552e-06 | 5.2257e-06 | 3.6376e-06 | 2.5146e-06 | 1.7262e-06 | 1.1769e-06 | 7.9676e-07
5 | -0.25 |  | 90 | 120 | 160 | 160 |  | 1 | 0.75 | 121.6667 | Medium-low confidence |  |  | 18.8114 | 353.8679 | 150 | 93.4% | 97.5589 | 145.7744 | 141.1634 | 137.4987 | 134.3547 | 131.5314 | 1.1667 | 66.6667 | 67.8333 | 69 | 70.1667 | 71.3333 | 72.5 | 73.6667 | 74.8333 | 76 | 77.1667 | 78.3333 | 79.5 | 80.6667 | 81.8333 | 83 | 84.1667 | 85.3333 | 86.5 | 87.6667 | 88.8333 | 90 | 91.1667 | 92.3333 | 93.5 | 94.6667 | 95.8333 | 97 | 98.1667 | 99.3333 | 100.5 | 101.6667 | 102.8333 | 104 | 105.1667 | 106.3333 | 107.5 | 108.6667 | 109.8333 | 111 | 112.1667 | 113.3333 | 114.5 | 115.6667 | 116.8333 | 118 | 119.1667 | 120.3333 | 121.5 | 122.6667 | 123.8333 | 125 | 126.1667 | 127.3333 | 128.5 | 129.6667 | 130.8333 | 132 | 133.1667 | 134.3333 | 135.5 | 136.6667 | 137.8333 | 139 | 140.1667 | 141.3333 | 142.5 | 143.6667 | 144.8333 | 146 | 147.1667 | 148.3333 | 149.5 | 150.6667 | 151.8333 | 153 | 154.1667 | 155.3333 | 156.5 | 157.6667 | 158.8333 | 160 | 161.1667 | 162.3333 | 163.5 | 164.6667 | 165.8333 | 167 | 168.1667 | 169.3333 | 170.5 | 171.6667 | 172.8333 | 174 | 175.1667 | 176.3333 | 177.5 | 178.6667 | 179.8333 | 181 | 182.1667 | 183.3333 | 0.00029528 | 0.0003533 | 0.00042111 | 0.00049999 | 0.00059138 | 0.00069679 | 0.00081783 | 0.00095622 | 0.0011137 | 0.0012922 | 0.0014935 | 0.0017196 | 0.0019723 | 0.0022534 | 0.0025647 | 0.0029078 | 0.0032841 | 0.0036949 | 0.0041412 | 0.0046235 | 0.0051422 | 0.0056971 | 0.0062876 | 0.0069128 | 0.0075709 | 0.0082598 | 0.0089769 | 0.0097187 | 0.010481 | 0.011261 | 0.012051 | 0.012848 | 0.013645 | 0.014435 | 0.015213 | 0.015971 | 0.016703 | 0.017401 | 0.018058 | 0.018668 | 0.019225 | 0.019723 | 0.020156 | 0.020519 | 0.020808 | 0.021021 | 0.021154 | 0.021207 | 0.021178 | 0.021067 | 0.020877 | 0.020609 | 0.020267 | 0.019853 | 0.019374 | 0.018833 | 0.018238 | 0.017593 | 0.016906 | 0.016183 | 0.015432 | 0.014659 | 0.013872 | 0.013076 | 0.012279 | 0.011486 | 0.010703 | 0.0099347 | 0.0091864 | 0.008462 | 0.0077647 | 0.0070975 | 0.0064628 | 0.0058622 | 0.005297 | 0.004768 | 0.0042753 | 0.0038188 | 0.0033979 | 0.0030118 | 0.0026594 | 0.0023392 | 0.0020496 | 0.001789 | 0.0015555 | 0.0013473 | 0.0011625 | 0.00099919 | 0.00085553 | 0.00072971 | 0.00062 | 0.00052477 | 0.00044245 | 0.00037162 | 0.00031093 | 0.00025915 | 0.00021517 | 0.00017796 | 0.00014662 | 0.00012034 | 9.8391e-05
6 |  | 40 | 40 | 120 | 200 | 200 |  | 1 | 1 | 120 | Low confidence |  |  | 53.9949 | 2915.4461 | 150 | 71.08% | 50.8028 | 189.1972 | 175.9621 | 165.4432 | 156.419 | 148.3149 | 2.6667 | -13.3333 | -10.6667 | -8 | -5.3333 | -2.6667 | 2.6645e-15 | 2.6667 | 5.3333 | 8 | 10.6667 | 13.3333 | 16 | 18.6667 | 21.3333 | 24 | 26.6667 | 29.3333 | 32 | 34.6667 | 37.3333 | 40 | 42.6667 | 45.3333 | 48 | 50.6667 | 53.3333 | 56 | 58.6667 | 61.3333 | 64 | 66.6667 | 69.3333 | 72 | 74.6667 | 77.3333 | 80 | 82.6667 | 85.3333 | 88 | 90.6667 | 93.3333 | 96 | 98.6667 | 101.3333 | 104 | 106.6667 | 109.3333 | 112 | 114.6667 | 117.3333 | 120 | 122.6667 | 125.3333 | 128 | 130.6667 | 133.3333 | 136 | 138.6667 | 141.3333 | 144 | 146.6667 | 149.3333 | 152 | 154.6667 | 157.3333 | 160 | 162.6667 | 165.3333 | 168 | 170.6667 | 173.3333 | 176 | 178.6667 | 181.3333 | 184 | 186.6667 | 189.3333 | 192 | 194.6667 | 197.3333 | 200 | 202.6667 | 205.3333 | 208 | 210.6667 | 213.3333 | 216 | 218.6667 | 221.3333 | 224 | 226.6667 | 229.3333 | 232 | 234.6667 | 237.3333 | 240 | 242.6667 | 245.3333 | 248 | 250.6667 | 253.3333 | 0.0003503 | 0.00039525 | 0.00044489 | 0.00049954 | 0.00055953 | 0.0006252 | 0.00069688 | 0.00077489 | 0.00085953 | 0.00095109 | 0.0010498 | 0.001156 | 0.0012698 | 0.0013915 | 0.001521 | 0.0016586 | 0.0018042 | 0.0019578 | 0.0021193 | 0.0022886 | 0.0024653 | 0.0026493 | 0.00284 | 0.003037 | 0.0032398 | 0.0034477 | 0.00366 | 0.0038759 | 0.0040946 | 0.004315 | 0.0045363 | 0.0047572 | 0.0049768 | 0.0051939 | 0.0054071 | 0.0056155 | 0.0058176 | 0.0060124 | 0.0061985 | 0.0063749 | 0.0065402 | 0.0066935 | 0.0068338 | 0.0069599 | 0.0070712 | 0.0071667 | 0.0072457 | 0.0073079 | 0.0073526 | 0.0073795 | 0.0073885 | 0.0073795 | 0.0073526 | 0.0073079 | 0.0072457 | 0.0071667 | 0.0070712 | 0.0069599 | 0.0068338 | 0.0066935 | 0.0065402 | 0.0063749 | 0.0061985 | 0.0060124 | 0.0058176 | 0.0056155 | 0.0054071 | 0.0051939 | 0.0049768 | 0.0047572 | 0.0045363 | 0.004315 | 0.0040946 | 0.0038759 | 0.00366 | 0.0034477 | 0.0032398 | 0.003037 | 0.00284 | 0.0026493 | 0.0024653 | 0.0022886 | 0.0021193 | 0.0019578 | 0.0018042 | 0.0016586 | 0.001521 | 0.0013915 | 0.0012698 | 0.001156 | 0.0010498 | 0.00095109 | 0.00085953 | 0.00077489 | 0.00069688 | 0.0006252 | 0.00055953 | 0.00049954 | 0.00044489 | 0.00039525 | 0.0003503
7 |  | 80 | 80 | 120 | 210 |  | 0.75 | 1 | 0.44444 | 128.3333 | Guesstimate |  |  | 52.8062 | 2788.5 | 150 | 65.92% | 60.6594 | 196.0073 | 183.0635 | 172.7762 | 163.9506 | 156.025 | 2.1667 | 36.6667 | 38.8333 | 41 | 43.1667 | 45.3333 | 47.5 | 49.6667 | 51.8333 | 54 | 56.1667 | 58.3333 | 60.5 | 62.6667 | 64.8333 | 67 | 69.1667 | 71.3333 | 73.5 | 75.6667 | 77.8333 | 80 | 82.1667 | 84.3333 | 86.5 | 88.6667 | 90.8333 | 93 | 95.1667 | 97.3333 | 99.5 | 101.6667 | 103.8333 | 106 | 108.1667 | 110.3333 | 112.5 | 114.6667 | 116.8333 | 119 | 121.1667 | 123.3333 | 125.5 | 127.6667 | 129.8333 | 132 | 134.1667 | 136.3333 | 138.5 | 140.6667 | 142.8333 | 145 | 147.1667 | 149.3333 | 151.5 | 153.6667 | 155.8333 | 158 | 160.1667 | 162.3333 | 164.5 | 166.6667 | 168.8333 | 171 | 173.1667 | 175.3333 | 177.5 | 179.6667 | 181.8333 | 184 | 186.1667 | 188.3333 | 190.5 | 192.6667 | 194.8333 | 197 | 199.1667 | 201.3333 | 203.5 | 205.6667 | 207.8333 | 210 | 212.1667 | 214.3333 | 216.5 | 218.6667 | 220.8333 | 223 | 225.1667 | 227.3333 | 229.5 | 231.6667 | 233.8333 | 236 | 238.1667 | 240.3333 | 242.5 | 244.6667 | 246.8333 | 249 | 251.1667 | 253.3333 | 0.0016745 | 0.0017966 | 0.0019243 | 0.0020577 | 0.0021967 | 0.002341 | 0.0024907 | 0.0026454 | 0.0028051 | 0.0029694 | 0.003138 | 0.0033106 | 0.0034868 | 0.0036663 | 0.0038485 | 0.0040329 | 0.0042191 | 0.0044064 | 0.0045943 | 0.0047822 | 0.0049694 | 0.0051553 | 0.005339 | 0.0055201 | 0.0056977 | 0.0058711 | 0.0060396 | 0.0062024 | 0.006359 | 0.0065086 | 0.0066504 | 0.0067839 | 0.0069085 | 0.0070235 | 0.0071284 | 0.0072227 | 0.007306 | 0.0073778 | 0.0074377 | 0.0074856 | 0.007521 | 0.007544 | 0.0075542 | 0.0075518 | 0.0075366 | 0.0075089 | 0.0074686 | 0.0074161 | 0.0073516 | 0.0072753 | 0.0071878 | 0.0070893 | 0.0069804 | 0.0068617 | 0.0067336 | 0.0065968 | 0.0064519 | 0.0062996 | 0.0061405 | 0.0059754 | 0.0058049 | 0.0056298 | 0.0054508 | 0.0052686 | 0.005084 | 0.0048976 | 0.00471 | 0.004522 | 0.0043343 | 0.0041473 | 0.0039617 | 0.0037781 | 0.0035969 | 0.0034186 | 0.0032438 | 0.0030726 | 0.0029056 | 0.0027431 | 0.0025853 | 0.0024325 | 0.0022849 | 0.0021426 | 0.0020058 | 0.0018745 | 0.0017489 | 0.001629 | 0.0015148 | 0.0014062 | 0.0013032 | 0.0012057 | 0.0011136 | 0.0010268 | 0.00094519 | 0.0008686 | 0.00079688 | 0.00072985 | 0.00066733 | 0.00060915 | 0.0005551 | 0.00050499 | 0.00045864
8 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
11 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 498 | 840 | 1434 |  |  |  |  | 882 |  |  |  | 86.5387 | 7488.9476 | 1050 | 97.39% | 633.0351 | 1130.9649 | 1083.3462 | 1045.5004 | 1013.032 | 983.8744 | 622.3839 | 627.5248 | 632.6657 | 637.8066 | 642.9475 | 648.0884 | 653.2294 | 658.3703 | 663.5112 | 668.6521 | 673.793 | 678.9339 | 684.0748 | 689.2158 | 694.3567 | 699.4976 | 704.6385 | 709.7794 | 714.9203 | 720.0612 | 725.2021 | 730.3431 | 735.484 | 740.6249 | 745.7658 | 750.9067 | 756.0476 | 761.1885 | 766.3295 | 771.4704 | 776.6113 | 781.7522 | 786.8931 | 792.034 | 797.1749 | 802.3158 | 807.4568 | 812.5977 | 817.7386 | 822.8795 | 828.0204 | 833.1613 | 838.3022 | 843.4432 | 848.5841 | 853.725 | 858.8659 | 864.0068 | 869.1477 | 874.2886 | 879.4295 | 884.5705 | 889.7114 | 894.8523 | 899.9932 | 905.1341 | 910.275 | 915.4159 | 920.5568 | 925.6978 | 930.8387 | 935.9796 | 941.1205 | 946.2614 | 951.4023 | 956.5432 | 961.6842 | 966.8251 | 971.966 | 977.1069 | 982.2478 | 987.3887 | 992.5296 | 997.6705 | 1002.8115 | 1007.9524 | 1013.0933 | 1018.2342 | 1023.3751 | 1028.516 | 1033.6569 | 1038.7979 | 1043.9388 | 1049.0797 | 1054.2206 | 1059.3615 | 1064.5024 | 1069.6433 | 1074.7842 | 1079.9252 | 1085.0661 | 1090.207 | 1095.3479 | 1100.4888 | 1105.6297 | 1110.7706 | 1115.9116 | 1121.0525 | 1126.1934 | 1131.3343 | 1136.4752 | 1141.6161 | 6.1095e-05 | 7.2629e-05 | 8.6035e-05 | 0.00010156 | 0.00011946 | 0.00014002 | 0.00016354 | 0.00019034 | 0.00022075 | 0.00025511 | 0.00029379 | 0.00033714 | 0.00038552 | 0.0004393 | 0.00049881 | 0.00056439 | 0.00063634 | 0.00071494 | 0.00080041 | 0.00089294 | 0.00099267 | 0.0010996 | 0.0012138 | 0.0013352 | 0.0014635 | 0.0015985 | 0.0017398 | 0.0018869 | 0.0020392 | 0.0021961 | 0.0023567 | 0.0025201 | 0.0026854 | 0.0028515 | 0.0030171 | 0.0031811 | 0.0033422 | 0.0034991 | 0.0036505 | 0.003795 | 0.0039313 | 0.0040582 | 0.0041744 | 0.0042788 | 0.0043704 | 0.0044482 | 0.0045114 | 0.0045594 | 0.0045917 | 0.004608 | 0.004608 | 0.0045917 | 0.0045594 | 0.0045114 | 0.0044482 | 0.0043704 | 0.0042788 | 0.0041744 | 0.0040582 | 0.0039313 | 0.003795 | 0.0036505 | 0.0034991 | 0.0033422 | 0.0031811 | 0.0030171 | 0.0028515 | 0.0026854 | 0.0025201 | 0.0023567 | 0.0021961 | 0.0020392 | 0.0018869 | 0.0017398 | 0.0015985 | 0.0014635 | 0.0013352 | 0.0012138 | 0.0010996 | 0.00099267 | 0.00089294 | 0.00080041 | 0.00071494 | 0.00063634 | 0.00056439 | 0.00049881 | 0.0004393 | 0.00038552 | 0.00033714 | 0.00029379 | 0.00025511 | 0.00022075 | 0.00019034 | 0.00016354 | 0.00014002 | 0.00011946 | 0.00010156 | 8.6035e-05 | 7.2629e-05 | 6.1095e-05 | 5.1212e-05
|  |  | Do not show currency formatting | [9 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 91.36% | 771.0962 | 992.9038 | 971.6916 | 954.8328 | 940.3695 | 927.3809 | [102 empty] | 6.1095e-05 | 7.2629e-05 | 8.6035e-05 | 0.00010156 | 0.00011946 | 0.00014002 | 0.00016354 | 0.00019034 | 0.00022075 | 0.00025511 | 0.00029379 | 0.00033714 | 0.00038552 | 0.0004393 | 0.00049881 | 0.00056439 | 0.00063634 | 0.00071494 | 0.00080041 | 0.00089294 | 0.00099267 | 0.0010996 | 0.0012138 | 0.0013352 | 0.0014635 | 0.0015985 | 0.0017398 | 0.0018869 | 0.0020392 | 0.0021961 | 0.0023567 | 0.0025201 | 0.0026854 | 0.0028515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[126 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0030171 | 0.0031811 | 0.0033422 | 0.0034991 | 0.0036505 | 0.003795 | 0.0039313 | 0.0040582 | 0.0041744 | 0.0042788 | 0.0043704 | 0.0044482 | 0.0045114 | 0.0045594 | 0.0045917 | 0.004608 | 0.004608 | 0.0045917 | 0.0045594 | 0.0045114 | 0.0044482 | 0.0043704 | 0.0042788 | 0.0041744 | 0.0040582 | 0.0039313 | 0.003795 | 0.0036505 | 0.0034991 | 0.0033422 | 0.0031811 | 0.0030171 | 0.0028515 | 0.0026854 | 0.0025201 | 0.0023567 | 0.0021961 | 0.0020392 | 0.0018869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | With | 0.8 | confidence | [119 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0017398 | 0.0015985 | 0.0014635 | 0.0013352 | 0.0012138 | 0.0010996 | 0.00099267 | 0.00089294 | 0.00080041 | 0.00071494 | 0.00063634 | 0.00056439 | 0.00049881 | 0.0004393 | 0.00038552 | 0.00033714 | 0.00029379 | 0.00025511 | 0.00022075 | 0.00019034 | 0.00016354 | 0.00014002 | 0.00011946 | 0.00010156 | 8.6035e-05 | 7.2629e-05 | 6.1095e-05 | 5.1212e-05
|  |  |  | The lowerbound threshold is | 771.0962 | [120 empty] | 6.1095e-05 | 7.2629e-05 | 8.6035e-05 | 0.00010156 | 0.00011946 | 0.00014002 | 0.00016354 | 0.00019034 | 0.00022075 | 0.00025511 | 0.00029379 | 0.00033714 | 0.00038552 | 0.0004393 | 0.00049881 | 0.00056439 | 0.00063634 | 0.00071494 | 0.00080041 | 0.00089294 | 0.00099267 | 0.0010996 | 0.0012138 | 0.0013352 | 0.0014635 | 0.0015985 | 0.0017398 | 0.0018869 | 0.0020392 | 0.0021961 | 0.0023567 | 0.0025201 | 0.0026854 | 0.0028515 | 0.0030171 | 0.0031811 | 0.0033422 | 0.0034991 | 0.0036505 | 0.003795 | 0.0039313 | 0.0040582 | 0.0041744 | 0.0042788 | 0.0043704 | 0.0044482 | 0.0045114 | 0.0045594 | 0.0045917 | 0.004608 | 0.004608 | 0.0045917 | 0.0045594 | 0.0045114 | 0.0044482 | 0.0043704 | 0.0042788 | 0.0041744 | 0.0040582 | 0.0039313 | 0.003795 | 0.0036505 | 0.0034991 | 0.0033422 | 0.0031811 | 0.0030171 | 0.0028515 | 0.0026854 | 0.0025201 | 0.0023567 | 0.0021961 | 0.0020392 | 0.0018869 | 0.0017398 | 0.0015985 | 0.0014635 | 0.0013352 | 0.0012138 | 0.0010996 | 0.00099267 | 0.00089294 | 0.00080041 | 0.00071494 | 0.00063634 | 0.00056439 | 0.00049881 | 0.0004393 | 0.00038552 | 0.00033714 | 0.00029379 | 0.00025511 | 0.00022075 | 0.00019034 | 0.00016354 | 0.00014002 | 0.00011946 | 0.00010156 | 8.6035e-05 | 7.2629e-05 | 6.1095e-05 | 5.1212e-05
|  |  |  | and the upperbound threshold is | 992.9038
|  |  |  | Between a lowerbound value of | 800 |  | Miss the pie
|  |  |  | and an upperbound value of | 1000 |  | chart? Press
|  |  |  | the range probability is | 0.74197 |  | CTRL and 6
|  |  |  | The lowerbound area covers | 0.17168 |  | to show the
|  |  |  | and the upperbound area covers | 0.086354 |  | pie chart
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Note: NORM.DIST and NORM.INV functions use the mean (i.e., the PERT expected value) which impliies probabilistic symmetry.
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on Q2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on R2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: Optionally, choose a minimum point-estimate for a single uncertainty by selecting a dropdown value in this column for any row. The percentage you choose will reduce the row's Most Likely point-estimate, and it will override the minimum point-estimate calculated by the heuristic in cell D2.
Note on C3: Optionally, manually enter a minimum point-estimate for a single uncertainty by entering a specific value in this column for any row. The value you enter will override the row's calculated, mininum point-estimate using percentage adjustments.
Note on D3: Use a simple heuristic to quickly create MINIMUM point-estimates for all rows. Do this by selecting a percentage in cell D2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column E and reducing it by the percentage value specified in cell D2. Optionally, choose a row-speciific heuristic by selecting a percentage in column B, or enter a specific minimum point-estimate in column C. (If you need to modify the dropdown choices in cell D2 or column B, you can do that in the Vlookups worksheet).
Note on E3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on F3: Use a simple heuristic to quickly create MAXIMUM point-estimates for all rows. Do this by selecting a percentage in cell F2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column E and increasing it by the percentage value specified in cell F2. Optionally, choose a row-speciific heuristic by selecting a percentage in column H, or enter a specific minimum point-estimate in column G. (If you need to modify the dropdown choices in cell F2 or column H, you can do that in the Vlookups worksheet).
Note on G3: Optionally, manually enter a maximum point-estimate for a single uncertainty by entering a specific value in this column for any row. The value you enter will override the row's calculated, maximum point-estimate using percentage adjustments.
Note on H3: Optionally, choose a maximum point-estimate for a single uncertainty by selecting a dropdown value in this column for any row. The percentage you choose will increase the row's Most Likely point-estimate, and it will override the maximum point-estimate calculated by the heuristic in cell F2.
Note on I3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on J3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on K3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on L3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on M3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on O3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on S3: You can choose different probabilities by entering a value between 1% and 99%.
Note on A13: Need more than just 10 rows to enter your estimates? Rows 14 through 103 are hidden. Unhide these rows to display 90 more rows like rows 4 through 13.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell F108, and/or choose the confidence lower and upperbound thresholds in cells F112 and F113.

## SPERT® Normal Charts
| Statistical PERT® (SPERT®) Normal Edition | [10 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[12 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 180 | 1 | 1 | 120 | Medium confidence |  |  | 24 | 576 | 150 | 89.44% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856 | 2 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104 | 106 | 108 | 110 | 112 | 114 | 116 | 118 | 120 | 122 | 124 | 126 | 128 | 130 | 132 | 134 | 136 | 138 | 140 | 142 | 144 | 146 | 148 | 150 | 152 | 154 | 156 | 158 | 160 | 162 | 164 | 166 | 168 | 170 | 172 | 174 | 176 | 178 | 180 | 182 | 184 | 186 | 188 | 190 | 192 | 194 | 196 | 198 | 200 | 202 | 204 | 206 | 208 | 210 | 212 | 214 | 216 | 218 | 220 | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
| 60 | 120 | 180 |  |  | 120 |  |  | 24 |  | 576 | 150 | 89.44% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 100% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
[122 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 0.8 | confidence | [117 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The lowerbound threshold is | 89.2428 | [118 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | and the upperbound threshold is | 150.7572 | [118 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | Between a lowerbound value of | 89 |  | Miss the pie
|  | and an upperbound value of | 151 |  | chart? Press
|  | the range probability is | 0.80353 |  | CTRL and 6
|  | The lowerbound area covers | 0.098236 |  | to show the
|  | and the upperbound area covers | 0.098236 |  | pie chart
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on M2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on N2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on O3: You can choose different probabilities by entering a value between 1% and 99%.

## SPERT® MC Simulation
| Statistical PERT® (SPERT®) Normal Edition | [12 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[14 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var | Rand() | Trial Outcome |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 180 | 1 | 1 | 120 | Medium confidence |  |  | 24 | 576 | 0.67507 | 130.8947 | 150 | 89.44% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856 | 2 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104 | 106 | 108 | 110 | 112 | 114 | 116 | 118 | 120 | 122 | 124 | 126 | 128 | 130 | 132 | 134 | 136 | 138 | 140 | 142 | 144 | 146 | 148 | 150 | 152 | 154 | 156 | 158 | 160 | 162 | 164 | 166 | 168 | 170 | 172 | 174 | 176 | 178 | 180 | 182 | 184 | 186 | 188 | 190 | 192 | 194 | 196 | 198 | 200 | 202 | 204 | 206 | 208 | 210 | 212 | 214 | 216 | 218 | 220 | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
| 60 | 120 | 180 |  |  | 120 |  |  | 24 |  | 576 |  |  | 150 | 89.44% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  |  |  | 1000 | 100% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
[16 empty] | SPERT Monte Carlo Simulation Results | [107 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 9.6% | 89.94% | 84.92% | 79.29% | 74.47% | 69.53% | [102 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 0.8 | confidence | [119 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | The lowerbound threshold is | 89.2428 | [120 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | and the upperbound threshold is | 150.7572
|  | Between a lowerbound value of | 89 |  | Miss the pie
|  | and an upperbound value of | 151 |  | chart? Press
|  | the range probability is | 0.80353 |  | CTRL and 6
|  | The lowerbound area covers | 0.098236 |  | to show the
|  | and the upperbound area covers | 0.098236 |  | pie chart
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Trial | Result
130.8947
1 | 132.4965
2 | 105.8257
3 | 137.5065
4 | 111.658
5 | 122.427
6 | 154.2068
7 | 96.0031
8 | 127.9971
9 | 115.6935
10 | 178.1687
11 | 136.9322
12 | 140.8109
13 | 130.1091
14 | 90.4709
15 | 121.1876
16 | 82.8961
17 | 83.5935
18 | 90.0669
19 | 136.8028
20 | 102.0361
21 | 69.0022
22 | 105.8027
23 | 119.9655
24 | 90.4592
25 | 86.8491
26 | 156.5646
27 | 158.1599
28 | 134.0565
29 | 123.1138
30 | 104.8465
31 | 171.6005
32 | 134.3972
33 | 111.1454
34 | 127.5943
35 | 97.5922
36 | 99.977
37 | 165.1438
38 | 126.7441
39 | 128.8869
40 | 100.8928
41 | 137.6985
42 | 91.7162
43 | 93.198
44 | 135.5545
45 | 119.0934
46 | 86.8194
47 | 161.7433
48 | 131.4485
49 | 124.6293
50 | 143.0134
51 | 136.5931
52 | 172.1041
53 | 132.7217
54 | 143.3336
55 | 122.5942
56 | 112.9443
57 | 123.5297
58 | 144.1781
59 | 105.4214
60 | 165.2485
61 | 148.3832
62 | 126.0585
63 | 125.5433
64 | 116.2163
65 | 148.453
66 | 140.2475
67 | 101.3203
68 | 98.252
69 | 123.0305
70 | 73.709
71 | 145.4867
72 | 108.2739
73 | 120.0872
74 | 87.1901
75 | 105.1349
76 | 117.0285
77 | 130.9365
78 | 116.861
79 | 105.0567
80 | 161.7685
81 | 102.3378
82 | 126.5597
83 | 110.0261
84 | 140.4423
85 | 115.612
86 | 103.2332
87 | 128.5016
88 | 144.5039
89 | 96.6806
90 | 117.7818
91 | 99.4104
92 | 119.3154
93 | 125.6606
94 | 79.1848
95 | 116.6881
96 | 146.1536
97 | 153.1133
98 | 155.0686
99 | 143.0294
100 | 95.8232
101 | 175.5796
102 | 113.4322
103 | 142.892
104 | 92.0336
105 | 94.8626
106 | 108.7362
107 | 142.62
108 | 121.4371
109 | 73.4033
110 | 145.5812
111 | 106.8054
112 | 138.6729
113 | 130.0665
114 | 145.5435
115 | 170.7459
116 | 132.627
117 | 74.9602
118 | 117.0172
119 | 125.3864
120 | 146.5809
121 | 81.3227
122 | 99.5182
123 | 99.8778
124 | 76.9849
125 | 138.3502
126 | 133.1284
127 | 130.2199
128 | 101.1928
129 | 131.3097
130 | 150.4363
131 | 112.8143
132 | 130.3025
133 | 88.1464
134 | 153.9147
135 | 54.7042
136 | 103.5493
137 | 146.6063
138 | 62.5169
139 | 137.6696
140 | 133.1177
141 | 137.1748
142 | 166.5946
143 | 99.3451
144 | 99.8549
145 | 124.285
146 | 143.6348
147 | 143.413
148 | 133.4396
149 | 94.712
150 | 143.9805
151 | 142.5696
152 | 124.8235
153 | 110.8978
154 | 122.8455
155 | 151.0292
156 | 146.7364
157 | 146.435
158 | 99.6044
159 | 106.3283
160 | 54.6078
161 | 101.674
162 | 68.7574
163 | 146.3962
164 | 131.9225
165 | 79.4909
166 | 94.5145
167 | 129.1455
168 | 132.0509
169 | 127.4972
170 | 106.8139
171 | 91.7963
172 | 83.1233
173 | 144.3747
174 | 100.4469
175 | 180.8399
176 | 124.477
177 | 110.71
178 | 129.712
179 | 136.148
180 | 140.6937
181 | 114.9847
182 | 132.2014
183 | 108.2369
184 | 142.0146
185 | 126.289
186 | 71.3108
187 | 127.1105
188 | 110.5788
189 | 115.5931
190 | 135.0993
191 | 125.9921
192 | 117.8158
193 | 153.0478
194 | 116.4977
195 | 145.3392
196 | 142.1322
197 | 155.3252
198 | 109.1235
199 | 110.0799
200 | 55.3119
201 | 132.855
202 | 134.9658
203 | 105.8789
204 | 102.0514
205 | 101.3192
206 | 121.5457
207 | 102.4988
208 | 141.1627
209 | 181.1315
210 | 82.2574
211 | 126.3433
212 | 101.0438
213 | 110.9242
214 | 101.3459
215 | 110.3488
216 | 105.4097
217 | 114.6898
218 | 118.2961
219 | 93.6542
220 | 173.3505
221 | 129.7966
222 | 124.2001
223 | 145.7917
224 | 150.3926
225 | 123.1395
226 | 139.1875
227 | 142.1769
228 | 93.1255
229 | 100.4891
230 | 119.8672
231 | 108.7507
232 | 112.0757
233 | 119.0405
234 | 152.5807
235 | 100.7422
236 | 145.342
237 | 117.8653
238 | 130.3978
239 | 128.5252
240 | 116.1895
241 | 156.2046
242 | 115.0863
243 | 141.5428
244 | 118.2014
245 | 94.044
246 | 132.3416
247 | 114.8071
248 | 68.0871
249 | 130.7935
250 | 68.3048
251 | 105.6281
252 | 155.6858
253 | 137.8781
254 | 125.8189
255 | 107.3357
256 | 142.7919
257 | 120.0405
258 | 119.6527
259 | 121.6778
260 | 116.1372
261 | 144.3745
262 | 132.8792
263 | 141.2619
264 | 152.4766
265 | 128.3705
266 | 103.5917
267 | 178.2313
268 | 108.2219
269 | 128.8355
270 | 140.0841
271 | 89.3391
272 | 88.7471
273 | 121.3482
274 | 123.2926
275 | 128.9267
276 | 130.253
277 | 128.9685
278 | 68.4481
279 | 55.4772
280 | 112.2072
281 | 93.5877
282 | 101.5305
283 | 109.5529
284 | 104.1024
285 | 143.2085
286 | 102.2125
287 | 131.5376
288 | 109.5706
289 | 87.5824
290 | 105.1759
291 | 133.2559
292 | 141.9226
293 | 153.2819
294 | 137.6804
295 | 93.3229
296 | 113.9441
297 | 128.6487
298 | 92.8078
299 | 100.3363
300 | 85.127
301 | 113.0512
302 | 90.1305
303 | 123.7667
304 | 123.8429
305 | 135.8439
306 | 114.7556
307 | 137.6289
308 | 130.5425
309 | 108.3931
310 | 124.5436
311 | 65.5059
312 | 103.3365
313 | 139.7156
314 | 97.543
315 | 145.0211
316 | 89.5977
317 | 82.1174
318 | 102.2788
319 | 148.5246
320 | 135.67
321 | 121.3549
322 | 94.4911
323 | 81.8694
324 | 159.3334
325 | 105.8793
326 | 124.9925
327 | 166.5036
328 | 131.4887
329 | 95.5433
330 | 127.6324
331 | 120.838
332 | 109.9237
333 | 148.8783
334 | 160.5736
335 | 92.91
336 | 157.9287
337 | 128.4673
338 | 98.8517
339 | 73.9288
340 | 87.7669
341 | 66.1379
342 | 145.7488
343 | 89.6852
344 | 116.8846
345 | 113.4545
346 | 96.6081
347 | 108.173
348 | 81.6335
349 | 134.9197
350 | 141.2145
351 | 151.0935
352 | 116.3605
353 | 153.5944
354 | 114.014
355 | 165.0354
356 | 148.0023
357 | 129.9507
358 | 202.2437
359 | 126.5469
360 | 155.8199
361 | 120.6224
362 | 83.2712
363 | 125.5655
364 | 152.6113
365 | 138.2182
366 | 76.767
367 | 173.3009
368 | 101.921
369 | 114.5966
370 | 109.6938
371 | 144.7512
372 | 111.3411
373 | 126.585
374 | 145.1439
375 | 93.9782
376 | 113.6036
377 | 75.8952
378 | 122.3418
379 | 120.3328
380 | 94.0426
381 | 153.4051
382 | 120.0033
383 | 125.3006
384 | 131.9599
385 | 135.9172
386 | 84.3033
387 | 83.7641
388 | 120.1657
389 | 122.6042
390 | 104.7495
391 | 74.0502
392 | 105.4437
393 | 158.8945
394 | 109.7085
395 | 112.4642
396 | 89.6441
397 | 91.5732
398 | 147.0114
399 | 127.7015
400 | 113.6635
401 | 124.0026
402 | 117.1166
403 | 109.4843
404 | 135.3072
405 | 101.0066
406 | 125.9864
407 | 118.0095
408 | 113.5612
409 | 85.2119
410 | 129.9657
411 | 137.0974
412 | 103.6162
413 | 127.8804
414 | 103.4837
415 | 141.8536
416 | 122.4857
417 | 85.0838
418 | 135.3427
419 | 101.6603
420 | 117.8576
421 | 179.3871
422 | 98.5866
423 | 103.6408
424 | 134.7832
425 | 131.6762
426 | 86.9557
427 | 121.0683
428 | 157.4651
429 | 113.8937
430 | 138.819
431 | 98.2377
432 | 134.7914
433 | 122.3477
434 | 160.8358
435 | 97.8019
436 | 122.6876
437 | 132.1746
438 | 118.685
439 | 124.1313
440 | 95.5398
441 | 149.8159
442 | 124.9662
443 | 152.2318
444 | 130.0307
445 | 139.1981
446 | 133.4618
447 | 117.4372
448 | 124.6548
449 | 135.1556
450 | 130.7509
451 | 98.6612
452 | 104.9252
453 | 124.5685
454 | 145.5468
455 | 97.0093
456 | 91.6397
457 | 123.3388
458 | 143.668
459 | 127.7508
460 | 149.097
461 | 111.4101
462 | 105.0048
463 | 127.9725
464 | 130.1756
465 | 93.0934
466 | 123.4226
467 | 116.7658
468 | 143.3664
469 | 141.5482
470 | 112.619
471 | 114.7439
472 | 118.5358
473 | 140.6348
474 | 119.4649
475 | 135.0716
476 | 155.3523
477 | 167.2289
478 | 120.0478
479 | 143.5656
480 | 92.3174
481 | 87.0737
482 | 122.7156
483 | 101.3755
484 | 120.8203
485 | 122.9642
486 | 140.7751
487 | 89.8875
488 | 149.3656
489 | 100.6256
490 | 115.9655
491 | 151.9105
492 | 75.3635
493 | 115.5705
494 | 126.2471
495 | 93.3666
496 | 117.4855
497 | 103.4505
498 | 147.4505
499 | 158.936
500 | 118.8005
501 | 132.0657
502 | 130.7012
503 | 110.5745
504 | 101.7642
505 | 101.0595
506 | 72.5606
507 | 131.1286
508 | 112.3862
509 | 128.8534
510 | 122.8325
511 | 97.0956
512 | 138.1902
513 | 146.7625
514 | 112.1335
515 | 151.4647
516 | 92.9389
517 | 117.8694
518 | 101.5767
519 | 135.1809
520 | 86.9177
521 | 130.0926
522 | 117.2934
523 | 129.1077
524 | 149.884
525 | 98.0736
526 | 126.205
527 | 116.3463
528 | 154.6954
529 | 145.5664
530 | 165.7807
531 | 187.8611
532 | 144.0205
533 | 120.0434
534 | 126.7878
535 | 66.1309
536 | 99.139
537 | 136.4642
538 | 97.9476
539 | 119.3768
540 | 137.2254
541 | 113.4508
542 | 147.9678
543 | 139.0556
544 | 144.8879
545 | 157.0777
546 | 116.3541
547 | 111.9612
548 | 148.6871
549 | 135.3154
550 | 141.853
551 | 95.9072
552 | 87.3537
553 | 129.7935
554 | 117.0229
555 | 91.4205
556 | 99.2451
557 | 95.9943
558 | 206.5376
559 | 100.2351
560 | 111.754
561 | 94.2643
562 | 79.271
563 | 103.9635
564 | 145.9887
565 | 126.8102
566 | 97.2133
567 | 77.5119
568 | 114.1097
569 | 109.4076
570 | 82.1853
571 | 159.5956
572 | 141.9783
573 | 104.1955
574 | 124.0358
575 | 92.2675
576 | 112.5984
577 | 149.8905
578 | 97.6379
579 | 115.7567
580 | 129.4687
581 | 99.1367
582 | 118.5431
583 | 128.4275
584 | 99.4836
585 | 90.2613
586 | 116.097
587 | 84.6868
588 | 102.3545
589 | 107.6943
590 | 125.7304
591 | 136.5927
592 | 154.1349
593 | 146.6796
594 | 85.468
595 | 142.7726
596 | 111.159
597 | 157.7176
598 | 35.775
599 | 113.936
600 | 156.0471
601 | 125.9803
602 | 154.8182
603 | 154.5829
604 | 162.8309
605 | 151.3479
606 | 166.6582
607 | 125.351
608 | 162.7744
609 | 89.2764
610 | 92.4137
611 | 111.5204
612 | 119.4725
613 | 98.3582
614 | 118.3164
615 | 144.1451
616 | 134.7714
617 | 117.965
618 | 160.1317
619 | 96.552
620 | 104.9508
621 | 144.1235
622 | 90.7612
623 | 115.6344
624 | 103.2569
625 | 137.8524
626 | 103.7617
627 | 84.8021
628 | 98.789
629 | 92.8724
630 | 124.0732
631 | 133.4621
632 | 116.3781
633 | 171.9161
634 | 105.1342
635 | 162.6087
636 | 135.4178
637 | 120.0012
638 | 131.4191
639 | 87.2498
640 | 123.2963
641 | 76.3321
642 | 140.4572
643 | 95.5035
644 | 147.4117
645 | 121.5292
646 | 96.1334
647 | 132.5532
648 | 89.3576
649 | 118.4323
650 | 85.9202
651 | 114.6404
652 | 127.5902
653 | 120.6711
654 | 132.9379
655 | 98.7839
656 | 95.8685
657 | 118.0058
658 | 166.1677
659 | 129.0629
660 | 148.3539
661 | 111.5392
662 | 134.4059
663 | 180.2533
664 | 106.4118
665 | 152.2747
666 | 122.6991
667 | 125.7765
668 | 140.3252
669 | 109.7476
670 | 109.7879
671 | 113.5824
672 | 137.7637
673 | 135.9537
674 | 90.6251
675 | 134.5099
676 | 152.7576
677 | 123.5984
678 | 127.772
679 | 107.3668
680 | 138.1028
681 | 135.4941
682 | 117.8156
683 | 136.9976
684 | 117.6779
685 | 129.8202
686 | 105.4171
687 | 122.5783
688 | 75.1609
689 | 149.2952
690 | 134.3436
691 | 138.7706
692 | 133.2059
693 | 114.8909
694 | 123.4498
695 | 89.8708
696 | 114.249
697 | 152.0565
698 | 148.836
699 | 101.0796
700 | 125.7564
701 | 96.084
702 | 142.4419
703 | 86.4169
704 | 84.6757
705 | 117.7668
706 | 118.8481
707 | 96.1132
708 | 153.3843
709 | 182.0029
710 | 121.6115
711 | 126.1787
712 | 103.992
713 | 130.6214
714 | 139.3254
715 | 137.8398
716 | 119.832
717 | 99.6058
718 | 148.597
719 | 141.7512
720 | 104.5277
721 | 115.5511
722 | 126.5842
723 | 118.5548
724 | 110.936
725 | 125.9045
726 | 132.6865
727 | 79.3053
728 | 145.1133
729 | 116.3108
730 | 133.3443
731 | 65.8576
732 | 105.0111
733 | 119.3575
734 | 99.8738
735 | 102.9853
736 | 106.9504
737 | 155.478
738 | 74.0912
739 | 102.6614
740 | 93.8328
741 | 176.4034
742 | 113.8427
743 | 104.2547
744 | 154.8201
745 | 134.7456
746 | 95.0678
747 | 131.2033
748 | 97.4297
749 | 154.6601
750 | 190.7024
751 | 109.576
752 | 122.7711
753 | 149.0334
754 | 92.7871
755 | 118.5814
756 | 129.4568
757 | 131.3014
758 | 72.7983
759 | 82.6775
760 | 123.5702
761 | 162.2365
762 | 159.0007
763 | 129.6697
764 | 180.5765
765 | 99.8385
766 | 135.2693
767 | 136.763
768 | 136.9753
769 | 121.3863
770 | 138.4651
771 | 104.8939
772 | 96.3297
773 | 166.9144
774 | 105.7672
775 | 115.6913
776 | 143.178
777 | 125.1673
778 | 159.9318
779 | 119.988
780 | 143.079
781 | 181.4757
782 | 179.754
783 | 101.6207
784 | 143.5147
785 | 95.9216
786 | 87.8405
787 | 120.5442
788 | 93.7957
789 | 125.0386
790 | 115.9392
791 | 138.3859
792 | 163.656
793 | 104.5616
794 | 115.2174
795 | 107.1872
796 | 138
797 | 118.3128
798 | 126.1174
799 | 121.2666
800 | 127.7337
801 | 93.1377
802 | 135.0676
803 | 58.3365
804 | 139.3444
805 | 92.2538
806 | 116.1993
807 | 116.4525
808 | 113.1155
809 | 126.4181
810 | 129.6098
811 | 88.3188
812 | 161.7634
813 | 141.3369
814 | 92.3897
815 | 83.9342
816 | 161.2367
817 | 119.9515
818 | 107.7661
819 | 77.9747
820 | 98.7931
821 | 117.5288
822 | 73.7855
823 | 112.8849
824 | 123.2923
825 | 104.5202
826 | 134.0291
827 | 83.9923
828 | 109.5514
829 | 83.7771
830 | 149.7295
831 | 124.9821
832 | 141.7027
833 | 92.2976
834 | 137.0722
835 | 102.3872
836 | 113.2981
837 | 135.3858
838 | 130.1014
839 | 124.2706
840 | 129.846
841 | 129.9448
842 | 114.7601
843 | 128.446
844 | 79.2151
845 | 147.5373
846 | 127.7912
847 | 115.0762
848 | 100.9511
849 | 140.684
850 | 101.4518
851 | 121.3681
852 | 159.4861
853 | 113.8094
854 | 51.1096
855 | 65.9776
856 | 129.4723
857 | 164.6022
858 | 91.2995
859 | 123.1074
860 | 106.1441
861 | 119.4734
862 | 134.8127
863 | 124.8145
864 | 129.5365
865 | 102.9031
866 | 122.8513
867 | 142.4999
868 | 109.4976
869 | 119.5909
870 | 142.4641
871 | 80.9536
872 | 120.8148
873 | 110.9246
874 | 145.856
875 | 85.371
876 | 69.5672
877 | 120.0814
878 | 99.5946
879 | 89.6915
880 | 175.8772
881 | 116.2875
882 | 77.0747
883 | 103.1518
884 | 72.9451
885 | 117.3704
886 | 134.4696
887 | 117.7745
888 | 141.4879
889 | 135.2188
890 | 106.3959
891 | 145.3706
892 | 151.5789
893 | 167.702
894 | 130.378
895 | 84.3142
896 | 155.7004
897 | 103.9763
898 | 141.6918
899 | 119.0238
900 | 150.6628
901 | 99.8217
902 | 144.8979
903 | 124.4877
904 | 136.1709
905 | 119.4272
906 | 127.8781
907 | 138.6201
908 | 132.5342
909 | 134.2158
910 | 84.7504
911 | 126.1757
912 | 108.7232
913 | 75.1924
914 | 103.8843
915 | 114.9259
916 | 143.6455
917 | 110.1397
918 | 113.9684
919 | 112.2223
920 | 131.2035
921 | 147.3732
922 | 119.1406
923 | 151.6159
924 | 123.1041
925 | 121.1114
926 | 107.909
927 | 114.6988
928 | 94.9121
929 | 142.4919
930 | 111.6718
931 | 132.1592
932 | 164.148
933 | 92.143
934 | 112.008
935 | 148.3073
936 | 125.5931
937 | 69.3889
938 | 134.1765
939 | 84.509
940 | 148.4521
941 | 89.8562
942 | 147.7589
943 | 152.8792
944 | 114.0781
945 | 92.5169
946 | 108.0893
947 | 99.6507
948 | 120.8674
949 | 120.0287
950 | 99.2629
951 | 102.1358
952 | 158.3365
953 | 154.1871
954 | 64.5685
955 | 104.7738
956 | 150.3702
957 | 117.0767
958 | 106.3403
959 | 149.8192
960 | 141.8982
961 | 103.22
962 | 73.6667
963 | 78.2753
964 | 115.5427
965 | 128.3849
966 | 108.0769
967 | 104.8448
968 | 122.9456
969 | 52.0682
970 | 109.8602
971 | 151.5019
972 | 147.3427
973 | 101.6677
974 | 110.0814
975 | 152.7879
976 | 123.1289
977 | 138.8904
978 | 78.6342
979 | 129.2786
980 | 132.651
981 | 136.4206
982 | 141.2467
983 | 110.8157
984 | 122.4189
985 | 133.8368
986 | 126.5879
987 | 112.064
988 | 148.3979
989 | 161.5815
990 | 131.239
991 | 144.8581
992 | 103.3812
993 | 130.4669
994 | 138.9826
995 | 106.6358
996 | 95.2086
997 | 91.8104
998 | 100.6323
999 | 125.242
1000 | 111.429
1001 | 77.9221
1002 | 94.7115
1003 | 109.5174
1004 | 80.2981
1005 | 106.233
1006 | 117.9415
1007 | 83.7661
1008 | 144.3367
1009 | 134.872
1010 | 89.6636
1011 | 111.6354
1012 | 98.6033
1013 | 87.8247
1014 | 135.8113
1015 | 69.3305
1016 | 115.2822
1017 | 91.9561
1018 | 127.926
1019 | 169.4283
1020 | 160.4713
1021 | 85.2562
1022 | 125.5698
1023 | 138.6947
1024 | 145.8918
1025 | 101.7605
1026 | 94.5383
1027 | 113.6606
1028 | 93.9725
1029 | 98.0947
1030 | 127.3688
1031 | 137.1821
1032 | 141.3515
1033 | 96.1314
1034 | 130.6341
1035 | 124.4329
1036 | 150.2416
1037 | 92.8208
1038 | 93.0075
1039 | 116.2651
1040 | 206.3253
1041 | 122.0815
1042 | 126.1228
1043 | 144.5158
1044 | 106.8794
1045 | 173.067
1046 | 86.1201
1047 | 105.6541
1048 | 125.4909
1049 | 109.9729
1050 | 97.5349
1051 | 100.5088
1052 | 111.6485
1053 | 181.8056
1054 | 69.8694
1055 | 131.0068
1056 | 112.0239
1057 | 133.4706
1058 | 113.4241
1059 | 86.4324
1060 | 77.4031
1061 | 132.4534
1062 | 128.7336
1063 | 111.179
1064 | 132.661
1065 | 117.7406
1066 | 126.3247
1067 | 139.4359
1068 | 95.0604
1069 | 125.3286
1070 | 123.9098
1071 | 91.3599
1072 | 135.4757
1073 | 104.4176
1074 | 150.1123
1075 | 106.3247
1076 | 106.5924
1077 | 126.7919
1078 | 106.2392
1079 | 139.889
1080 | 141.686
1081 | 149.5456
1082 | 104.7188
1083 | 171.3965
1084 | 63.3539
1085 | 115.9203
1086 | 113.6711
1087 | 98.3222
1088 | 135.4332
1089 | 120.2642
1090 | 102.1642
1091 | 123.1572
1092 | 101.531
1093 | 116.3228
1094 | 123.192
1095 | 112.8657
1096 | 121.4087
1097 | 130.2031
1098 | 105.7957
1099 | 171.7292
1100 | 124.9199
1101 | 119.512
1102 | 80.9953
1103 | 140.2731
1104 | 148.2991
1105 | 98.9013
1106 | 173.992
1107 | 103.5649
1108 | 134.2146
1109 | 108.1736
1110 | 106.8793
1111 | 139.2856
1112 | 96.9891
1113 | 103.471
1114 | 91.1309
1115 | 116.1146
1116 | 138.7389
1117 | 132.1618
1118 | 106.3178
1119 | 118.7895
1120 | 85.5883
1121 | 101.0737
1122 | 119.2532
1123 | 127.5672
1124 | 135.7543
1125 | 132.7664
1126 | 106.0953
1127 | 98.5651
1128 | 144.842
1129 | 142.7525
1130 | 136.3904
1131 | 110.7039
1132 | 129.3092
1133 | 119.912
1134 | 110.9834
1135 | 162.4756
1136 | 147.2643
1137 | 105.8921
1138 | 149.115
1139 | 130.1452
1140 | 121.6361
1141 | 146.1108
1142 | 132.9801
1143 | 132.7485
1144 | 128.7521
1145 | 138.4556
1146 | 91.0579
1147 | 152.1624
1148 | 115.1974
1149 | 117.2936
1150 | 117.7609
1151 | 94.3906
1152 | 166.3152
1153 | 115.0161
1154 | 108.71
1155 | 137.9565
1156 | 76.2438
1157 | 132.2409
1158 | 152.5783
1159 | 83.1888
1160 | 76.5886
1161 | 129.9106
1162 | 96.9512
1163 | 143.3036
1164 | 120.3061
1165 | 111.2052
1166 | 130.9916
1167 | 124.8945
1168 | 119.3722
1169 | 145.7924
1170 | 105.1993
1171 | 127.2377
1172 | 115.8583
1173 | 161.4009
1174 | 106.932
1175 | 132.6787
1176 | 135.312
1177 | 111.0773
1178 | 100.6284
1179 | 122.6209
1180 | 115.8983
1181 | 112.1857
1182 | 102.5551
1183 | 139.663
1184 | 120.8984
1185 | 99.9314
1186 | 108.7131
1187 | 149.6087
1188 | 124.1952
1189 | 114.8875
1190 | 134.2215
1191 | 112.8405
1192 | 161.4514
1193 | 134.052
1194 | 101.1616
1195 | 85.3739
1196 | 79.1063
1197 | 123.3468
1198 | 153.6877
1199 | 156.1974
1200 | 112.3962
1201 | 119.8438
1202 | 130.2893
1203 | 79.941
1204 | 133.8626
1205 | 126.6385
1206 | 103.9363
1207 | 125.7674
1208 | 165.4656
1209 | 103.6283
1210 | 126.5252
1211 | 93.4626
1212 | 101.8834
1213 | 145.3286
1214 | 103.075
1215 | 85.5966
1216 | 127.5457
1217 | 152.2576
1218 | 126.4416
1219 | 150.7907
1220 | 137.473
1221 | 72.4488
1222 | 143.4304
1223 | 120.3474
1224 | 147.3239
1225 | 151.8757
1226 | 147.85
1227 | 83.6214
1228 | 107.0638
1229 | 111.9284
1230 | 157.2654
1231 | 88.0315
1232 | 150.2032
1233 | 127.7282
1234 | 138.9164
1235 | 92.9742
1236 | 71.6893
1237 | 108.8142
1238 | 125.1853
1239 | 130.0785
1240 | 148.7233
1241 | 111.9946
1242 | 108.4482
1243 | 146.2419
1244 | 95.9103
1245 | 141.7308
1246 | 109.4379
1247 | 82.3785
1248 | 131.786
1249 | 100.5344
1250 | 103.4115
1251 | 123.1235
1252 | 127.0595
1253 | 132.2433
1254 | 71.4463
1255 | 111.5777
1256 | 116.172
1257 | 120.8663
1258 | 106.0385
1259 | 177.8823
1260 | 98.8255
1261 | 67.6811
1262 | 98.0769
1263 | 112.2069
1264 | 110.9257
1265 | 121.2315
1266 | 108.9365
1267 | 119.9343
1268 | 120.9055
1269 | 137.5598
1270 | 97.8141
1271 | 115.7847
1272 | 148.6928
1273 | 149.6882
1274 | 124.9839
1275 | 75.6422
1276 | 147.4404
1277 | 114.2148
1278 | 103.4265
1279 | 160.4388
1280 | 95.3579
1281 | 100.4098
1282 | 114.0306
1283 | 138.4801
1284 | 147.3974
1285 | 143.5004
1286 | 70.5407
1287 | 167.2009
1288 | 85.2206
1289 | 124.1616
1290 | 83.5355
1291 | 94.0853
1292 | 118.6206
1293 | 120.2843
1294 | 141.7064
1295 | 121.1813
1296 | 114.3591
1297 | 103.2343
1298 | 156.7777
1299 | 111.3575
1300 | 93.5076
1301 | 125.6596
1302 | 125.6533
1303 | 90.2656
1304 | 160.7676
1305 | 128.3332
1306 | 120.0806
1307 | 75.5525
1308 | 96.5107
1309 | 139.6135
1310 | 127.5068
1311 | 131.1949
1312 | 120.4198
1313 | 108.4216
1314 | 138.9798
1315 | 116.2736
1316 | 166.0626
1317 | 85.0674
1318 | 99.0203
1319 | 132.5681
1320 | 112.1043
1321 | 126.0696
1322 | 140.3577
1323 | 130.2596
1324 | 148.6074
1325 | 99.2234
1326 | 96.3568
1327 | 130.5531
1328 | 125.9293
1329 | 98.6149
1330 | 97.9587
1331 | 108.4853
1332 | 148.962
1333 | 118.5553
1334 | 145.935
1335 | 140.4361
1336 | 172.0867
1337 | 121.3422
1338 | 104.3575
1339 | 130.3738
1340 | 121.5486
1341 | 96.4012
1342 | 130.8848
1343 | 128.8951
1344 | 100.0573
1345 | 131.8409
1346 | 94.1501
1347 | 78.8744
1348 | 163.5563
1349 | 160.7229
1350 | 82.9558
1351 | 65.4828
1352 | 107.8633
1353 | 92.8906
1354 | 108.8902
1355 | 124.6404
1356 | 147.4488
1357 | 123.2547
1358 | 129.178
1359 | 182.7617
1360 | 128.6918
1361 | 92.8315
1362 | 126.035
1363 | 127.045
1364 | 129.1963
1365 | 156.9055
1366 | 111.1235
1367 | 155.2815
1368 | 84.2665
1369 | 122.2758
1370 | 101.6755
1371 | 107.52
1372 | 95.2383
1373 | 119.0455
1374 | 109.0772
1375 | 146.5093
1376 | 137.1409
1377 | 92.8834
1378 | 152.0926
1379 | 92.5093
1380 | 139.9149
1381 | 115.1196
1382 | 163.9458
1383 | 116.1154
1384 | 104.9926
1385 | 106.3845
1386 | 84.2249
1387 | 122.7902
1388 | 119.3866
1389 | 141.11
1390 | 113.422
1391 | 107.1351
1392 | 131.7723
1393 | 79.2538
1394 | 78.0033
1395 | 91.8777
1396 | 131.055
1397 | 144.735
1398 | 109.3173
1399 | 130.8883
1400 | 108.3172
1401 | 70.9447
1402 | 143.1941
1403 | 168.5512
1404 | 90.7284
1405 | 99.5916
1406 | 81.0045
1407 | 124.6722
1408 | 144.3262
1409 | 134.2048
1410 | 89.0463
1411 | 110.4485
1412 | 98.4038
1413 | 102.6294
1414 | 98.9988
1415 | 71.9181
1416 | 136.359
1417 | 127.9882
1418 | 156.4741
1419 | 80.0797
1420 | 112.9271
1421 | 147.8448
1422 | 83.3227
1423 | 119.7804
1424 | 149.2753
1425 | 131.7178
1426 | 108.773
1427 | 89.0608
1428 | 116.634
1429 | 103.8433
1430 | 113.512
1431 | 151.802
1432 | 129.7939
1433 | 125.6359
1434 | 109.7817
1435 | 109.2195
1436 | 102.5089
1437 | 110.3807
1438 | 100.145
1439 | 119.7911
1440 | 105.465
1441 | 149.4864
1442 | 122.3086
1443 | 122.0098
1444 | 139.6463
1445 | 107.1039
1446 | 100.673
1447 | 128.1104
1448 | 138.2475
1449 | 107.6934
1450 | 152.4257
1451 | 85.7609
1452 | 166.1588
1453 | 136.6971
1454 | 92.4865
1455 | 99.9137
1456 | 91.926
1457 | 96.9837
1458 | 114.0991
1459 | 127.9657
1460 | 105.3058
1461 | 110.8217
1462 | 134.3154
1463 | 132.0843
1464 | 119.473
1465 | 97.082
1466 | 108.5787
1467 | 141.8088
1468 | 166.2056
1469 | 140.6751
1470 | 136.572
1471 | 134.3233
1472 | 115.7681
1473 | 97.7468
1474 | 82.489
1475 | 127.2836
1476 | 102.3346
1477 | 93.1904
1478 | 92.1695
1479 | 86.198
1480 | 114.8352
1481 | 92.6335
1482 | 112.9146
1483 | 93.0587
1484 | 92.427
1485 | 139.7987
1486 | 130.4588
1487 | 141.3647
1488 | 122.7808
1489 | 169.0985
1490 | 153.5486
1491 | 100.7524
1492 | 154.7247
1493 | 175.0218
1494 | 123.5
1495 | 80.3169
1496 | 144.1705
1497 | 114.5396
1498 | 43.3358
1499 | 84.3162
1500 | 99.9266
1501 | 96.3041
1502 | 110.116
1503 | 160.3065
1504 | 90.7733
1505 | 150.333
1506 | 130.2341
1507 | 91.3381
1508 | 103.9687
1509 | 52.4895
1510 | 131.8499
1511 | 114.0998
1512 | 118.911
1513 | 159.3253
1514 | 83.2283
1515 | 120.1493
1516 | 90.1914
1517 | 130.3188
1518 | 107.724
1519 | 114.5314
1520 | 103.5703
1521 | 137.9939
1522 | 124.8024
1523 | 74.188
1524 | 119.6303
1525 | 108.6438
1526 | 161.7552
1527 | 124.6615
1528 | 173.5501
1529 | 131.9315
1530 | 159.9116
1531 | 137.5838
1532 | 137.5529
1533 | 121.4286
1534 | 103.3919
1535 | 127.5576
1536 | 137.6686
1537 | 122.1245
1538 | 173.6082
1539 | 142.0151
1540 | 128.6574
1541 | 96.1052
1542 | 78.3628
1543 | 123.9886
1544 | 91.2586
1545 | 124.5176
1546 | 120.7693
1547 | 138.3129
1548 | 115.2342
1549 | 149.7402
1550 | 126.0125
1551 | 98.3575
1552 | 113.1138
1553 | 112.7004
1554 | 94.4115
1555 | 115.7345
1556 | 132.0098
1557 | 97.7549
1558 | 91.6775
1559 | 97.356
1560 | 139.7772
1561 | 106.1359
1562 | 119.7409
1563 | 103.2862
1564 | 142.5546
1565 | 116.0208
1566 | 131.6576
1567 | 106.607
1568 | 111.7992
1569 | 141.6198
1570 | 109.9834
1571 | 50.9807
1572 | 141.8927
1573 | 112.3307
1574 | 130.3702
1575 | 118.6739
1576 | 89.5183
1577 | 133.0355
1578 | 149.9593
1579 | 113.0094
1580 | 125.6937
1581 | 99.85
1582 | 120.0887
1583 | 110.3517
1584 | 155.0375
1585 | 122.7443
1586 | 101.9617
1587 | 110.3671
1588 | 108.4212
1589 | 92.7868
1590 | 133.0606
1591 | 160.5945
1592 | 183.5024
1593 | 105.5015
1594 | 161.7643
1595 | 131.6544
1596 | 119.7601
1597 | 152.3865
1598 | 150.9369
1599 | 119.1434
1600 | 117.3681
1601 | 129.2791
1602 | 109.8378
1603 | 124.9688
1604 | 94.1001
1605 | 66.5452
1606 | 88.8961
1607 | 134.645
1608 | 136.7908
1609 | 159.0275
1610 | 145.6969
1611 | 147.2615
1612 | 127.0122
1613 | 108.8887
1614 | 148.7863
1615 | 166.5523
1616 | 139.6395
1617 | 144.8412
1618 | 117.4912
1619 | 101.2288
1620 | 92.4337
1621 | 111.7263
1622 | 89.6159
1623 | 89.3436
1624 | 127.866
1625 | 157.4711
1626 | 111.2626
1627 | 134.2911
1628 | 75.0321
1629 | 114.112
1630 | 117.8633
1631 | 104.0263
1632 | 126.0507
1633 | 134.8269
1634 | 140.5863
1635 | 112.1084
1636 | 131.6143
1637 | 103.4599
1638 | 136.4655
1639 | 78.6719
1640 | 127.3978
1641 | 131.7873
1642 | 135.9312
1643 | 115.6978
1644 | 130.4104
1645 | 129.5433
1646 | 110.1037
1647 | 116.6419
1648 | 131.8724
1649 | 55.6269
1650 | 122.4266
1651 | 116.7541
1652 | 101.3897
1653 | 119.9679
1654 | 144.4899
1655 | 97.6
1656 | 77.8043
1657 | 67.7618
1658 | 163.8043
1659 | 133.8149
1660 | 92.8002
1661 | 135.6371
1662 | 133.0576
1663 | 127.7132
1664 | 109.6079
1665 | 129.9322
1666 | 139.4424
1667 | 131.7227
1668 | 123.8038
1669 | 117.5698
1670 | 92.0915
1671 | 116.868
1672 | 115.3941
1673 | 129.8307
1674 | 102.4979
1675 | 65.5477
1676 | 151.5971
1677 | 108.8021
1678 | 133.1943
1679 | 135.6003
1680 | 98.5774
1681 | 122.1964
1682 | 98.8242
1683 | 94.7962
1684 | 156.5502
1685 | 133.4661
1686 | 122.1662
1687 | 126.233
1688 | 104.3203
1689 | 145.0572
1690 | 98.6369
1691 | 119.0372
1692 | 99.0155
1693 | 93.1186
1694 | 169.2138
1695 | 112.3251
1696 | 125.7861
1697 | 126.9249
1698 | 52.4762
1699 | 131.5002
1700 | 178.1313
1701 | 93.0146
1702 | 136.7902
1703 | 100.0516
1704 | 68.2583
1705 | 117.3636
1706 | 134.2528
1707 | 93.453
1708 | 148.8259
1709 | 104.1097
1710 | 124.4024
1711 | 88.6958
1712 | 159.9471
1713 | 85.6255
1714 | 94.3373
1715 | 122.8266
1716 | 107.648
1717 | 96.241
1718 | 120.2156
1719 | 109.5072
1720 | 134.9973
1721 | 166.232
1722 | 131.5876
1723 | 170.5895
1724 | 131.7472
1725 | 120.9185
1726 | 102.8238
1727 | 150.3994
1728 | 119.0163
1729 | 166.7987
1730 | 97.5118
1731 | 118.7101
1732 | 136.977
1733 | 135.5863
1734 | 133.4679
1735 | 119.9181
1736 | 72.3854
1737 | 119.2108
1738 | 121.2846
1739 | 167.6059
1740 | 78.1921
1741 | 141.3344
1742 | 133.6646
1743 | 116.3075
1744 | 93.1739
1745 | 124.4356
1746 | 74.1006
1747 | 86.2996
1748 | 68.139
1749 | 80.6988
1750 | 97.7779
1751 | 110.1691
1752 | 96.926
1753 | 99.0548
1754 | 160.2354
1755 | 84.045
1756 | 105.2976
1757 | 104.6462
1758 | 132.4814
1759 | 132.3471
1760 | 157.6562
1761 | 127.3493
1762 | 100.7278
1763 | 81.1759
1764 | 92.7525
1765 | 121.9299
1766 | 100.5095
1767 | 119.0203
1768 | 130.1255
1769 | 95.0763
1770 | 122.5285
1771 | 97.1468
1772 | 79.8215
1773 | 127.2413
1774 | 121.9495
1775 | 102.1791
1776 | 133.1339
1777 | 105.8507
1778 | 101.9281
1779 | 73.6897
1780 | 117.2661
1781 | 114.9016
1782 | 126.915
1783 | 122.5816
1784 | 133.6576
1785 | 116.7055
1786 | 84.9946
1787 | 125.4143
1788 | 107.0675
1789 | 136.4334
1790 | 98.2106
1791 | 149.0053
1792 | 105.0877
1793 | 145.7841
1794 | 105.3078
1795 | 119.117
1796 | 122.9234
1797 | 111.6333
1798 | 135.1575
1799 | 173.0434
1800 | 133.6658
1801 | 97.6755
1802 | 99.7793
1803 | 133.8048
1804 | 156.6477
1805 | 90.8065
1806 | 106.0427
1807 | 104.1742
1808 | 146.9346
1809 | 74.8667
1810 | 149.924
1811 | 130.8002
1812 | 140.9384
1813 | 78.7391
1814 | 138.5002
1815 | 115.671
1816 | 169.7078
1817 | 137.5482
1818 | 130.7333
1819 | 135.2221
1820 | 59.4305
1821 | 142.6302
1822 | 109.3047
1823 | 148.6406
1824 | 117.0161
1825 | 113.4432
1826 | 114.6679
1827 | 129.1806
1828 | 117.6164
1829 | 122.5563
1830 | 124.8577
1831 | 99.4838
1832 | 128.1256
1833 | 92.3188
1834 | 116.8586
1835 | 79.0842
1836 | 134.7238
1837 | 124.2466
1838 | 123.64
1839 | 104.1731
1840 | 149.7978
1841 | 83.1841
1842 | 129.9282
1843 | 120.2257
1844 | 116.9586
1845 | 127.5496
1846 | 102.2823
1847 | 120.5354
1848 | 119.9344
1849 | 140.1235
1850 | 117.6937
1851 | 109.4165
1852 | 118.8799
1853 | 128.4141
1854 | 134.2122
1855 | 131.457
1856 | 128.8021
1857 | 70.8122
1858 | 84.0725
1859 | 131.2307
1860 | 164.546
1861 | 112.4197
1862 | 149.1341
1863 | 93.6893
1864 | 132.1035
1865 | 117.7932
1866 | 149.6325
1867 | 134.1675
1868 | 124.2156
1869 | 126.6844
1870 | 70.6983
1871 | 123.4634
1872 | 96.9212
1873 | 118.7514
1874 | 101.6361
1875 | 146.6279
1876 | 119.6274
1877 | 158.5341
1878 | 117.9818
1879 | 125.5501
1880 | 115.6168
1881 | 123.3078
1882 | 170.6673
1883 | 150.1599
1884 | 147.884
1885 | 99.8511
1886 | 127.9402
1887 | 142.7098
1888 | 143.2828
1889 | 99.0694
1890 | 133.6824
1891 | 120.2942
1892 | 115.271
1893 | 84.2622
1894 | 117.0424
1895 | 93.3567
1896 | 154.0918
1897 | 139.3283
1898 | 115.0994
1899 | 171.9162
1900 | 167.3468
1901 | 83.7424
1902 | 136.8821
1903 | 118.1371
1904 | 129.1261
1905 | 130.6062
1906 | 144.1539
1907 | 109.7633
1908 | 92.8495
1909 | 82.4715
1910 | 119.0049
1911 | 77.1155
1912 | 141.8078
1913 | 119.8998
1914 | 173.5425
1915 | 99.4468
1916 | 98.9018
1917 | 103.832
1918 | 86.0016
1919 | 122.5515
1920 | 117.0688
1921 | 126.6237
1922 | 104.2348
1923 | 125.4671
1924 | 88.075
1925 | 94.2125
1926 | 131.8894
1927 | 112.3254
1928 | 158.7731
1929 | 117.6352
1930 | 128.5702
1931 | 124.6049
1932 | 138.359
1933 | 149.5064
1934 | 101.2964
1935 | 123.5869
1936 | 115.147
1937 | 118.6352
1938 | 88.8145
1939 | 89.3423
1940 | 88.6806
1941 | 160.6841
1942 | 131.0305
1943 | 111.0405
1944 | 150.6209
1945 | 154.8244
1946 | 99.2371
1947 | 99.9566
1948 | 108.6064
1949 | 138.6646
1950 | 86.7865
1951 | 136.5829
1952 | 94.1243
1953 | 125.4596
1954 | 143.0925
1955 | 145.0499
1956 | 138.2066
1957 | 95.8637
1958 | 141.5608
1959 | 141.6944
1960 | 125.1791
1961 | 149.9348
1962 | 126.8354
1963 | 115.3996
1964 | 115.8162
1965 | 106.6067
1966 | 118.2761
1967 | 108.4443
1968 | 117.8571
1969 | 133.184
1970 | 122.2813
1971 | 147.8473
1972 | 74.7994
1973 | 109.9384
1974 | 106.7798
1975 | 117.6511
1976 | 121.1998
1977 | 155.9261
1978 | 152.5351
1979 | 147.7628
1980 | 133.0353
1981 | 126.2038
1982 | 103.9366
1983 | 129.5215
1984 | 87.3972
1985 | 112.3654
1986 | 99.6189
1987 | 130.7899
1988 | 137.8596
1989 | 77.5622
1990 | 108.2772
1991 | 135.7027
1992 | 110.2324
1993 | 114.1327
1994 | 105.8496
1995 | 131.0407
1996 | 108.4973
1997 | 145.1592
1998 | 127.2276
1999 | 140.708
2000 | 78.4253
2001 | 132.4826
2002 | 70.0386
2003 | 160.4192
2004 | 118.3639
2005 | 126.4997
2006 | 139.9658
2007 | 118.6356
2008 | 134.5584
2009 | 109.3205
2010 | 162.3891
2011 | 115.1216
2012 | 101.0067
2013 | 99.1332
2014 | 102.5388
2015 | 88.3943
2016 | 135.7706
2017 | 144.0543
2018 | 144.5183
2019 | 130.4378
2020 | 110.7111
2021 | 117.6229
2022 | 112.6921
2023 | 154.9963
2024 | 99.9033
2025 | 136.4581
2026 | 95.9606
2027 | 112.9145
2028 | 112.781
2029 | 113.8267
2030 | 127.5374
2031 | 136.1342
2032 | 81.5748
2033 | 102.5488
2034 | 117.7582
2035 | 125.5637
2036 | 142.9199
2037 | 136.368
2038 | 125.2739
2039 | 135.442
2040 | 142.7397
2041 | 114.2987
2042 | 133.5263
2043 | 136.9255
2044 | 108.7348
2045 | 88.7705
2046 | 128.3341
2047 | 124.7304
2048 | 113.4624
2049 | 119.7549
2050 | 160.7029
2051 | 137.5189
2052 | 126.6235
2053 | 97.7065
2054 | 109.0692
2055 | 96.2481
2056 | 120.2701
2057 | 96.1091
2058 | 124.9425
2059 | 91.3646
2060 | 119.4469
2061 | 134.5113
2062 | 86.1408
2063 | 139.8203
2064 | 103.6965
2065 | 123.1633
2066 | 119.616
2067 | 120.1624
2068 | 113.7202
2069 | 141.5202
2070 | 141.0713
2071 | 75.2899
2072 | 120.5293
2073 | 122.492
2074 | 157.5803
2075 | 149.9472
2076 | 106.6453
2077 | 162.8545
2078 | 101.1984
2079 | 121.8415
2080 | 96.0968
2081 | 95.5293
2082 | 131.5612
2083 | 105.0156
2084 | 124.4422
2085 | 91.4039
2086 | 97.0932
2087 | 126.4739
2088 | 116.379
2089 | 135.9816
2090 | 130.6133
2091 | 63.214
2092 | 117.8917
2093 | 139.0635
2094 | 120.2833
2095 | 126.3785
2096 | 169.0948
2097 | 164.4964
2098 | 115.1874
2099 | 179.0076
2100 | 147.6207
2101 | 121.5022
2102 | 130.5916
2103 | 103.9834
2104 | 129.9141
2105 | 104.257
2106 | 143.3474
2107 | 115.3695
2108 | 111.3893
2109 | 102.2155
2110 | 90.6494
2111 | 135.7815
2112 | 93.4155
2113 | 142.208
2114 | 81.9248
2115 | 95.0194
2116 | 125.66
2117 | 119.0293
2118 | 101.5102
2119 | 114.3897
2120 | 137.8994
2121 | 77.4932
2122 | 112.2365
2123 | 102.4031
2124 | 111.8003
2125 | 127.5415
2126 | 138.193
2127 | 106.3969
2128 | 67.0505
2129 | 116.5549
2130 | 101.6535
2131 | 94.5454
2132 | 83.7391
2133 | 122.2048
2134 | 156.5374
2135 | 108.1793
2136 | 128.4878
2137 | 126.5166
2138 | 121.2174
2139 | 134.1611
2140 | 141.8591
2141 | 147.0318
2142 | 145.0109
2143 | 127.1997
2144 | 128.5294
2145 | 121.9819
2146 | 100.7923
2147 | 129.3495
2148 | 83.2873
2149 | 96.0332
2150 | 121.0572
2151 | 132.1945
2152 | 123.6057
2153 | 118.4301
2154 | 127.4734
2155 | 137.1457
2156 | 157.8764
2157 | 147.9411
2158 | 84.6359
2159 | 136.3614
2160 | 114.2963
2161 | 105.4834
2162 | 122.5483
2163 | 89.8795
2164 | 90.9574
2165 | 153.827
2166 | 109.5323
2167 | 86.2832
2168 | 125.2842
2169 | 132.2764
2170 | 106.4326
2171 | 144.1247
2172 | 118.2166
2173 | 87.6126
2174 | 137.3529
2175 | 78.5214
2176 | 120.7335
2177 | 127.1
2178 | 131.6724
2179 | 137.6533
2180 | 131.5848
2181 | 128.2726
2182 | 106.4569
2183 | 156.7605
2184 | 96.1273
2185 | 125.1864
2186 | 129.6792
2187 | 140.766
2188 | 91.2283
2189 | 133.1749
2190 | 96.8297
2191 | 118.8271
2192 | 112.6228
2193 | 157.1589
2194 | 112.2969
2195 | 123.8313
2196 | 106.6771
2197 | 112.5418
2198 | 102.203
2199 | 56.3456
2200 | 109.5722
2201 | 148.2476
2202 | 106.3163
2203 | 130.6299
2204 | 112.345
2205 | 117.0772
2206 | 130.6312
2207 | 102.2899
2208 | 91.1116
2209 | 79.5182
2210 | 161.3089
2211 | 117.0826
2212 | 111.24
2213 | 99.4303
2214 | 148.4909
2215 | 157.4432
2216 | 104.5713
2217 | 82.6509
2218 | 145.7106
2219 | 84.8017
2220 | 111.5043
2221 | 140.7375
2222 | 131.085
2223 | 124.0472
2224 | 115.3398
2225 | 122.0052
2226 | 118.7869
2227 | 119.7276
2228 | 106.7093
2229 | 78.5551
2230 | 129.7067
2231 | 100.129
2232 | 153.0777
2233 | 127.7048
2234 | 127.4015
2235 | 124.0549
2236 | 125.3522
2237 | 94.716
2238 | 91.7281
2239 | 131.5268
2240 | 148.7098
2241 | 137.8513
2242 | 125.7154
2243 | 108.3174
2244 | 139.5598
2245 | 143.8318
2246 | 138.0622
2247 | 133.0578
2248 | 144.3696
2249 | 117.3404
2250 | 46.42
2251 | 148.0989
2252 | 67.3918
2253 | 79.9808
2254 | 125.594
2255 | 131.2727
2256 | 109.2481
2257 | 146.4546
2258 | 116.8128
2259 | 133.041
2260 | 82.9994
2261 | 121.1587
2262 | 114.8902
2263 | 116.4138
2264 | 106.4394
2265 | 83.8808
2266 | 125.9127
2267 | 110.6886
2268 | 131.122
2269 | 138.8729
2270 | 96.4143
2271 | 114.094
2272 | 142.1294
2273 | 66.8215
2274 | 115.292
2275 | 163.4855
2276 | 121.171
2277 | 110.8874
2278 | 117.194
2279 | 91.1747
2280 | 77.2424
2281 | 130.1251
2282 | 106.8175
2283 | 106.4483
2284 | 132.6464
2285 | 151.1431
2286 | 113.2656
2287 | 144.8305
2288 | 126.1784
2289 | 130.3254
2290 | 141.6878
2291 | 128.9203
2292 | 107.2158
2293 | 110.3567
2294 | 160.5697
2295 | 139.227
2296 | 144.4694
2297 | 106.8497
2298 | 102.1457
2299 | 160.3841
2300 | 97.4128
2301 | 142.9824
2302 | 146.4214
2303 | 124.2482
2304 | 101.7142
2305 | 148.2383
2306 | 157.4517
2307 | 101.8539
2308 | 119.3632
2309 | 160.2581
2310 | 154.6908
2311 | 114.6872
2312 | 105.0964
2313 | 142.377
2314 | 129.7963
2315 | 164.0659
2316 | 97.0225
2317 | 154.6661
2318 | 67.9059
2319 | 109.5471
2320 | 105.4868
2321 | 84.5441
2322 | 83.8029
2323 | 114.3646
2324 | 75.6207
2325 | 163.6224
2326 | 94.6539
2327 | 89.0258
2328 | 104.3101
2329 | 128.0062
2330 | 105.3203
2331 | 92.9039
2332 | 135.094
2333 | 129.4508
2334 | 150.1094
2335 | 101.1138
2336 | 128.2327
2337 | 157.4484
2338 | 148.8279
2339 | 137.2931
2340 | 120.2476
2341 | 115.425
2342 | 111.8111
2343 | 155.6827
2344 | 90.4705
2345 | 116.7403
2346 | 137.6835
2347 | 98.6702
2348 | 109.7137
2349 | 93.7966
2350 | 130.9212
2351 | 131.2532
2352 | 114.1202
2353 | 121.1775
2354 | 122.6965
2355 | 149.6307
2356 | 100.0228
2357 | 141.6721
2358 | 140.0016
2359 | 163.0996
2360 | 155.8509
2361 | 113.5193
2362 | 125.6397
2363 | 76.0986
2364 | 102.9315
2365 | 111.436
2366 | 139.2062
2367 | 91.4313
2368 | 101.2434
2369 | 119.4209
2370 | 143.3876
2371 | 150.779
2372 | 127.9412
2373 | 103.0672
2374 | 108.8909
2375 | 108.4961
2376 | 148.6468
2377 | 94.0525
2378 | 122.3444
2379 | 98.3919
2380 | 102.0873
2381 | 121.5946
2382 | 125.9466
2383 | 74.3426
2384 | 86.9927
2385 | 138.3505
2386 | 115.6574
2387 | 159.7918
2388 | 114.0268
2389 | 107.9542
2390 | 114.3262
2391 | 106.8491
2392 | 129.6469
2393 | 108.6099
2394 | 87.4964
2395 | 133.3948
2396 | 111.2329
2397 | 162.8839
2398 | 139.0913
2399 | 109.2542
2400 | 188.9536
2401 | 109.7586
2402 | 80.0824
2403 | 122.2743
2404 | 123.9203
2405 | 155.3144
2406 | 134.0569
2407 | 139.689
2408 | 107.6579
2409 | 142.4088
2410 | 147.0011
2411 | 150.3678
2412 | 122.4945
2413 | 110.4577
2414 | 130.1938
2415 | 88.3881
2416 | 124.5282
2417 | 155.8033
2418 | 126.9532
2419 | 176.4903
2420 | 129.8165
2421 | 97.7691
2422 | 154.4563
2423 | 119.8759
2424 | 162.76
2425 | 101.4128
2426 | 133.2199
2427 | 138.0997
2428 | 119.3107
2429 | 95.6717
2430 | 71.6087
2431 | 90.1658
2432 | 103.3835
2433 | 94.3329
2434 | 158.9203
2435 | 111.0074
2436 | 155.2499
2437 | 122.6244
2438 | 154.7365
2439 | 117.7536
2440 | 129.0567
2441 | 88.3117
2442 | 142.9144
2443 | 98.1324
2444 | 114.7895
2445 | 126.0117
2446 | 99.0931
2447 | 67.3042
2448 | 84.1323
2449 | 128.3251
2450 | 105.0737
2451 | 148.8978
2452 | 136.4287
2453 | 124.3704
2454 | 159.4694
2455 | 112.7223
2456 | 122.996
2457 | 112.86
2458 | 123.8871
2459 | 90.8672
2460 | 87.3127
2461 | 106.5937
2462 | 120.0342
2463 | 96.0446
2464 | 123.4672
2465 | 126.6215
2466 | 87.1086
2467 | 159.6952
2468 | 133.0847
2469 | 125.186
2470 | 112.9087
2471 | 111.3327
2472 | 73.203
2473 | 110.3159
2474 | 118.1698
2475 | 155.2813
2476 | 143.8572
2477 | 137.2822
2478 | 144.3499
2479 | 145.1981
2480 | 151.7592
2481 | 113.2957
2482 | 136.7022
2483 | 138.8763
2484 | 140.3938
2485 | 130.4578
2486 | 144.7654
2487 | 146.9863
2488 | 130.4261
2489 | 110.3666
2490 | 128.3242
2491 | 122.457
2492 | 57.8087
2493 | 167.9225
2494 | 127.8168
2495 | 65.9445
2496 | 136.58
2497 | 142.5913
2498 | 122.9305
2499 | 119.8302
2500 | 121.1036
2501 | 111.3187
2502 | 144.6661
2503 | 97.2811
2504 | 132.3507
2505 | 117.9915
2506 | 141.4808
2507 | 144.9498
2508 | 122.0475
2509 | 152.2962
2510 | 68.912
2511 | 135.314
2512 | 172.4225
2513 | 117.9808
2514 | 104.2794
2515 | 121.7809
2516 | 91.074
2517 | 112.5804
2518 | 96.7761
2519 | 103.3908
2520 | 158.3075
2521 | 124.2174
2522 | 135.4406
2523 | 126.1406
2524 | 129.3647
2525 | 75.0788
2526 | 156.2802
2527 | 133.7858
2528 | 97.4228
2529 | 119.4207
2530 | 77.465
2531 | 162.7157
2532 | 183.5466
2533 | 140.5214
2534 | 121.2183
2535 | 169.7098
2536 | 143.0262
2537 | 102.0528
2538 | 128.4296
2539 | 93.1593
2540 | 114.955
2541 | 105.1103
2542 | 89.9784
2543 | 109.1937
2544 | 104.0672
2545 | 113.2093
2546 | 111.7665
2547 | 179.5717
2548 | 82.9113
2549 | 112.98
2550 | 121.8881
2551 | 52.911
2552 | 96.9772
2553 | 158.6543
2554 | 124.2648
2555 | 144.5152
2556 | 114.2575
2557 | 126.8047
2558 | 110.4848
2559 | 59.6703
2560 | 156.5511
2561 | 107.0854
2562 | 149.2405
2563 | 96.7041
2564 | 127.3968
2565 | 111.6828
2566 | 103.2759
2567 | 93.9133
2568 | 98.0566
2569 | 146.4541
2570 | 148.7501
2571 | 107.35
2572 | 117.7358
2573 | 136.2518
2574 | 127.9164
2575 | 87.497
2576 | 101.5532
2577 | 117.1877
2578 | 126.4124
2579 | 167.207
2580 | 88.9163
2581 | 106.6649
2582 | 99.0397
2583 | 123.8516
2584 | 119.7791
2585 | 132.5596
2586 | 135.8155
2587 | 117.7716
2588 | 170.5021
2589 | 107.6304
2590 | 90.5228
2591 | 79.6644
2592 | 120.5074
2593 | 140.0099
2594 | 79.0964
2595 | 127.8323
2596 | 91.8463
2597 | 97.6048
2598 | 120.5435
2599 | 119.4086
2600 | 100.9404
2601 | 94.9648
2602 | 126.1553
2603 | 151.7994
2604 | 95.4483
2605 | 120.3287
2606 | 108.1213
2607 | 90.8535
2608 | 114.2177
2609 | 96.9123
2610 | 98.7239
2611 | 162.359
2612 | 124.2076
2613 | 125.4525
2614 | 157.8347
2615 | 124.704
2616 | 110.4056
2617 | 156.3211
2618 | 90.9265
2619 | 154.7317
2620 | 104.6837
2621 | 73.0308
2622 | 93.9343
2623 | 135.9827
2624 | 120.591
2625 | 133.4649
2626 | 106.4097
2627 | 93.2621
2628 | 157.1302
2629 | 114.5832
2630 | 65.9419
2631 | 140.6704
2632 | 113.3243
2633 | 137.3224
2634 | 104.1699
2635 | 130.2385
2636 | 173.9419
2637 | 61.827
2638 | 100.359
2639 | 135.7006
2640 | 151.6296
2641 | 162.087
2642 | 121.4205
2643 | 151.8365
2644 | 105.7422
2645 | 151.2814
2646 | 68.034
2647 | 109.2146
2648 | 90.6849
2649 | 135.1279
2650 | 131.019
2651 | 130.7183
2652 | 109.6874
2653 | 107.9179
2654 | 153.5406
2655 | 124.5207
2656 | 118.2079
2657 | 101.4114
2658 | 103.6001
2659 | 87.7612
2660 | 80.6684
2661 | 116.6554
2662 | 93.4151
2663 | 133.2506
2664 | 142.9977
2665 | 108.0653
2666 | 145.3083
2667 | 105.1707
2668 | 143.422
2669 | 123.6177
2670 | 135.4797
2671 | 92.6686
2672 | 66.2891
2673 | 76.5478
2674 | 138.008
2675 | 112.1786
2676 | 94.5189
2677 | 94.5866
2678 | 147.7249
2679 | 132.4059
2680 | 138.5948
2681 | 104.8605
2682 | 169.0498
2683 | 132.5121
2684 | 105.6478
2685 | 125.2967
2686 | 119.4878
2687 | 110.1905
2688 | 70.6449
2689 | 104.2449
2690 | 164.3991
2691 | 109.1172
2692 | 105.3031
2693 | 125.1712
2694 | 139.8614
2695 | 87.6749
2696 | 110.9226
2697 | 123.1057
2698 | 117.9248
2699 | 123.877
2700 | 84.1396
2701 | 128.0624
2702 | 100.5038
2703 | 107.7282
2704 | 39.2062
2705 | 131.1582
2706 | 109.5668
2707 | 107.6159
2708 | 175.9481
2709 | 156.619
2710 | 88.591
2711 | 134.4799
2712 | 125.7454
2713 | 116.1837
2714 | 114.6724
2715 | 130.0645
2716 | 122.6934
2717 | 96.1443
2718 | 145.0761
2719 | 123.325
2720 | 117.4397
2721 | 114.0329
2722 | 96.3135
2723 | 101.2578
2724 | 131.7625
2725 | 151.1798
2726 | 135.1212
2727 | 133.4261
2728 | 105.7168
2729 | 144.465
2730 | 157.131
2731 | 180.3955
2732 | 76.9022
2733 | 119.6139
2734 | 90.1855
2735 | 123.3973
2736 | 104.6914
2737 | 69.99
2738 | 159.7053
2739 | 108.6523
2740 | 75.8322
2741 | 127.1822
2742 | 139.0598
2743 | 102.2464
2744 | 92.1105
2745 | 91.7489
2746 | 84.1315
2747 | 149.3162
2748 | 84.5569
2749 | 95.2432
2750 | 127.8969
2751 | 109.1584
2752 | 136.9603
2753 | 119.3572
2754 | 97.3291
2755 | 115.3945
2756 | 96.6098
2757 | 123.7388
2758 | 106.0594
2759 | 137.4848
2760 | 153.8879
2761 | 111.7183
2762 | 135.3581
2763 | 128.132
2764 | 99.736
2765 | 115.5189
2766 | 103.8768
2767 | 107.5158
2768 | 119.9223
2769 | 171.3564
2770 | 92.7556
2771 | 106.5774
2772 | 148.8352
2773 | 140.631
2774 | 169.4026
2775 | 113.01
2776 | 138.3423
2777 | 126.0599
2778 | 122.3986
2779 | 82.4187
2780 | 100.4439
2781 | 95.0239
2782 | 122.8236
2783 | 134.5398
2784 | 118.7067
2785 | 110.5552
2786 | 134.9455
2787 | 80.7788
2788 | 160.5482
2789 | 99.4577
2790 | 100.7525
2791 | 125.7222
2792 | 158.6402
2793 | 113.1856
2794 | 138.4685
2795 | 107.1731
2796 | 183.7186
2797 | 99.2523
2798 | 97.5657
2799 | 164.4695
2800 | 132.8075
2801 | 125.1129
2802 | 108.4085
2803 | 89.8658
2804 | 131.8708
2805 | 85.3406
2806 | 93.7932
2807 | 142.0281
2808 | 122.0362
2809 | 153.3835
2810 | 128.6275
2811 | 117.3644
2812 | 134.9751
2813 | 88.211
2814 | 105.6489
2815 | 131.5046
2816 | 82.5143
2817 | 135.9527
2818 | 120.7726
2819 | 83.8241
2820 | 130.2106
2821 | 152.3628
2822 | 112.3106
2823 | 128.4722
2824 | 151.5962
2825 | 121.6655
2826 | 108.1882
2827 | 116.8682
2828 | 211.2496
2829 | 150.927
2830 | 115.4863
2831 | 80.5261
2832 | 138.657
2833 | 138.9062
2834 | 132.8303
2835 | 144.3193
2836 | 132.9591
2837 | 128.539
2838 | 125.4839
2839 | 139.6756
2840 | 85.8249
2841 | 132.8249
2842 | 73.5611
2843 | 113.2733
2844 | 133.694
2845 | 98.3565
2846 | 123.5882
2847 | 127.8855
2848 | 152.0656
2849 | 72.2413
2850 | 122.289
2851 | 121.5538
2852 | 123.7351
2853 | 110.5965
2854 | 91.9946
2855 | 132.0445
2856 | 107.9231
2857 | 133.6288
2858 | 114.0074
2859 | 126.8714
2860 | 106.306
2861 | 138.4119
2862 | 104.1133
2863 | 122.9135
2864 | 117.8198
2865 | 159.9839
2866 | 133.1295
2867 | 111.5284
2868 | 140.3834
2869 | 112.6507
2870 | 118.6659
2871 | 137.6984
2872 | 107.5275
2873 | 85.4202
2874 | 123.2522
2875 | 128.7485
2876 | 125.0417
2877 | 125.6625
2878 | 116.0042
2879 | 105.7351
2880 | 100.4454
2881 | 95.0968
2882 | 146.4001
2883 | 86.2873
2884 | 86.5114
2885 | 140.6602
2886 | 147.2186
2887 | 159.1597
2888 | 147.0583
2889 | 140.5905
2890 | 111.8276
2891 | 160.1027
2892 | 103.9371
2893 | 102.3591
2894 | 154.1885
2895 | 134.246
2896 | 119.1495
2897 | 126.565
2898 | 90.1638
2899 | 89.8382
2900 | 129.2978
2901 | 118.7515
2902 | 132.0476
2903 | 90.9218
2904 | 114.4188
2905 | 115.4958
2906 | 150.998
2907 | 100.7907
2908 | 144.7643
2909 | 76.8466
2910 | 153.6732
2911 | 136.1524
2912 | 88.2976
2913 | 96.7448
2914 | 138.1503
2915 | 114.3637
2916 | 122.4067
2917 | 107.1187
2918 | 119.7844
2919 | 148.217
2920 | 128.5896
2921 | 121.1082
2922 | 103.7612
2923 | 103.3291
2924 | 100.1752
2925 | 136.3446
2926 | 115.5043
2927 | 64.5476
2928 | 113.8119
2929 | 153.9703
2930 | 134.4614
2931 | 128.5062
2932 | 165.0158
2933 | 149.1557
2934 | 142.8193
2935 | 114.3324
2936 | 126.3294
2937 | 131.3004
2938 | 154.3852
2939 | 113.5583
2940 | 139.6654
2941 | 114.6075
2942 | 112.1939
2943 | 106.3228
2944 | 149.386
2945 | 142.2544
2946 | 116.8983
2947 | 105.5499
2948 | 107.1763
2949 | 168.3891
2950 | 101.931
2951 | 140.997
2952 | 162.7239
2953 | 132.2199
2954 | 117.8921
2955 | 140.5662
2956 | 119.5936
2957 | 106.7453
2958 | 126.3152
2959 | 83.8393
2960 | 147.5854
2961 | 75.784
2962 | 96.2967
2963 | 112.4056
2964 | 133.2256
2965 | 160.2812
2966 | 122.786
2967 | 127.3042
2968 | 149.354
2969 | 123.6434
2970 | 163.2656
2971 | 85.5013
2972 | 122.2075
2973 | 93.8973
2974 | 145.7404
2975 | 145.0381
2976 | 133.7187
2977 | 120.552
2978 | 123.0168
2979 | 91.5527
2980 | 139.407
2981 | 125.0372
2982 | 92.0303
2983 | 137.0734
2984 | 130.3361
2985 | 143.94
2986 | 123.1155
2987 | 70.4819
2988 | 150.3392
2989 | 99.6703
2990 | 150.5478
2991 | 71.396
2992 | 86.9741
2993 | 112.8422
2994 | 37.8285
2995 | 139.9408
2996 | 132.4469
2997 | 137.3379
2998 | 101.9641
2999 | 93.8136
3000 | 141.163
3001 | 140.2063
3002 | 129.9923
3003 | 89.6863
3004 | 159.8338
3005 | 147.4365
3006 | 107.8898
3007 | 118.7775
3008 | 104.7523
3009 | 131.6941
3010 | 131.9448
3011 | 111.9966
3012 | 93.2226
3013 | 125.3864
3014 | 120.2016
3015 | 126.9209
3016 | 125.2619
3017 | 92.7012
3018 | 136.4751
3019 | 91.3022
3020 | 150.9833
3021 | 66.7142
3022 | 149.9528
3023 | 172.2844
3024 | 120.7011
3025 | 104.2959
3026 | 123.9193
3027 | 120.436
3028 | 112.4804
3029 | 108.8185
3030 | 171.7876
3031 | 86.3644
3032 | 144.3995
3033 | 82.8699
3034 | 130.5041
3035 | 111.3205
3036 | 107.6158
3037 | 142.4142
3038 | 116.9054
3039 | 129.6842
3040 | 128.3304
3041 | 114.5142
3042 | 103.7742
3043 | 121.1675
3044 | 135.354
3045 | 106.023
3046 | 132.5385
3047 | 111.7228
3048 | 115.8009
3049 | 79.4492
3050 | 128.2754
3051 | 138.703
3052 | 112.062
3053 | 105.7546
3054 | 123.0235
3055 | 140.4661
3056 | 124.7456
3057 | 115.9828
3058 | 114.6807
3059 | 127.7747
3060 | 96.9329
3061 | 117.3234
3062 | 98.668
3063 | 86.6247
3064 | 114.6762
3065 | 107.915
3066 | 128.6437
3067 | 109.1286
3068 | 110.47
3069 | 100.2835
3070 | 73.9679
3071 | 189.2101
3072 | 161.3136
3073 | 159.6365
3074 | 128.4423
3075 | 116.9592
3076 | 166.9935
3077 | 113.8411
3078 | 115.1178
3079 | 124.326
3080 | 110.4859
3081 | 108.4258
3082 | 119.2738
3083 | 139.5391
3084 | 112.0234
3085 | 111.7773
3086 | 111.4407
3087 | 135.2411
3088 | 151.6779
3089 | 158.2471
3090 | 117.4446
3091 | 87.4843
3092 | 148.6909
3093 | 167.5959
3094 | 118.8287
3095 | 103.552
3096 | 161.9324
3097 | 143.2205
3098 | 109.4164
3099 | 165.5248
3100 | 130.8979
3101 | 73.4134
3102 | 100.1103
3103 | 121.0455
3104 | 130.1372
3105 | 95.6026
3106 | 93.3421
3107 | 138.3355
3108 | 121.7294
3109 | 154.3214
3110 | 162.0005
3111 | 127.2733
3112 | 131.731
3113 | 148.5146
3114 | 105.12
3115 | 132.9393
3116 | 155.7008
3117 | 118.5933
3118 | 89.7367
3119 | 86.9543
3120 | 134.9942
3121 | 120.6611
3122 | 131.7531
3123 | 106.3288
3124 | 91.7012
3125 | 89.1411
3126 | 104.2406
3127 | 105.9898
3128 | 123.0717
3129 | 143.2415
3130 | 124.2462
3131 | 129.5867
3132 | 111.1623
3133 | 148.0385
3134 | 106.1682
3135 | 130.261
3136 | 114.7269
3137 | 152.7859
3138 | 136.3095
3139 | 110.7085
3140 | 91.1823
3141 | 110.3845
3142 | 140.5538
3143 | 134.5475
3144 | 108.2306
3145 | 102.7186
3146 | 100.9445
3147 | 116.0159
3148 | 107.7919
3149 | 118.3921
3150 | 112.5123
3151 | 164.1476
3152 | 124.807
3153 | 140.8991
3154 | 167.542
3155 | 141.0718
3156 | 130.0663
3157 | 100.0368
3158 | 154.6021
3159 | 113.1974
3160 | 120.8714
3161 | 113.1017
3162 | 113.4673
3163 | 97.1941
3164 | 116.5809
3165 | 121.3169
3166 | 69.9451
3167 | 105.7712
3168 | 137.2733
3169 | 106.9131
3170 | 103.1817
3171 | 141.1026
3172 | 119.6571
3173 | 147.9989
3174 | 108.3474
3175 | 73.978
3176 | 129.8165
3177 | 127.2221
3178 | 145.2813
3179 | 96.1808
3180 | 141.7778
3181 | 107.9775
3182 | 127.1833
3183 | 130.7779
3184 | 91.4146
3185 | 107.9062
3186 | 112.3045
3187 | 112.9619
3188 | 129.4834
3189 | 144.1272
3190 | 152.9728
3191 | 146.2077
3192 | 111.5981
3193 | 110.4294
3194 | 148.6641
3195 | 111.21
3196 | 119.3507
3197 | 138.6983
3198 | 95.6203
3199 | 126.5714
3200 | 90.6234
3201 | 124.437
3202 | 103.6932
3203 | 140.6811
3204 | 150.3667
3205 | 111.1525
3206 | 118.4795
3207 | 75.3927
3208 | 112.9522
3209 | 118.7533
3210 | 151.5992
3211 | 167.1685
3212 | 93.1941
3213 | 128.902
3214 | 113.5921
3215 | 118.4169
3216 | 107.515
3217 | 95.0624
3218 | 101.602
3219 | 101.7613
3220 | 99.1862
3221 | 131.9727
3222 | 101.3521
3223 | 94.2226
3224 | 128.7899
3225 | 152.2191
3226 | 94.707
3227 | 134.006
3228 | 129.1338
3229 | 143.2476
3230 | 56.5248
3231 | 130.1647
3232 | 124.0782
3233 | 153.3434
3234 | 135.881
3235 | 120.5755
3236 | 94.9089
3237 | 162.0551
3238 | 132.3507
3239 | 94.7327
3240 | 131.4778
3241 | 77.8005
3242 | 111.3892
3243 | 119.2586
3244 | 103.6074
3245 | 106.7531
3246 | 110.4108
3247 | 132.8068
3248 | 72.197
3249 | 68.4679
3250 | 113.3094
3251 | 162.4998
3252 | 139.8554
3253 | 157.9243
3254 | 126.2392
3255 | 140.5462
3256 | 115.3591
3257 | 115.6085
3258 | 117.4313
3259 | 81.144
3260 | 126.2216
3261 | 101.4967
3262 | 129.3569
3263 | 114.7214
3264 | 165.2425
3265 | 111.066
3266 | 129.9837
3267 | 107.1683
3268 | 117.5528
3269 | 91.8256
3270 | 147.1451
3271 | 111.3916
3272 | 173.9487
3273 | 135.5054
3274 | 140.6201
3275 | 128.3061
3276 | 134.5173
3277 | 170.1372
3278 | 106.9605
3279 | 108.781
3280 | 152.9554
3281 | 105.0073
3282 | 87.4203
3283 | 119.3602
3284 | 103.7024
3285 | 129.8082
3286 | 145.6756
3287 | 97.2483
3288 | 121.8412
3289 | 106.3567
3290 | 134.8212
3291 | 103.2277
3292 | 159.2675
3293 | 134.4912
3294 | 122.3502
3295 | 156.7231
3296 | 133.7274
3297 | 94.988
3298 | 80.0422
3299 | 130.5046
3300 | 146.0942
3301 | 166.6533
3302 | 142.5025
3303 | 97.9018
3304 | 194.2519
3305 | 129.9538
3306 | 84.0956
3307 | 131.0184
3308 | 157.0392
3309 | 101.0414
3310 | 95.6767
3311 | 131.5108
3312 | 160.1348
3313 | 103.8491
3314 | 121.9647
3315 | 91.8303
3316 | 100.6478
3317 | 153.3587
3318 | 141.4854
3319 | 134.8924
3320 | 95.6559
3321 | 100.545
3322 | 109.2422
3323 | 132.4803
3324 | 97.2139
3325 | 107.8647
3326 | 53.7533
3327 | 93.1793
3328 | 85.4461
3329 | 135.4699
3330 | 148.1367
3331 | 178.8161
3332 | 144.6341
3333 | 113.5854
3334 | 135.5307
3335 | 98.1246
3336 | 152.1457
3337 | 110.322
3338 | 125.6431
3339 | 132.9559
3340 | 129.3707
3341 | 121.1754
3342 | 130.4688
3343 | 118.0831
3344 | 137.8797
3345 | 101.7795
3346 | 105.0785
3347 | 135.964
3348 | 115.9273
3349 | 103.7691
3350 | 128.6197
3351 | 106.8768
3352 | 97.5194
3353 | 153.8508
3354 | 101.3391
3355 | 148.6268
3356 | 125.3489
3357 | 128.8105
3358 | 150.6107
3359 | 104.2219
3360 | 88.1734
3361 | 143.2533
3362 | 126.4339
3363 | 129.4353
3364 | 116.3972
3365 | 110.3968
3366 | 142.7825
3367 | 90.7116
3368 | 114.9545
3369 | 118.8832
3370 | 158.917
3371 | 148.2979
3372 | 163.7962
3373 | 126.9571
3374 | 114.3957
3375 | 133.9134
3376 | 144.5086
3377 | 142.7439
3378 | 108.1538
3379 | 118.594
3380 | 88.7816
3381 | 91.0888
3382 | 113.0246
3383 | 170.9506
3384 | 152.5981
3385 | 154.9457
3386 | 61.8277
3387 | 107.6145
3388 | 140.3659
3389 | 124.9675
3390 | 139.2185
3391 | 90.3331
3392 | 136.1572
3393 | 115.1256
3394 | 84.9897
3395 | 123.7544
3396 | 107.8793
3397 | 96.4537
3398 | 121.0999
3399 | 120.8595
3400 | 149.1131
3401 | 97.098
3402 | 113.7565
3403 | 102.6343
3404 | 142.3843
3405 | 116.5504
3406 | 106.998
3407 | 114.4914
3408 | 126.2538
3409 | 125.346
3410 | 118.2863
3411 | 114.4604
3412 | 125.2697
3413 | 93.6906
3414 | 147.2237
3415 | 151.1685
3416 | 76.9688
3417 | 118.942
3418 | 114.0763
3419 | 148.1886
3420 | 107.6477
3421 | 116.3565
3422 | 93.4712
3423 | 130.3237
3424 | 132.7902
3425 | 115.8298
3426 | 112.6881
3427 | 92.8653
3428 | 151.2276
3429 | 138.7983
3430 | 160.3669
3431 | 150.317
3432 | 136.5632
3433 | 109.3215
3434 | 89.6472
3435 | 95.5913
3436 | 88.6103
3437 | 121.0941
3438 | 92.5732
3439 | 141.7118
3440 | 133.2866
3441 | 138.9607
3442 | 136.9917
3443 | 108.8068
3444 | 124.07
3445 | 100.5513
3446 | 132.4524
3447 | 137.4319
3448 | 135.8549
3449 | 135.8079
3450 | 135.1219
3451 | 123.4682
3452 | 99.7088
3453 | 102.253
3454 | 105.8177
3455 | 140.99
3456 | 120.0835
3457 | 155.1023
3458 | 134.276
3459 | 144.4828
3460 | 107.2575
3461 | 105.944
3462 | 120.0341
3463 | 140.2244
3464 | 135.7312
3465 | 106.6911
3466 | 142.8326
3467 | 144.544
3468 | 157.9949
3469 | 86.1714
3470 | 95.77
3471 | 119.7729
3472 | 82.8213
3473 | 132.1847
3474 | 75.4567
3475 | 124.4639
3476 | 126.243
3477 | 143.5081
3478 | 147.7759
3479 | 108.9329
3480 | 139.5204
3481 | 155.5757
3482 | 95.8132
3483 | 98.4092
3484 | 99.9692
3485 | 132.4318
3486 | 110.031
3487 | 115.5377
3488 | 178.1803
3489 | 153.2304
3490 | 139.4296
3491 | 101.0568
3492 | 68.7816
3493 | 120.491
3494 | 100.2605
3495 | 132.2558
3496 | 119.7707
3497 | 143.5456
3498 | 87.3635
3499 | 108.8267
3500 | 104.6094
3501 | 155.5879
3502 | 113.7987
3503 | 112.1798
3504 | 135.3634
3505 | 136.5223
3506 | 130.2649
3507 | 107.758
3508 | 131.3239
3509 | 123.6329
3510 | 123.2921
3511 | 121.7962
3512 | 92.7644
3513 | 91.8064
3514 | 132.7685
3515 | 110.5286
3516 | 109.9725
3517 | 172.0877
3518 | 108.5844
3519 | 120.2325
3520 | 143.5448
3521 | 154.4082
3522 | 100.2984
3523 | 112.7
3524 | 102.126
3525 | 138.9912
3526 | 154.7187
3527 | 169.3124
3528 | 107.8937
3529 | 114.9555
3530 | 129.7931
3531 | 111.5577
3532 | 103.3747
3533 | 124.9191
3534 | 157.2159
3535 | 119.8018
3536 | 99.833
3537 | 105.6461
3538 | 133.236
3539 | 104.7081
3540 | 109.9847
3541 | 142.2424
3542 | 119.6216
3543 | 144.3718
3544 | 130.4462
3545 | 141.0051
3546 | 128.7856
3547 | 168.5695
3548 | 135.1553
3549 | 104.6637
3550 | 102.7109
3551 | 80.4804
3552 | 112.2148
3553 | 123.6215
3554 | 117.3509
3555 | 131.1958
3556 | 147.3653
3557 | 150.3739
3558 | 129.5806
3559 | 168.6367
3560 | 100.2342
3561 | 151.8076
3562 | 98.0072
3563 | 144.2715
3564 | 96.6007
3565 | 125.4832
3566 | 75.6982
3567 | 107.7399
3568 | 134.3447
3569 | 123.8878
3570 | 123.0539
3571 | 126.3728
3572 | 124.371
3573 | 108.4401
3574 | 153.1433
3575 | 152.5009
3576 | 146.1166
3577 | 115.6945
3578 | 94.316
3579 | 90.6679
3580 | 174.3858
3581 | 106.2198
3582 | 126.4507
3583 | 112.8514
3584 | 107.7966
3585 | 89.2906
3586 | 123.1743
3587 | 119.0785
3588 | 121.4439
3589 | 90.8755
3590 | 129.2281
3591 | 102.2485
3592 | 114.1282
3593 | 113.395
3594 | 125.7975
3595 | 91.2597
3596 | 109.3864
3597 | 119.767
3598 | 112.853
3599 | 132.1226
3600 | 150.5629
3601 | 148.3421
3602 | 177.8504
3603 | 152.0186
3604 | 96.8655
3605 | 94.5
3606 | 167.0767
3607 | 136.0887
3608 | 115.3944
3609 | 101.2137
3610 | 128.2725
3611 | 79.0833
3612 | 127.3608
3613 | 128.8448
3614 | 116.4497
3615 | 89.8405
3616 | 80.5509
3617 | 129.7351
3618 | 151.1135
3619 | 99.5857
3620 | 131.9366
3621 | 134.9087
3622 | 98.0968
3623 | 87.1938
3624 | 119.015
3625 | 140.9225
3626 | 129.7562
3627 | 110.2534
3628 | 142.8977
3629 | 178.6019
3630 | 127.229
3631 | 120.037
3632 | 110.6494
3633 | 128.0731
3634 | 149.2926
3635 | 127.0159
3636 | 96.3761
3637 | 74.4566
3638 | 82.1526
3639 | 164.282
3640 | 182.6222
3641 | 123.3226
3642 | 74.3717
3643 | 139.2791
3644 | 65.0575
3645 | 126.8631
3646 | 133.9048
3647 | 126.7511
3648 | 111.1207
3649 | 128.599
3650 | 141.8401
3651 | 148.2026
3652 | 117.9177
3653 | 106.536
3654 | 116.8215
3655 | 98.4165
3656 | 132.0862
3657 | 124.7422
3658 | 157.4838
3659 | 138.8353
3660 | 104.5665
3661 | 99.3776
3662 | 170.5869
3663 | 120.3495
3664 | 134.2734
3665 | 85.7135
3666 | 134.3308
3667 | 123.6596
3668 | 124.1657
3669 | 120.7516
3670 | 158.5945
3671 | 119.0043
3672 | 123.104
3673 | 101.3749
3674 | 156.2052
3675 | 87.357
3676 | 93.7602
3677 | 104.3942
3678 | 127.2262
3679 | 110.368
3680 | 127.583
3681 | 99.599
3682 | 94.9979
3683 | 100.977
3684 | 105.5381
3685 | 102.1275
3686 | 156.3519
3687 | 133.8743
3688 | 156.4283
3689 | 108.5654
3690 | 128.861
3691 | 142.7901
3692 | 135.092
3693 | 152.3348
3694 | 143.7893
3695 | 116.8613
3696 | 128.9197
3697 | 135.8599
3698 | 105.6351
3699 | 77.6422
3700 | 127.5846
3701 | 110.3147
3702 | 101.2223
3703 | 135.0994
3704 | 125.1711
3705 | 107.5271
3706 | 148.9859
3707 | 100.1502
3708 | 99.7936
3709 | 140.8458
3710 | 101.4714
3711 | 73.1633
3712 | 143.7621
3713 | 162.5125
3714 | 95.1335
3715 | 112.4232
3716 | 138.1438
3717 | 118.3614
3718 | 124.0592
3719 | 158.1514
3720 | 145.1911
3721 | 109.4464
3722 | 104.921
3723 | 101.1699
3724 | 130.9467
3725 | 94.9157
3726 | 122.657
3727 | 92.5418
3728 | 126.1428
3729 | 132.9287
3730 | 124.9951
3731 | 136.9014
3732 | 42.0941
3733 | 113.5233
3734 | 154.4995
3735 | 92.4047
3736 | 124.0242
3737 | 82.5203
3738 | 112.8437
3739 | 92.4824
3740 | 125.0922
3741 | 122.9437
3742 | 109.7144
3743 | 111.7405
3744 | 140.1877
3745 | 94.1485
3746 | 156.0409
3747 | 128.8828
3748 | 178.3319
3749 | 109.5769
3750 | 126.6771
3751 | 74.0158
3752 | 103.2252
3753 | 134.1659
3754 | 124.8091
3755 | 104.366
3756 | 111.1139
3757 | 89.4689
3758 | 112.1961
3759 | 133.3521
3760 | 86.9165
3761 | 91.3655
3762 | 104.841
3763 | 87.5895
3764 | 129.1937
3765 | 118.9902
3766 | 144.3293
3767 | 80.6835
3768 | 86.8573
3769 | 100.48
3770 | 131.1078
3771 | 124.2353
3772 | 128.5186
3773 | 140.5244
3774 | 128.1997
3775 | 136.3018
3776 | 124.9245
3777 | 116.3121
3778 | 119.4074
3779 | 111.7289
3780 | 120.0781
3781 | 153.6741
3782 | 150.6195
3783 | 116.3875
3784 | 123.5747
3785 | 147.6672
3786 | 148.2326
3787 | 128.077
3788 | 111.6166
3789 | 100.6891
3790 | 138.6133
3791 | 128.6088
3792 | 139.2704
3793 | 149.633
3794 | 91.5538
3795 | 134.0669
3796 | 96.8254
3797 | 140.1188
3798 | 95.8661
3799 | 102.5633
3800 | 103.2817
3801 | 120.9705
3802 | 140.26
3803 | 137.5261
3804 | 136.1348
3805 | 97.7591
3806 | 125.6895
3807 | 144.4187
3808 | 136.4924
3809 | 130.8582
3810 | 134.5016
3811 | 117.8492
3812 | 132.352
3813 | 132.466
3814 | 87.3372
3815 | 146.9559
3816 | 119.6862
3817 | 138.8977
3818 | 136.6563
3819 | 100.494
3820 | 81.5483
3821 | 139.4321
3822 | 128.5585
3823 | 136.7104
3824 | 142.4902
3825 | 185.2905
3826 | 88.0721
3827 | 123.8841
3828 | 64.4782
3829 | 121.1585
3830 | 102.1856
3831 | 100.9873
3832 | 145.8914
3833 | 167.5888
3834 | 146.6543
3835 | 145.5919
3836 | 131.9136
3837 | 121.5946
3838 | 135.4361
3839 | 80.1052
3840 | 82.7181
3841 | 153.8936
3842 | 130.8727
3843 | 119.2278
3844 | 114.9122
3845 | 102.1801
3846 | 101.9628
3847 | 86.1394
3848 | 116.5834
3849 | 127.0755
3850 | 116.952
3851 | 170.4438
3852 | 117.7708
3853 | 164.5011
3854 | 143.3851
3855 | 82.0637
3856 | 113.7184
3857 | 109.7558
3858 | 120.1592
3859 | 126.7673
3860 | 102.1113
3861 | 141.4322
3862 | 123.4037
3863 | 159.2336
3864 | 111.9947
3865 | 91.6786
3866 | 144.0941
3867 | 187.8305
3868 | 125.5397
3869 | 153.7771
3870 | 130.4252
3871 | 154.8234
3872 | 125.011
3873 | 133.4321
3874 | 128.9037
3875 | 113.4747
3876 | 120.1446
3877 | 91.2196
3878 | 92.0168
3879 | 148.2358
3880 | 151.0931
3881 | 78.9922
3882 | 75.5016
3883 | 111.9949
3884 | 141.0303
3885 | 131.2217
3886 | 124.1659
3887 | 141.7779
3888 | 119.4642
3889 | 125.683
3890 | 100.9281
3891 | 102.6293
3892 | 110.8715
3893 | 177.6793
3894 | 75.1282
3895 | 133.5645
3896 | 149.6429
3897 | 134.6324
3898 | 114.6271
3899 | 110.2146
3900 | 111.8917
3901 | 96.6544
3902 | 93.9913
3903 | 162.6591
3904 | 106.5734
3905 | 157.3076
3906 | 110.9673
3907 | 176.0514
3908 | 108.8117
3909 | 151.3368
3910 | 116.6364
3911 | 137.2601
3912 | 112.3763
3913 | 121.6176
3914 | 135.1725
3915 | 160.1422
3916 | 143.7273
3917 | 124.3524
3918 | 138.4613
3919 | 116.9359
3920 | 105.0057
3921 | 95.6165
3922 | 95.3835
3923 | 127.9743
3924 | 109.4473
3925 | 142.7263
3926 | 97.1119
3927 | 105.1158
3928 | 120.1916
3929 | 130.2448
3930 | 158.082
3931 | 105.6531
3932 | 109.978
3933 | 149.1762
3934 | 132.858
3935 | 90.1624
3936 | 140.4955
3937 | 134.5202
3938 | 113.0546
3939 | 111.5606
3940 | 117.542
3941 | 129.8979
3942 | 139.1098
3943 | 133.4762
3944 | 99.736
3945 | 121.2318
3946 | 137.5668
3947 | 175.3793
3948 | 112.9869
3949 | 72.7095
3950 | 112.0098
3951 | 104.4759
3952 | 95.2993
3953 | 127.6916
3954 | 114.2222
3955 | 123.73
3956 | 107.0857
3957 | 151.91
3958 | 103.8797
3959 | 118.2787
3960 | 90.1425
3961 | 90.7557
3962 | 105.5005
3963 | 182.0898
3964 | 133.5179
3965 | 114.0701
3966 | 110.4224
3967 | 154.517
3968 | 109.6737
3969 | 115.5129
3970 | 144.095
3971 | 130.5606
3972 | 121.2873
3973 | 119.5946
3974 | 110.058
3975 | 126.4096
3976 | 126.482
3977 | 89.4289
3978 | 129.2805
3979 | 97.039
3980 | 87.4883
3981 | 151.0226
3982 | 114.5259
3983 | 101.2835
3984 | 118.6995
3985 | 85.7582
3986 | 75.9719
3987 | 118.238
3988 | 117.1327
3989 | 80.1583
3990 | 137.1179
3991 | 115.5271
3992 | 110.6789
3993 | 129.2391
3994 | 89.9266
3995 | 89.0546
3996 | 122.8262
3997 | 91.3245
3998 | 105.0158
3999 | 110.6631
4000 | 128.2606
4001 | 69.1547
4002 | 132.5899
4003 | 81.4854
4004 | 88.2396
4005 | 124.9142
4006 | 103.9197
4007 | 122.5161
4008 | 96.4194
4009 | 98.6732
4010 | 120.1933
4011 | 171.9889
4012 | 87.5448
4013 | 98.3994
4014 | 97.0222
4015 | 123.9364
4016 | 95.6225
4017 | 76.9766
4018 | 92.7128
4019 | 68.5649
4020 | 111.0797
4021 | 91.3765
4022 | 149.6937
4023 | 87.832
4024 | 118.4334
4025 | 120.9174
4026 | 104.9894
4027 | 119.9742
4028 | 111.9557
4029 | 126.5648
4030 | 77.3934
4031 | 97.04
4032 | 120.4977
4033 | 147.9029
4034 | 107.5682
4035 | 109.1832
4036 | 100.2594
4037 | 178.422
4038 | 157.3126
4039 | 108.4595
4040 | 110.3298
4041 | 150.8091
4042 | 109.8306
4043 | 125.4727
4044 | 115.5049
4045 | 162.8748
4046 | 123.9104
4047 | 141.7485
4048 | 98.7928
4049 | 127.0448
4050 | 140.3784
4051 | 141.5909
4052 | 139.9822
4053 | 106.5386
4054 | 144.5952
4055 | 126.3035
4056 | 140.6803
4057 | 153.6236
4058 | 144.1592
4059 | 121.1901
4060 | 131.0059
4061 | 115.4857
4062 | 110.8763
4063 | 122.7887
4064 | 76.5709
4065 | 97.2579
4066 | 157.2189
4067 | 140.5897
4068 | 115.7704
4069 | 101.5148
4070 | 91.2734
4071 | 89.2908
4072 | 96.9575
4073 | 94.3195
4074 | 157.1868
4075 | 134.7718
4076 | 197.9567
4077 | 127.5337
4078 | 115.4737
4079 | 140.6963
4080 | 103.1829
4081 | 139.6436
4082 | 108.2137
4083 | 139.1131
4084 | 116.928
4085 | 128.5373
4086 | 88.1751
4087 | 120.9804
4088 | 118.4405
4089 | 128.4151
4090 | 98.6288
4091 | 113.8118
4092 | 122.3442
4093 | 81.2247
4094 | 127.2557
4095 | 118.7736
4096 | 133.8714
4097 | 151.1494
4098 | 98.588
4099 | 121.0796
4100 | 113.9714
4101 | 138.5104
4102 | 78.9199
4103 | 122.6189
4104 | 106.2472
4105 | 122.1685
4106 | 127.4592
4107 | 91.8575
4108 | 112.0173
4109 | 122.881
4110 | 110.6909
4111 | 103.7097
4112 | 114.7395
4113 | 96.748
4114 | 177.6033
4115 | 125.1537
4116 | 110.5275
4117 | 105.2384
4118 | 164.0684
4119 | 134.3098
4120 | 125.8254
4121 | 128.2625
4122 | 127.8636
4123 | 130.3675
4124 | 128.5293
4125 | 89.7668
4126 | 133.5875
4127 | 134.0039
4128 | 126.2275
4129 | 133.4912
4130 | 152.5417
4131 | 145.9261
4132 | 138.9366
4133 | 124.9585
4134 | 78.6031
4135 | 118.3386
4136 | 143.7815
4137 | 160.2158
4138 | 128.3327
4139 | 118.9383
4140 | 112.6341
4141 | 133.5833
4142 | 116.5289
4143 | 121.2673
4144 | 142.9593
4145 | 142.2092
4146 | 136.3831
4147 | 77.2219
4148 | 92.7636
4149 | 144.6755
4150 | 134.7896
4151 | 119.3986
4152 | 94.452
4153 | 134.5377
4154 | 117.5381
4155 | 130.0303
4156 | 130.0367
4157 | 118.4628
4158 | 112
4159 | 135.581
4160 | 80.3591
4161 | 95.1963
4162 | 108.6167
4163 | 152.8613
4164 | 140.526
4165 | 133.025
4166 | 155.991
4167 | 124.5674
4168 | 130.601
4169 | 144.4873
4170 | 133.4615
4171 | 180.1423
4172 | 146.0526
4173 | 101.9609
4174 | 125.0246
4175 | 135.4265
4176 | 126.6721
4177 | 89.7938
4178 | 113.4815
4179 | 103.4857
4180 | 153.2538
4181 | 92.8907
4182 | 102.4779
4183 | 162.6601
4184 | 128.5976
4185 | 113.3548
4186 | 87.6689
4187 | 118.5061
4188 | 142.7769
4189 | 108.6483
4190 | 111.4405
4191 | 107.529
4192 | 149.4486
4193 | 124.6448
4194 | 122.4176
4195 | 99.32
4196 | 110.019
4197 | 112.1654
4198 | 112.6053
4199 | 139.9182
4200 | 108.1501
4201 | 133.678
4202 | 98.5453
4203 | 79.1878
4204 | 140.3654
4205 | 101.0424
4206 | 107.7255
4207 | 146.8533
4208 | 85.1596
4209 | 54.7581
4210 | 133.0703
4211 | 179.7978
4212 | 96.2641
4213 | 91.5471
4214 | 156.497
4215 | 153.7574
4216 | 93.4906
4217 | 152.4015
4218 | 135.3664
4219 | 138.925
4220 | 104.3177
4221 | 115.2003
4222 | 117.4734
4223 | 115.2545
4224 | 156.7178
4225 | 110.7425
4226 | 130.7942
4227 | 112.5174
4228 | 148.8892
4229 | 120.2552
4230 | 116.1392
4231 | 93.9336
4232 | 99.1532
4233 | 106.0336
4234 | 106.7689
4235 | 128.6378
4236 | 137.2586
4237 | 115.1118
4238 | 125.575
4239 | 103.5789
4240 | 131.0459
4241 | 103.5916
4242 | 109.4253
4243 | 119.468
4244 | 104.2215
4245 | 66.3321
4246 | 114.8703
4247 | 118.4838
4248 | 141.2861
4249 | 102.8532
4250 | 102.7373
4251 | 99.3293
4252 | 156.8908
4253 | 135.4542
4254 | 134.4392
4255 | 96.3081
4256 | 149.3153
4257 | 92.3111
4258 | 148.0692
4259 | 85.8781
4260 | 144.7627
4261 | 128.7092
4262 | 95.664
4263 | 85.6022
4264 | 89.2008
4265 | 165.2737
4266 | 103.6606
4267 | 133.0391
4268 | 141.3185
4269 | 118.8575
4270 | 125.9098
4271 | 121.5782
4272 | 158.2244
4273 | 84.9749
4274 | 76.7704
4275 | 100.8353
4276 | 109.3735
4277 | 90.3853
4278 | 97.9415
4279 | 149.5012
4280 | 144.9622
4281 | 152.9892
4282 | 139.11
4283 | 96.4815
4284 | 134.505
4285 | 156.9696
4286 | 91.1237
4287 | 110.211
4288 | 103.883
4289 | 139.7641
4290 | 131.2706
4291 | 113.3048
4292 | 97.7733
4293 | 136.439
4294 | 132.0325
4295 | 90.6768
4296 | 108.7943
4297 | 92.7335
4298 | 138.8305
4299 | 133.7431
4300 | 127.1321
4301 | 48.627
4302 | 113.4024
4303 | 132.7081
4304 | 127.1037
4305 | 156.6497
4306 | 95.0661
4307 | 100.9275
4308 | 131.6991
4309 | 132.2272
4310 | 141.7762
4311 | 88.9483
4312 | 125.5859
4313 | 99.4093
4314 | 93.2431
4315 | 109.8959
4316 | 126.9047
4317 | 104.7318
4318 | 103.0653
4319 | 72.9064
4320 | 104.5093
4321 | 102.039
4322 | 139.8213
4323 | 94.5887
4324 | 84.2007
4325 | 112.0763
4326 | 110.3739
4327 | 129.1111
4328 | 83.7301
4329 | 125.7724
4330 | 92.6643
4331 | 105.3413
4332 | 130.6235
4333 | 135.0918
4334 | 60.4679
4335 | 108.9976
4336 | 87.2641
4337 | 97.7458
4338 | 119.4399
4339 | 116.8352
4340 | 113.0736
4341 | 149.2693
4342 | 113.4038
4343 | 122.8328
4344 | 134.4977
4345 | 117.1287
4346 | 92.0075
4347 | 131.8065
4348 | 98.4676
4349 | 132.8648
4350 | 95.0117
4351 | 116.6662
4352 | 122.0628
4353 | 150.2322
4354 | 92.2761
4355 | 120.2905
4356 | 77.809
4357 | 103.0144
4358 | 148.4594
4359 | 102.8777
4360 | 137.2471
4361 | 104.403
4362 | 100.4131
4363 | 144.7472
4364 | 107.0262
4365 | 137.882
4366 | 124.2426
4367 | 135.0232
4368 | 97.1891
4369 | 134.9351
4370 | 63.4725
4371 | 107.3554
4372 | 71.2563
4373 | 171.5738
4374 | 111.7744
4375 | 149.515
4376 | 131.9764
4377 | 126.7153
4378 | 119.1789
4379 | 112.9039
4380 | 138.2643
4381 | 139.8985
4382 | 138.1402
4383 | 152.0934
4384 | 105.2209
4385 | 117.313
4386 | 127.9702
4387 | 150.7067
4388 | 143.6624
4389 | 142.7104
4390 | 122.9054
4391 | 141.5696
4392 | 122.4155
4393 | 75.0264
4394 | 149.0983
4395 | 120.9506
4396 | 120.0262
4397 | 125.5396
4398 | 117.8743
4399 | 99.0056
4400 | 116.9219
4401 | 125.5698
4402 | 131.1354
4403 | 121.1094
4404 | 96.967
4405 | 99.8304
4406 | 127.0605
4407 | 181.2673
4408 | 103.7282
4409 | 129.5787
4410 | 115.3929
4411 | 113.6155
4412 | 139.6292
4413 | 141.8596
4414 | 122.2956
4415 | 150.1781
4416 | 150.0158
4417 | 115.5242
4418 | 143.5621
4419 | 110.6892
4420 | 111.2508
4421 | 136.3939
4422 | 98.9547
4423 | 101.5996
4424 | 132.4885
4425 | 125.6052
4426 | 95.7029
4427 | 81.6716
4428 | 110.8704
4429 | 142.4651
4430 | 108.5072
4431 | 142.9293
4432 | 97.798
4433 | 118.4873
4434 | 125.3657
4435 | 111.3716
4436 | 90.7984
4437 | 110.5522
4438 | 138.5219
4439 | 130.7644
4440 | 131.6943
4441 | 131.4313
4442 | 92.4729
4443 | 130.8442
4444 | 134.9945
4445 | 104.1988
4446 | 127.5863
4447 | 156.0576
4448 | 150.0865
4449 | 132.9906
4450 | 88.6013
4451 | 135.25
4452 | 110.3773
4453 | 117.8655
4454 | 118.9655
4455 | 127.4553
4456 | 142.701
4457 | 126.1423
4458 | 110.8331
4459 | 47.5695
4460 | 116.758
4461 | 151.1031
4462 | 158.4811
4463 | 118.8417
4464 | 126.3654
4465 | 139.9252
4466 | 155.5208
4467 | 126.789
4468 | 145.4536
4469 | 111.6705
4470 | 145.6824
4471 | 111.273
4472 | 127.9957
4473 | 84.7081
4474 | 103.5976
4475 | 104.8726
4476 | 147.3525
4477 | 105.2943
4478 | 132.2005
4479 | 98.4257
4480 | 180.871
4481 | 118.9164
4482 | 153.1205
4483 | 124.7991
4484 | 96.3729
4485 | 118.9605
4486 | 92.8865
4487 | 77.2395
4488 | 89.5632
4489 | 77.214
4490 | 98.9762
4491 | 121.8661
4492 | 114.1183
4493 | 106.4305
4494 | 135.9792
4495 | 119.5004
4496 | 137.2423
4497 | 139.2009
4498 | 99.2898
4499 | 100.8903
4500 | 120.4673
4501 | 108.8828
4502 | 99.8164
4503 | 144.9321
4504 | 146.3974
4505 | 136.3813
4506 | 83.0052
4507 | 140.7259
4508 | 139.6944
4509 | 141.2896
4510 | 108.4484
4511 | 113.298
4512 | 131.8078
4513 | 137.5506
4514 | 91.6321
4515 | 127.7776
4516 | 171.6337
4517 | 130.5103
4518 | 122.5954
4519 | 137.4916
4520 | 96.5174
4521 | 73.6243
4522 | 112.058
4523 | 157.4204
4524 | 113.6848
4525 | 126.3689
4526 | 136.1651
4527 | 131.5138
4528 | 147.0391
4529 | 148.2687
4530 | 127.5412
4531 | 100.1136
4532 | 142.3888
4533 | 101.9131
4534 | 109.1568
4535 | 71.0505
4536 | 104.914
4537 | 116.6534
4538 | 144.9548
4539 | 111.2163
4540 | 96.0586
4541 | 135.8068
4542 | 130.5948
4543 | 109.965
4544 | 109.5978
4545 | 116.2423
4546 | 141.6263
4547 | 128.0328
4548 | 110.5122
4549 | 149.718
4550 | 143.499
4551 | 101.2926
4552 | 110.6779
4553 | 116.4823
4554 | 111.3213
4555 | 158.245
4556 | 154.7928
4557 | 138.4393
4558 | 105.3161
4559 | 102.4768
4560 | 103.5816
4561 | 113.8919
4562 | 152.8986
4563 | 100.8
4564 | 96.8484
4565 | 103.3748
4566 | 112.3169
4567 | 102.0876
4568 | 105.0043
4569 | 88.622
4570 | 116.8132
4571 | 72.9967
4572 | 129.6321
4573 | 171.1695
4574 | 101.9919
4575 | 127.1364
4576 | 108.2936
4577 | 111.6425
4578 | 128.8604
4579 | 110.308
4580 | 137.3599
4581 | 101.1801
4582 | 98.471
4583 | 154.4477
4584 | 76.1004
4585 | 110.4158
4586 | 173.952
4587 | 112.269
4588 | 145.4973
4589 | 107.4871
4590 | 180.8116
4591 | 112.5427
4592 | 63.7388
4593 | 122.0393
4594 | 117.0608
4595 | 105.2378
4596 | 91.9796
4597 | 131.2871
4598 | 88.849
4599 | 99.9633
4600 | 117.2852
4601 | 94.1535
4602 | 105.7351
4603 | 120.9914
4604 | 142.0065
4605 | 164.876
4606 | 129.296
4607 | 108.6595
4608 | 163.631
4609 | 124.9119
4610 | 108.7373
4611 | 124.8886
4612 | 87.986
4613 | 98.8849
4614 | 130.9805
4615 | 85.8074
4616 | 108.3562
4617 | 86.5127
4618 | 115.3255
4619 | 105.1403
4620 | 124.2267
4621 | 119.6637
4622 | 111.4965
4623 | 92.453
4624 | 119.7371
4625 | 86.5069
4626 | 116.8171
4627 | 124.2293
4628 | 99.9909
4629 | 103.3979
4630 | 108.3769
4631 | 169.6012
4632 | 156.9935
4633 | 78.6524
4634 | 140.373
4635 | 125.3829
4636 | 152.0903
4637 | 144.7631
4638 | 118.412
4639 | 120.8898
4640 | 146.0558
4641 | 164.7624
4642 | 140.8474
4643 | 142.4366
4644 | 141.8329
4645 | 80.5054
4646 | 99.177
4647 | 146.7795
4648 | 121.7888
4649 | 115.7403
4650 | 106.0152
4651 | 120.6119
4652 | 137.4563
4653 | 118.7513
4654 | 147.4342
4655 | 85.8474
4656 | 113.1552
4657 | 90.0895
4658 | 81.6434
4659 | 104.915
4660 | 120.8984
4661 | 137.4992
4662 | 134.009
4663 | 125.2252
4664 | 111.4292
4665 | 132.2931
4666 | 141.0973
4667 | 97.3893
4668 | 117.6339
4669 | 128.3626
4670 | 129.5421
4671 | 124.94
4672 | 82.8123
4673 | 89.4933
4674 | 161.1641
4675 | 98.3642
4676 | 135.6862
4677 | 115.7515
4678 | 134.7809
4679 | 138.338
4680 | 98.6287
4681 | 145.3816
4682 | 110.7989
4683 | 82.9077
4684 | 85.2237
4685 | 110.3207
4686 | 112.034
4687 | 99.4979
4688 | 98.7451
4689 | 87.0877
4690 | 116.9096
4691 | 135.7386
4692 | 115.2275
4693 | 89.0452
4694 | 126.9456
4695 | 112.7479
4696 | 122.5899
4697 | 127.9749
4698 | 90.8951
4699 | 109.043
4700 | 86.2506
4701 | 118.0342
4702 | 118.1419
4703 | 124.2937
4704 | 134.3146
4705 | 121.5395
4706 | 119.2699
4707 | 116.6472
4708 | 127.124
4709 | 110.5729
4710 | 95.5136
4711 | 98.3609
4712 | 119.567
4713 | 164.5343
4714 | 114.3154
4715 | 87.3444
4716 | 102.5363
4717 | 97.4263
4718 | 130.9697
4719 | 91.4932
4720 | 174.1707
4721 | 111.8743
4722 | 110.8703
4723 | 124.3761
4724 | 107.3992
4725 | 124.255
4726 | 152.9976
4727 | 108.5395
4728 | 114.8811
4729 | 143.0346
4730 | 110.3234
4731 | 145.6049
4732 | 152.0145
4733 | 137.1134
4734 | 94.1673
4735 | 114.3121
4736 | 133.0841
4737 | 131.4611
4738 | 124.6062
4739 | 130.3533
4740 | 86.002
4741 | 139.9922
4742 | 118.6018
4743 | 109.1117
4744 | 103.8863
4745 | 82.1429
4746 | 43.7559
4747 | 127.1745
4748 | 132.6018
4749 | 158.3315
4750 | 123.6875
4751 | 149.8543
4752 | 137.6993
4753 | 70.628
4754 | 100.2274
4755 | 129.0338
4756 | 150.2838
4757 | 68.1899
4758 | 95.8342
4759 | 101.2988
4760 | 119.3015
4761 | 95.2163
4762 | 112.0806
4763 | 99.2573
4764 | 157.4368
4765 | 82.0693
4766 | 101.3581
4767 | 120.9681
4768 | 84.9084
4769 | 120.2068
4770 | 125.2395
4771 | 90.1855
4772 | 93.0085
4773 | 117.4385
4774 | 122.2657
4775 | 103.7559
4776 | 102.5733
4777 | 150.3962
4778 | 143.2169
4779 | 87.4813
4780 | 107.06
4781 | 156.0989
4782 | 92.9802
4783 | 103.4594
4784 | 105.3482
4785 | 157.372
4786 | 135.6046
4787 | 102.2871
4788 | 137.1844
4789 | 159.4358
4790 | 98.3456
4791 | 119.3059
4792 | 113.6501
4793 | 164.0329
4794 | 90.3961
4795 | 96.3447
4796 | 156.3694
4797 | 111.3989
4798 | 89.9441
4799 | 105.9453
4800 | 107.6154
4801 | 140.2153
4802 | 143.0112
4803 | 143.1333
4804 | 114.589
4805 | 159.0108
4806 | 151.1998
4807 | 86.199
4808 | 128.7098
4809 | 111.8897
4810 | 100.0039
4811 | 131.4037
4812 | 132.8283
4813 | 172.466
4814 | 100.1429
4815 | 93.5195
4816 | 118.0594
4817 | 137.1773
4818 | 166.644
4819 | 140.5582
4820 | 139.7317
4821 | 127.9788
4822 | 135.0182
4823 | 70.4992
4824 | 185.3761
4825 | 136.8625
4826 | 99.5116
4827 | 119.6745
4828 | 92.4363
4829 | 118.8064
4830 | 149.722
4831 | 114.4111
4832 | 101.458
4833 | 130.4604
4834 | 107.935
4835 | 110.567
4836 | 144.1975
4837 | 181.0132
4838 | 127.5448
4839 | 96.7445
4840 | 94.555
4841 | 90.5352
4842 | 144.2741
4843 | 115.4807
4844 | 96.9603
4845 | 110.2613
4846 | 107.6658
4847 | 97.6232
4848 | 93.4269
4849 | 138.5228
4850 | 80.0052
4851 | 95.4552
4852 | 152.3198
4853 | 88.722
4854 | 122.6498
4855 | 151.0585
4856 | 97.9658
4857 | 146.0812
4858 | 77.6797
4859 | 120.2321
4860 | 178.7599
4861 | 142.6735
4862 | 102.049
4863 | 159.8249
4864 | 131.2499
4865 | 110.2943
4866 | 160.0415
4867 | 143.6889
4868 | 137.0891
4869 | 96.8451
4870 | 91.9033
4871 | 96.3382
4872 | 92.5963
4873 | 164.4053
4874 | 97.6252
4875 | 70.5477
4876 | 130.6912
4877 | 101.5512
4878 | 159.278
4879 | 141.1269
4880 | 116.8512
4881 | 117.2581
4882 | 109.1221
4883 | 117.2598
4884 | 150.2179
4885 | 115.0126
4886 | 108.6882
4887 | 141.1895
4888 | 127.8369
4889 | 109.1989
4890 | 118.1405
4891 | 121.5217
4892 | 151.329
4893 | 164.1188
4894 | 167.6498
4895 | 120.1219
4896 | 97.4158
4897 | 159.6099
4898 | 138.6855
4899 | 148.2318
4900 | 169.4155
4901 | 147.5639
4902 | 105.2356
4903 | 128.467
4904 | 137.5776
4905 | 157.5136
4906 | 154.4587
4907 | 123.3962
4908 | 147.4627
4909 | 140.625
4910 | 57.8507
4911 | 118.3779
4912 | 145.7772
4913 | 129.9429
4914 | 101.6295
4915 | 120.0272
4916 | 78.0503
4917 | 155.2055
4918 | 138.2862
4919 | 116.3003
4920 | 150.1474
4921 | 121.668
4922 | 128.2758
4923 | 115.9291
4924 | 162.8707
4925 | 142.0968
4926 | 137.9577
4927 | 155.421
4928 | 136.5161
4929 | 180.0775
4930 | 137.4018
4931 | 160.1384
4932 | 151.9413
4933 | 73.8501
4934 | 100.6182
4935 | 142.423
4936 | 124.3874
4937 | 114.0515
4938 | 139.835
4939 | 111.8341
4940 | 117.5446
4941 | 143.8174
4942 | 155.6096
4943 | 123.7066
4944 | 111.6907
4945 | 114.6016
4946 | 92.6917
4947 | 91.3647
4948 | 158.5913
4949 | 132.3255
4950 | 98.616
4951 | 110.2104
4952 | 142.9343
4953 | 90.3858
4954 | 92.6018
4955 | 112.4906
4956 | 64.2029
4957 | 95.8732
4958 | 75.84
4959 | 133.4726
4960 | 108.928
4961 | 113.3159
4962 | 143.2227
4963 | 126.2689
4964 | 116.5471
4965 | 113.0187
4966 | 135.6173
4967 | 118.7911
4968 | 131.4349
4969 | 114.2908
4970 | 148.4564
4971 | 109.9589
4972 | 198.3145
4973 | 140.5864
4974 | 129.634
4975 | 133.2477
4976 | 125.1431
4977 | 105.6107
4978 | 124.4456
4979 | 78.7013
4980 | 157.8773
4981 | 98.6445
4982 | 115.8071
4983 | 125.7791
4984 | 171.7326
4985 | 156.397
4986 | 160.097
4987 | 116.9778
4988 | 92.804
4989 | 115.2634
4990 | 99.9892
4991 | 156.3176
4992 | 143.3123
4993 | 150.7511
4994 | 98.1439
4995 | 127.4507
4996 | 145.0555
4997 | 101.4982
4998 | 142.834
4999 | 144.1112
5000 | 104.0361
5001 | 135.0203
5002 | 154.2337
5003 | 115.808
5004 | 132.8959
5005 | 134.9476
5006 | 126.7655
5007 | 121.5663
5008 | 101.3215
5009 | 104.2298
5010 | 98.4246
5011 | 120.8165
5012 | 103.2608
5013 | 126.0277
5014 | 108.3514
5015 | 82.8047
5016 | 158.4143
5017 | 169.2335
5018 | 125.0796
5019 | 138.1219
5020 | 132.946
5021 | 115.2099
5022 | 71.342
5023 | 148.5769
5024 | 104.3751
5025 | 104.2737
5026 | 79.7649
5027 | 133.2279
5028 | 103.5245
5029 | 106.3642
5030 | 90.2696
5031 | 118.0596
5032 | 104.7594
5033 | 141.8786
5034 | 121.6871
5035 | 133.0451
5036 | 155.2054
5037 | 98.8317
5038 | 107.5812
5039 | 135.3904
5040 | 138.005
5041 | 89.1055
5042 | 105.6777
5043 | 115.3745
5044 | 106.3583
5045 | 103.4575
5046 | 154.8908
5047 | 139.3574
5048 | 69.9156
5049 | 144.9806
5050 | 165.1429
5051 | 106.232
5052 | 147.5421
5053 | 124.2562
5054 | 156.6703
5055 | 119.9703
5056 | 110.975
5057 | 128.8349
5058 | 101.3316
5059 | 117.6291
5060 | 111.2645
5061 | 117.6702
5062 | 95.9388
5063 | 141.6736
5064 | 108.0722
5065 | 98.6497
5066 | 134.1551
5067 | 76.7883
5068 | 113.4762
5069 | 72.8879
5070 | 91.513
5071 | 86.2606
5072 | 151.5089
5073 | 134.3454
5074 | 112.0806
5075 | 85.6382
5076 | 146.0328
5077 | 117.2301
5078 | 135.7546
5079 | 134.2191
5080 | 86.6296
5081 | 158.2838
5082 | 105.1073
5083 | 107.3603
5084 | 121.7157
5085 | 120.1064
5086 | 130.7463
5087 | 69.2641
5088 | 144.0753
5089 | 158.3919
5090 | 111.1777
5091 | 133.1234
5092 | 129.4763
5093 | 128.7699
5094 | 119.7317
5095 | 125.3439
5096 | 82.1012
5097 | 155.7279
5098 | 114.3396
5099 | 96.7182
5100 | 104.9688
5101 | 158.6746
5102 | 117.0658
5103 | 97.035
5104 | 92.993
5105 | 102.4575
5106 | 167.4265
5107 | 125.8683
5108 | 92.0546
5109 | 110.6863
5110 | 124.9486
5111 | 120.2751
5112 | 128.916
5113 | 99.8796
5114 | 157.1842
5115 | 118.4782
5116 | 84.7973
5117 | 179.286
5118 | 136.2858
5119 | 118.9186
5120 | 140.0638
5121 | 137.8063
5122 | 93.6582
5123 | 99.4758
5124 | 94.0457
5125 | 130.3426
5126 | 170.5208
5127 | 136.9845
5128 | 128.6346
5129 | 146.7708
5130 | 78.5329
5131 | 157.0246
5132 | 79.7256
5133 | 127.4477
5134 | 126.8822
5135 | 80.7902
5136 | 97.0081
5137 | 109.0428
5138 | 156.7137
5139 | 153.988
5140 | 114.5088
5141 | 145.4871
5142 | 132.4771
5143 | 107.1108
5144 | 77.4194
5145 | 73.6606
5146 | 113.828
5147 | 152.9727
5148 | 91.3446
5149 | 95.1589
5150 | 92.7589
5151 | 112.2946
5152 | 135.9345
5153 | 133.2774
5154 | 130.8739
5155 | 100.3743
5156 | 129.9972
5157 | 107.1771
5158 | 130.0902
5159 | 167.3648
5160 | 125.3287
5161 | 131.3675
5162 | 120.1525
5163 | 166.5282
5164 | 141.5103
5165 | 90.7362
5166 | 115.2775
5167 | 143.5554
5168 | 134.6542
5169 | 93.753
5170 | 110.5858
5171 | 126.9123
5172 | 136.8007
5173 | 147.0356
5174 | 141.0775
5175 | 99.9885
5176 | 117.8598
5177 | 155.6811
5178 | 96.8999
5179 | 133.4575
5180 | 123.94
5181 | 104.3269
5182 | 108.0728
5183 | 118.2675
5184 | 107.0404
5185 | 142.6706
5186 | 133.8504
5187 | 101.2275
5188 | 122.6872
5189 | 161.402
5190 | 162.4101
5191 | 118.9856
5192 | 130.585
5193 | 118.5997
5194 | 136.1564
5195 | 97.7354
5196 | 140.9369
5197 | 113.9198
5198 | 143.4434
5199 | 122.4286
5200 | 117.5211
5201 | 136.4387
5202 | 147.5091
5203 | 126.8733
5204 | 123.0886
5205 | 146.678
5206 | 58.8147
5207 | 119.5143
5208 | 90.4605
5209 | 74.6661
5210 | 131.4477
5211 | 127.4318
5212 | 116.14
5213 | 137.1727
5214 | 115.4962
5215 | 119.8692
5216 | 126.7259
5217 | 80.8512
5218 | 163.7167
5219 | 90.7394
5220 | 120.2064
5221 | 150.7254
5222 | 139.0736
5223 | 72.5867
5224 | 131.1236
5225 | 153.1079
5226 | 120.3808
5227 | 146.5167
5228 | 116.855
5229 | 117.83
5230 | 120.2258
5231 | 108.9103
5232 | 139.6832
5233 | 129.0938
5234 | 97.5759
5235 | 158.9738
5236 | 105.2483
5237 | 137.4262
5238 | 94.7217
5239 | 87.5606
5240 | 100.4516
5241 | 131.7537
5242 | 88.1179
5243 | 85.4446
5244 | 128.0018
5245 | 98.1654
5246 | 134.2609
5247 | 172.4308
5248 | 83.6293
5249 | 157.3894
5250 | 148.8177
5251 | 112.8457
5252 | 139.9612
5253 | 114.6101
5254 | 113.884
5255 | 112.2334
5256 | 121.6738
5257 | 85.6946
5258 | 132.6776
5259 | 169.8226
5260 | 138.1798
5261 | 91.4887
5262 | 130.8004
5263 | 104.4828
5264 | 105.2097
5265 | 113.6864
5266 | 155.4949
5267 | 116.1188
5268 | 120.3731
5269 | 161.8559
5270 | 83.8887
5271 | 116.6998
5272 | 136.1445
5273 | 94.05
5274 | 106.7088
5275 | 124.0068
5276 | 76.9299
5277 | 97.5775
5278 | 95.4724
5279 | 88.5703
5280 | 118.2014
5281 | 141.9982
5282 | 112.7389
5283 | 123.1117
5284 | 84.0395
5285 | 154.4799
5286 | 156.099
5287 | 133.8196
5288 | 126.9076
5289 | 131.2787
5290 | 102.3387
5291 | 78.5578
5292 | 141.5777
5293 | 84.4294
5294 | 174.976
5295 | 109.3916
5296 | 109.5345
5297 | 88.6039
5298 | 97.7905
5299 | 75.6066
5300 | 124.1127
5301 | 100.4946
5302 | 100.9931
5303 | 125.3964
5304 | 90.3988
5305 | 150.3543
5306 | 102.8105
5307 | 121.9531
5308 | 140.3142
5309 | 119.0544
5310 | 104.3007
5311 | 106.062
5312 | 92.8392
5313 | 136.543
5314 | 137.5325
5315 | 105.0949
5316 | 170.1608
5317 | 86.5519
5318 | 102.3702
5319 | 120.0165
5320 | 123.3098
5321 | 89.6309
5322 | 110.7476
5323 | 133.947
5324 | 92.2592
5325 | 117.0071
5326 | 136.1511
5327 | 136.3882
5328 | 96.131
5329 | 125.5654
5330 | 133.7047
5331 | 106.4707
5332 | 103.712
5333 | 93.4306
5334 | 105.8316
5335 | 94.6714
5336 | 152.838
5337 | 123.0368
5338 | 126.6947
5339 | 150.7587
5340 | 128.5796
5341 | 142.4695
5342 | 150.5828
5343 | 144.2837
5344 | 131.9574
5345 | 127.3631
5346 | 115.5031
5347 | 156.3247
5348 | 113.5333
5349 | 135.4916
5350 | 118.2601
5351 | 146.0496
5352 | 151.1994
5353 | 155.2797
5354 | 116.866
5355 | 131.8143
5356 | 78.7301
5357 | 141.1806
5358 | 120.6287
5359 | 136.092
5360 | 119.0969
5361 | 108.3688
5362 | 97.2426
5363 | 113.831
5364 | 114.4708
5365 | 131.3155
5366 | 86.7626
5367 | 100.1428
5368 | 146.3778
5369 | 97.8745
5370 | 144.2398
5371 | 137.2421
5372 | 127.0805
5373 | 151.8504
5374 | 144.815
5375 | 130.7653
5376 | 144.206
5377 | 77.8965
5378 | 124.4321
5379 | 162.6251
5380 | 154.9164
5381 | 83.9498
5382 | 139.8346
5383 | 141.6172
5384 | 125.925
5385 | 112.5388
5386 | 167.0014
5387 | 134.38
5388 | 48.042
5389 | 94.6542
5390 | 104.6507
5391 | 98.4484
5392 | 103.05
5393 | 80.6055
5394 | 170.5899
5395 | 88.3661
5396 | 108.6307
5397 | 113.5801
5398 | 89.6926
5399 | 101.3782
5400 | 121.9908
5401 | 98.2836
5402 | 121.0666
5403 | 106.5081
5404 | 76.671
5405 | 92.0417
5406 | 106.8427
5407 | 80.3652
5408 | 146.3118
5409 | 89.5504
5410 | 144.1841
5411 | 95.6432
5412 | 106.4676
5413 | 145.8241
5414 | 168.3487
5415 | 152.2905
5416 | 119.0412
5417 | 87.0467
5418 | 124.2213
5419 | 123.2277
5420 | 141.9561
5421 | 110.998
5422 | 163.2508
5423 | 156.907
5424 | 80.2489
5425 | 124.4081
5426 | 118.3639
5427 | 115.2641
5428 | 119.6383
5429 | 121.7514
5430 | 119.0197
5431 | 107.7555
5432 | 140.8189
5433 | 98.0155
5434 | 103.5175
5435 | 80.1816
5436 | 111.3843
5437 | 108.27
5438 | 117.8882
5439 | 130.2967
5440 | 114.991
5441 | 116.2681
5442 | 112.2201
5443 | 97.4228
5444 | 121.0384
5445 | 92.3742
5446 | 104.7939
5447 | 138.1976
5448 | 126.0086
5449 | 67.3407
5450 | 121.2406
5451 | 113.9619
5452 | 133.5416
5453 | 130.9812
5454 | 123.1274
5455 | 121.0083
5456 | 116.605
5457 | 99.3277
5458 | 104.1816
5459 | 144.5606
5460 | 140.8639
5461 | 83.3836
5462 | 136.4212
5463 | 124.0119
5464 | 149.2753
5465 | 134.1325
5466 | 102.6224
5467 | 86.3341
5468 | 123.1234
5469 | 113.4158
5470 | 152.5089
5471 | 120.9369
5472 | 183.7178
5473 | 132.1895
5474 | 140.5487
5475 | 65.2861
5476 | 134.0125
5477 | 139.3841
5478 | 134.1865
5479 | 106.449
5480 | 119.0172
5481 | 115.4436
5482 | 115.5331
5483 | 115.5083
5484 | 85.4963
5485 | 128.2252
5486 | 164.8441
5487 | 111.3195
5488 | 132.9416
5489 | 142.3764
5490 | 104.1696
5491 | 109.0391
5492 | 115.679
5493 | 109.9282
5494 | 121.6142
5495 | 145.9926
5496 | 128.9442
5497 | 134.0369
5498 | 122.4326
5499 | 115.4527
5500 | 161.9944
5501 | 117.8729
5502 | 124.5051
5503 | 149.2896
5504 | 140.5806
5505 | 131.9852
5506 | 103.5556
5507 | 122.6014
5508 | 113.656
5509 | 140.3059
5510 | 112.603
5511 | 104.96
5512 | 144.5437
5513 | 130.4307
5514 | 104.8895
5515 | 123.2684
5516 | 141.119
5517 | 128.7669
5518 | 143.9281
5519 | 110.4536
5520 | 103.7599
5521 | 97.2366
5522 | 92.7105
5523 | 118.5093
5524 | 180.9284
5525 | 167.3588
5526 | 124.4697
5527 | 118.7345
5528 | 116.9707
5529 | 88.6792
5530 | 99.2896
5531 | 143.6943
5532 | 138.5712
5533 | 127.8882
5534 | 96.7873
5535 | 117.3506
5536 | 90.4079
5537 | 136.8955
5538 | 115.78
5539 | 116.8633
5540 | 144.1573
5541 | 106.9835
5542 | 141.1992
5543 | 167.0144
5544 | 174.0248
5545 | 129.8292
5546 | 171.8776
5547 | 126.3796
5548 | 126.7788
5549 | 152.2145
5550 | 110.4559
5551 | 91.856
5552 | 110.7099
5553 | 125.7612
5554 | 74.88
5555 | 130.6818
5556 | 160.0581
5557 | 127.0284
5558 | 155.5393
5559 | 166.1411
5560 | 143.1488
5561 | 144.7018
5562 | 117.676
5563 | 159.7715
5564 | 147.4855
5565 | 109.3248
5566 | 125.761
5567 | 129.6709
5568 | 103.1572
5569 | 106.9945
5570 | 145.1494
5571 | 131.3879
5572 | 115.4589
5573 | 102.3496
5574 | 122.9678
5575 | 105.9077
5576 | 91.2341
5577 | 114.291
5578 | 122.6225
5579 | 81.3019
5580 | 121.016
5581 | 151.7407
5582 | 119.3816
5583 | 111.4639
5584 | 104.1825
5585 | 121.8523
5586 | 112.1552
5587 | 112.5625
5588 | 100.7559
5589 | 113.6076
5590 | 114.6816
5591 | 123.0041
5592 | 89.1011
5593 | 114.8142
5594 | 125.312
5595 | 146.1645
5596 | 104.7296
5597 | 111.2832
5598 | 98.3188
5599 | 95.3894
5600 | 141.7108
5601 | 173.634
5602 | 105.9622
5603 | 86.5486
5604 | 108.2329
5605 | 102.9049
5606 | 135.964
5607 | 131.6657
5608 | 97.1636
5609 | 141.2596
5610 | 153.7757
5611 | 133.8318
5612 | 86.1388
5613 | 108.2341
5614 | 156.6488
5615 | 105.1088
5616 | 146.5049
5617 | 103.1562
5618 | 154.4748
5619 | 82.1303
5620 | 94.0966
5621 | 160.0813
5622 | 154.7223
5623 | 137.6235
5624 | 114.6459
5625 | 120.6252
5626 | 117.8851
5627 | 156.4205
5628 | 110.4832
5629 | 84.2559
5630 | 133.3813
5631 | 143.0444
5632 | 104.7469
5633 | 151.5201
5634 | 142.2009
5635 | 85.1692
5636 | 119.0262
5637 | 150.0157
5638 | 120.7847
5639 | 172.1058
5640 | 101.3142
5641 | 86.7816
5642 | 98.6198
5643 | 106.5554
5644 | 110.0879
5645 | 184.6179
5646 | 101.1118
5647 | 138.7579
5648 | 88.0908
5649 | 142.6513
5650 | 117.6281
5651 | 123.2999
5652 | 122.7515
5653 | 110.602
5654 | 83.6047
5655 | 140.7991
5656 | 142.1343
5657 | 139.6875
5658 | 137.491
5659 | 114.1613
5660 | 138.6919
5661 | 124.5035
5662 | 101.9086
5663 | 110.2076
5664 | 151.2618
5665 | 76.3767
5666 | 131.8361
5667 | 135.3362
5668 | 108.5883
5669 | 172.4157
5670 | 97.4145
5671 | 84.7807
5672 | 121.4765
5673 | 124.9694
5674 | 75.7269
5675 | 110.1367
5676 | 94.2956
5677 | 148.3502
5678 | 132.0604
5679 | 149.0806
5680 | 161.4177
5681 | 123.8059
5682 | 88.1054
5683 | 156.4115
5684 | 114.6484
5685 | 153.2341
5686 | 123.8376
5687 | 86.1154
5688 | 113.6224
5689 | 88.6764
5690 | 82.5783
5691 | 126.9914
5692 | 125.1774
5693 | 105.5133
5694 | 154.2408
5695 | 145.1001
5696 | 122.4513
5697 | 91.9262
5698 | 124.4339
5699 | 109.4368
5700 | 116.1138
5701 | 115.4656
5702 | 128.4588
5703 | 78.2059
5704 | 151.3225
5705 | 130.0255
5706 | 146.0523
5707 | 88.0558
5708 | 105.0938
5709 | 109.9268
5710 | 110.5076
5711 | 128.8192
5712 | 124.9024
5713 | 108.558
5714 | 130.9045
5715 | 131.9303
5716 | 138.6525
5717 | 141.8424
5718 | 108.6765
5719 | 102.8306
5720 | 91.481
5721 | 107.3576
5722 | 106.938
5723 | 120.8568
5724 | 125.3979
5725 | 134.9257
5726 | 100.9993
5727 | 105.8275
5728 | 131.0928
5729 | 170.1682
5730 | 113.5042
5731 | 116.5878
5732 | 108.1615
5733 | 131.9869
5734 | 118.3921
5735 | 80.2681
5736 | 81.9173
5737 | 109.0284
5738 | 177.5534
5739 | 104.7191
5740 | 120.7933
5741 | 154.0304
5742 | 108.1324
5743 | 128.5141
5744 | 97.6377
5745 | 135.8617
5746 | 94.2014
5747 | 152.8815
5748 | 131.5874
5749 | 109.4677
5750 | 128.1239
5751 | 93.623
5752 | 126.1361
5753 | 140.7911
5754 | 135.4394
5755 | 86.1407
5756 | 108.4229
5757 | 153.3804
5758 | 130.6847
5759 | 114.8308
5760 | 92.289
5761 | 103.5027
5762 | 127
5763 | 84.9921
5764 | 107.1843
5765 | 117.7251
5766 | 103.6365
5767 | 90.6764
5768 | 111.2474
5769 | 135.1311
5770 | 151.0484
5771 | 121.5812
5772 | 124.268
5773 | 176.1488
5774 | 147.6891
5775 | 148.6773
5776 | 138.5236
5777 | 133.4934
5778 | 130.527
5779 | 104.1189
5780 | 76.3802
5781 | 112.1914
5782 | 118.7863
5783 | 121.4363
5784 | 157.7381
5785 | 118.5082
5786 | 124.3743
5787 | 130.8117
5788 | 158.0432
5789 | 78.8847
5790 | 99.4996
5791 | 136.8177
5792 | 147.9091
5793 | 125.0079
5794 | 120.5478
5795 | 116.8585
5796 | 101.1248
5797 | 112.077
5798 | 91.1521
5799 | 99.094
5800 | 161.8349
5801 | 94.7306
5802 | 103.2728
5803 | 143.223
5804 | 98.5772
5805 | 111.9966
5806 | 94.3896
5807 | 132.8516
5808 | 127.5573
5809 | 134.217
5810 | 122.9844
5811 | 145.0242
5812 | 72.0075
5813 | 120.2713
5814 | 111.247
5815 | 155.7596
5816 | 146.8635
5817 | 57.8208
5818 | 127.8743
5819 | 123.3819
5820 | 103.1583
5821 | 135.4449
5822 | 123.6155
5823 | 135.4594
5824 | 127.9697
5825 | 84.6592
5826 | 98.832
5827 | 95.0927
5828 | 194.4773
5829 | 180.3794
5830 | 153.867
5831 | 83.277
5832 | 167.7257
5833 | 125.2048
5834 | 90.082
5835 | 119.7572
5836 | 126.4004
5837 | 138.1547
5838 | 116.2048
5839 | 112.8205
5840 | 144.5456
5841 | 104.1887
5842 | 161.8573
5843 | 134.768
5844 | 118.5785
5845 | 128.1361
5846 | 94.4963
5847 | 144.4989
5848 | 123.8472
5849 | 127.3237
5850 | 107.2733
5851 | 113.9915
5852 | 118.4491
5853 | 120.1086
5854 | 100.5539
5855 | 123.2372
5856 | 114.4702
5857 | 140.6007
5858 | 89.7529
5859 | 69.9494
5860 | 118.1012
5861 | 121.6341
5862 | 142.486
5863 | 73.1513
5864 | 109.5285
5865 | 134.893
5866 | 103.1234
5867 | 94.3407
5868 | 140.1794
5869 | 114.8272
5870 | 140.3823
5871 | 123.4516
5872 | 114.05
5873 | 147.6374
5874 | 109.3703
5875 | 128.1706
5876 | 143.3478
5877 | 87.6459
5878 | 139.6741
5879 | 95.9479
5880 | 106.9516
5881 | 125.1036
5882 | 90.2319
5883 | 123.7176
5884 | 87.3722
5885 | 131.2477
5886 | 93.9483
5887 | 152.8864
5888 | 119.1198
5889 | 121.1929
5890 | 139.5811
5891 | 52.09
5892 | 121.845
5893 | 92.1551
5894 | 129.7375
5895 | 100.3252
5896 | 158.6504
5897 | 123.8458
5898 | 111.6353
5899 | 137.6026
5900 | 159.2404
5901 | 78.2836
5902 | 121.1018
5903 | 125.5833
5904 | 140.532
5905 | 124.2434
5906 | 88.2224
5907 | 109.0346
5908 | 132.0246
5909 | 120.3686
5910 | 82.8282
5911 | 159.0595
5912 | 106.2896
5913 | 138.7208
5914 | 101.1748
5915 | 108.9022
5916 | 109.6787
5917 | 135.2268
5918 | 106.3083
5919 | 135.4098
5920 | 77.5806
5921 | 135.2127
5922 | 107.1337
5923 | 134.0508
5924 | 121.9625
5925 | 112.2306
5926 | 146.3031
5927 | 71.3874
5928 | 80.235
5929 | 112.4511
5930 | 132.1911
5931 | 86.1946
5932 | 158.3542
5933 | 118.7554
5934 | 75.2936
5935 | 150.7932
5936 | 111.9771
5937 | 135.5604
5938 | 140.093
5939 | 176.3273
5940 | 107.7697
5941 | 103.6142
5942 | 84.665
5943 | 125.3287
5944 | 104.1005
5945 | 150.2136
5946 | 121.1517
5947 | 112.6992
5948 | 118.4637
5949 | 159.5018
5950 | 153.4033
5951 | 171.0638
5952 | 141.7654
5953 | 79.1279
5954 | 146.5311
5955 | 145.3496
5956 | 143.4275
5957 | 65.0157
5958 | 100.2449
5959 | 154.751
5960 | 104.8047
5961 | 113.9042
5962 | 135.2287
5963 | 98.2564
5964 | 99.7037
5965 | 127.5704
5966 | 122.9344
5967 | 105.5087
5968 | 144.3782
5969 | 64.8854
5970 | 119.194
5971 | 105.062
5972 | 91.2086
5973 | 125.7425
5974 | 118.962
5975 | 89.9365
5976 | 130.8375
5977 | 103.8621
5978 | 81.7548
5979 | 114.6513
5980 | 123.6689
5981 | 90.0751
5982 | 158.5927
5983 | 131.6472
5984 | 111.0048
5985 | 124.0391
5986 | 149.8319
5987 | 158.3865
5988 | 119.4743
5989 | 92.8086
5990 | 129.1847
5991 | 91.8256
5992 | 116.1781
5993 | 100.1649
5994 | 99.0572
5995 | 134.7484
5996 | 177.3291
5997 | 119.6879
5998 | 79.7499
5999 | 121.5723
6000 | 123.8807
6001 | 75.7699
6002 | 127.215
6003 | 145.109
6004 | 96.1404
6005 | 149.2853
6006 | 151.7991
6007 | 178.7915
6008 | 84.2196
6009 | 103.0109
6010 | 152.7876
6011 | 99.3876
6012 | 95.4614
6013 | 147.0731
6014 | 136.0204
6015 | 136.788
6016 | 114.1446
6017 | 127.3134
6018 | 71.3401
6019 | 135.7753
6020 | 151.4116
6021 | 147.3714
6022 | 107.2533
6023 | 108.0719
6024 | 130.8607
6025 | 98.0497
6026 | 91.6575
6027 | 159.4348
6028 | 88.3204
6029 | 117.7849
6030 | 137.4706
6031 | 125.4401
6032 | 113.8845
6033 | 144.6951
6034 | 81.7041
6035 | 112.6137
6036 | 105.2613
6037 | 132.1416
6038 | 126.6659
6039 | 120.9631
6040 | 116.3969
6041 | 87.3219
6042 | 123.0246
6043 | 150.5737
6044 | 153.6913
6045 | 143.6159
6046 | 83.7215
6047 | 122.3019
6048 | 94.4999
6049 | 111.5334
6050 | 110.7667
6051 | 139.9043
6052 | 148.8892
6053 | 114.8098
6054 | 139.3979
6055 | 98.8057
6056 | 121.1216
6057 | 117.2233
6058 | 124.0785
6059 | 111.7776
6060 | 137.2035
6061 | 96.9296
6062 | 109.8108
6063 | 88.4387
6064 | 147.7107
6065 | 49.7818
6066 | 137.3561
6067 | 127.2397
6068 | 108.4241
6069 | 123.3
6070 | 146.245
6071 | 146.3537
6072 | 85.0335
6073 | 91.4368
6074 | 164.391
6075 | 112.1512
6076 | 114.931
6077 | 107.8537
6078 | 146.7316
6079 | 81.8829
6080 | 159.0863
6081 | 87.1204
6082 | 108.7173
6083 | 134.201
6084 | 114.1231
6085 | 116.3103
6086 | 145.3996
6087 | 129.0117
6088 | 149.2036
6089 | 114.5741
6090 | 127
6091 | 122.913
6092 | 128.9398
6093 | 127.6517
6094 | 146.2884
6095 | 89.9354
6096 | 189.6918
6097 | 146.4569
6098 | 125.4394
6099 | 140.6029
6100 | 87.6602
6101 | 161.6287
6102 | 142.7883
6103 | 130.2655
6104 | 122.3167
6105 | 96.8156
6106 | 115.7341
6107 | 95.3447
6108 | 132.2104
6109 | 126.1441
6110 | 118.3136
6111 | 117.5958
6112 | 123.3057
6113 | 148.6806
6114 | 158.4109
6115 | 103.5882
6116 | 104.768
6117 | 112.4064
6118 | 95.6073
6119 | 147.9009
6120 | 143.8864
6121 | 167.6368
6122 | 85.6931
6123 | 148.2189
6124 | 113.7888
6125 | 145.7768
6126 | 149.937
6127 | 120.8204
6128 | 129.8574
6129 | 147.7173
6130 | 100.5071
6131 | 141.5917
6132 | 157.0752
6133 | 94.5976
6134 | 86.6674
6135 | 140.8002
6136 | 106.5748
6137 | 127
6138 | 153.9925
6139 | 118.7476
6140 | 81.9587
6141 | 91.2607
6142 | 76.8146
6143 | 131.9311
6144 | 133.6204
6145 | 101.9269
6146 | 100.5552
6147 | 184.6394
6148 | 109.9523
6149 | 66.2126
6150 | 118.8031
6151 | 73.9357
6152 | 114.8294
6153 | 91.0245
6154 | 111.3979
6155 | 76.5543
6156 | 125.5352
6157 | 160.1114
6158 | 104.0106
6159 | 86.5674
6160 | 82.7277
6161 | 138.722
6162 | 134.1393
6163 | 146.3492
6164 | 87.5845
6165 | 125.3724
6166 | 139.9818
6167 | 98.1954
6168 | 121.7178
6169 | 106.3549
6170 | 82.858
6171 | 139.4167
6172 | 97.7775
6173 | 70.1102
6174 | 110.309
6175 | 84.4584
6176 | 140.6334
6177 | 75.7459
6178 | 118.9814
6179 | 102.193
6180 | 116.5046
6181 | 164.16
6182 | 90.6142
6183 | 164.2534
6184 | 108.5098
6185 | 107.5217
6186 | 83.0139
6187 | 151.2735
6188 | 118.8451
6189 | 107.8459
6190 | 141.2009
6191 | 136.8979
6192 | 169.4996
6193 | 152.3147
6194 | 106.3565
6195 | 151.0756
6196 | 117.6577
6197 | 95.3522
6198 | 118.3913
6199 | 91.4598
6200 | 118.7755
6201 | 151.0727
6202 | 100.2428
6203 | 99.7332
6204 | 141.4782
6205 | 132.7239
6206 | 89.4889
6207 | 131.9937
6208 | 95.6511
6209 | 111.5102
6210 | 113.3117
6211 | 111.0359
6212 | 141.4182
6213 | 115.9864
6214 | 140.1236
6215 | 52.5626
6216 | 143.595
6217 | 142.8033
6218 | 104.1335
6219 | 120.6967
6220 | 88.6797
6221 | 96.3473
6222 | 154.6919
6223 | 94.6873
6224 | 148.8439
6225 | 164.1979
6226 | 98.0193
6227 | 88.0231
6228 | 117.0526
6229 | 127.1193
6230 | 125.1644
6231 | 160.4659
6232 | 80.043
6233 | 129.8519
6234 | 116.2438
6235 | 168.1776
6236 | 130.0097
6237 | 109.9894
6238 | 111.5827
6239 | 123.207
6240 | 150.7224
6241 | 147.7142
6242 | 142.8898
6243 | 160.1328
6244 | 162.2977
6245 | 134.0426
6246 | 46.4689
6247 | 99.1239
6248 | 134.0465
6249 | 94.5581
6250 | 134.7105
6251 | 159.1143
6252 | 153.2544
6253 | 98.3106
6254 | 134.3637
6255 | 116.7086
6256 | 111.4025
6257 | 108.9419
6258 | 130.2543
6259 | 112.8931
6260 | 168.8548
6261 | 76.9804
6262 | 107.6894
6263 | 144.3203
6264 | 71.7926
6265 | 155.984
6266 | 128.9278
6267 | 103.598
6268 | 123.9566
6269 | 142.6337
6270 | 100.0484
6271 | 97.306
6272 | 141.9617
6273 | 96.9506
6274 | 89.897
6275 | 92.3306
6276 | 115.5097
6277 | 132.958
6278 | 89.9249
6279 | 109.91
6280 | 117.7892
6281 | 101.6725
6282 | 108.3937
6283 | 93.7301
6284 | 127.5981
6285 | 133.793
6286 | 145.6159
6287 | 146.0864
6288 | 170.0887
6289 | 142.8606
6290 | 85.0661
6291 | 123.4617
6292 | 124.1052
6293 | 115.8122
6294 | 72.6001
6295 | 102.7122
6296 | 104.064
6297 | 126.2861
6298 | 105.5221
6299 | 61.6049
6300 | 134.9489
6301 | 116.9472
6302 | 120.9874
6303 | 153.9627
6304 | 142.0804
6305 | 70.2954
6306 | 92.5093
6307 | 103.6823
6308 | 139.1592
6309 | 118.5794
6310 | 127.9224
6311 | 146.2027
6312 | 92.566
6313 | 112.0061
6314 | 138.7214
6315 | 121.8567
6316 | 151.2866
6317 | 119.2286
6318 | 132.487
6319 | 118.3418
6320 | 131.7611
6321 | 123.0659
6322 | 105.0644
6323 | 139.6497
6324 | 124.2188
6325 | 137.1936
6326 | 87.8313
6327 | 134.4998
6328 | 96.8899
6329 | 128.662
6330 | 114.9668
6331 | 144.7043
6332 | 91.6227
6333 | 121.1888
6334 | 115.4993
6335 | 134.6731
6336 | 134.2727
6337 | 145.2433
6338 | 158.0458
6339 | 109.0339
6340 | 131.7028
6341 | 91.0925
6342 | 110.2305
6343 | 101.6086
6344 | 98.9654
6345 | 112.9105
6346 | 116.3722
6347 | 144.1887
6348 | 117.8858
6349 | 150.4399
6350 | 113.371
6351 | 130.4911
6352 | 120.4013
6353 | 127.2939
6354 | 167.6686
6355 | 138.7389
6356 | 141.9719
6357 | 65.5333
6358 | 124.8682
6359 | 129.1606
6360 | 92.5233
6361 | 128.6467
6362 | 143.722
6363 | 100.278
6364 | 104.7147
6365 | 117.9319
6366 | 159.5281
6367 | 146.9465
6368 | 126.9554
6369 | 142.6083
6370 | 129.2146
6371 | 151.9593
6372 | 131.4097
6373 | 126.7822
6374 | 134.7344
6375 | 156.2778
6376 | 144.9894
6377 | 74.7424
6378 | 167.6607
6379 | 154.2542
6380 | 145.944
6381 | 108.3376
6382 | 101.5905
6383 | 133.4701
6384 | 116.9375
6385 | 118.915
6386 | 105.524
6387 | 139.3334
6388 | 123.8519
6389 | 162.9831
6390 | 90.2981
6391 | 117.8933
6392 | 120.2964
6393 | 146.4736
6394 | 103.4134
6395 | 115.1976
6396 | 134.3087
6397 | 142.3153
6398 | 154.4605
6399 | 88.8239
6400 | 93.757
6401 | 106.7025
6402 | 130.1779
6403 | 44.7874
6404 | 136.6492
6405 | 112.386
6406 | 135.5933
6407 | 152.2472
6408 | 128.7258
6409 | 151.7556
6410 | 118.3478
6411 | 105.2075
6412 | 102.6464
6413 | 43.3947
6414 | 118.92
6415 | 139.1218
6416 | 137.187
6417 | 145.4614
6418 | 139.1659
6419 | 129.8215
6420 | 63.3361
6421 | 126.4552
6422 | 174.8649
6423 | 124.0089
6424 | 85.5936
6425 | 116.1864
6426 | 140.2773
6427 | 115.6579
6428 | 120.2048
6429 | 103.9763
6430 | 111.6623
6431 | 115.0769
6432 | 76.8537
6433 | 173.7299
6434 | 132.3402
6435 | 140.4954
6436 | 147.262
6437 | 132.0174
6438 | 129.8921
6439 | 127.1031
6440 | 121.2934
6441 | 141.1249
6442 | 151.9313
6443 | 104.3237
6444 | 104.8641
6445 | 126.1633
6446 | 145.77
6447 | 135.093
6448 | 130.642
6449 | 104.629
6450 | 153.4648
6451 | 108.1558
6452 | 84.755
6453 | 94.3447
6454 | 93.9475
6455 | 112.4443
6456 | 133.1846
6457 | 143.1261
6458 | 144.1332
6459 | 145.2316
6460 | 109.8123
6461 | 138.8901
6462 | 127.6937
6463 | 109.533
6464 | 125.1656
6465 | 111.3567
6466 | 80.0569
6467 | 120.0189
6468 | 138.4869
6469 | 158.5721
6470 | 114.4447
6471 | 112.3518
6472 | 114.4945
6473 | 133.4932
6474 | 131.5663
6475 | 101.178
6476 | 129.776
6477 | 153.2583
6478 | 77.878
6479 | 115.0897
6480 | 104.0047
6481 | 139.1827
6482 | 117.6521
6483 | 153.4088
6484 | 106.8361
6485 | 128.2602
6486 | 118.179
6487 | 129.484
6488 | 153.435
6489 | 92.8977
6490 | 114.2641
6491 | 150.054
6492 | 95.1392
6493 | 165.758
6494 | 95.8769
6495 | 111.8512
6496 | 122.8444
6497 | 89.8133
6498 | 126.6608
6499 | 117.2153
6500 | 96.6914
6501 | 139.192
6502 | 110.8701
6503 | 129.6928
6504 | 140.3448
6505 | 123.0743
6506 | 79.4985
6507 | 75.4781
6508 | 125.7847
6509 | 108.0535
6510 | 152.4704
6511 | 115.9367
6512 | 102.8959
6513 | 113.2249
6514 | 138.3897
6515 | 143.4592
6516 | 127.6224
6517 | 90.5507
6518 | 108.2567
6519 | 93.7281
6520 | 149.7291
6521 | 101.3963
6522 | 108.9869
6523 | 144.2307
6524 | 105.8021
6525 | 119.2236
6526 | 118.2164
6527 | 133.4084
6528 | 96.6935
6529 | 148.5782
6530 | 107.5963
6531 | 125.2404
6532 | 110.2016
6533 | 87.3189
6534 | 115.0093
6535 | 138.5327
6536 | 151.9964
6537 | 141.8538
6538 | 115.1075
6539 | 109.3378
6540 | 127.0229
6541 | 113.7535
6542 | 148.3369
6543 | 126.2423
6544 | 146.0681
6545 | 156.5688
6546 | 114.1399
6547 | 137.6471
6548 | 127.0542
6549 | 149.3449
6550 | 115.5483
6551 | 132.3337
6552 | 131.5029
6553 | 125.9354
6554 | 137.1224
6555 | 115.8787
6556 | 148.6663
6557 | 98.0781
6558 | 107.5736
6559 | 90.7722
6560 | 173.8195
6561 | 67.4591
6562 | 108.356
6563 | 130.8144
6564 | 108.5756
6565 | 154.2721
6566 | 133.6003
6567 | 96.9771
6568 | 125.9398
6569 | 129.7012
6570 | 151.7551
6571 | 79.7105
6572 | 104.9811
6573 | 64.2164
6574 | 94.7377
6575 | 93.1612
6576 | 137.7881
6577 | 121.0776
6578 | 148.4199
6579 | 118.7805
6580 | 149.2396
6581 | 105.4792
6582 | 156.8939
6583 | 141.8502
6584 | 115.1924
6585 | 160.4218
6586 | 208.1186
6587 | 108.9445
6588 | 154.9156
6589 | 92.3254
6590 | 148.5026
6591 | 145.8853
6592 | 165.4671
6593 | 142.6762
6594 | 90.4042
6595 | 120.5468
6596 | 105.5228
6597 | 101.8435
6598 | 123.9091
6599 | 146.1339
6600 | 119.6061
6601 | 96.7709
6602 | 124.2474
6603 | 112.2985
6604 | 116.6487
6605 | 147.4537
6606 | 171.435
6607 | 112.6419
6608 | 106.5308
6609 | 133.3665
6610 | 133.4085
6611 | 96.5157
6612 | 74.0362
6613 | 103.3368
6614 | 96.0278
6615 | 117.8281
6616 | 139.6309
6617 | 115.4981
6618 | 114.0433
6619 | 129.6238
6620 | 116.0886
6621 | 91.8391
6622 | 116.598
6623 | 136.0637
6624 | 134.7304
6625 | 158.7364
6626 | 164.2366
6627 | 112.762
6628 | 133.4968
6629 | 157.3066
6630 | 138.344
6631 | 137.3023
6632 | 144.7151
6633 | 121.9428
6634 | 147.9274
6635 | 128.4622
6636 | 129.4516
6637 | 96.5317
6638 | 139.3416
6639 | 111.69
6640 | 162.598
6641 | 156.9648
6642 | 136.6029
6643 | 122.7544
6644 | 67.1306
6645 | 114.1514
6646 | 114.4043
6647 | 175.5986
6648 | 122.2455
6649 | 113.3468
6650 | 113.9101
6651 | 98.2494
6652 | 94.2924
6653 | 118.6684
6654 | 132.128
6655 | 129.219
6656 | 91.8973
6657 | 144.1386
6658 | 99.4838
6659 | 119.3854
6660 | 129.1982
6661 | 112.0306
6662 | 94.1731
6663 | 122.6398
6664 | 137.1415
6665 | 52.4891
6666 | 137.8528
6667 | 164.4531
6668 | 96.7044
6669 | 83.1164
6670 | 109.1363
6671 | 107.9565
6672 | 109.3017
6673 | 114.0542
6674 | 132.0324
6675 | 102.3207
6676 | 150.7788
6677 | 130.8401
6678 | 105.9311
6679 | 95.894
6680 | 108.2496
6681 | 83.6847
6682 | 112.3226
6683 | 144.0679
6684 | 122.1538
6685 | 104.0029
6686 | 118.6313
6687 | 94.4149
6688 | 83.8199
6689 | 146.7253
6690 | 155.8683
6691 | 126.0226
6692 | 105.0715
6693 | 133.5307
6694 | 98.3722
6695 | 100.7981
6696 | 93.4419
6697 | 128.1011
6698 | 105.1234
6699 | 137.5145
6700 | 95.6614
6701 | 119.0875
6702 | 123.5745
6703 | 152.1056
6704 | 137.9423
6705 | 119.5275
6706 | 129.387
6707 | 113.6348
6708 | 109.8047
6709 | 95.2117
6710 | 100.2962
6711 | 144.0399
6712 | 111.6394
6713 | 100.2663
6714 | 119.2675
6715 | 119.7472
6716 | 94.217
6717 | 144.6442
6718 | 113.3786
6719 | 117.1668
6720 | 104.2021
6721 | 123.156
6722 | 91.2971
6723 | 114.042
6724 | 140.44
6725 | 93.1793
6726 | 95.6522
6727 | 98.4544
6728 | 113.0252
6729 | 149.0149
6730 | 131.8821
6731 | 112.4016
6732 | 167.6437
6733 | 123.8124
6734 | 74.0338
6735 | 113.5157
6736 | 100.3039
6737 | 151.2822
6738 | 106.6456
6739 | 113.4229
6740 | 117.3159
6741 | 85.9332
6742 | 145.2214
6743 | 101.8047
6744 | 115.4927
6745 | 84.5829
6746 | 107.1639
6747 | 110.4449
6748 | 122.3765
6749 | 157.6832
6750 | 105.2646
6751 | 97.4869
6752 | 131.0289
6753 | 125.0961
6754 | 100.4247
6755 | 129.1749
6756 | 139.9265
6757 | 72.0768
6758 | 103.1007
6759 | 133.9408
6760 | 141.3349
6761 | 67.5659
6762 | 109.7143
6763 | 75.2065
6764 | 94.6354
6765 | 114.8817
6766 | 82.7023
6767 | 160.6355
6768 | 131.7325
6769 | 85.0323
6770 | 112.4621
6771 | 101.3099
6772 | 88.7228
6773 | 88.0493
6774 | 119.826
6775 | 88.6133
6776 | 156.6832
6777 | 141.9677
6778 | 103.5304
6779 | 112.4591
6780 | 92.775
6781 | 114.1624
6782 | 113.162
6783 | 94.3097
6784 | 138.8009
6785 | 113.6929
6786 | 80.9369
6787 | 138.1877
6788 | 110.0861
6789 | 156.0091
6790 | 101.554
6791 | 111.718
6792 | 100.0409
6793 | 112.7252
6794 | 120.0712
6795 | 155.0364
6796 | 155.5262
6797 | 111.4222
6798 | 132.3892
6799 | 138.6098
6800 | 94.4291
6801 | 142.5593
6802 | 90.0889
6803 | 126.2259
6804 | 124.467
6805 | 138.4937
6806 | 86.8967
6807 | 130.5225
6808 | 124.7275
6809 | 110.653
6810 | 161.0961
6811 | 117.6763
6812 | 136.9568
6813 | 99.9061
6814 | 71.6441
6815 | 129.3994
6816 | 149.6053
6817 | 116.0549
6818 | 144.0568
6819 | 135.7238
6820 | 146.5958
6821 | 124.3147
6822 | 133.5718
6823 | 163.522
6824 | 116.1752
6825 | 124.5109
6826 | 80.683
6827 | 131.656
6828 | 149.2593
6829 | 179.7968
6830 | 84.0047
6831 | 116.3565
6832 | 117.7051
6833 | 148.4835
6834 | 160.6558
6835 | 138.4338
6836 | 112.5268
6837 | 119.9078
6838 | 106.4586
6839 | 116.1909
6840 | 130.8233
6841 | 105.8527
6842 | 82.5237
6843 | 115.2252
6844 | 134.0313
6845 | 119.19
6846 | 130.8124
6847 | 129.564
6848 | 137.0896
6849 | 96.2043
6850 | 164.5316
6851 | 136.616
6852 | 106.1266
6853 | 111.8274
6854 | 109.5066
6855 | 67.944
6856 | 105.9461
6857 | 88.3377
6858 | 113.1524
6859 | 122.9509
6860 | 147.4382
6861 | 115.4316
6862 | 136.7737
6863 | 107.2403
6864 | 111.5484
6865 | 110.6515
6866 | 123.6022
6867 | 120.303
6868 | 116.4178
6869 | 136.1716
6870 | 69.7211
6871 | 125.3209
6872 | 96.3526
6873 | 116.3083
6874 | 95.6211
6875 | 144.9238
6876 | 154.812
6877 | 88.4311
6878 | 134.77
6879 | 140.597
6880 | 109.5519
6881 | 125.3954
6882 | 125.06
6883 | 115.6356
6884 | 137.2556
6885 | 161.0423
6886 | 100.9406
6887 | 82.3458
6888 | 119.4954
6889 | 107.2309
6890 | 88.9914
6891 | 107.9042
6892 | 81.5386
6893 | 143.8887
6894 | 160.9718
6895 | 113.7866
6896 | 110.5606
6897 | 140.7878
6898 | 113.828
6899 | 125.9926
6900 | 153.895
6901 | 115.3409
6902 | 100.3623
6903 | 134.2731
6904 | 114.3523
6905 | 89.0928
6906 | 135.6288
6907 | 124.1488
6908 | 141.4908
6909 | 122.2656
6910 | 100.4535
6911 | 173.9819
6912 | 149.9387
6913 | 142.1598
6914 | 134.0713
6915 | 126.1391
6916 | 124.6243
6917 | 137.6581
6918 | 141.0589
6919 | 139.9719
6920 | 101.3791
6921 | 122.4438
6922 | 95.1065
6923 | 104.5208
6924 | 120.6572
6925 | 54.9983
6926 | 151.4409
6927 | 133.7244
6928 | 100.0979
6929 | 129.7665
6930 | 138.9818
6931 | 121.9877
6932 | 132.7042
6933 | 109.2149
6934 | 119.9459
6935 | 130.3107
6936 | 117.9305
6937 | 126.324
6938 | 95.8166
6939 | 117.2686
6940 | 106.6257
6941 | 102.8419
6942 | 96.1691
6943 | 95.5895
6944 | 146.9671
6945 | 99.5368
6946 | 102.2528
6947 | 163.6023
6948 | 130.0694
6949 | 158.706
6950 | 150.0369
6951 | 158.4431
6952 | 101.3288
6953 | 89.436
6954 | 91.51
6955 | 109.3702
6956 | 111.2648
6957 | 113.9159
6958 | 126.4844
6959 | 79.8418
6960 | 146.0697
6961 | 125.2199
6962 | 132.0289
6963 | 122.9809
6964 | 88.2149
6965 | 128.2411
6966 | 77.2599
6967 | 149.8149
6968 | 113.8541
6969 | 132.6419
6970 | 136.545
6971 | 133.8478
6972 | 89.8766
6973 | 100.4715
6974 | 177.4482
6975 | 121.1291
6976 | 91.2405
6977 | 147.2409
6978 | 170.8437
6979 | 101.4149
6980 | 105.5778
6981 | 136.0175
6982 | 137.7743
6983 | 124.492
6984 | 100.4329
6985 | 92.5183
6986 | 124.5595
6987 | 102.4445
6988 | 120.2533
6989 | 88.6921
6990 | 136.5013
6991 | 171.771
6992 | 149.6445
6993 | 100.021
6994 | 92.387
6995 | 86.1786
6996 | 130.4154
6997 | 110.9508
6998 | 110.3973
6999 | 117.3333
7000 | 145.5875
7001 | 136.0629
7002 | 118.8046
7003 | 121.5415
7004 | 59.4812
7005 | 133.8822
7006 | 110.7928
7007 | 153.7246
7008 | 145.9238
7009 | 111.3555
7010 | 91.672
7011 | 115.336
7012 | 132.6034
7013 | 94.8398
7014 | 63.3171
7015 | 114.2128
7016 | 166.9513
7017 | 76.1833
7018 | 123.5372
7019 | 126.5973
7020 | 81.2738
7021 | 89.8239
7022 | 117.0708
7023 | 144.9691
7024 | 121.5438
7025 | 88.547
7026 | 143.9058
7027 | 120.6603
7028 | 114.4245
7029 | 87.1533
7030 | 123.5856
7031 | 113.6649
7032 | 140.4407
7033 | 144.3606
7034 | 169.5663
7035 | 104.2952
7036 | 120.0652
7037 | 95.9603
7038 | 132.6199
7039 | 138.4427
7040 | 89.2354
7041 | 118.5538
7042 | 112.6616
7043 | 118.737
7044 | 114.4507
7045 | 126.5552
7046 | 107.0353
7047 | 109.4798
7048 | 95.4471
7049 | 115.8437
7050 | 160.6808
7051 | 137.2364
7052 | 135.8722
7053 | 105.2016
7054 | 129.7052
7055 | 134.0608
7056 | 136.2804
7057 | 132.4053
7058 | 121.3331
7059 | 102.7375
7060 | 158.9213
7061 | 123.6383
7062 | 149.6204
7063 | 102.4948
7064 | 110.159
7065 | 122.4059
7066 | 129.2892
7067 | 114.6564
7068 | 132.3241
7069 | 110.5909
7070 | 139.7899
7071 | 129.1062
7072 | 125.4275
7073 | 141.0911
7074 | 131.7614
7075 | 101.0267
7076 | 105.017
7077 | 85.726
7078 | 100.3854
7079 | 128.7369
7080 | 89.1461
7081 | 114.0458
7082 | 139.4574
7083 | 111.2661
7084 | 117.8282
7085 | 148.2077
7086 | 101.0939
7087 | 110.7819
7088 | 128.8362
7089 | 79.7781
7090 | 140.8492
7091 | 109.5697
7092 | 131.7781
7093 | 75.4164
7094 | 153.712
7095 | 123.4725
7096 | 138.0754
7097 | 118.0079
7098 | 124.9478
7099 | 85.9611
7100 | 133.7637
7101 | 98.9428
7102 | 110.5772
7103 | 106.5846
7104 | 118.0974
7105 | 107.8318
7106 | 114.7073
7107 | 112.9415
7108 | 125.8215
7109 | 140.7167
7110 | 118.1998
7111 | 142.0137
7112 | 128.4253
7113 | 147.1504
7114 | 127.5461
7115 | 94.495
7116 | 114.0164
7117 | 171.5552
7118 | 126.8481
7119 | 120.7099
7120 | 109.6979
7121 | 145.4017
7122 | 80.6039
7123 | 114.9453
7124 | 105.1217
7125 | 108.4771
7126 | 113.4473
7127 | 126.6093
7128 | 123.7702
7129 | 114.1562
7130 | 108.6532
7131 | 100.6532
7132 | 115.7879
7133 | 134.0259
7134 | 105.7835
7135 | 169.5552
7136 | 137.4171
7137 | 75.7003
7138 | 85.7558
7139 | 109.6324
7140 | 118.1097
7141 | 104.9822
7142 | 119.779
7143 | 143.0729
7144 | 145.6094
7145 | 112.9987
7146 | 134.8162
7147 | 134.3835
7148 | 119.0188
7149 | 115.7672
7150 | 126.164
7151 | 104.7455
7152 | 164.6028
7153 | 133.2695
7154 | 107.4479
7155 | 148.9399
7156 | 83.6652
7157 | 129.3804
7158 | 103.8775
7159 | 83.6077
7160 | 101.2766
7161 | 171.4616
7162 | 148.1999
7163 | 100.4279
7164 | 130.3494
7165 | 134.7573
7166 | 146.9565
7167 | 116.3635
7168 | 153.8781
7169 | 158.474
7170 | 123.3493
7171 | 105.2389
7172 | 87.9562
7173 | 175.9783
7174 | 128.2527
7175 | 150.8817
7176 | 102.3509
7177 | 123.5079
7178 | 89.5172
7179 | 90.6325
7180 | 109.5522
7181 | 87.0737
7182 | 94.5308
7183 | 115.194
7184 | 98.3268
7185 | 87.5407
7186 | 128.5965
7187 | 117.474
7188 | 116.5972
7189 | 148.33
7190 | 89.3815
7191 | 120.7479
7192 | 110.7281
7193 | 79.8729
7194 | 129.4482
7195 | 143.5848
7196 | 130.9404
7197 | 112.9837
7198 | 101.3901
7199 | 141.8557
7200 | 102.8427
7201 | 130.05
7202 | 147.9845
7203 | 125.8293
7204 | 113.8398
7205 | 128.2529
7206 | 143.0248
7207 | 97.5881
7208 | 89.5088
7209 | 77.2097
7210 | 117.505
7211 | 122.4277
7212 | 133.5535
7213 | 158.6072
7214 | 129.0445
7215 | 140.2772
7216 | 101.5435
7217 | 92.5443
7218 | 141.0545
7219 | 91.1928
7220 | 92.1419
7221 | 115.6129
7222 | 145.4685
7223 | 127.9599
7224 | 139.9857
7225 | 149.9164
7226 | 115.9756
7227 | 83.5105
7228 | 128.413
7229 | 120.9481
7230 | 116.5473
7231 | 152.8614
7232 | 106.9469
7233 | 76.6006
7234 | 146.5237
7235 | 114.5341
7236 | 133.6947
7237 | 92.2291
7238 | 133.37
7239 | 125.059
7240 | 123.8424
7241 | 85.7494
7242 | 94.7849
7243 | 123.0979
7244 | 144.8956
7245 | 128.4566
7246 | 122.9845
7247 | 160.0338
7248 | 128.9802
7249 | 78.2716
7250 | 154.1067
7251 | 122.5835
7252 | 106.5766
7253 | 87.4515
7254 | 109.9539
7255 | 123.1976
7256 | 124.7427
7257 | 97.406
7258 | 139.6023
7259 | 120.6507
7260 | 80.3718
7261 | 66.6374
7262 | 126.5204
7263 | 103.3377
7264 | 145.2019
7265 | 155.7418
7266 | 151.5882
7267 | 140.8573
7268 | 105.6988
7269 | 125.8405
7270 | 79.0664
7271 | 151.5795
7272 | 125.0572
7273 | 131.8386
7274 | 137.4102
7275 | 138.9366
7276 | 100.9599
7277 | 101.4715
7278 | 124.0588
7279 | 93.0104
7280 | 140.8833
7281 | 143.9532
7282 | 136.1256
7283 | 146.1441
7284 | 68.8585
7285 | 128.493
7286 | 152.7675
7287 | 124.101
7288 | 49.2406
7289 | 100.6771
7290 | 154.3579
7291 | 149.531
7292 | 118.8919
7293 | 94.6742
7294 | 108.3031
7295 | 137.0939
7296 | 163.6781
7297 | 161.3767
7298 | 101.1296
7299 | 70.0239
7300 | 137.4352
7301 | 139.1523
7302 | 101.7978
7303 | 120.2552
7304 | 125.8075
7305 | 116.7486
7306 | 123.8078
7307 | 160.0496
7308 | 91.1937
7309 | 140.1147
7310 | 148.7496
7311 | 168.7975
7312 | 104.0239
7313 | 115.4773
7314 | 118.171
7315 | 160.553
7316 | 75.1126
7317 | 162.2331
7318 | 158.2419
7319 | 120.3106
7320 | 103.324
7321 | 140.7257
7322 | 73.5934
7323 | 93.8169
7324 | 96.3804
7325 | 87.4268
7326 | 124.2797
7327 | 110.8758
7328 | 141.6477
7329 | 99.6837
7330 | 129.2267
7331 | 131.8279
7332 | 125.5714
7333 | 124.5582
7334 | 97.0614
7335 | 132.1596
7336 | 107.5812
7337 | 138.2785
7338 | 149.2674
7339 | 92.3475
7340 | 92.3472
7341 | 91.7042
7342 | 127.4896
7343 | 121.5264
7344 | 128.991
7345 | 151.5035
7346 | 141.7144
7347 | 98.8599
7348 | 125.5686
7349 | 113.2343
7350 | 95.8599
7351 | 52.9883
7352 | 99.3361
7353 | 138.8728
7354 | 166.8792
7355 | 139.4109
7356 | 117.8567
7357 | 105.4785
7358 | 111.4711
7359 | 101.7538
7360 | 93.3588
7361 | 142.3504
7362 | 116.9002
7363 | 119.9666
7364 | 112.3059
7365 | 143.9073
7366 | 98.2529
7367 | 105.2367
7368 | 146.9026
7369 | 88.2543
7370 | 168.3993
7371 | 141.6737
7372 | 96.682
7373 | 106.2254
7374 | 117.9724
7375 | 103.1345
7376 | 73.0612
7377 | 90.5421
7378 | 119.1219
7379 | 102.9852
7380 | 147.5105
7381 | 132.015
7382 | 106.9458
7383 | 96.6571
7384 | 133.7411
7385 | 125.5443
7386 | 117.0543
7387 | 153.8019
7388 | 146.3755
7389 | 87.8886
7390 | 154.4594
7391 | 118.2295
7392 | 104.9757
7393 | 138.3229
7394 | 99.8439
7395 | 150.4766
7396 | 139.9294
7397 | 149.9565
7398 | 156.9095
7399 | 144.8486
7400 | 138.0427
7401 | 110.1463
7402 | 108.3529
7403 | 111.1813
7404 | 113.7361
7405 | 129.6432
7406 | 99.9643
7407 | 91.0023
7408 | 98.7121
7409 | 138.2946
7410 | 98.0736
7411 | 157.264
7412 | 81.6306
7413 | 97.3919
7414 | 110.9925
7415 | 94.4916
7416 | 92.7756
7417 | 109.6019
7418 | 105.9023
7419 | 129.0593
7420 | 110.0128
7421 | 92.37
7422 | 135.6594
7423 | 93.7361
7424 | 134.7007
7425 | 99.3485
7426 | 120.7297
7427 | 89.2116
7428 | 124.9201
7429 | 115.5142
7430 | 167.1547
7431 | 144.0024
7432 | 118.8461
7433 | 99.1761
7434 | 110.8697
7435 | 144.584
7436 | 73.3879
7437 | 130.652
7438 | 134.6898
7439 | 122.7559
7440 | 144.6706
7441 | 144.6989
7442 | 145.2942
7443 | 141.2567
7444 | 132.9042
7445 | 102.3699
7446 | 116.6829
7447 | 141.7896
7448 | 103.1397
7449 | 96.6008
7450 | 112.6251
7451 | 142.6127
7452 | 78.1713
7453 | 106.8561
7454 | 109.8567
7455 | 114.2395
7456 | 109.8973
7457 | 158.5552
7458 | 131.2038
7459 | 139.2734
7460 | 84.5151
7461 | 85.5193
7462 | 100.6363
7463 | 118.3409
7464 | 109.7545
7465 | 114.8049
7466 | 113.0196
7467 | 121.9662
7468 | 126.674
7469 | 152.6751
7470 | 100.4787
7471 | 132.6128
7472 | 92.9922
7473 | 127.752
7474 | 106.6646
7475 | 154.5167
7476 | 140.8106
7477 | 106.8655
7478 | 130.1226
7479 | 101.9207
7480 | 140.231
7481 | 115.9406
7482 | 159.3502
7483 | 160.6895
7484 | 93.0429
7485 | 120.4322
7486 | 104.8482
7487 | 85.6524
7488 | 117.4208
7489 | 65.2002
7490 | 148.9979
7491 | 144.5784
7492 | 93.8151
7493 | 139.3298
7494 | 70.4668
7495 | 127.4065
7496 | 110.5058
7497 | 118.6369
7498 | 87.3521
7499 | 136.3091
7500 | 82.3687
7501 | 140.4212
7502 | 119.4108
7503 | 112.4862
7504 | 133.498
7505 | 75.8218
7506 | 144.3251
7507 | 143.8596
7508 | 116.7206
7509 | 119.5166
7510 | 130.1512
7511 | 133.6525
7512 | 142.0632
7513 | 135.297
7514 | 104.9919
7515 | 115.6455
7516 | 112.7322
7517 | 122.721
7518 | 118.7419
7519 | 118.7331
7520 | 103.4788
7521 | 107.5698
7522 | 136.0927
7523 | 95.8409
7524 | 131.2517
7525 | 137.8244
7526 | 150.8134
7527 | 133.5118
7528 | 129.7404
7529 | 132.8244
7530 | 96.7014
7531 | 75.1034
7532 | 142.929
7533 | 120.9354
7534 | 124.7421
7535 | 116.4793
7536 | 151.4111
7537 | 91.5498
7538 | 109.3425
7539 | 109.2551
7540 | 107.4812
7541 | 86.1979
7542 | 153.7454
7543 | 112.3445
7544 | 70.5827
7545 | 129.5124
7546 | 134.1846
7547 | 143.4842
7548 | 82.3928
7549 | 100.9141
7550 | 110.0418
7551 | 114.3468
7552 | 65.2604
7553 | 129.0409
7554 | 80.1665
7555 | 132.1487
7556 | 131.378
7557 | 116.0883
7558 | 120.644
7559 | 125.7112
7560 | 133.512
7561 | 143.3292
7562 | 144.098
7563 | 111.1745
7564 | 138.9619
7565 | 104.052
7566 | 113.9122
7567 | 90.8118
7568 | 105.2282
7569 | 157.8696
7570 | 142.9863
7571 | 185.5893
7572 | 127.7462
7573 | 136.1639
7574 | 107.7888
7575 | 133.7405
7576 | 131.3833
7577 | 138.3165
7578 | 128.8859
7579 | 86.3565
7580 | 112.7645
7581 | 88.3372
7582 | 146.1031
7583 | 68.1315
7584 | 83.8624
7585 | 119.7815
7586 | 128.857
7587 | 120.6186
7588 | 129.4197
7589 | 112.3233
7590 | 94.7347
7591 | 107.301
7592 | 113.4869
7593 | 115.7081
7594 | 151.3587
7595 | 115.1863
7596 | 101.8673
7597 | 103.1858
7598 | 141.188
7599 | 107.7822
7600 | 109.5333
7601 | 102.4616
7602 | 146.5364
7603 | 155.4224
7604 | 141.5337
7605 | 129.8514
7606 | 108.9955
7607 | 109.6842
7608 | 157.7746
7609 | 100.8372
7610 | 123.1168
7611 | 115.1124
7612 | 78.2613
7613 | 110.3803
7614 | 119.439
7615 | 134.9957
7616 | 129.9481
7617 | 162.9179
7618 | 139.0281
7619 | 96.5289
7620 | 158.7708
7621 | 105.258
7622 | 141.7748
7623 | 149.2012
7624 | 127.6826
7625 | 123.4043
7626 | 87.5358
7627 | 138.0545
7628 | 102.5078
7629 | 103.748
7630 | 84.8649
7631 | 93.0955
7632 | 95.2189
7633 | 130.1553
7634 | 139.6843
7635 | 95.4809
7636 | 155.0061
7637 | 124.227
7638 | 93.6849
7639 | 92.4537
7640 | 122.9232
7641 | 128.7254
7642 | 104.8477
7643 | 61.8558
7644 | 121.885
7645 | 117.5214
7646 | 134.7828
7647 | 167.2983
7648 | 146.4514
7649 | 137.2138
7650 | 109.5086
7651 | 127.2808
7652 | 117.7503
7653 | 111.104
7654 | 105.1172
7655 | 164.7882
7656 | 149.5244
7657 | 141.0169
7658 | 81.0609
7659 | 144.6655
7660 | 104.8387
7661 | 95.8401
7662 | 93.9773
7663 | 146.5031
7664 | 129.5282
7665 | 122.0664
7666 | 111.7037
7667 | 84.5929
7668 | 106.2187
7669 | 99.9739
7670 | 112.0862
7671 | 151.39
7672 | 112.7494
7673 | 100.9004
7674 | 121.9301
7675 | 89.8332
7676 | 108.3314
7677 | 122.2753
7678 | 100.1261
7679 | 122.6388
7680 | 140.1523
7681 | 99.3435
7682 | 111.7553
7683 | 140.8018
7684 | 104.0707
7685 | 111.8013
7686 | 96.915
7687 | 108.3394
7688 | 139.9058
7689 | 73.4882
7690 | 119.5973
7691 | 118.1353
7692 | 151.9166
7693 | 105.4587
7694 | 102.9244
7695 | 132.6076
7696 | 158.7831
7697 | 132.6383
7698 | 56.7497
7699 | 107.2088
7700 | 101.583
7701 | 97.937
7702 | 117.686
7703 | 148.9194
7704 | 131.7086
7705 | 98.5379
7706 | 100.2208
7707 | 138.7214
7708 | 111.3044
7709 | 128.102
7710 | 107.2265
7711 | 103.9979
7712 | 183.2662
7713 | 131.0022
7714 | 142.1153
7715 | 163.4212
7716 | 100.0767
7717 | 85.1058
7718 | 137.1259
7719 | 125.4721
7720 | 138.0939
7721 | 141.3088
7722 | 110.3967
7723 | 174.9644
7724 | 85.875
7725 | 104.6165
7726 | 144.662
7727 | 107.3391
7728 | 140.7828
7729 | 126.0893
7730 | 112.7726
7731 | 100.5074
7732 | 129.502
7733 | 104.6696
7734 | 143.9059
7735 | 119.8807
7736 | 124.0911
7737 | 133.1753
7738 | 120.7961
7739 | 124.976
7740 | 136.4576
7741 | 103.6472
7742 | 133.8374
7743 | 161.1559
7744 | 123.3054
7745 | 113.5311
7746 | 60.3594
7747 | 108.5219
7748 | 110.2523
7749 | 96.0952
7750 | 123.4697
7751 | 154.5161
7752 | 89.2786
7753 | 137.9536
7754 | 133.2691
7755 | 86.9814
7756 | 61.7497
7757 | 139.4359
7758 | 132.4376
7759 | 108.5878
7760 | 96.0111
7761 | 146.0641
7762 | 104.5673
7763 | 132.5609
7764 | 126.6844
7765 | 110.2916
7766 | 112.4821
7767 | 155.829
7768 | 111.7296
7769 | 79.581
7770 | 92.5758
7771 | 125.6998
7772 | 109.4184
7773 | 161.1556
7774 | 129.1695
7775 | 158.2169
7776 | 131.2431
7777 | 156.3256
7778 | 107.8112
7779 | 130.3103
7780 | 110.2964
7781 | 92.5556
7782 | 158.7398
7783 | 78.275
7784 | 110.593
7785 | 153.6488
7786 | 166.8776
7787 | 129.6651
7788 | 131.1656
7789 | 125.0355
7790 | 112.8447
7791 | 141.0236
7792 | 126.0391
7793 | 153.0644
7794 | 122.1685
7795 | 124.2343
7796 | 119.1608
7797 | 131.9586
7798 | 128.865
7799 | 93.0704
7800 | 137.9587
7801 | 71.0841
7802 | 101.6676
7803 | 99.7949
7804 | 142.7973
7805 | 116.6774
7806 | 129.6053
7807 | 133.007
7808 | 102.8006
7809 | 107.7781
7810 | 90.6211
7811 | 152.3808
7812 | 120.613
7813 | 117.5833
7814 | 139.8849
7815 | 125.0188
7816 | 126.6689
7817 | 92.5223
7818 | 92.6596
7819 | 120.9648
7820 | 114.4801
7821 | 119.0038
7822 | 117.1832
7823 | 123.1735
7824 | 111.6818
7825 | 125.704
7826 | 98.6823
7827 | 120.684
7828 | 105.4327
7829 | 81.9184
7830 | 116.1485
7831 | 115.9839
7832 | 89.4088
7833 | 111.8445
7834 | 73.9422
7835 | 145.6047
7836 | 150.4503
7837 | 115.2752
7838 | 68.655
7839 | 191.3792
7840 | 143.5495
7841 | 151.7654
7842 | 132.7035
7843 | 73.5901
7844 | 114.4808
7845 | 127.9263
7846 | 139.8103
7847 | 109.3726
7848 | 94.822
7849 | 163.8468
7850 | 103.8996
7851 | 162.8985
7852 | 125.1738
7853 | 88.2278
7854 | 155.3113
7855 | 121.5659
7856 | 131.2043
7857 | 141.6835
7858 | 124.1368
7859 | 133.2133
7860 | 115.1821
7861 | 153.3049
7862 | 79.2287
7863 | 89.2949
7864 | 113.0262
7865 | 82.5589
7866 | 121.5084
7867 | 145.4478
7868 | 151.8189
7869 | 125.7643
7870 | 114.0012
7871 | 110.1892
7872 | 104.5464
7873 | 109.8275
7874 | 162.6337
7875 | 117.0859
7876 | 136.0995
7877 | 123.0323
7878 | 104.1066
7879 | 142.0703
7880 | 119.5192
7881 | 97.3353
7882 | 129.5133
7883 | 133.9938
7884 | 159.0454
7885 | 70.3662
7886 | 91.1352
7887 | 117.2362
7888 | 117.4888
7889 | 128.1322
7890 | 166.6032
7891 | 132.2738
7892 | 147.7293
7893 | 129.5316
7894 | 124.3246
7895 | 133.8377
7896 | 100.2609
7897 | 137.0813
7898 | 124.0316
7899 | 174.4302
7900 | 98.199
7901 | 85.9574
7902 | 115.8574
7903 | 128.2518
7904 | 66.0826
7905 | 89.4316
7906 | 108.9842
7907 | 122.2959
7908 | 137.636
7909 | 103.6081
7910 | 102.867
7911 | 105.852
7912 | 105.5341
7913 | 118.8223
7914 | 139.7573
7915 | 94.2968
7916 | 142.3368
7917 | 110.9877
7918 | 135.6947
7919 | 109.7095
7920 | 87.2255
7921 | 90.2118
7922 | 155.9007
7923 | 124.4285
7924 | 154.0122
7925 | 59.8957
7926 | 100.2493
7927 | 74.184
7928 | 131.5103
7929 | 128.5199
7930 | 119.3704
7931 | 103.9898
7932 | 144.3476
7933 | 103.0147
7934 | 107.8903
7935 | 140.7281
7936 | 120.0035
7937 | 116.0944
7938 | 76.5263
7939 | 120.7546
7940 | 119.9319
7941 | 91.2949
7942 | 182.4778
7943 | 142.5693
7944 | 113.7385
7945 | 97.1819
7946 | 166.6591
7947 | 123.3685
7948 | 123.248
7949 | 99.6571
7950 | 123.3233
7951 | 109.8613
7952 | 139.3837
7953 | 124.4913
7954 | 93.4862
7955 | 154.2122
7956 | 102.6088
7957 | 136.2027
7958 | 88.0452
7959 | 146.6397
7960 | 102.8702
7961 | 159.5854
7962 | 132.6867
7963 | 123.9233
7964 | 93.823
7965 | 116.2219
7966 | 75.251
7967 | 96.3598
7968 | 131.0547
7969 | 89.0661
7970 | 116.856
7971 | 125.1728
7972 | 98.5162
7973 | 146.6038
7974 | 137.4217
7975 | 115.1215
7976 | 161.8608
7977 | 146.9781
7978 | 96.2544
7979 | 92.7625
7980 | 143.3252
7981 | 154.5798
7982 | 89.1303
7983 | 133.4234
7984 | 158.4298
7985 | 97.7887
7986 | 90.5678
7987 | 87.3167
7988 | 133.6609
7989 | 138.9663
7990 | 98.3472
7991 | 145.6596
7992 | 105.7603
7993 | 123.7699
7994 | 57.1795
7995 | 133.4938
7996 | 82.8135
7997 | 115.2637
7998 | 118.4408
7999 | 110.8127
8000 | 107.47
8001 | 134.9856
8002 | 115.2013
8003 | 118.5656
8004 | 119.8322
8005 | 104.1339
8006 | 133.3068
8007 | 123.555
8008 | 98.3436
8009 | 137.2536
8010 | 94.3822
8011 | 114.2707
8012 | 166.1559
8013 | 129.6265
8014 | 83.588
8015 | 130.3452
8016 | 90.877
8017 | 163.2349
8018 | 168.6307
8019 | 123.9411
8020 | 96.9606
8021 | 153.4684
8022 | 146.0365
8023 | 127.4108
8024 | 184.2203
8025 | 121.797
8026 | 105.5813
8027 | 128.4975
8028 | 109.6825
8029 | 144.6287
8030 | 121.5055
8031 | 150.2739
8032 | 115.0883
8033 | 126.3284
8034 | 142.8099
8035 | 141.2995
8036 | 152.4742
8037 | 137.2681
8038 | 164.0769
8039 | 95.9385
8040 | 107.5844
8041 | 103.9726
8042 | 130.3502
8043 | 121.4488
8044 | 122.2752
8045 | 136.9179
8046 | 125.7694
8047 | 142.5496
8048 | 110.6209
8049 | 106.3981
8050 | 140.0002
8051 | 124.5928
8052 | 129.2015
8053 | 109.0419
8054 | 150.1677
8055 | 122.2615
8056 | 88.2129
8057 | 107.1696
8058 | 117.8893
8059 | 119.9634
8060 | 131.5438
8061 | 109.2195
8062 | 117.5848
8063 | 103.8696
8064 | 97.1173
8065 | 103.213
8066 | 106.751
8067 | 131.6724
8068 | 128.6661
8069 | 144.8431
8070 | 77.2433
8071 | 144.312
8072 | 138.9741
8073 | 142.4321
8074 | 152.3964
8075 | 109.0867
8076 | 113.6616
8077 | 118.9907
8078 | 127.4869
8079 | 89.3018
8080 | 100.5018
8081 | 158.8618
8082 | 124.0446
8083 | 130.2713
8084 | 132.1742
8085 | 79.6641
8086 | 137.8408
8087 | 127.784
8088 | 120.0535
8089 | 128.3671
8090 | 113.5435
8091 | 91.4943
8092 | 75.2149
8093 | 131.8612
8094 | 123.6577
8095 | 73.2273
8096 | 133.2253
8097 | 125.7533
8098 | 143.656
8099 | 90.6993
8100 | 68.4846
8101 | 135.5395
8102 | 140.8969
8103 | 129.5142
8104 | 112.9078
8105 | 130.1051
8106 | 115.5793
8107 | 139.3572
8108 | 106.08
8109 | 100.0221
8110 | 107.604
8111 | 104.2214
8112 | 83.3325
8113 | 109.7801
8114 | 118.0804
8115 | 143.7281
8116 | 87.1005
8117 | 99.5907
8118 | 70.2244
8119 | 87.0648
8120 | 147.9281
8121 | 136.4602
8122 | 82.3215
8123 | 97.1971
8124 | 96.4844
8125 | 87.84
8126 | 120.7064
8127 | 100.405
8128 | 114.7129
8129 | 128.9283
8130 | 112.9861
8131 | 116.7211
8132 | 108.1189
8133 | 137.0892
8134 | 94.7903
8135 | 143.9619
8136 | 80.0087
8137 | 87.9868
8138 | 130.5683
8139 | 156.6067
8140 | 97.8084
8141 | 97.1199
8142 | 122.395
8143 | 133.7114
8144 | 132.5405
8145 | 91.0567
8146 | 114.3845
8147 | 140.0319
8148 | 109.4946
8149 | 79.502
8150 | 101.3367
8151 | 88.1023
8152 | 88.6144
8153 | 109.4405
8154 | 144.8367
8155 | 126.42
8156 | 125.2918
8157 | 133.3586
8158 | 128.3572
8159 | 164.6101
8160 | 99.8358
8161 | 107.6441
8162 | 114.425
8163 | 124.8406
8164 | 145.8232
8165 | 92.9531
8166 | 98.9125
8167 | 105.1544
8168 | 34.7912
8169 | 141.8657
8170 | 101.5799
8171 | 153.0347
8172 | 123.892
8173 | 127.4994
8174 | 102.4753
8175 | 79.3174
8176 | 137.384
8177 | 126.8524
8178 | 155.7517
8179 | 132.6144
8180 | 129.8529
8181 | 133.1948
8182 | 103.5588
8183 | 147.2817
8184 | 111.5603
8185 | 100.9593
8186 | 87.1864
8187 | 98.5594
8188 | 126.7165
8189 | 149.3262
8190 | 93.6892
8191 | 107.9507
8192 | 110.1147
8193 | 86.7995
8194 | 117.3834
8195 | 140.6548
8196 | 99.1774
8197 | 122.912
8198 | 143.674
8199 | 142.4358
8200 | 123.8219
8201 | 123.8643
8202 | 147.9938
8203 | 111.8839
8204 | 119.971
8205 | 126.2618
8206 | 143.1467
8207 | 140.6366
8208 | 129.0907
8209 | 88.8091
8210 | 105.424
8211 | 93.401
8212 | 142.9013
8213 | 118.916
8214 | 109.8408
8215 | 98.4395
8216 | 169.2064
8217 | 132.4699
8218 | 94.0804
8219 | 140.9706
8220 | 133.6299
8221 | 129.866
8222 | 69.2256
8223 | 125.4524
8224 | 85.9059
8225 | 78.3617
8226 | 100.9066
8227 | 130.8583
8228 | 82.6409
8229 | 106.9012
8230 | 114.6775
8231 | 138.6617
8232 | 140.8242
8233 | 131.1839
8234 | 126.1462
8235 | 101.5283
8236 | 143.4027
8237 | 103.5273
8238 | 83.2181
8239 | 122.2483
8240 | 140.3526
8241 | 152.5306
8242 | 119.3383
8243 | 124.6283
8244 | 99.0986
8245 | 128.3571
8246 | 122.1777
8247 | 142.0403
8248 | 138.4288
8249 | 138.3588
8250 | 149.2033
8251 | 139.8697
8252 | 108.3119
8253 | 96.6886
8254 | 168.3249
8255 | 55.9928
8256 | 116.9144
8257 | 117.3525
8258 | 168.1027
8259 | 99.6063
8260 | 65.0459
8261 | 92.1852
8262 | 154.9457
8263 | 146.8385
8264 | 135.5445
8265 | 150.5987
8266 | 147.1949
8267 | 96.4513
8268 | 122.175
8269 | 161.2504
8270 | 159.9689
8271 | 133.2975
8272 | 151.011
8273 | 103.2383
8274 | 83.4497
8275 | 153.5633
8276 | 158.5591
8277 | 115.9389
8278 | 121.4023
8279 | 148.0375
8280 | 100.9874
8281 | 131.4786
8282 | 113.6423
8283 | 161.1463
8284 | 68.7417
8285 | 145.1039
8286 | 141.4828
8287 | 127.9516
8288 | 124.2803
8289 | 117.4713
8290 | 150.6116
8291 | 81.0458
8292 | 141.4329
8293 | 113.8484
8294 | 123.9979
8295 | 116.3508
8296 | 172.6395
8297 | 92.8215
8298 | 71.8958
8299 | 123.0152
8300 | 85.1311
8301 | 124.5609
8302 | 127.0342
8303 | 132.9249
8304 | 95.836
8305 | 150.4478
8306 | 145.3802
8307 | 135.4971
8308 | 159.1716
8309 | 97.2757
8310 | 158.087
8311 | 120.5379
8312 | 145.1144
8313 | 142.0128
8314 | 127.7719
8315 | 138.4282
8316 | 150.7735
8317 | 140.7726
8318 | 146.0952
8319 | 104.6321
8320 | 114.2258
8321 | 118.2822
8322 | 168.6103
8323 | 127.7633
8324 | 122.5206
8325 | 119.5251
8326 | 98.8818
8327 | 117.3559
8328 | 127.8838
8329 | 122.0088
8330 | 195.0552
8331 | 69.9447
8332 | 116.9956
8333 | 168.6355
8334 | 103.1913
8335 | 118.9959
8336 | 134.0695
8337 | 125.9046
8338 | 128.7557
8339 | 111.6539
8340 | 112.6251
8341 | 86.4866
8342 | 142.7382
8343 | 131.0107
8344 | 126.514
8345 | 86.3141
8346 | 113.0853
8347 | 121.9438
8348 | 74.0881
8349 | 132.6162
8350 | 149.1278
8351 | 116.5146
8352 | 160.0172
8353 | 106.3874
8354 | 80.4975
8355 | 120.9236
8356 | 100.0761
8357 | 112.7134
8358 | 128.124
8359 | 154.1798
8360 | 104.0902
8361 | 92.2889
8362 | 92.0811
8363 | 136.2006
8364 | 122.7177
8365 | 113.4394
8366 | 135.2629
8367 | 144.3172
8368 | 118.0949
8369 | 106.6315
8370 | 92.1707
8371 | 130.4825
8372 | 109.5291
8373 | 101.1348
8374 | 102.5523
8375 | 121.1706
8376 | 115.4932
8377 | 112.2661
8378 | 125.8735
8379 | 122.9804
8380 | 131.6068
8381 | 99.4826
8382 | 89.283
8383 | 95.0074
8384 | 128.0319
8385 | 99.8699
8386 | 133.5967
8387 | 142.8277
8388 | 170.5529
8389 | 97.9674
8390 | 98.6112
8391 | 134.9108
8392 | 91.7877
8393 | 110.3646
8394 | 106.7082
8395 | 128.5402
8396 | 124.507
8397 | 144.7862
8398 | 155.5068
8399 | 130.2974
8400 | 166.4036
8401 | 86.1475
8402 | 122.8689
8403 | 113.4976
8404 | 100.7784
8405 | 93.2101
8406 | 146.8577
8407 | 111.2015
8408 | 115.6554
8409 | 141.3441
8410 | 112.8919
8411 | 92.7619
8412 | 150.0695
8413 | 93.0146
8414 | 84.4944
8415 | 124.4669
8416 | 96.7432
8417 | 111.8411
8418 | 102.9345
8419 | 162.7073
8420 | 125.2656
8421 | 152.8639
8422 | 114.679
8423 | 118.0547
8424 | 99.3584
8425 | 108.843
8426 | 112.9675
8427 | 125.8006
8428 | 105.2424
8429 | 109.3083
8430 | 124.8624
8431 | 116.9729
8432 | 110.2917
8433 | 150.2976
8434 | 94.8399
8435 | 126.5047
8436 | 151.5776
8437 | 127.0617
8438 | 159.945
8439 | 109.9447
8440 | 181.6726
8441 | 146.9533
8442 | 78.5721
8443 | 128.797
8444 | 123.7426
8445 | 104.3523
8446 | 86.3435
8447 | 128.6705
8448 | 96.1383
8449 | 126.5636
8450 | 113.6043
8451 | 121.2247
8452 | 75.6458
8453 | 118.4424
8454 | 114.6419
8455 | 101.0498
8456 | 114.6873
8457 | 81.9469
8458 | 119.7547
8459 | 128.6934
8460 | 78.5887
8461 | 93.2011
8462 | 108.8261
8463 | 151.654
8464 | 119.5043
8465 | 169.6176
8466 | 140.806
8467 | 122.732
8468 | 116.0499
8469 | 130.2455
8470 | 123.9886
8471 | 103.0997
8472 | 96.2732
8473 | 102.6163
8474 | 77.4176
8475 | 123.9639
8476 | 123.9278
8477 | 101.7274
8478 | 121.4295
8479 | 136.5971
8480 | 99.3803
8481 | 123.6396
8482 | 134.5608
8483 | 115.2238
8484 | 110.6275
8485 | 116.0668
8486 | 126.0904
8487 | 138.7059
8488 | 132.5431
8489 | 108.9967
8490 | 124.3453
8491 | 87.9488
8492 | 107.671
8493 | 118.6119
8494 | 132.0401
8495 | 120.3649
8496 | 77.3952
8497 | 126.7549
8498 | 115.5065
8499 | 80.156
8500 | 143.8974
8501 | 98.5427
8502 | 100.2675
8503 | 146.2868
8504 | 144.7837
8505 | 124.8755
8506 | 127.6011
8507 | 107.9178
8508 | 142.7085
8509 | 101.9307
8510 | 135.2703
8511 | 87.5742
8512 | 129.5678
8513 | 98.2742
8514 | 100.0593
8515 | 146.8701
8516 | 131.6691
8517 | 140.2998
8518 | 119.7866
8519 | 92.4036
8520 | 74.5354
8521 | 124.396
8522 | 118.594
8523 | 135.9431
8524 | 101.171
8525 | 111.4361
8526 | 142.7517
8527 | 102.7127
8528 | 199.0401
8529 | 116.3585
8530 | 139.0842
8531 | 81.1786
8532 | 134.6904
8533 | 93.1693
8534 | 123.1816
8535 | 177.1739
8536 | 120.2689
8537 | 104.3338
8538 | 129.1263
8539 | 132.2581
8540 | 131.7609
8541 | 117.104
8542 | 108.1126
8543 | 122.7382
8544 | 108.6013
8545 | 150.3657
8546 | 85.3516
8547 | 132.3411
8548 | 135.0331
8549 | 123.9853
8550 | 133.722
8551 | 137.2288
8552 | 123.5029
8553 | 107.4473
8554 | 148.5139
8555 | 169.4275
8556 | 106.7933
8557 | 115.4269
8558 | 148.7768
8559 | 121.9108
8560 | 139.6635
8561 | 128.4876
8562 | 118.791
8563 | 134.1927
8564 | 108.0829
8565 | 95.1103
8566 | 160.6509
8567 | 142.1507
8568 | 136.2404
8569 | 143.4679
8570 | 124.4584
8571 | 124.0835
8572 | 78.1996
8573 | 131.9637
8574 | 138.5823
8575 | 103.2768
8576 | 127.5023
8577 | 89.5995
8578 | 102.2538
8579 | 153.8481
8580 | 135.005
8581 | 134.5751
8582 | 127.242
8583 | 140.7676
8584 | 139.9949
8585 | 90.8333
8586 | 115.945
8587 | 131.6724
8588 | 118.5334
8589 | 111.4771
8590 | 98.5391
8591 | 129.8424
8592 | 140.9371
8593 | 91.6066
8594 | 73.4403
8595 | 122.6344
8596 | 150.5028
8597 | 158.463
8598 | 158.166
8599 | 155.3383
8600 | 132.0713
8601 | 117.4925
8602 | 108.0841
8603 | 124.4589
8604 | 119.8617
8605 | 96.4136
8606 | 128.9574
8607 | 147.4433
8608 | 117.7929
8609 | 98.2795
8610 | 156.8772
8611 | 133.631
8612 | 100.2844
8613 | 127.1983
8614 | 102.4524
8615 | 164.2512
8616 | 123.8089
8617 | 133.0207
8618 | 99.4059
8619 | 94.1606
8620 | 136.4416
8621 | 152.3964
8622 | 117.6727
8623 | 145.6607
8624 | 115.682
8625 | 88.469
8626 | 156.3752
8627 | 110.3008
8628 | 134.5873
8629 | 93.4182
8630 | 141.7397
8631 | 87.8055
8632 | 152.6979
8633 | 146.8128
8634 | 121.5838
8635 | 123.5278
8636 | 130.0257
8637 | 165.4499
8638 | 118.6895
8639 | 83.7884
8640 | 147.4036
8641 | 152.4169
8642 | 100.9071
8643 | 102.0258
8644 | 143.2664
8645 | 96.3938
8646 | 85.3174
8647 | 135.3872
8648 | 129.2329
8649 | 127.947
8650 | 126.0746
8651 | 93.5588
8652 | 174.8799
8653 | 167.759
8654 | 120.957
8655 | 115.6386
8656 | 113.2317
8657 | 179.1262
8658 | 121.2345
8659 | 123.7466
8660 | 110.5755
8661 | 137.2643
8662 | 93.6321
8663 | 134.2837
8664 | 79.3766
8665 | 95.6104
8666 | 93.8909
8667 | 134.4475
8668 | 111.8638
8669 | 129.6127
8670 | 179.5288
8671 | 107.2206
8672 | 95.4301
8673 | 57.6865
8674 | 82.2842
8675 | 139.3995
8676 | 148.9853
8677 | 128.1986
8678 | 158.0018
8679 | 125.2962
8680 | 115.7811
8681 | 144.2532
8682 | 100.7419
8683 | 159.5913
8684 | 87.7248
8685 | 98.9217
8686 | 130.5453
8687 | 92.4222
8688 | 95.3854
8689 | 116.4644
8690 | 147.0607
8691 | 110.4216
8692 | 125.9663
8693 | 153.5966
8694 | 133.5787
8695 | 110.7834
8696 | 123.8544
8697 | 114.7884
8698 | 79.1133
8699 | 122.2109
8700 | 113.0275
8701 | 105.5425
8702 | 128.9755
8703 | 133.0327
8704 | 114.0305
8705 | 75.2676
8706 | 148.1492
8707 | 124.9643
8708 | 108.3613
8709 | 159.8984
8710 | 120.0637
8711 | 103.4451
8712 | 135.8428
8713 | 149.0008
8714 | 141.2596
8715 | 186.6046
8716 | 178.4809
8717 | 82.9093
8718 | 145.5833
8719 | 93.0226
8720 | 132.0928
8721 | 132.6317
8722 | 89.6405
8723 | 115.5499
8724 | 136.0338
8725 | 82.127
8726 | 127.2431
8727 | 89.9812
8728 | 116.9973
8729 | 85.6692
8730 | 155.6399
8731 | 89.0304
8732 | 124.0355
8733 | 121.6673
8734 | 74.2942
8735 | 96.0114
8736 | 108.7091
8737 | 96.2392
8738 | 136.5982
8739 | 108.7212
8740 | 78.4297
8741 | 143.2592
8742 | 162.6906
8743 | 145.2888
8744 | 125.0376
8745 | 117.7306
8746 | 109.3694
8747 | 132.6424
8748 | 149.7681
8749 | 149.717
8750 | 113.3724
8751 | 150.4203
8752 | 110.9871
8753 | 155.8903
8754 | 144.6444
8755 | 106.1903
8756 | 104.5386
8757 | 102.0668
8758 | 87.876
8759 | 81.0661
8760 | 140.9333
8761 | 126.864
8762 | 99.9426
8763 | 100.9446
8764 | 96.7439
8765 | 100.4159
8766 | 156.7046
8767 | 124.7196
8768 | 147.9999
8769 | 136.5626
8770 | 129.5693
8771 | 148.5683
8772 | 110.2883
8773 | 147.4541
8774 | 59.4425
8775 | 130.1953
8776 | 103.9808
8777 | 98.578
8778 | 118.8558
8779 | 106.4699
8780 | 138.2808
8781 | 72.5916
8782 | 101.5025
8783 | 137.3349
8784 | 153.973
8785 | 131.2468
8786 | 128.6707
8787 | 137.1345
8788 | 167.9581
8789 | 100.8211
8790 | 96.1403
8791 | 90.2045
8792 | 132.6549
8793 | 86.8289
8794 | 88.7232
8795 | 140.6605
8796 | 127.277
8797 | 142.7417
8798 | 98.3717
8799 | 71.8696
8800 | 85.0475
8801 | 133.1265
8802 | 95.1644
8803 | 167.2822
8804 | 135.0501
8805 | 114.8268
8806 | 117.8724
8807 | 147.0646
8808 | 112.4241
8809 | 106.0812
8810 | 98.8166
8811 | 109.4432
8812 | 113.8823
8813 | 164.3933
8814 | 173.5939
8815 | 92.7731
8816 | 124.6572
8817 | 130.9777
8818 | 78.8487
8819 | 139.4988
8820 | 75.7881
8821 | 120.1302
8822 | 110.4561
8823 | 126.6329
8824 | 141.8972
8825 | 88.7491
8826 | 134.3868
8827 | 120.4749
8828 | 80.1316
8829 | 93.3881
8830 | 116.8783
8831 | 98.8652
8832 | 139.2292
8833 | 138.2825
8834 | 148.9525
8835 | 126.9897
8836 | 129.9747
8837 | 54.5265
8838 | 124.9304
8839 | 126.5563
8840 | 100.5693
8841 | 90.7554
8842 | 170.8974
8843 | 93.8419
8844 | 152.7697
8845 | 143.8921
8846 | 98.3162
8847 | 129.9134
8848 | 69.3364
8849 | 136.9947
8850 | 141.0728
8851 | 88.4058
8852 | 49.0845
8853 | 148.8886
8854 | 113.9699
8855 | 136.4529
8856 | 130.8141
8857 | 94.2725
8858 | 132.1514
8859 | 136.3833
8860 | 111.3922
8861 | 135.6366
8862 | 136.0884
8863 | 124.9882
8864 | 82.2548
8865 | 149.3526
8866 | 157.6184
8867 | 179.0381
8868 | 105.3622
8869 | 73.4708
8870 | 97.2281
8871 | 99.3667
8872 | 112.1233
8873 | 88.1696
8874 | 130.8244
8875 | 86.29
8876 | 107.4191
8877 | 115.5687
8878 | 108.3189
8879 | 142.9973
8880 | 139.8417
8881 | 91.5341
8882 | 108.1203
8883 | 138.4486
8884 | 128.5409
8885 | 102.0373
8886 | 146.5315
8887 | 102.4715
8888 | 158.136
8889 | 131.2079
8890 | 98.1433
8891 | 98.7618
8892 | 108.9434
8893 | 118.0811
8894 | 165.3421
8895 | 136.5417
8896 | 180.1266
8897 | 113.4322
8898 | 117.3287
8899 | 116.382
8900 | 86.069
8901 | 85.7586
8902 | 125.8989
8903 | 99.6455
8904 | 131.5124
8905 | 96.0069
8906 | 162.7487
8907 | 127.9192
8908 | 140.4197
8909 | 114.2647
8910 | 130.0536
8911 | 125.8368
8912 | 96.1479
8913 | 123.8227
8914 | 75.8796
8915 | 90.5505
8916 | 108.3541
8917 | 164.3426
8918 | 117.2129
8919 | 130.0057
8920 | 108.7488
8921 | 114.7709
8922 | 134.0568
8923 | 112.5726
8924 | 152.7205
8925 | 125.4289
8926 | 114.9697
8927 | 130.1952
8928 | 143.9489
8929 | 71.6882
8930 | 142.3876
8931 | 82.2436
8932 | 129.3376
8933 | 129.0735
8934 | 71.6394
8935 | 128.6836
8936 | 82.1776
8937 | 133.0401
8938 | 105.5391
8939 | 145.3586
8940 | 129.5923
8941 | 142.0175
8942 | 150.7146
8943 | 124.8523
8944 | 132.5565
8945 | 127.6309
8946 | 117.3801
8947 | 169.0479
8948 | 162.2351
8949 | 111.668
8950 | 114.2725
8951 | 128.7934
8952 | 99.3725
8953 | 86.224
8954 | 128.4526
8955 | 106.4667
8956 | 120.4136
8957 | 121.6579
8958 | 148.4468
8959 | 155.2388
8960 | 121.2574
8961 | 164.1052
8962 | 116.1071
8963 | 128.1279
8964 | 121.9922
8965 | 124.6504
8966 | 105.4197
8967 | 106.8063
8968 | 87.2382
8969 | 131.4051
8970 | 146.0765
8971 | 139.6544
8972 | 90.5947
8973 | 136.3054
8974 | 124.3362
8975 | 138.079
8976 | 110.19
8977 | 125.349
8978 | 141.9018
8979 | 126.8104
8980 | 111.1139
8981 | 175.25
8982 | 107.318
8983 | 149.3116
8984 | 91.1079
8985 | 93.7128
8986 | 108.3322
8987 | 146.1671
8988 | 105.6066
8989 | 89.994
8990 | 124.1569
8991 | 131.5775
8992 | 143.9364
8993 | 133.0763
8994 | 156.6696
8995 | 102.1914
8996 | 85.4945
8997 | 140.0735
8998 | 88.0542
8999 | 79.8883
9000 | 112.736
9001 | 126.9683
9002 | 140.2839
9003 | 124.5665
9004 | 144.4652
9005 | 131.3071
9006 | 103.0251
9007 | 104.4106
9008 | 136.8941
9009 | 95.2739
9010 | 123.8584
9011 | 94.1532
9012 | 131.8873
9013 | 98.7995
9014 | 163.8148
9015 | 110.4495
9016 | 99.9101
9017 | 148.2589
9018 | 118.2199
9019 | 99.6495
9020 | 53.0307
9021 | 88.095
9022 | 121.8123
9023 | 67.8913
9024 | 109.3018
9025 | 151.6292
9026 | 81.5337
9027 | 89.1146
9028 | 96.9955
9029 | 113.098
9030 | 122.938
9031 | 95.1203
9032 | 172.7073
9033 | 122.6036
9034 | 170.4734
9035 | 108.1752
9036 | 157.3154
9037 | 136.7198
9038 | 139.2264
9039 | 133.8072
9040 | 74.9452
9041 | 75.4689
9042 | 105.7345
9043 | 108.9108
9044 | 135.6861
9045 | 130.4305
9046 | 123.2469
9047 | 96.4994
9048 | 116.0181
9049 | 114.1355
9050 | 98.108
9051 | 85.4034
9052 | 140.0772
9053 | 127.4249
9054 | 138.0327
9055 | 105.0724
9056 | 138.5416
9057 | 123.8303
9058 | 117.7782
9059 | 151.6763
9060 | 109.0629
9061 | 148.4233
9062 | 66.0183
9063 | 130.044
9064 | 97.3096
9065 | 115.8699
9066 | 117.4999
9067 | 102.0831
9068 | 111.8466
9069 | 120.8376
9070 | 110.5952
9071 | 79.1415
9072 | 125.5728
9073 | 101.525
9074 | 131.9022
9075 | 80.6387
9076 | 117.7837
9077 | 91.0041
9078 | 76.0584
9079 | 82.986
9080 | 141.5848
9081 | 131.5441
9082 | 104.682
9083 | 141.7165
9084 | 112.9709
9085 | 71.6753
9086 | 127.4875
9087 | 98.3849
9088 | 156.5064
9089 | 130.8956
9090 | 118.7034
9091 | 114.8299
9092 | 120.6837
9093 | 153.6303
9094 | 144.6249
9095 | 110.3736
9096 | 137.4866
9097 | 186.6127
9098 | 134.0133
9099 | 131.4879
9100 | 154.3562
9101 | 121.9331
9102 | 132.6834
9103 | 116.0973
9104 | 105.1472
9105 | 125.7662
9106 | 152.2981
9107 | 101.8577
9108 | 132.9893
9109 | 118.2044
9110 | 112.2655
9111 | 149.3173
9112 | 132.7739
9113 | 80.8255
9114 | 135.2303
9115 | 60.3782
9116 | 125.7455
9117 | 106.3904
9118 | 119.9123
9119 | 158.3978
9120 | 106.8494
9121 | 121.7777
9122 | 89.5739
9123 | 147.5139
9124 | 75.3852
9125 | 159.6062
9126 | 103.9155
9127 | 127.137
9128 | 120.9393
9129 | 140.6313
9130 | 133.2956
9131 | 119.5134
9132 | 173.2523
9133 | 88.2894
9134 | 101.7699
9135 | 112.0728
9136 | 159.9677
9137 | 104.3301
9138 | 113.4531
9139 | 99.1451
9140 | 159.1196
9141 | 133.7336
9142 | 100.1534
9143 | 101.159
9144 | 124.6605
9145 | 121.1644
9146 | 75.25
9147 | 155.487
9148 | 108.3134
9149 | 131.9469
9150 | 160.0423
9151 | 106.6539
9152 | 80.6652
9153 | 113.0267
9154 | 84.3609
9155 | 125.7756
9156 | 125.9019
9157 | 142.035
9158 | 72.2449
9159 | 100.1289
9160 | 115.2954
9161 | 122.6063
9162 | 149.632
9163 | 163.5806
9164 | 103.7021
9165 | 136.2057
9166 | 88.6963
9167 | 136.557
9168 | 82.5069
9169 | 118.8278
9170 | 99.2235
9171 | 103.9623
9172 | 122.3593
9173 | 118.2707
9174 | 110.0115
9175 | 121.2187
9176 | 114.3396
9177 | 138.2198
9178 | 168.0559
9179 | 141.3596
9180 | 138.8226
9181 | 106.9516
9182 | 133.7556
9183 | 124.6533
9184 | 101.0733
9185 | 83.8721
9186 | 114.046
9187 | 108.2632
9188 | 147.4691
9189 | 95.591
9190 | 111.7822
9191 | 141.0615
9192 | 132.6994
9193 | 105.0932
9194 | 125.3393
9195 | 126.1313
9196 | 86.0205
9197 | 134.906
9198 | 128.4399
9199 | 90.0523
9200 | 116.3722
9201 | 128.0089
9202 | 91.2496
9203 | 121.2951
9204 | 114.0627
9205 | 99.5729
9206 | 55.3297
9207 | 91.5809
9208 | 136.4193
9209 | 131.1122
9210 | 110.6198
9211 | 112.8433
9212 | 141.6754
9213 | 129.9782
9214 | 131.8528
9215 | 94.2683
9216 | 90.0974
9217 | 89.9331
9218 | 110.2328
9219 | 90.8818
9220 | 121.9322
9221 | 167.3705
9222 | 107.0166
9223 | 107.1497
9224 | 107.1344
9225 | 129.0357
9226 | 87.2761
9227 | 87.0573
9228 | 130.0098
9229 | 102.4208
9230 | 146.2615
9231 | 114.2076
9232 | 156.1892
9233 | 143.1013
9234 | 101.3316
9235 | 127.0451
9236 | 126.1254
9237 | 114.7828
9238 | 109.5692
9239 | 96.2803
9240 | 89.6175
9241 | 96.4606
9242 | 127.9218
9243 | 99.4094
9244 | 129.8122
9245 | 126.0197
9246 | 136.1925
9247 | 80.0144
9248 | 71.5237
9249 | 111.9389
9250 | 112.2547
9251 | 115.0853
9252 | 102.1998
9253 | 119.1952
9254 | 113.5442
9255 | 90.1964
9256 | 98.7752
9257 | 148.9533
9258 | 144.7891
9259 | 142.912
9260 | 111.5066
9261 | 155.4474
9262 | 115.4179
9263 | 139.0062
9264 | 69.024
9265 | 120.9828
9266 | 123.6072
9267 | 114.0673
9268 | 103.181
9269 | 125.4558
9270 | 127.1753
9271 | 103.6594
9272 | 110.9206
9273 | 142.3398
9274 | 83.6607
9275 | 130.0963
9276 | 144.2031
9277 | 118.2283
9278 | 165.673
9279 | 94.7032
9280 | 126.4781
9281 | 117.703
9282 | 135.4544
9283 | 110.2147
9284 | 144.139
9285 | 98.2211
9286 | 147.0431
9287 | 128.4804
9288 | 65.1084
9289 | 123.998
9290 | 144.5119
9291 | 96.3851
9292 | 90.1461
9293 | 100.2739
9294 | 63.7348
9295 | 103.7069
9296 | 103.6549
9297 | 114.1729
9298 | 149.6173
9299 | 158.3333
9300 | 115.1531
9301 | 132.222
9302 | 106.733
9303 | 129.6078
9304 | 137.4666
9305 | 148.6444
9306 | 139.8555
9307 | 107.0413
9308 | 124.0056
9309 | 124.0487
9310 | 143.8671
9311 | 121.1743
9312 | 106.8514
9313 | 162.0593
9314 | 103.2134
9315 | 113.7541
9316 | 96.6574
9317 | 107.9182
9318 | 151.0592
9319 | 137.9791
9320 | 68.0562
9321 | 118.2435
9322 | 133.317
9323 | 131.7312
9324 | 111.1463
9325 | 128.1418
9326 | 149.134
9327 | 163.3389
9328 | 171.6426
9329 | 152.7628
9330 | 74.6321
9331 | 117.2454
9332 | 133.8283
9333 | 85.5093
9334 | 148.3957
9335 | 88.6022
9336 | 104.5576
9337 | 106.4203
9338 | 163.5086
9339 | 101.1869
9340 | 93.9328
9341 | 109.8647
9342 | 89.5896
9343 | 106.2618
9344 | 114.9014
9345 | 141.1287
9346 | 143.73
9347 | 140.0155
9348 | 109.7521
9349 | 177.7422
9350 | 120.5198
9351 | 94.1508
9352 | 151.5293
9353 | 111.8604
9354 | 80.9348
9355 | 87.9456
9356 | 93.7129
9357 | 178.1039
9358 | 131.311
9359 | 122.4755
9360 | 134.1685
9361 | 134.7552
9362 | 115.4162
9363 | 109.6743
9364 | 94.8271
9365 | 159.0893
9366 | 127.9107
9367 | 92.7621
9368 | 98.3149
9369 | 120.6964
9370 | 133.3532
9371 | 126.1478
9372 | 120.5172
9373 | 136.2058
9374 | 114.9066
9375 | 105.0737
9376 | 86.7964
9377 | 116.213
9378 | 106.8778
9379 | 97.1169
9380 | 113.7218
9381 | 107.6047
9382 | 117.6361
9383 | 109.435
9384 | 141.136
9385 | 111.8871
9386 | 133.0489
9387 | 94.1757
9388 | 125.0686
9389 | 130.6251
9390 | 89.1213
9391 | 95.2621
9392 | 92.1233
9393 | 85.517
9394 | 93.0961
9395 | 100.6293
9396 | 121.9487
9397 | 106.8585
9398 | 103.8071
9399 | 88.9754
9400 | 126.7517
9401 | 101.0231
9402 | 123.8193
9403 | 119.2866
9404 | 147.0328
9405 | 138.7082
9406 | 110.839
9407 | 158.7735
9408 | 120.7005
9409 | 156.773
9410 | 168.8046
9411 | 85.906
9412 | 148.8815
9413 | 127.6221
9414 | 130.0627
9415 | 99.1619
9416 | 129.4428
9417 | 150.9718
9418 | 143.762
9419 | 97.5892
9420 | 126.5267
9421 | 140.2309
9422 | 96.1246
9423 | 136.5856
9424 | 149.6196
9425 | 73.3978
9426 | 85.7801
9427 | 91.2289
9428 | 117.6691
9429 | 139.5126
9430 | 111.7547
9431 | 131.8478
9432 | 117.2962
9433 | 145.2678
9434 | 132.9736
9435 | 145.2517
9436 | 149.85
9437 | 117.4489
9438 | 138.2632
9439 | 76.1987
9440 | 106.3277
9441 | 137.0514
9442 | 97.4548
9443 | 92.3346
9444 | 155.2929
9445 | 120.215
9446 | 108.9532
9447 | 94.607
9448 | 145.3354
9449 | 139.232
9450 | 84.4716
9451 | 132.6033
9452 | 78.0919
9453 | 138.446
9454 | 130.8854
9455 | 136.9868
9456 | 134.8162
9457 | 116.9232
9458 | 121.3974
9459 | 183.8612
9460 | 136.9397
9461 | 125.1032
9462 | 121.2042
9463 | 82.4498
9464 | 109.7393
9465 | 141.7471
9466 | 168.8117
9467 | 135.7092
9468 | 107.4971
9469 | 176.6933
9470 | 81.5941
9471 | 156.0535
9472 | 127.8501
9473 | 93.0103
9474 | 142.5015
9475 | 115.1835
9476 | 82.1922
9477 | 76.5432
9478 | 93.8333
9479 | 136.696
9480 | 140.3406
9481 | 97.1488
9482 | 106.9707
9483 | 116.0852
9484 | 80.9969
9485 | 108.5666
9486 | 152.7386
9487 | 159.1044
9488 | 140.2309
9489 | 150.8081
9490 | 137.3361
9491 | 126.1365
9492 | 93.6118
9493 | 78.0062
9494 | 124.7907
9495 | 148.6278
9496 | 110.2797
9497 | 134.6456
9498 | 169.7757
9499 | 96.5833
9500 | 131.2445
9501 | 126.9142
9502 | 126.9996
9503 | 69.3981
9504 | 125.4787
9505 | 142.7905
9506 | 119.4052
9507 | 112.1796
9508 | 116.2254
9509 | 112.8446
9510 | 137.3364
9511 | 96.326
9512 | 100.8835
9513 | 145.0348
9514 | 101.0434
9515 | 140.0618
9516 | 142.6279
9517 | 152.8541
9518 | 162.4068
9519 | 131.7053
9520 | 122.8015
9521 | 111.8917
9522 | 149.8639
9523 | 135.7564
9524 | 113.2439
9525 | 122.7459
9526 | 109.9965
9527 | 109.7098
9528 | 102.614
9529 | 96.2065
9530 | 124.834
9531 | 118.9976
9532 | 148.3474
9533 | 152.1974
9534 | 132.7485
9535 | 141.199
9536 | 125.0772
9537 | 115.9762
9538 | 112.0585
9539 | 146.6386
9540 | 114.9722
9541 | 85.4361
9542 | 137.8184
9543 | 89.181
9544 | 136.9506
9545 | 129.3002
9546 | 110.286
9547 | 75.0215
9548 | 119.1797
9549 | 120.9147
9550 | 107.9459
9551 | 178.3199
9552 | 124.6756
9553 | 143.1838
9554 | 149.337
9555 | 138.6761
9556 | 111.4756
9557 | 109.9303
9558 | 143.1232
9559 | 87.1875
9560 | 125.0031
9561 | 113.5357
9562 | 154.5746
9563 | 154.7845
9564 | 103.2106
9565 | 132.2891
9566 | 111.1834
9567 | 139.5728
9568 | 202.8374
9569 | 109.4289
9570 | 92.6296
9571 | 109.0472
9572 | 105.8549
9573 | 158.632
9574 | 89.9538
9575 | 126.168
9576 | 122.8087
9577 | 123.5878
9578 | 63.2412
9579 | 117.2229
9580 | 110.5272
9581 | 136.4622
9582 | 166.6006
9583 | 99.4041
9584 | 105.4577
9585 | 127.2058
9586 | 120.2225
9587 | 127.4181
9588 | 121.5107
9589 | 180.2422
9590 | 91.1333
9591 | 143.2275
9592 | 128.5718
9593 | 139.5996
9594 | 136.7861
9595 | 142.7391
9596 | 140.6965
9597 | 149.2324
9598 | 112.1731
9599 | 149.1941
9600 | 115.9096
9601 | 109.7602
9602 | 136.6523
9603 | 186.3114
9604 | 120.1404
9605 | 161.4365
9606 | 114.0672
9607 | 147.027
9608 | 97.6746
9609 | 136.7949
9610 | 92.0565
9611 | 115.7019
9612 | 135.0464
9613 | 89.0289
9614 | 152.2269
9615 | 134.9339
9616 | 108.7264
9617 | 156.7543
9618 | 111.3409
9619 | 129.8681
9620 | 154.9954
9621 | 112.0304
9622 | 148.6849
9623 | 99.2885
9624 | 91.3818
9625 | 87.0944
9626 | 140.6224
9627 | 119.2591
9628 | 137.4435
9629 | 114.1345
9630 | 114.2914
9631 | 139.9531
9632 | 60.3489
9633 | 152.7601
9634 | 116.7369
9635 | 107.2587
9636 | 121.4001
9637 | 126.5985
9638 | 116.4424
9639 | 117.6691
9640 | 57.5177
9641 | 94.3106
9642 | 105.9395
9643 | 84.4123
9644 | 101.3268
9645 | 141.1668
9646 | 104.4548
9647 | 143.8838
9648 | 141.5101
9649 | 95.4904
9650 | 115.3992
9651 | 181.4554
9652 | 138.0063
9653 | 154.2781
9654 | 99.8423
9655 | 114.7221
9656 | 128.4859
9657 | 110.2792
9658 | 153.1488
9659 | 132.3626
9660 | 129.2109
9661 | 128.2655
9662 | 96.7267
9663 | 131.0475
9664 | 126.7257
9665 | 104.3257
9666 | 145.5363
9667 | 93.945
9668 | 126.5805
9669 | 92.8182
9670 | 86.8302
9671 | 147.1711
9672 | 95.2001
9673 | 61.4584
9674 | 104.5456
9675 | 131.802
9676 | 122.8178
9677 | 101.173
9678 | 148.9124
9679 | 95.4643
9680 | 93.2542
9681 | 113.1673
9682 | 74.9988
9683 | 100.6768
9684 | 163.9403
9685 | 61.8794
9686 | 103.4795
9687 | 122.7635
9688 | 122.1271
9689 | 107.4405
9690 | 121.8777
9691 | 155.9253
9692 | 85.5908
9693 | 164.3362
9694 | 140.9341
9695 | 123.4987
9696 | 149.6004
9697 | 66.8553
9698 | 136.3012
9699 | 107.1575
9700 | 131.8516
9701 | 153.966
9702 | 151.9338
9703 | 100.4251
9704 | 118.1495
9705 | 159.0543
9706 | 113.9558
9707 | 128.8297
9708 | 86.9004
9709 | 131.9075
9710 | 104.3725
9711 | 150.8623
9712 | 74.5713
9713 | 171.9519
9714 | 156.7632
9715 | 97.4776
9716 | 118.049
9717 | 137.9845
9718 | 78.6694
9719 | 144.5524
9720 | 115.9626
9721 | 104.1642
9722 | 105.0792
9723 | 119.4282
9724 | 156.3911
9725 | 150.1307
9726 | 127.4454
9727 | 132.5964
9728 | 108.5978
9729 | 98.4554
9730 | 122.9801
9731 | 99.739
9732 | 127.5894
9733 | 84.4195
9734 | 141.6938
9735 | 103.2118
9736 | 125.1338
9737 | 108.0062
9738 | 126.6872
9739 | 95.5676
9740 | 131.7316
9741 | 73.158
9742 | 108.8841
9743 | 122.6245
9744 | 105.051
9745 | 118.543
9746 | 104.8188
9747 | 125.5489
9748 | 140.6535
9749 | 153.6649
9750 | 114.3506
9751 | 112.6304
9752 | 109.1534
9753 | 138.2327
9754 | 116.591
9755 | 126.8857
9756 | 142.129
9757 | 101.3224
9758 | 136.4209
9759 | 122.7052
9760 | 111.1724
9761 | 128.6751
9762 | 122.9686
9763 | 120.8714
9764 | 125.9157
9765 | 134.6308
9766 | 66.5262
9767 | 91.9988
9768 | 120.181
9769 | 119.3535
9770 | 88.2002
9771 | 127.8257
9772 | 94.9088
9773 | 93.3318
9774 | 112.2199
9775 | 152.5108
9776 | 142.756
9777 | 90.2629
9778 | 161.1907
9779 | 64.2208
9780 | 120.2181
9781 | 58.7949
9782 | 164.5532
9783 | 78.8835
9784 | 128.9407
9785 | 113.0566
9786 | 140.5975
9787 | 116.6122
9788 | 111.0804
9789 | 129.5729
9790 | 80.7808
9791 | 108.0116
9792 | 174.4246
9793 | 92.9723
9794 | 124.4208
9795 | 128.2076
9796 | 127.041
9797 | 126.5131
9798 | 149.6027
9799 | 150.8504
9800 | 123.412
9801 | 112.7436
9802 | 114.1454
9803 | 160.316
9804 | 130.6204
9805 | 145.5563
9806 | 110.322
9807 | 103.7232
9808 | 76.3544
9809 | 78.7822
9810 | 98.334
9811 | 80.5744
9812 | 99.2693
9813 | 145.8442
9814 | 140.8386
9815 | 118.7681
9816 | 101.3398
9817 | 117.9149
9818 | 123.927
9819 | 128.6439
9820 | 112.0453
9821 | 98.9624
9822 | 127.7944
9823 | 107.4203
9824 | 85.7123
9825 | 133.4587
9826 | 146.6566
9827 | 83.2048
9828 | 108.4929
9829 | 102.4946
9830 | 154.2131
9831 | 135.5995
9832 | 163.8716
9833 | 111.627
9834 | 111.9261
9835 | 125.2868
9836 | 119.913
9837 | 77.3941
9838 | 86.9317
9839 | 93.7395
9840 | 102.3689
9841 | 149.0032
9842 | 134.136
9843 | 122.363
9844 | 125.4881
9845 | 94.3825
9846 | 129.5762
9847 | 133.3887
9848 | 149.2736
9849 | 181.1911
9850 | 165.4827
9851 | 106.9312
9852 | 132.0119
9853 | 80.5833
9854 | 146.026
9855 | 84.1023
9856 | 135.1355
9857 | 77.6814
9858 | 169.6192
9859 | 98.2855
9860 | 136.4396
9861 | 143.9992
9862 | 107.0759
9863 | 129.2074
9864 | 112.407
9865 | 137.1128
9866 | 116.1327
9867 | 128.3502
9868 | 113.3554
9869 | 121.1108
9870 | 84.1453
9871 | 86.7842
9872 | 116.9241
9873 | 100.514
9874 | 101.9948
9875 | 120.331
9876 | 113.0164
9877 | 146.9742
9878 | 129.47
9879 | 96.3024
9880 | 100.1288
9881 | 52.1628
9882 | 108.4099
9883 | 123.7192
9884 | 139.5034
9885 | 96.075
9886 | 132.3695
9887 | 118.2948
9888 | 110.6372
9889 | 128.1064
9890 | 79.355
9891 | 157.0196
9892 | 152.603
9893 | 122.151
9894 | 89.5488
9895 | 134.5564
9896 | 155.439
9897 | 163.9023
9898 | 100.2183
9899 | 84.1441
9900 | 116.1159
9901 | 129.7047
9902 | 122.3444
9903 | 119.0832
9904 | 103.1848
9905 | 68.9257
9906 | 81.9208
9907 | 132.1241
9908 | 121.4607
9909 | 136.7789
9910 | 126.0684
9911 | 96.2495
9912 | 126.3747
9913 | 124.9429
9914 | 79.4294
9915 | 83.4487
9916 | 155.6143
9917 | 78.8579
9918 | 129.1073
9919 | 134.5914
9920 | 150.571
9921 | 101.8358
9922 | 132.7282
9923 | 100.5228
9924 | 111.6398
9925 | 140.4514
9926 | 115.7067
9927 | 114.389
9928 | 108.5793
9929 | 151.0513
9930 | 108.8051
9931 | 103.9397
9932 | 142.0395
9933 | 125.573
9934 | 144.1963
9935 | 163.7087
9936 | 96.6793
9937 | 109.5794
9938 | 110.5611
9939 | 142.5156
9940 | 95.8981
9941 | 117.3555
9942 | 100.2435
9943 | 149.372
9944 | 142.2915
9945 | 115.263
9946 | 118.1465
9947 | 121.1812
9948 | 120.24
9949 | 130.9989
9950 | 122.5833
9951 | 132.3975
9952 | 138.586
9953 | 97.9731
9954 | 95.2022
9955 | 136.339
9956 | 112.0189
9957 | 108.8608
9958 | 129.4962
9959 | 108.847
9960 | 137.8727
9961 | 163.856
9962 | 113.3931
9963 | 108.0743
9964 | 93.4118
9965 | 108.4587
9966 | 126.4227
9967 | 129.6048
9968 | 120.4936
9969 | 96.4314
9970 | 134.3564
9971 | 136.1703
9972 | 103.2922
9973 | 136.9107
9974 | 131.4301
9975 | 141.5745
9976 | 124.04
9977 | 133.204
9978 | 143.4158
9979 | 123.5062
9980 | 133.4755
9981 | 111.7415
9982 | 141.8526
9983 | 143.7796
9984 | 155.9632
9985 | 113.1455
9986 | 106.337
9987 | 110.6267
9988 | 94.533
9989 | 95.8104
9990 | 93.6692
9991 | 131.483
9992 | 69.6048
9993 | 138.0924
9994 | 126.8801
9995 | 131.0446
9996 | 137.7899
9997 | 134.1634
9998 | 105.9525
9999 | 89.018
10000 | 121.2621
Note on O2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on P2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on Q3: You can choose different probabilities by entering a value between 1% and 99%.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## SPERT® Normal - Agile Forecast
Statistical PERT® (SPERT®) Normal Edition | This is an experimental worksheet for agile team forecasting |  |  |  |  | Scenario 1 | Scenario 2 | Scenario 3
| Scenario 1 | Scenario 2 | Scenario 3 |  | 1 | 16 | 16 | 16 | ← Columns Q through T are hidden; they are used to create scenario calculations and probabilities
The starting date for our next release is | 2019-04-01 |  |  |  | 2 | 16 | 16 | 16
We'll use | 2 |  |  | week sprints | 3 | 16 | 16 | 16
We'll most likely complete about | 18 |  |  | story points (or user stories or features) per sprint | 4 | 16 | 16 | 16
We have | Medium confidence |  |  | that the most likely outcome will regularly occur | 5 | 16 | 16 | 16
In a worst-case scenario, we would complete only | 10 |  |  | story points (or user stories or features) | 6 | 16 | 16 | 16
In a best-case scenario, we might possibly complete | 30 |  |  | story points (or user stories or features) | 7 | 16 | 16 | 16
Our Product Backlog or next release represents about | 200 |  |  | story points of effort (or user stories or features) | 8 | 16 | 16 | 16
We desire | 0.5 | 0.66 | 0.75 | confidence in each sprint iteration | 9 | 16 | 16 | 16
Be sure this indicator is green or yellow → | 0.66667 | 0.66667 | 0.66667 | if red, check your inputs and ensure this is a bell-shaped uncertainty | 10 | 16 | 16 | 16
So, on average, we expect each sprint will finish | 18.6667 | 18.6667 | 18.6667 | story points (or user stories or features) per sprint | 11 | 16 | 16 | 16
For this uncertainty, the SPERT standard deviation is | 4 | 4 | 4 | that is: (MAX - MIN) * SPERT RSM | 12 |  | 16 | 16
Given this, we forecast that we'll complete at least | 18.6667 | 17.0168 | 15.9687 | story points (or user stories or features) each sprint (for the confidence level expressed in cell C6) | 13 |  |  | 16
We'll need | 10.7143 | 11.7531 | 12.5245 | sprints to do all the work of the Product Backlog or the next release | 14
So, we'll need about | 22 | 24 | 26 | business weeks | 15
During this time, there is/are |  |  |  | extra days (working or non-working) | 16
In total, the number of days needed are | 154 | 168 | 182 | which includes both working + non-working days | 17
So, we will complete the Product Backlog or next release on | 2019-09-02 | 2019-09-16 | 2019-09-30 | or earlier, with | 18
| 0.65616 | 0.95837 | 0.99845 | confidence in our forecast (under all these assumptions) | 19
20
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP |  |  |  |  | 21
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com |  |  |  |  | 22
Watch a Pluralsight course on Statistical PERT® Normal Edition |  |  |  |  | 23
Watch Statistical PERT videos on YouTube |  |  |  |  | 24
Connect with or follow William W. Davis on LinkedIn |  |  |  |  | 25
Follow Statistical PERT on Twitter to learn when new updates are released |  |  |  |  | 26
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the |  |  |  |  | 27
GNU General Public License as published by the Free Software Foundation, either version 3 of the License, |  |  |  |  | 28
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify |  |  |  |  | 29
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet. |  |  |  |  | 30
On both verbatim and modified copies of this file, you must always retain the original copyright notice, |  |  |  |  | 31
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License. |  |  |  |  | 32
33
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY; |  |  |  |  | 34
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE. |  |  |  |  | 35
See the GNU General Public License for more details (https://www.gnu.org/licenses/). |  |  |  |  | 36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
[6 empty] | 13.2665 | 13.8564 | 14.4222

## SPERT® Normal - Agile Forecast2
Statistical PERT® (SPERT®) Normal Edition | This is a special worksheet for agile team forecasting |  |  |  |  | Scenario 1 | Scenario 2 | Scenario 3
| Scenario 1 | Scenario 2 | Scenario 3 |  | 1 | 16 | 16 | 16 | ← Columns Q through T are hidden; they are used to create scenario calculations and probabilities
The starting date for our next release is | 2020-06-01 |  |  |  | 2 | 16 | 16 | 16
We'll use | 2 |  |  | week sprints | 3 | 16 | 16 | 16
We'll most likely complete about | 18 |  |  | story points (or user stories or features) per sprint | 4 | 16 | 16 | 16
We have | Medium confidence |  |  | that the most likely outcome will regularly occur | 5 | 16 | 16 | 16
In a worst-case scenario, we would complete only | 10 |  |  | story points (or user stories or features) | 6 | 16 | 16 | 16
In a best-case scenario, we might possibly complete | 30 |  |  | story points (or user stories or features) | 7 | 16 | 16 | 16
Our Product Backlog or next release represents about | 200 |  |  | story points of effort (or user stories or features) | 8 | 16 | 16 | 16
We desire | 0.5 | 0.66 | 0.75 | confidence in each sprint iteration | 9 | 16 | 16 | 16
Be sure this indicator is green or yellow → | 0.66667 | 0.66667 | 0.66667 | if red, check your inputs and ensure this is a bell-shaped uncertainty | 10 | 16 | 16 | 16
So, on average, we expect each sprint will finish | 18.6667 | 18.6667 | 18.6667 | story points (or user stories or features) per sprint | 11 | 16 | 16 | 16
For this uncertainty, the SPERT standard deviation is | 4 | 4 | 4 | that is: (MAX - MIN) * SPERT RSM | 12 |  | 16 | 16
Optional: Use your own standard deviation |  |  |  | You can override SPERT's standard deviation using an explicit standard deviation derived from historical data
Given this, we forecast that we'll complete at least | 18.6667 | 17.0168 | 15.9687 | story points (or user stories or features) each sprint (for the confidence level expressed in cell C6) | 13 |  |  | 16
We'll need | 10.7143 | 11.7531 | 12.5245 | sprints to do all the work of the Product Backlog or the next release | 14
So, we'll need about | 22 | 24 | 26 | business weeks | 15
During this time, there is/are |  |  |  | extra days (working or non-working) | 16
In total, the number of days needed are | 154 | 168 | 182 | which includes both working + non-working days | 17
So, we will complete the Product Backlog or next release on | 2020-11-02 | 2020-11-16 | 2020-11-30 | or earlier, with | 18
| 0.65616 | 0.95837 | 0.99845 | confidence in our forecast (under all these assumptions) | 19
20
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP |  |  |  |  | 21
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com |  |  |  |  | 22
Watch a Pluralsight course on Statistical PERT® Normal Edition |  |  |  |  | 23
Watch Statistical PERT videos on YouTube |  |  |  |  | 24
Connect with or follow William W. Davis on LinkedIn |  |  |  |  | 25
Follow Statistical PERT on Twitter to learn when new updates are released |  |  |  |  | 26
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the |  |  |  |  | 27
GNU General Public License as published by the Free Software Foundation, either version 3 of the License, |  |  |  |  | 28
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify |  |  |  |  | 29
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet. |  |  |  |  | 30
On both verbatim and modified copies of this file, you must always retain the original copyright notice, |  |  |  |  | 31
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License. |  |  |  |  | 32
33
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY; |  |  |  |  | 34
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE. |  |  |  |  | 35
See the GNU General Public License for more details (https://www.gnu.org/licenses/). |  |  |  |  | 36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
[6 empty] | 13.2665 | 13.8564 | 14.4222

## VLookups
SPERT Most Likely Subjective Terms | RSM | Min | Most Likely | Max
Near certainty | 0.070711 | 1 | 98 | 1 |  | Dropdown values for the Most Likely Confidence selection
High confidence | 0.11381 | 3 | 94 | 3 |  | Ratio Scale Multiplier used in the SPERT Standard Deviation formula
Medium-high confidence | 0.1569 | 5 | 90 | 5 |  | Number of trials out of 100, used to create the Most Likely Confidence pie chart
Medium confidence | 0.2 | 8 | 84 | 8
Medium-low confidence | 0.26873 | 14 | 72 | 14 | Note: Changing the SPERT Most Likely Subjective Terms may cause the data validation
Low confidence | 0.33747 | 23 | 54 | 23 | to break (for the Most Likely Confidence column) due to an Excel bug. If that occurs, just
Guesstimate | 0.4062 | 33 | 34 | 33 | re-edit the data validation by re-selecting these list items.
These are the Minimum heuristic percentages used in the 'SPERT Normal (1-Point entry)' and 'SPERT Normal (Mixed entry)' worksheets to create a minimum value for a 3-point estimate. You can add to, remove, or change this list. | -0.05
-0.1
-0.15
-0.2
-0.25
-0.3
-0.35
-0.4
-0.5
-0.6
-0.7
These are the Maximum heuristic percentages used in the 'SPERT Normal (1-Point entry)' and 'SPERT Normal (Mixed entry)' worksheets to create a maximum value for a 3-point estimate. You can add to, remove, or change this list. | 0.1
0.2
0.3
0.4
0.5
0.75
1
1.25
1.5
1.75
2
Choose which side of the normal curve to display
Show Left-Side Area | FALSE | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
Show Right-Side Area | TRUE | Show the likelihood that an uncertainty will EXCEED the SPERT estimates below
Choose whether to show currency formatting
Show currency formatting | TRUE
Do not show currency formatting | FALSE
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Ratio Scale Modeler
| HIGHER Confidence |  |  |  | MEDIUM Confidence |  |  |  | LOWER Confidence
|  | Standard Devation: | 8.4853 |  |  | Standard Devation: | 24 |  |  | Standard Devation: | 48.7442
|  | Ratio Scale Modifier: | 0.070711 |  |  | Ratio Scale Modifier: | 0.2 |  |  | Ratio Scale Modifier: | 0.4062
|  | Mean: | 120 |  |  | Mean: | 120 |  |  | Mean: | 120
| Minimum | Most Likely | Maximum |  | Minimum | Most Likely | Maximum |  | Minimum | Most Likely | Maximum
PERT Estimate: | 60 | 120 | 180 | PERT Estimate: | 60 | 120 | 180 | PERT Estimate: | 60 | 120 | 180
Distribution: | 1 | 98 | 1 | Distribution: | 8 | 84 | 8 | Distribution: | 33 | 34 | 33
1 | 60 | 120 | 180 | 1 | 60 | 120 | 180 | 1 | 60 | 120 | 180
2 |  | 120 |  | 2 | 60 | 120 | 180 | 2 | 60 | 120 | 180
3 |  | 120 |  | 3 | 60 | 120 | 180 | 3 | 60 | 120 | 180
4 |  | 120 |  | 4 | 60 | 120 | 180 | 4 | 60 | 120 | 180
5 |  | 120 |  | 5 | 60 | 120 | 180 | 5 | 60 | 120 | 180
6 |  | 120 |  | 6 | 60 | 120 | 180 | 6 | 60 | 120 | 180
7 |  | 120 |  | 7 | 60 | 120 | 180 | 7 | 60 | 120 | 180
8 |  | 120 |  | 8 | 60 | 120 | 180 | 8 | 60 | 120 | 180
9 |  | 120 |  | 9 |  | 120 |  | 9 | 60 | 120 | 180
10 |  | 120 |  | 10 |  | 120 |  | 10 | 60 | 120 | 180
11 |  | 120 |  | 11 |  | 120 |  | 11 | 60 | 120 | 180
12 |  | 120 |  | 12 |  | 120 |  | 12 | 60 | 120 | 180
13 |  | 120 |  | 13 |  | 120 |  | 13 | 60 | 120 | 180
14 |  | 120 |  | 14 |  | 120 |  | 14 | 60 | 120 | 180
15 |  | 120 |  | 15 |  | 120 |  | 15 | 60 | 120 | 180
16 |  | 120 |  | 16 |  | 120 |  | 16 | 60 | 120 | 180
17 |  | 120 |  | 17 |  | 120 |  | 17 | 60 | 120 | 180
18 |  | 120 |  | 18 |  | 120 |  | 18 | 60 | 120 | 180
19 |  | 120 |  | 19 |  | 120 |  | 19 | 60 | 120 | 180
20 |  | 120 |  | 20 |  | 120 |  | 20 | 60 | 120 | 180
21 |  | 120 |  | 21 |  | 120 |  | 21 | 60 | 120 | 180
22 |  | 120 |  | 22 |  | 120 |  | 22 | 60 | 120 | 180
23 |  | 120 |  | 23 |  | 120 |  | 23 | 60 | 120 | 180
24 |  | 120 |  | 24 |  | 120 |  | 24 | 60 | 120 | 180
25 |  | 120 |  | 25 |  | 120 |  | 25 | 60 | 120 | 180
26 |  | 120 |  | 26 |  | 120 |  | 26 | 60 | 120 | 180
27 |  | 120 |  | 27 |  | 120 |  | 27 | 60 | 120 | 180
28 |  | 120 |  | 28 |  | 120 |  | 28 | 60 | 120 | 180
29 |  | 120 |  | 29 |  | 120 |  | 29 | 60 | 120 | 180
30 |  | 120 |  | 30 |  | 120 |  | 30 | 60 | 120 | 180
31 |  | 120 |  | 31 |  | 120 |  | 31 | 60 | 120 | 180
32 |  | 120 |  | 32 |  | 120 |  | 32 | 60 | 120 | 180
33 |  | 120 |  | 33 |  | 120 |  | 33 | 60 | 120 | 180
34 |  | 120 |  | 34 |  | 120 |  | 34 |  | 120
35 |  | 120 |  | 35 |  | 120 |  | 35
36 |  | 120 |  | 36 |  | 120 |  | 36
37 |  | 120 |  | 37 |  | 120 |  | 37
38 |  | 120 |  | 38 |  | 120 |  | 38
39 |  | 120 |  | 39 |  | 120 |  | 39
40 |  | 120 |  | 40 |  | 120 |  | 40
41 |  | 120 |  | 41 |  | 120 |  | 41
42 |  | 120 |  | 42 |  | 120 |  | 42
43 |  | 120 |  | 43 |  | 120 |  | 43
44 |  | 120 |  | 44 |  | 120 |  | 44
45 |  | 120 |  | 45 |  | 120 |  | 45
46 |  | 120 |  | 46 |  | 120 |  | 46
47 |  | 120 |  | 47 |  | 120 |  | 47
48 |  | 120 |  | 48 |  | 120 |  | 48
49 |  | 120 |  | 49 |  | 120 |  | 49
50 |  | 120 |  | 50 |  | 120 |  | 50
51 |  | 120 |  | 51 |  | 120 |  | 51
52 |  | 120 |  | 52 |  | 120 |  | 52
53 |  | 120 |  | 53 |  | 120 |  | 53
54 |  | 120 |  | 54 |  | 120 |  | 54
55 |  | 120 |  | 55 |  | 120 |  | 55
56 |  | 120 |  | 56 |  | 120 |  | 56
57 |  | 120 |  | 57 |  | 120 |  | 57
58 |  | 120 |  | 58 |  | 120 |  | 58
59 |  | 120 |  | 59 |  | 120 |  | 59
60 |  | 120 |  | 60 |  | 120 |  | 60
61 |  | 120 |  | 61 |  | 120 |  | 61
62 |  | 120 |  | 62 |  | 120 |  | 62
63 |  | 120 |  | 63 |  | 120 |  | 63
64 |  | 120 |  | 64 |  | 120 |  | 64
65 |  | 120 |  | 65 |  | 120 |  | 65
66 |  | 120 |  | 66 |  | 120 |  | 66
67 |  | 120 |  | 67 |  | 120 |  | 67
68 |  | 120 |  | 68 |  | 120 |  | 68
69 |  | 120 |  | 69 |  | 120 |  | 69
70 |  | 120 |  | 70 |  | 120 |  | 70
71 |  | 120 |  | 71 |  | 120 |  | 71
72 |  | 120 |  | 72 |  | 120 |  | 72
73 |  | 120 |  | 73 |  | 120 |  | 73
74 |  | 120 |  | 74 |  | 120 |  | 74
75 |  | 120 |  | 75 |  | 120 |  | 75
76 |  | 120 |  | 76 |  | 120 |  | 76
77 |  | 120 |  | 77 |  | 120 |  | 77
78 |  | 120 |  | 78 |  | 120 |  | 78
79 |  | 120 |  | 79 |  | 120 |  | 79
80 |  | 120 |  | 80 |  | 120 |  | 80
81 |  | 120 |  | 81 |  | 120 |  | 81
82 |  | 120 |  | 82 |  | 120 |  | 82
83 |  | 120 |  | 83 |  | 120 |  | 83
84 |  | 120 |  | 84 |  | 120 |  | 84
85 |  | 120 |  | 85 |  |  |  | 85
86 |  | 120 |  | 86 |  |  |  | 86
87 |  | 120 |  | 87 |  |  |  | 87
88 |  | 120 |  | 88 |  |  |  | 88
89 |  | 120 |  | 89 |  |  |  | 89
90 |  | 120 |  | 90 |  |  |  | 90
91 |  | 120 |  | 91 |  |  |  | 91
92 |  | 120 |  | 92 |  |  |  | 92
93 |  | 120 |  | 93 |  |  |  | 93
94 |  | 120 |  | 94 |  |  |  | 94
95 |  | 120 |  | 95 |  |  |  | 95
96 |  | 120 |  | 96 |  |  |  | 96
97 |  | 120 |  | 97 |  |  |  | 97
98 |  | 120 |  | 98 |  |  |  | 98
99 |  |  |  | 99 |  |  |  | 99
100 |  |  |  | 100 |  |  |  | 100
Version 4a – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Collabinart®
Collabinart® Experience Collaboration through Interpretive Art™
At the 2018 PMI Global Conference,
attendees experienced Collabinart®.
Collabinart is a freely-licensed
team-building and training
framework to build collaboration
skills using masterpiece artworks.
Use Collabinart at any point in a
team's journey together. Develop
team camaraderie, active listening
skills, and collaboration skills.
It's fun, free, and effective.
Visit the Collabinart website
to learn more.
The Young Shepherdess (1865)
William-Adolphe Bouguereau
San Diego Museum of Art

## Change Log
Date | Version | Description
2019-12-07 | 4a | Add the "Your SD" standard deviation option to override the SPERT SD (standard deviation)
2019-07-12 | 3.0.3 | Format and painting title on Collabinart tab.
2019-07-09 | 3.0.2 | Format GNU GPL page, replace ™ with ® on Collabinart tab, minor formatting on Agile Forecast tab and GNU footer links (all tabs) to https
2019-06-30 | 3.0.1 | Added full GNU GPL license, updated footer language.
2019-03-10 | 3.0 | Added: Sparklines, tri-colored combo charts, Practice Forecasting and Super Simple SPERT tabs, 3-scenario agile forecasting
2018-11-17 | 2.4 | Changed the % calculation for the whole release in the "Agile Forecast" tab
2018-09-22 | 2.3 | Added a new tab "Agile Forecast" for agile team estimation/forecasting
2017-03-01 | 2.2 | Added new tab 'for Beginners' to make it easy and non-threatening to use Statistical PERT for smart people who don't love statistics :-)
2017-02-03 | 2.1 | Added new tab 'Mixed Mode' allowing manual 3-point entry and/or global or line-level heuristics
2017-01-12 | 2.0.2 | Removed the dash to read, "Statistical PERT® Normal Edition" and "SPERT® Normal Edition"
2017-01-03 | 2.0.1 | Changed '(1-point entry)' & '(3-point entry)' tabs so cells L104 and L106 only show probabilities when a planning estimate is entered
2017-01-01 | 2.0 | Added: '(1-Point entry)' tab to create 3-pt estimates with heuristics, show left/right side probabilities, enhanced formatting.
2016-10-06 | 1.4.1 | Added HTTPS to links. Renamed "SPERT Graphs…" to "SPERT Charts…"
2016-10-03 | 1.4 | Added a pie chart to 'SPERT Graphs…' worksheet and removed "Unskewed" probabilities which used the mode instead of mean
2016-09-21 | 1.3a | Changed links to HTTPS, added a SPERT logo to the Welcome tab, and changed pie chart so upperbound is red, lowerbound is green
2016-09-10 | 1.3 | Added a confidence interval probability and pie chart for all estimated tasks
2016-07-09 | 1.2 | Added traffic light indicators to check for a valid 3-point estimate and implied bell-shape of the task
2016-07-03 | 1.1 | Added new worksheet, SPERT Bell-Curve for Task Duration to show the implied, normal bell-shaped curve
2015-10-09 | 1.02 | Formatting changes for the PMI article on ProjectManagement.com; updated formulas in cols O - T.
2015-09-17 | 1.01 | Changed formulas in cells M4:M15, N4:N15 so the Most Likely value in column C is > 0 (not > 4)
2015-07-31 | 1.00 | Initial release

## GNU GPL
GNU GENERAL PUBLIC LICENSE
Version 3, 29 June 2007
Copyright (C) 2007 Free Software Foundation, Inc. <https://fsf.org/>
Everyone is permitted to copy and distribute verbatim copies
of this license document, but changing it is not allowed.
Preamble
The GNU General Public License is a free, copyleft license for
software and other kinds of works.
The licenses for most software and other practical works are designed
to take away your freedom to share and change the works. By contrast,
the GNU General Public License is intended to guarantee your freedom to
share and change all versions of a program--to make sure it remains free
software for all its users. We, the Free Software Foundation, use the
GNU General Public License for most of our software; it applies also to
any other work released this way by its authors. You can apply it to
your programs, too.
When we speak of free software, we are referring to freedom, not
price. Our General Public Licenses are designed to make sure that you
have the freedom to distribute copies of free software (and charge for
them if you wish), that you receive source code or can get it if you
want it, that you can change the software or use pieces of it in new
free programs, and that you know you can do these things.
To protect your rights, we need to prevent others from denying you
these rights or asking you to surrender the rights. Therefore, you have
certain responsibilities if you distribute copies of the software, or if
you modify it: responsibilities to respect the freedom of others.
For example, if you distribute copies of such a program, whether
gratis or for a fee, you must pass on to the recipients the same
freedoms that you received. You must make sure that they, too, receive
or can get the source code. And you must show them these terms so they
know their rights.
Developers that use the GNU GPL protect your rights with two steps:
(1) assert copyright on the software, and (2) offer you this License
giving you legal permission to copy, distribute and/or modify it.
For the developers' and authors' protection, the GPL clearly explains
that there is no warranty for this free software. For both users' and
authors' sake, the GPL requires that modified versions be marked as
changed, so that their problems will not be attributed erroneously to
authors of previous versions.
Some devices are designed to deny users access to install or run
modified versions of the software inside them, although the manufacturer
can do so. This is fundamentally incompatible with the aim of
protecting users' freedom to change the software. The systematic
pattern of such abuse occurs in the area of products for individuals to
use, which is precisely where it is most unacceptable. Therefore, we
have designed this version of the GPL to prohibit the practice for those
products. If such problems arise substantially in other domains, we
stand ready to extend this provision to those domains in future versions
of the GPL, as needed to protect the freedom of users.
Finally, every program is threatened constantly by software patents.
States should not allow patents to restrict development and use of
software on general-purpose computers, but in those that do, we wish to
avoid the special danger that patents applied to a free program could
make it effectively proprietary. To prevent this, the GPL assures that
patents cannot be used to render the program non-free.
The precise terms and conditions for copying, distribution and
modification follow.
TERMS AND CONDITIONS
0. Definitions.
"This License" refers to version 3 of the GNU General Public License.
"Copyright" also means copyright-like laws that apply to other kinds of
works, such as semiconductor masks.
"The Program" refers to any copyrightable work licensed under this
License. Each licensee is addressed as "you". "Licensees" and
"recipients" may be individuals or organizations.
To "modify" a work means to copy from or adapt all or part of the work
in a fashion requiring copyright permission, other than the making of an
exact copy. The resulting work is called a "modified version" of the
earlier work or a work "based on" the earlier work.
A "covered work" means either the unmodified Program or a work based
on the Program.
To "propagate" a work means to do anything with it that, without
permission, would make you directly or secondarily liable for
infringement under applicable copyright law, except executing it on a
computer or modifying a private copy. Propagation includes copying,
distribution (with or without modification), making available to the
public, and in some countries other activities as well.
To "convey" a work means any kind of propagation that enables other
parties to make or receive copies. Mere interaction with a user through
a computer network, with no transfer of a copy, is not conveying.
An interactive user interface displays "Appropriate Legal Notices"
to the extent that it includes a convenient and prominently visible
feature that (1) displays an appropriate copyright notice, and (2)
tells the user that there is no warranty for the work (except to the
extent that warranties are provided), that licensees may convey the
work under this License, and how to view a copy of this License. If
the interface presents a list of user commands or options, such as a
menu, a prominent item in the list meets this criterion.
1. Source Code.
The "source code" for a work means the preferred form of the work
for making modifications to it. "Object code" means any non-source
form of a work.
A "Standard Interface" means an interface that either is an official
standard defined by a recognized standards body, or, in the case of
interfaces specified for a particular programming language, one that
is widely used among developers working in that language.
The "System Libraries" of an executable work include anything, other
than the work as a whole, that (a) is included in the normal form of
packaging a Major Component, but which is not part of that Major
Component, and (b) serves only to enable use of the work with that
Major Component, or to implement a Standard Interface for which an
implementation is available to the public in source code form. A
"Major Component", in this context, means a major essential component
(kernel, window system, and so on) of the specific operating system
(if any) on which the executable work runs, or a compiler used to
produce the work, or an object code interpreter used to run it.
The "Corresponding Source" for a work in object code form means all
the source code needed to generate, install, and (for an executable
work) run the object code and to modify the work, including scripts to
control those activities. However, it does not include the work's
System Libraries, or general-purpose tools or generally available free
programs which are used unmodified in performing those activities but
which are not part of the work. For example, Corresponding Source
includes interface definition files associated with source files for
the work, and the source code for shared libraries and dynamically
linked subprograms that the work is specifically designed to require,
such as by intimate data communication or control flow between those
subprograms and other parts of the work.
The Corresponding Source need not include anything that users
can regenerate automatically from other parts of the Corresponding
Source.
The Corresponding Source for a work in source code form is that
same work.
2. Basic Permissions.
All rights granted under this License are granted for the term of
copyright on the Program, and are irrevocable provided the stated
conditions are met. This License explicitly affirms your unlimited
permission to run the unmodified Program. The output from running a
covered work is covered by this License only if the output, given its
content, constitutes a covered work. This License acknowledges your
rights of fair use or other equivalent, as provided by copyright law.
You may make, run and propagate covered works that you do not
convey, without conditions so long as your license otherwise remains
in force. You may convey covered works to others for the sole purpose
of having them make modifications exclusively for you, or provide you
with facilities for running those works, provided that you comply with
the terms of this License in conveying all material for which you do
not control copyright. Those thus making or running the covered works
for you must do so exclusively on your behalf, under your direction
and control, on terms that prohibit them from making any copies of
your copyrighted material outside their relationship with you.
Conveying under any other circumstances is permitted solely under
the conditions stated below. Sublicensing is not allowed; section 10
makes it unnecessary.
3. Protecting Users' Legal Rights From Anti-Circumvention Law.
No covered work shall be deemed part of an effective technological
measure under any applicable law fulfilling obligations under article
11 of the WIPO copyright treaty adopted on 20 December 1996, or
similar laws prohibiting or restricting circumvention of such
measures.
When you convey a covered work, you waive any legal power to forbid
circumvention of technological measures to the extent such circumvention
is effected by exercising rights under this License with respect to
the covered work, and you disclaim any intention to limit operation or
modification of the work as a means of enforcing, against the work's
users, your or third parties' legal rights to forbid circumvention of
technological measures.
4. Conveying Verbatim Copies.
You may convey verbatim copies of the Program's source code as you
receive it, in any medium, provided that you conspicuously and
appropriately publish on each copy an appropriate copyright notice;
keep intact all notices stating that this License and any
non-permissive terms added in accord with section 7 apply to the code;
keep intact all notices of the absence of any warranty; and give all
recipients a copy of this License along with the Program.
You may charge any price or no price for each copy that you convey,
and you may offer support or warranty protection for a fee.
5. Conveying Modified Source Versions.
You may convey a work based on the Program, or the modifications to
produce it from the Program, in the form of source code under the
terms of section 4, provided that you also meet all of these conditions:
a) The work must carry prominent notices stating that you modified
it, and giving a relevant date.
b) The work must carry prominent notices stating that it is
released under this License and any conditions added under section
7. This requirement modifies the requirement in section 4 to
"keep intact all notices".
c) You must license the entire work, as a whole, under this
License to anyone who comes into possession of a copy. This
License will therefore apply, along with any applicable section 7
additional terms, to the whole of the work, and all its parts,
regardless of how they are packaged. This License gives no
permission to license the work in any other way, but it does not
invalidate such permission if you have separately received it.
d) If the work has interactive user interfaces, each must display
Appropriate Legal Notices; however, if the Program has interactive
interfaces that do not display Appropriate Legal Notices, your
work need not make them do so.
A compilation of a covered work with other separate and independent
works, which are not by their nature extensions of the covered work,
and which are not combined with it such as to form a larger program,
in or on a volume of a storage or distribution medium, is called an
"aggregate" if the compilation and its resulting copyright are not
used to limit the access or legal rights of the compilation's users
beyond what the individual works permit. Inclusion of a covered work
in an aggregate does not cause this License to apply to the other
parts of the aggregate.
6. Conveying Non-Source Forms.
You may convey a covered work in object code form under the terms
of sections 4 and 5, provided that you also convey the
machine-readable Corresponding Source under the terms of this License,
in one of these ways:
a) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by the
Corresponding Source fixed on a durable physical medium
customarily used for software interchange.
b) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by a
written offer, valid for at least three years and valid for as
long as you offer spare parts or customer support for that product
model, to give anyone who possesses the object code either (1) a
copy of the Corresponding Source for all the software in the
product that is covered by this License, on a durable physical
medium customarily used for software interchange, for a price no
more than your reasonable cost of physically performing this
conveying of source, or (2) access to copy the
Corresponding Source from a network server at no charge.
c) Convey individual copies of the object code with a copy of the
written offer to provide the Corresponding Source. This
alternative is allowed only occasionally and noncommercially, and
only if you received the object code with such an offer, in accord
with subsection 6b.
d) Convey the object code by offering access from a designated
place (gratis or for a charge), and offer equivalent access to the
Corresponding Source in the same way through the same place at no
further charge. You need not require recipients to copy the
Corresponding Source along with the object code. If the place to
copy the object code is a network server, the Corresponding Source
may be on a different server (operated by you or a third party)
that supports equivalent copying facilities, provided you maintain
clear directions next to the object code saying where to find the
Corresponding Source. Regardless of what server hosts the
Corresponding Source, you remain obligated to ensure that it is
available for as long as needed to satisfy these requirements.
e) Convey the object code using peer-to-peer transmission, provided
you inform other peers where the object code and Corresponding
Source of the work are being offered to the general public at no
charge under subsection 6d.
A separable portion of the object code, whose source code is excluded
from the Corresponding Source as a System Library, need not be
included in conveying the object code work.
A "User Product" is either (1) a "consumer product", which means any
tangible personal property which is normally used for personal, family,
or household purposes, or (2) anything designed or sold for incorporation
into a dwelling. In determining whether a product is a consumer product,
doubtful cases shall be resolved in favor of coverage. For a particular
product received by a particular user, "normally used" refers to a
typical or common use of that class of product, regardless of the status
of the particular user or of the way in which the particular user
actually uses, or expects or is expected to use, the product. A product
is a consumer product regardless of whether the product has substantial
commercial, industrial or non-consumer uses, unless such uses represent
the only significant mode of use of the product.
"Installation Information" for a User Product means any methods,
procedures, authorization keys, or other information required to install
and execute modified versions of a covered work in that User Product from
a modified version of its Corresponding Source. The information must
suffice to ensure that the continued functioning of the modified object
code is in no case prevented or interfered with solely because
modification has been made.
If you convey an object code work under this section in, or with, or
specifically for use in, a User Product, and the conveying occurs as
part of a transaction in which the right of possession and use of the
User Product is transferred to the recipient in perpetuity or for a
fixed term (regardless of how the transaction is characterized), the
Corresponding Source conveyed under this section must be accompanied
by the Installation Information. But this requirement does not apply
if neither you nor any third party retains the ability to install
modified object code on the User Product (for example, the work has
been installed in ROM).
The requirement to provide Installation Information does not include a
requirement to continue to provide support service, warranty, or updates
for a work that has been modified or installed by the recipient, or for
the User Product in which it has been modified or installed. Access to a
network may be denied when the modification itself materially and
adversely affects the operation of the network or violates the rules and
protocols for communication across the network.
Corresponding Source conveyed, and Installation Information provided,
in accord with this section must be in a format that is publicly
documented (and with an implementation available to the public in
source code form), and must require no special password or key for
unpacking, reading or copying.
7. Additional Terms.
"Additional permissions" are terms that supplement the terms of this
License by making exceptions from one or more of its conditions.
Additional permissions that are applicable to the entire Program shall
be treated as though they were included in this License, to the extent
that they are valid under applicable law. If additional permissions
apply only to part of the Program, that part may be used separately
under those permissions, but the entire Program remains governed by
this License without regard to the additional permissions.
When you convey a copy of a covered work, you may at your option
remove any additional permissions from that copy, or from any part of
it. (Additional permissions may be written to require their own
removal in certain cases when you modify the work.) You may place
additional permissions on material, added by you to a covered work,
for which you have or can give appropriate copyright permission.
Notwithstanding any other provision of this License, for material you
add to a covered work, you may (if authorized by the copyright holders of
that material) supplement the terms of this License with terms:
a) Disclaiming warranty or limiting liability differently from the
terms of sections 15 and 16 of this License; or
b) Requiring preservation of specified reasonable legal notices or
author attributions in that material or in the Appropriate Legal
Notices displayed by works containing it; or
c) Prohibiting misrepresentation of the origin of that material, or
requiring that modified versions of such material be marked in
reasonable ways as different from the original version; or
d) Limiting the use for publicity purposes of names of licensors or
authors of the material; or
e) Declining to grant rights under trademark law for use of some
trade names, trademarks, or service marks; or
f) Requiring indemnification of licensors and authors of that
material by anyone who conveys the material (or modified versions of
it) with contractual assumptions of liability to the recipient, for
any liability that these contractual assumptions directly impose on
those licensors and authors.
All other non-permissive additional terms are considered "further
restrictions" within the meaning of section 10. If the Program as you
received it, or any part of it, contains a notice stating that it is
governed by this License along with a term that is a further
restriction, you may remove that term. If a license document contains
a further restriction but permits relicensing or conveying under this
License, you may add to a covered work material governed by the terms
of that license document, provided that the further restriction does
not survive such relicensing or conveying.
If you add terms to a covered work in accord with this section, you
must place, in the relevant source files, a statement of the
additional terms that apply to those files, or a notice indicating
where to find the applicable terms.
Additional terms, permissive or non-permissive, may be stated in the
form of a separately written license, or stated as exceptions;
the above requirements apply either way.
8. Termination.
You may not propagate or modify a covered work except as expressly
provided under this License. Any attempt otherwise to propagate or
modify it is void, and will automatically terminate your rights under
this License (including any patent licenses granted under the third
paragraph of section 11).
However, if you cease all violation of this License, then your
license from a particular copyright holder is reinstated (a)
provisionally, unless and until the copyright holder explicitly and
finally terminates your license, and (b) permanently, if the copyright
holder fails to notify you of the violation by some reasonable means
prior to 60 days after the cessation.
Moreover, your license from a particular copyright holder is
reinstated permanently if the copyright holder notifies you of the
violation by some reasonable means, this is the first time you have
received notice of violation of this License (for any work) from that
copyright holder, and you cure the violation prior to 30 days after
your receipt of the notice.
Termination of your rights under this section does not terminate the
licenses of parties who have received copies or rights from you under
this License. If your rights have been terminated and not permanently
reinstated, you do not qualify to receive new licenses for the same
material under section 10.
9. Acceptance Not Required for Having Copies.
You are not required to accept this License in order to receive or
run a copy of the Program. Ancillary propagation of a covered work
occurring solely as a consequence of using peer-to-peer transmission
to receive a copy likewise does not require acceptance. However,
nothing other than this License grants you permission to propagate or
modify any covered work. These actions infringe copyright if you do
not accept this License. Therefore, by modifying or propagating a
covered work, you indicate your acceptance of this License to do so.
10. Automatic Licensing of Downstream Recipients.
Each time you convey a covered work, the recipient automatically
receives a license from the original licensors, to run, modify and
propagate that work, subject to this License. You are not responsible
for enforcing compliance by third parties with this License.
An "entity transaction" is a transaction transferring control of an
organization, or substantially all assets of one, or subdividing an
organization, or merging organizations. If propagation of a covered
work results from an entity transaction, each party to that
transaction who receives a copy of the work also receives whatever
licenses to the work the party's predecessor in interest had or could
give under the previous paragraph, plus a right to possession of the
Corresponding Source of the work from the predecessor in interest, if
the predecessor has it or can get it with reasonable efforts.
You may not impose any further restrictions on the exercise of the
rights granted or affirmed under this License. For example, you may
not impose a license fee, royalty, or other charge for exercise of
rights granted under this License, and you may not initiate litigation
(including a cross-claim or counterclaim in a lawsuit) alleging that
any patent claim is infringed by making, using, selling, offering for
sale, or importing the Program or any portion of it.
11. Patents.
A "contributor" is a copyright holder who authorizes use under this
License of the Program or a work on which the Program is based. The
work thus licensed is called the contributor's "contributor version".
A contributor's "essential patent claims" are all patent claims
owned or controlled by the contributor, whether already acquired or
hereafter acquired, that would be infringed by some manner, permitted
by this License, of making, using, or selling its contributor version,
but do not include claims that would be infringed only as a
consequence of further modification of the contributor version. For
purposes of this definition, "control" includes the right to grant
patent sublicenses in a manner consistent with the requirements of
this License.
Each contributor grants you a non-exclusive, worldwide, royalty-free
patent license under the contributor's essential patent claims, to
make, use, sell, offer for sale, import and otherwise run, modify and
propagate the contents of its contributor version.
In the following three paragraphs, a "patent license" is any express
agreement or commitment, however denominated, not to enforce a patent
(such as an express permission to practice a patent or covenant not to
sue for patent infringement). To "grant" such a patent license to a
party means to make such an agreement or commitment not to enforce a
patent against the party.
If you convey a covered work, knowingly relying on a patent license,
and the Corresponding Source of the work is not available for anyone
to copy, free of charge and under the terms of this License, through a
publicly available network server or other readily accessible means,
then you must either (1) cause the Corresponding Source to be so
available, or (2) arrange to deprive yourself of the benefit of the
patent license for this particular work, or (3) arrange, in a manner
consistent with the requirements of this License, to extend the patent
license to downstream recipients. "Knowingly relying" means you have
actual knowledge that, but for the patent license, your conveying the
covered work in a country, or your recipient's use of the covered work
in a country, would infringe one or more identifiable patents in that
country that you have reason to believe are valid.
If, pursuant to or in connection with a single transaction or
arrangement, you convey, or propagate by procuring conveyance of, a
covered work, and grant a patent license to some of the parties
receiving the covered work authorizing them to use, propagate, modify
or convey a specific copy of the covered work, then the patent license
you grant is automatically extended to all recipients of the covered
work and works based on it.
A patent license is "discriminatory" if it does not include within
the scope of its coverage, prohibits the exercise of, or is
conditioned on the non-exercise of one or more of the rights that are
specifically granted under this License. You may not convey a covered
work if you are a party to an arrangement with a third party that is
in the business of distributing software, under which you make payment
to the third party based on the extent of your activity of conveying
the work, and under which the third party grants, to any of the
parties who would receive the covered work from you, a discriminatory
patent license (a) in connection with copies of the covered work
conveyed by you (or copies made from those copies), or (b) primarily
for and in connection with specific products or compilations that
contain the covered work, unless you entered into that arrangement,
or that patent license was granted, prior to 28 March 2007.
Nothing in this License shall be construed as excluding or limiting
any implied license or other defenses to infringement that may
otherwise be available to you under applicable patent law.
12. No Surrender of Others' Freedom.
If conditions are imposed on you (whether by court order, agreement or
otherwise) that contradict the conditions of this License, they do not
excuse you from the conditions of this License. If you cannot convey a
covered work so as to satisfy simultaneously your obligations under this
License and any other pertinent obligations, then as a consequence you may
not convey it at all. For example, if you agree to terms that obligate you
to collect a royalty for further conveying from those to whom you convey
the Program, the only way you could satisfy both those terms and this
License would be to refrain entirely from conveying the Program.
13. Use with the GNU Affero General Public License.
Notwithstanding any other provision of this License, you have
permission to link or combine any covered work with a work licensed
under version 3 of the GNU Affero General Public License into a single
combined work, and to convey the resulting work. The terms of this
License will continue to apply to the part which is the covered work,
but the special requirements of the GNU Affero General Public License,
section 13, concerning interaction through a network will apply to the
combination as such.
14. Revised Versions of this License.
The Free Software Foundation may publish revised and/or new versions of
the GNU General Public License from time to time. Such new versions will
be similar in spirit to the present version, but may differ in detail to
address new problems or concerns.
Each version is given a distinguishing version number. If the
Program specifies that a certain numbered version of the GNU General
Public License "or any later version" applies to it, you have the
option of following the terms and conditions either of that numbered
version or of any later version published by the Free Software
Foundation. If the Program does not specify a version number of the
GNU General Public License, you may choose any version ever published
by the Free Software Foundation.
If the Program specifies that a proxy can decide which future
versions of the GNU General Public License can be used, that proxy's
public statement of acceptance of a version permanently authorizes you
to choose that version for the Program.
Later license versions may give you additional or different
permissions. However, no additional obligations are imposed on any
author or copyright holder as a result of your choosing to follow a
later version.
15. Disclaimer of Warranty.
THERE IS NO WARRANTY FOR THE PROGRAM, TO THE EXTENT PERMITTED BY
APPLICABLE LAW. EXCEPT WHEN OTHERWISE STATED IN WRITING THE COPYRIGHT
HOLDERS AND/OR OTHER PARTIES PROVIDE THE PROGRAM "AS IS" WITHOUT WARRANTY
OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO,
THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR
PURPOSE. THE ENTIRE RISK AS TO THE QUALITY AND PERFORMANCE OF THE PROGRAM
IS WITH YOU. SHOULD THE PROGRAM PROVE DEFECTIVE, YOU ASSUME THE COST OF
ALL NECESSARY SERVICING, REPAIR OR CORRECTION.
16. Limitation of Liability.
IN NO EVENT UNLESS REQUIRED BY APPLICABLE LAW OR AGREED TO IN WRITING
WILL ANY COPYRIGHT HOLDER, OR ANY OTHER PARTY WHO MODIFIES AND/OR CONVEYS
THE PROGRAM AS PERMITTED ABOVE, BE LIABLE TO YOU FOR DAMAGES, INCLUDING ANY
GENERAL, SPECIAL, INCIDENTAL OR CONSEQUENTIAL DAMAGES ARISING OUT OF THE
USE OR INABILITY TO USE THE PROGRAM (INCLUDING BUT NOT LIMITED TO LOSS OF
DATA OR DATA BEING RENDERED INACCURATE OR LOSSES SUSTAINED BY YOU OR THIRD
PARTIES OR A FAILURE OF THE PROGRAM TO OPERATE WITH ANY OTHER PROGRAMS),
EVEN IF SUCH HOLDER OR OTHER PARTY HAS BEEN ADVISED OF THE POSSIBILITY OF
SUCH DAMAGES.
17. Interpretation of Sections 15 and 16.
If the disclaimer of warranty and limitation of liability provided
above cannot be given local legal effect according to their terms,
reviewing courts shall apply local law that most closely approximates
an absolute waiver of all civil liability in connection with the
Program, unless a warranty or assumption of liability accompanies a
copy of the Program in return for a fee.
END OF TERMS AND CONDITIONS