## Welcome!
Welcome to Statistical PERT® Normal Edition
Statistical PERT® (SPERT®) is a freely licensed, probabilistic, estimation technique. Use Statistical PERT | All models are wrong, but some are useful.
to estimate uncertainties that have bell-shaped risk properties, like: task duration, work effort, | George E. P. Box, British statistician (1919-2013)
revenue, expenses, agile story points, project portfolios, event attendance, and more.
Statistical PERT® Normal Edition uses Excel's two normal distribution functions, NORM.DIST and | Facts are stubborn things, but statistics are pliable.
NORM.INV to model mild-to-moderately skewed uncertainties. To model a wider range of | Mark Twain, American humorist (1835-1910)
bell-shaped uncertainties, try Statistical PERT® Beta Edition which uses Excel's two beta
distribution functions, BETA.DIST and BETA.INV. It's freely licensed, too!
This example workbook is intended to help you quickly get started. You can also download
a Quick Start guide for Statistical PERT® Normal Edition. The Quick Start guide explains the
essential things you need to know to use this Statistical PERT® Normal Edition spreadsheet.
All Statistical PERT downloads share the same three steps for making a probablistic estimate:
1) Create a 3-point estimate (minimum, most likely, maximum)
2) Render a subjective judgment about the most likely outcome
3) Select any probabilistic planning estimate, or make a risk-based forecast
If you have any questions, suggestions, or comments, I'd love to hear from you! | New with Version 3 -- Dynamic, tri-colored, bell-shaped curves!
Contact me!
Plus:
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP | - New! Super Simple SPERT worksheet
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com | - New! Line Sparklines to visualize the 3-point uncertainty of every row
Watch a Pluralsight course on Statistical PERT® Normal Edition | - Enhanced! Agile forecasting using up to three scenarios
Watch Statistical PERT videos on YouTube | - A link to a brand-new Pluralsight course on estimating using SPERT
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Practice Forecasting
Statistical PERT® (SPERT®) Normal Edition - Practice Forecasting
Practice forecasting! How many pennies are in this jar?
Use the "Super Simple SPERT®" worksheet to create your first forecast!
First, estimate the most likely number of pennies in the jar, and enter your estimate into cell C4. This is your anchor estimate.
Second, estimate the minimum possible number of pennies in the jar, and enter your estimate into cell C3.
Third, estimate the maximum possible number of pennies in the jar, and enter your estimate into cell C5.
Your most likely estimate should be approximately midway between your minimum and maximum estimates.
Fourth, choose a subjective judgment (in cell C9) about HOW LIKELY your "most likely" will be close to the actual count.
Fifth, enter a planning estimate in cell 12. Choose any number between your minimum and maximum estimates.
Now see if you can answer questions like these by forecasting:
- How probable is the actual number of pennies in the jar less than your planning estimate?
- How probable is the actual number of pennies in the jar greater than your planning estimate?
- If I sell the jar for $30 (change the planning estimate to 3000), what is the chance I'll make a profit? What if I sell for $40? $50? $60?
- What is the 50/50 estimate (that is, 50% likely the true value is less than the 50/50 estimate, and 50% likely it is more)?
- If I told you that the jar contains not less than 2000 pennies and not more than 8000 pennies, would your forecast change? How?
An estimate is somebody's idea about the true value of something unknown.
A prediction is somebody's single idea about the true value of something unknown.
A forecast is somebody's varied idea about the true value of something unknown.
A forecast creates a range of possibilities with associated probabilities of occurrence.
Want to know the actual number of pennies in this jar? Unhide rows 26-35 ↓↓↓
The short answer: The actual number is 4,532 pennies. Maybe.
The long answer: I only counted one-third of the jar's pennies, then I estimated the uncounted coins.
To do that, I began by taking 15 random samples of 100 pennies out of the jar and weighing each sample,
then finding the average weight of 100 pennies. Pennies weigh either 2.5g (1982-present) or 3.11g (pre-1982).
I used the average weight of 100 pennies to calculate, by weight, the remaining two-thirds of the pennies in the jar.
So, I never counted ALL the pennies! But I did use some real data to create my forecasted mode of 4,532 pennies.
It's highly improbable that there are fewer than 4,412 pennies or more than 4,652 pennies.
Don't worry if your penny count forecast was way off. Forecasting is easy to do but hard to master.
Good forecasting is an empirical process. Make a forecast, observe, learn, then re-forecast.
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Super Simple SPERT®
Statistical PERT® (SPERT®) Normal Edition Super Simple SPERT®
Think about an uncertain outcome. Then, fill-in the yellow cells, below:
Enter your uncertainty's minimum value → | 50 | What's the minimum possible value or outcome for your uncertainty?
HINT: DO THIS FIRST → → → Enter your uncertainty's most likely value → | 100 | What's the most-likely-to-occur value or outcome for your uncertainty? This is your anchor estimate.
Enter your uncertainty's maximum value → | 150 | What's the maximum possible value or outcome for your uncertainty?
Validate your values → | 1 | See a green checkmark? Keep going! See a yellow exclamation mark? Check your 3-point entry to see if it's correct.
Check if this is a bell-shaped uncertainty → | 1 | See a green or yellow light? Keep going! See a red light? SPERT won't work well for this estimate scenario.
100
How confident are you in the most likely outcome? → | Medium confidence | Render a subjective judgment (your opinion) about HOW LIKELY the Most Likely outcome really is
Here's your implied, bell-shaped curve → |  | Based upon your entries, this is how SPERT models your uncertainty using the normal distribution
20
Enter a planning estimate → | 75 | Your planning estimate is any interesting number between your minimum and maximum estimates
Choose either the left- or right-side area → | Show Left-Side Area | You can obtain SPERT estimates from either the left- or right-side area of the bell-curve
Your planning estimate of 75 is greater than 11% of all possible outcomes → | 0.10565 | 89% of all possible outcomes exceed your planning estimate of 75
Enter any percentage between 1% and 99% → | 0.5 | Below, SPERT will calculate an estimate for you
The SPERT estimate of 100 is greater than 50% of all possible outcomes → | 100 | 50% of all possible outcomes exceed the SPERT estimate of 100
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
X-axis increments | 1.6667 | This, along with the grayed-out table below, is only used to create a Sparkline
16.6667 | 3.3882e-06
18.3333 | 4.7781e-06
20 | 6.6915e-06
21.6667 | 9.3064e-06
23.3333 | 1.2854e-05
25 | 1.763e-05
26.6667 | 2.4014e-05
28.3333 | 3.2482e-05
30 | 4.3634e-05
31.6667 | 5.8209e-05
33.3333 | 7.7114e-05
35 | 0.00010145
36.6667 | 0.00013255
38.3333 | 0.00017198
40 | 0.00022159
41.6667 | 0.00028354
43.3333 | 0.0003603
45 | 0.00045468
46.6667 | 0.0005698
48.3333 | 0.00070913
50 | 0.00087642
51.6667 | 0.0010757
53.3333 | 0.0013111
55 | 0.001587
56.6667 | 0.0019076
58.3333 | 0.0022772
60 | 0.0026995
61.6667 | 0.0031781
63.3333 | 0.0037156
65 | 0.0043139
66.6667 | 0.0049739
68.3333 | 0.0056951
70 | 0.0064759
71.6667 | 0.0073127
73.3333 | 0.0082005
75 | 0.0091325
76.6667 | 0.0101
78.3333 | 0.011093
80 | 0.012099
81.6667 | 0.013104
83.3333 | 0.014096
85 | 0.015057
86.6667 | 0.015972
88.3333 | 0.016826
90 | 0.017603
91.6667 | 0.018289
93.3333 | 0.018869
95 | 0.019333
96.6667 | 0.019672
98.3333 | 0.019878
100 | 0.019947
101.6667 | 0.019878
103.3333 | 0.019672
105 | 0.019333
106.6667 | 0.018869
108.3333 | 0.018289
110 | 0.017603
111.6667 | 0.016826
113.3333 | 0.015972
115 | 0.015057
116.6667 | 0.014096
118.3333 | 0.013104
120 | 0.012099
121.6667 | 0.011093
123.3333 | 0.0101
125 | 0.0091325
126.6667 | 0.0082005
128.3333 | 0.0073127
130 | 0.0064759
131.6667 | 0.0056951
133.3333 | 0.0049739
135 | 0.0043139
136.6667 | 0.0037156
138.3333 | 0.0031781
140 | 0.0026995
141.6667 | 0.0022772
143.3333 | 0.0019076
145 | 0.001587
146.6667 | 0.0013111
148.3333 | 0.0010757
150 | 0.00087642
151.6667 | 0.00070913
153.3333 | 0.0005698
155 | 0.00045468
156.6667 | 0.0003603
158.3333 | 0.00028354
160 | 0.00022159
161.6667 | 0.00017198
163.3333 | 0.00013255
165 | 0.00010145
166.6667 | 7.7114e-05
168.3333 | 5.8209e-05
170 | 4.3634e-05
171.6667 | 3.2482e-05
173.3333 | 2.4014e-05
175 | 1.763e-05
176.6667 | 1.2854e-05
178.3333 | 9.3064e-06
180 | 6.6915e-06
181.6667 | 4.7781e-06
183.3333 | 3.3882e-06
↑ Rows 36 through 138 are hidden; they are used to create the bell-curve Sparkline

## SPERT® Normal for Beginners
Statistical PERT® (SPERT®) Normal Edition for Beginners
First, enter a three-point estimate for any uncertainty
| Minimum | Most Likely | Maximum | [6 empty] | SPERT Var
| 60 | 120 | 240 | Use SPERT to estimate task duration, work effort, agile story points, cost, revenue, event attendance, etc. | [5 empty] | 1296
|  |  | Validate your bell-shaped uncertainty | 1 | 0.5 | A green checkmark means you have correctly entered minimum, most likely and maximum point-estimates. A green or yellow light means you have a suitable, bell-shaped uncertainty. If it's red, try changing your three-point estimate.
[5 empty] | The PERT Mean is the average result | PERT Mean
[5 empty] | (It's also called the expected result) | 130 | The PERT Mean is calculated using the PERT formula: (Minimum + 4(Most Likely) + Maximum) / 6
[6 empty] | Render a subjective judgment about HOW LIKELY | Most Likely Confidence
[6 empty] | the Most Likely outcome really is | Medium confidence | This choice influences the implied bell-shaped curve for the uncertainty you are estimating
This normal distribution graph shows the bell-shaped curve for your uncertainty | [7 empty] | Curve | The bell-shaped curve will change depending on your 3-point estimate and your subjective judgment about the Most Likely outcome (above)
Note: Even if your 3-point estimate indicates skewing, SPERT Normal Edition fits your uncertainty into a normally-distributed, bell-shaped curve
This is the SPERT Standard Deviation for your uncertainty | [8 empty] | SPERT SD |  | You don't have to know this or do anything with this, but SPERT needs this
36
[9 empty] | Show probabilities from either the left-side area or right-side area |  | Show Left-Side Area |  | Read the red text below to see how this choice affects the SPERT estimates
[11 empty] | Planning Estimate | SPERT Probability | Note: This is a cumulative probability, so the SPERT Probability is the likelihood that
the Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty's actual outcome*
[9 empty] | Enter a Planning Estimate and see its likelihood of occurrence under SPERT Probability |  | 150 | 71.07% | * This is true if you choose Show Left-Side Area in the dropdown control above. If you choose Show Right-Side Area,
you'll see the SPERT Probability that your Planning Estimate will be EXCEEDED by the uncertainty's actual outcome.
Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[12 empty] | Here, you'll see several SPERT estimates with different probabilities of occurrence | SPERT Probabilistic Estimates
[12 empty] | You can change these cumulative probability choices (enter values between 1% and 99%) → | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7
[12 empty] | Find a SPERT Probablistic Estimate that best matches your risk propensity → | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 148.8784
Choose whether to show currency formatting
Do not show currency formatting
That's it! Now try using the (3-Point entry) worksheet!
Or, use the (1-Point entry) worksheet, where two heuristics automatically calculate the Minimum and Maximum point-estimates
| -0.5 | << Heuristics >> | 1 | (You can change the dropdown options on the Vlookups worksheet)
| Minimum | Most Likely | Maximum
| 60 | 120 | 240
Try selecting a different dropdown percentage by clicking above the Minimum and Maximum cell headings,
and see the value changes for the minimum and maximum point-estimates in the green-shaded cells.
The rest of the (1-Point entry) worksheet works exactly the same way as the (3-Point entry) worksheet.
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
| X-axis increments | 3 | This, along with the grayed-out table below, is only used to create a Sparkline
| 0 | 1.633e-05
| 3 | 2.1987e-05
| 6 | 2.9399e-05
| 9 | 3.9037e-05
| 12 | 5.1477e-05
| 15 | 6.7411e-05
| 18 | 8.7667e-05
| 21 | 0.00011322
| 24 | 0.00014521
| 27 | 0.00018495
| 30 | 0.00023393
| 33 | 0.00029384
| 36 | 0.00036654
| 39 | 0.00045406
| 42 | 0.00055858
| 45 | 0.00068241
| 48 | 0.00082792
| 51 | 0.00099751
| 54 | 0.0011935
| 57 | 0.0014182
| 60 | 0.0016734
| 63 | 0.001961
| 66 | 0.002282
| 69 | 0.0026372
| 72 | 0.0030267
| 75 | 0.0034496
| 78 | 0.0039043
| 81 | 0.0043885
| 84 | 0.0048986
| 87 | 0.0054301
| 90 | 0.0059776
| 93 | 0.0065348
| 96 | 0.0070944
| 99 | 0.0076487
| 102 | 0.0081893
| 105 | 0.0087074
| 108 | 0.0091942
| 111 | 0.009641
| 114 | 0.01004
| 117 | 0.010382
| 120 | 0.010662
| 123 | 0.010874
| 126 | 0.011014
| 129 | 0.011077
| 132 | 0.011065
| 135 | 0.010975
| 138 | 0.010811
| 141 | 0.010576
| 144 | 0.010275
| 147 | 0.0099125
| 150 | 0.009497
| 153 | 0.0090359
| 156 | 0.0085377
| 159 | 0.0080112
| 162 | 0.0074651
| 165 | 0.0069081
| 168 | 0.0063484
| 171 | 0.0057937
| 174 | 0.0052508
| 177 | 0.0047259
| 180 | 0.004224
| 183 | 0.0037493
| 186 | 0.0033049
| 189 | 0.0028931
| 192 | 0.002515
| 195 | 0.0021712
| 198 | 0.0018614
| 201 | 0.0015848
| 204 | 0.00134
| 207 | 0.0011251
| 210 | 0.00093816
| 213 | 0.00077686
| 216 | 0.00063884
| 219 | 0.00052171
| 222 | 0.00042311
| 225 | 0.00034076
| 228 | 0.00027255
| 231 | 0.00021648
| 234 | 0.00017075
| 237 | 0.00013375
| 240 | 0.00010405
| 243 | 8.0378e-05
| 246 | 6.1664e-05
| 249 | 4.6979e-05
| 252 | 3.5544e-05
| 255 | 2.6706e-05
| 258 | 1.9927e-05
| 261 | 1.4766e-05
| 264 | 1.0865e-05
| 267 | 7.9401e-06
| 270 | 5.7622e-06
| 273 | 4.1528e-06
| 276 | 2.9722e-06
| 279 | 2.1125e-06
| 282 | 1.491e-06
| 285 | 1.0451e-06
| 288 | 7.2752e-07
| 291 | 5.0292e-07
| 294 | 3.4525e-07
| 297 | 2.3537e-07
| 300 | 1.5935e-07
↑ Rows 62 through 164 are hidden; they are used to create the bell-curve Sparkline
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on G8: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H11: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I14: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on J17: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on L22: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on M22: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on N29: You can choose different probabilities by entering a value between 1% and 99%.
Note on B39: Use a simple heuristic to quickly create MINIMUM point-estimates. Do this by selecting a percentage in cell B2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and reducing it by the percentage value specified in cell B2. If you want, overwrite any cell formula in column B to manually enter a non-calculated, minimum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell B2, you can do that in the Vlookups worksheet).
Note on C39: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D39: Use a simple heuristic to quickly create MAXIMUM point-estimates. Do this by selecting a percentage in cell D2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and increasing it by the percentage value specified in cell D2. If you want, overwrite any cell formula in column D to manually enter a non-calculated, maximum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell D2, you can do that in the Vlookups worksheet).

## SPERT® Normal (1-Point entry)
| Statistical PERT® (SPERT®) Normal Edition 1-Point Entry | [10 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
| -0.5 | << Heuristics >> | 1 | [8 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.5 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 0.5 | 130 | Near certainty |  |  | 12.7279 | 162 | 150 | 94.19% | 113.6885 | 146.3115 | 143.1916 | 140.7121 | 138.5849 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 6.9685e-25 | 7.5266e-24 | 7.6901e-23 | 7.4325e-22 | 6.7954e-21 | 5.8771e-20 | 4.8082e-19 | 3.7212e-18 | 2.7243e-17 | 1.8866e-16 | 1.236e-15 | 7.6593e-15 | 4.49e-14 | 2.4899e-13 | 1.3061e-12 | 6.4812e-12 | 3.0423e-11 | 1.3509e-10 | 5.6743e-10 | 2.2547e-09 | 8.4746e-09 | 3.0132e-08 | 1.0135e-07 | 3.2245e-07 | 9.705e-07 | 2.7631e-06 | 7.4417e-06 | 1.8959e-05 | 4.5691e-05 | 0.00010417 | 0.00022464 | 0.00045827 | 0.00088437 | 0.0016144 | 0.0027878 | 0.004554 | 0.0070371 | 0.010286 | 0.014223 | 0.018605 | 0.02302 | 0.026945 | 0.029834 | 0.031247 | 0.030959 | 0.029016 | 0.025726 | 0.021576 | 0.017117 | 0.012846 | 0.0091198 | 0.0061245 | 0.0038907 | 0.0023381 | 0.0013291 | 0.00071473 | 0.00036357 | 0.00017495 | 7.9636e-05 | 3.4291e-05 | 1.3967e-05 | 5.3818e-06 | 1.9616e-06 | 6.7634e-07 | 2.206e-07 | 6.8061e-08 | 1.9864e-08 | 5.4843e-09 | 1.4323e-09 | 3.5386e-10 | 8.2698e-11 | 1.8282e-11 | 3.8233e-12 | 7.5635e-13 | 1.4154e-13 | 2.5056e-14 | 4.1957e-15 | 6.6463e-16 | 9.9592e-17 | 1.4117e-17 | 1.8929e-18 | 2.401e-19 | 2.8809e-20 | 3.2699e-21 | 3.5109e-22 | 3.5659e-23 | 3.426e-24 | 3.1138e-25 | 2.6771e-26 | 2.1772e-27 | 1.675e-28 | 1.219e-29 | 8.392e-31 | 5.4651e-32 | 3.3667e-33 | 1.9619e-34 | 1.0815e-35 | 5.6397e-37 | 2.7819e-38 | 1.2981e-39 | 5.73e-41
2 | 60 | 120 | 240 | 1 | 0.5 | 130 | High confidence |  |  | 20.4853 | 419.6468 | 150 | 83.55% | 103.7471 | 156.2529 | 151.2316 | 147.2408 | 143.8171 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5037e-11 | 8.7797e-11 | 2.1534e-10 | 5.1695e-10 | 1.2147e-09 | 2.7936e-09 | 6.2885e-09 | 1.3855e-08 | 2.9879e-08 | 6.3069e-08 | 1.303e-07 | 2.6349e-07 | 5.215e-07 | 1.0103e-06 | 1.9157e-06 | 3.5553e-06 | 6.4583e-06 | 1.1483e-05 | 1.9983e-05 | 3.4038e-05 | 5.6748e-05 | 9.2603e-05 | 0.00014791 | 0.00023122 | 0.0003538 | 0.00052988 | 0.00077674 | 0.0011145 | 0.0015651 | 0.0021513 | 0.0028943 | 0.0038113 | 0.0049124 | 0.0061972 | 0.0076522 | 0.0092483 | 0.01094 | 0.012667 | 0.014355 | 0.015923 | 0.017287 | 0.01837 | 0.019107 | 0.019451 | 0.019382 | 0.018903 | 0.018045 | 0.01686 | 0.015419 | 0.013801 | 0.012092 | 0.010369 | 0.008703 | 0.0071497 | 0.0057491 | 0.0045247 | 0.0034855 | 0.002628 | 0.0019395 | 0.0014009 | 0.00099046 | 0.0006854 | 0.00046423 | 0.00030776 | 0.0001997 | 0.00012683 | 7.8844e-05 | 4.7972e-05 | 2.8569e-05 | 1.6653e-05 | 9.5011e-06 | 5.3056e-06 | 2.8999e-06 | 1.5514e-06 | 8.1236e-07 | 4.1635e-07 | 2.0886e-07 | 1.0255e-07 | 4.9284e-08 | 2.3182e-08 | 1.0673e-08 | 4.8097e-09 | 2.1214e-09 | 9.1585e-10 | 3.87e-10 | 1.6006e-10 | 6.4793e-11 | 2.5672e-11 | 9.9562e-12 | 3.7792e-12 | 1.4041e-12 | 5.106e-13 | 1.8174e-13 | 6.3315e-14 | 2.159e-14 | 7.2056e-15 | 2.3539e-15 | 7.5263e-16 | 2.3554e-16 | 7.215e-17 | 2.1632e-17
3 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-high confidence |  |  | 28.2426 | 797.6468 | 150 | 76.06% | 93.8056 | 166.1944 | 159.2716 | 153.7696 | 149.0494 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5419e-07 | 5.7429e-07 | 9.2071e-07 | 1.4595e-06 | 2.2877e-06 | 3.5457e-06 | 5.4336e-06 | 8.2335e-06 | 1.2336e-05 | 1.8275e-05 | 2.677e-05 | 3.8775e-05 | 5.5531e-05 | 7.8637e-05 | 0.00011011 | 0.00015244 | 0.00020869 | 0.00028248 | 0.00037807 | 0.00050034 | 0.00065472 | 0.00084712 | 0.0010838 | 0.0013709 | 0.0017148 | 0.0021208 | 0.0025935 | 0.0031359 | 0.0037493 | 0.0044324 | 0.0051812 | 0.0059885 | 0.0068439 | 0.0077337 | 0.0086412 | 0.0095468 | 0.010429 | 0.011265 | 0.012031 | 0.012706 | 0.013267 | 0.013698 | 0.013985 | 0.014117 | 0.01409 | 0.013906 | 0.01357 | 0.013094 | 0.012492 | 0.011785 | 0.010993 | 0.010139 | 0.0092464 | 0.0083379 | 0.0074342 | 0.0065542 | 0.0057134 | 0.0049247 | 0.0041972 | 0.003537 | 0.0029473 | 0.0024283 | 0.0019782 | 0.0015935 | 0.0012692 | 0.00099957 | 0.00077838 | 0.00059933 | 0.0004563 | 0.0003435 | 0.00025568 | 0.00018818 | 0.00013695 | 9.8545e-05 | 7.0115e-05 | 4.9327e-05 | 3.4313e-05 | 2.3601e-05 | 1.6051e-05 | 1.0794e-05 | 7.1773e-06 | 4.7189e-06 | 3.0677e-06 | 1.9719e-06 | 1.2533e-06 | 7.8765e-07 | 4.8945e-07 | 3.0073e-07 | 1.8271e-07 | 1.0976e-07 | 6.5193e-08 | 3.8289e-08 | 2.2235e-08 | 1.2768e-08 | 7.2492e-09 | 4.0697e-09 | 2.2591e-09 | 1.24e-09 | 6.7294e-10 | 3.6112e-10 | 1.9161e-10
4 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium confidence |  |  | 36 | 1296 | 150 | 71.07% | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 1.633e-05 | 2.1987e-05 | 2.9399e-05 | 3.9037e-05 | 5.1477e-05 | 6.7411e-05 | 8.7667e-05 | 0.00011322 | 0.00014521 | 0.00018495 | 0.00023393 | 0.00029384 | 0.00036654 | 0.00045406 | 0.00055858 | 0.00068241 | 0.00082792 | 0.00099751 | 0.0011935 | 0.0014182 | 0.0016734 | 0.001961 | 0.002282 | 0.0026372 | 0.0030267 | 0.0034496 | 0.0039043 | 0.0043885 | 0.0048986 | 0.0054301 | 0.0059776 | 0.0065348 | 0.0070944 | 0.0076487 | 0.0081893 | 0.0087074 | 0.0091942 | 0.009641 | 0.01004 | 0.010382 | 0.010662 | 0.010874 | 0.011014 | 0.011077 | 0.011065 | 0.010975 | 0.010811 | 0.010576 | 0.010275 | 0.0099125 | 0.009497 | 0.0090359 | 0.0085377 | 0.0080112 | 0.0074651 | 0.0069081 | 0.0063484 | 0.0057937 | 0.0052508 | 0.0047259 | 0.004224 | 0.0037493 | 0.0033049 | 0.0028931 | 0.002515 | 0.0021712 | 0.0018614 | 0.0015848 | 0.00134 | 0.0011251 | 0.00093816 | 0.00077686 | 0.00063884 | 0.00052171 | 0.00042311 | 0.00034076 | 0.00027255 | 0.00021648 | 0.00017075 | 0.00013375 | 0.00010405 | 8.0378e-05 | 6.1664e-05 | 4.6979e-05 | 3.5544e-05 | 2.6706e-05 | 1.9927e-05 | 1.4766e-05 | 1.0865e-05 | 7.9401e-06 | 5.7622e-06 | 4.1528e-06 | 2.9722e-06 | 2.1125e-06 | 1.491e-06 | 1.0451e-06 | 7.2752e-07 | 5.0292e-07 | 3.4525e-07 | 2.3537e-07 | 1.5935e-07
5 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-low confidence |  |  | 48.3721 | 2339.8615 | 150 | 66.04% | 68.0086 | 191.9914 | 180.1345 | 170.711 | 162.6265 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00022281 | 0.00026272 | 0.00030858 | 0.00036106 | 0.00042084 | 0.00048864 | 0.00056518 | 0.0006512 | 0.00074744 | 0.0008546 | 0.00097338 | 0.0011044 | 0.0012483 | 0.0014054 | 0.0015763 | 0.0017612 | 0.0019602 | 0.0021733 | 0.0024004 | 0.002641 | 0.0028945 | 0.0031602 | 0.0034371 | 0.0037239 | 0.0040191 | 0.004321 | 0.0046278 | 0.0049373 | 0.0052474 | 0.0055555 | 0.0058591 | 0.0061556 | 0.0064422 | 0.0067163 | 0.0069752 | 0.0072163 | 0.007437 | 0.0076351 | 0.0078083 | 0.0079548 | 0.008073 | 0.0081615 | 0.0082192 | 0.0082456 | 0.0082403 | 0.0082034 | 0.0081353 | 0.0080368 | 0.0079091 | 0.0077534 | 0.0075717 | 0.0073658 | 0.0071381 | 0.0068908 | 0.0066265 | 0.0063479 | 0.0060577 | 0.0057585 | 0.0054532 | 0.0051441 | 0.004834 | 0.0045251 | 0.0042197 | 0.0039198 | 0.0036273 | 0.0033436 | 0.0030704 | 0.0028086 | 0.0025593 | 0.0023232 | 0.0021007 | 0.0018923 | 0.001698 | 0.0015178 | 0.0013515 | 0.0011988 | 0.0010593 | 0.00093245 | 0.00081762 | 0.00071418 | 0.00062143 | 0.00053865 | 0.00046511 | 0.00040006 | 0.00034279 | 0.00029259 | 0.00024878 | 0.00021072 | 0.0001778 | 0.00014945 | 0.00012513 | 0.00010437 | 8.6719e-05 | 7.1777e-05 | 5.9181e-05 | 4.8608e-05 | 3.9771e-05 | 3.2416e-05 | 2.6319e-05 | 2.1287e-05 | 1.7151e-05
6 | 60 | 120 | 240 | 1 | 0.5 | 130 | Low confidence |  |  | 60.7442 | 3689.8615 | 150 | 62.9% | 52.1531 | 207.8469 | 192.9573 | 181.1236 | 170.9714 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00066504 | 0.00073828 | 0.00081758 | 0.00090321 | 0.00099536 | 0.0010943 | 0.0012 | 0.0013128 | 0.0014327 | 0.0015598 | 0.001694 | 0.0018352 | 0.0019834 | 0.0021383 | 0.0022997 | 0.0024673 | 0.0026406 | 0.0028192 | 0.0030025 | 0.00319 | 0.003381 | 0.0035746 | 0.0037701 | 0.0039667 | 0.0041633 | 0.004359 | 0.0045528 | 0.0047436 | 0.0049304 | 0.005112 | 0.0052874 | 0.0054556 | 0.0056153 | 0.0057657 | 0.0059056 | 0.0060343 | 0.0061507 | 0.006254 | 0.0063437 | 0.0064189 | 0.0064792 | 0.0065241 | 0.0065534 | 0.0065667 | 0.006564 | 0.0065454 | 0.0065109 | 0.0064608 | 0.0063954 | 0.0063154 | 0.0062211 | 0.0061133 | 0.0059927 | 0.0058602 | 0.0057167 | 0.0055631 | 0.0054004 | 0.0052297 | 0.0050521 | 0.0048686 | 0.0046804 | 0.0044884 | 0.0042939 | 0.0040978 | 0.0039011 | 0.0037048 | 0.0035098 | 0.003317 | 0.0031271 | 0.0029409 | 0.0027591 | 0.0025822 | 0.0024108 | 0.0022452 | 0.0020859 | 0.0019332 | 0.0017874 | 0.0016485 | 0.0015167 | 0.001392 | 0.0012745 | 0.001164 | 0.0010605 | 0.00096391 | 0.00087395 | 0.00079046 | 0.0007132 | 0.00064193 | 0.00057637 | 0.00051624 | 0.00046127 | 0.00041114 | 0.00036557 | 0.00032425 | 0.00028691 | 0.00025325 | 0.00022299 | 0.00019587 | 0.00017163 | 0.00015002 | 0.00013081
7 | 60 | 120 | 240 | 1 | 0.5 | 130 | Guesstimate |  |  | 73.1163 | 5346 | 150 | 60.78% | 36.2976 | 223.7024 | 205.7802 | 191.5363 | 179.3162 | 130 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.0011232 | 0.0012071 | 0.0012952 | 0.0013874 | 0.0014836 | 0.0015839 | 0.001688 | 0.001796 | 0.0019077 | 0.0020229 | 0.0021415 | 0.0022632 | 0.0023878 | 0.002515 | 0.0026445 | 0.002776 | 0.0029092 | 0.0030436 | 0.0031789 | 0.0033147 | 0.0034504 | 0.0035856 | 0.0037198 | 0.0038526 | 0.0039834 | 0.0041117 | 0.004237 | 0.0043588 | 0.0044766 | 0.0045898 | 0.0046979 | 0.0048005 | 0.0048971 | 0.0049872 | 0.0050705 | 0.0051465 | 0.0052148 | 0.0052751 | 0.0053272 | 0.0053707 | 0.0054055 | 0.0054313 | 0.0054481 | 0.0054558 | 0.0054542 | 0.0054435 | 0.0054237 | 0.0053949 | 0.0053572 | 0.0053108 | 0.0052559 | 0.0051929 | 0.005122 | 0.0050435 | 0.0049579 | 0.0048656 | 0.004767 | 0.0046625 | 0.0045526 | 0.0044378 | 0.0043187 | 0.0041956 | 0.0040693 | 0.0039401 | 0.0038085 | 0.0036752 | 0.0035406 | 0.0034052 | 0.0032694 | 0.0031338 | 0.0029987 | 0.0028647 | 0.002732 | 0.0026011 | 0.0024723 | 0.0023459 | 0.0022223 | 0.0021016 | 0.0019841 | 0.00187 | 0.0017596 | 0.0016529 | 0.00155 | 0.0014511 | 0.0013562 | 0.0012654 | 0.0011787 | 0.0010961 | 0.0010175 | 0.00094303 | 0.00087251 | 0.00080591 | 0.00074314 | 0.0006841 | 0.0006287 | 0.00057681 | 0.00052831 | 0.00048308 | 0.00044098 | 0.00040187 | 0.00036561
8 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
11 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 420 | 840 | 1680 |  |  | 910 |  |  |  | 118.537 | 14051.0166 | 1050 | 88.12% | 551.5647 | 1268.4353 | 1199.8785 | 1145.3918 | 1098.6471 | 910 | 554.389 | 561.4308 | 568.4727 | 575.5145 | 582.5563 | 589.5981 | 596.6399 | 603.6817 | 610.7235 | 617.7653 | 624.8071 | 631.8489 | 638.8907 | 645.9325 | 652.9743 | 660.0161 | 667.0579 | 674.0997 | 681.1415 | 688.1833 | 695.2251 | 702.2669 | 709.3087 | 716.3505 | 723.3923 | 730.4341 | 737.4759 | 744.5177 | 751.5595 | 758.6013 | 765.6431 | 772.6849 | 779.7267 | 786.7685 | 793.8103 | 800.8521 | 807.8939 | 814.9357 | 821.9775 | 829.0193 | 836.0611 | 843.1029 | 850.1447 | 857.1865 | 864.2283 | 871.2701 | 878.3119 | 885.3537 | 892.3955 | 899.4373 | 906.4791 | 913.5209 | 920.5627 | 927.6045 | 934.6463 | 941.6881 | 948.7299 | 955.7717 | 962.8135 | 969.8553 | 976.8971 | 983.9389 | 990.9807 | 998.0225 | 1005.0643 | 1012.1061 | 1019.1479 | 1026.1897 | 1033.2315 | 1040.2733 | 1047.3151 | 1054.3569 | 1061.3987 | 1068.4405 | 1075.4823 | 1082.5241 | 1089.5659 | 1096.6077 | 1103.6495 | 1110.6913 | 1117.7331 | 1124.7749 | 1131.8167 | 1138.8585 | 1145.9003 | 1152.9421 | 1159.9839 | 1167.0257 | 1174.0675 | 1181.1093 | 1188.1511 | 1195.1929 | 1202.2347 | 1209.2765 | 1216.3183 | 1223.3601 | 1230.4019 | 1237.4437 | 1244.4855 | 1251.5273 | 1258.5692 | 1265.611 | 4.4603e-05 | 5.3023e-05 | 6.281e-05 | 7.4142e-05 | 8.721e-05 | 0.00010222 | 0.00011939 | 0.00013896 | 0.00016116 | 0.00018625 | 0.00021448 | 0.00024613 | 0.00028146 | 0.00032071 | 0.00036416 | 0.00041204 | 0.00046456 | 0.00052194 | 0.00058434 | 0.0006519 | 0.0007247 | 0.0008028 | 0.00088618 | 0.00097477 | 0.0010684 | 0.001167 | 0.0012701 | 0.0013775 | 0.0014887 | 0.0016033 | 0.0017205 | 0.0018398 | 0.0019605 | 0.0020817 | 0.0022027 | 0.0023224 | 0.00244 | 0.0025546 | 0.0026651 | 0.0027706 | 0.0028701 | 0.0029627 | 0.0030475 | 0.0031238 | 0.0031906 | 0.0032474 | 0.0032936 | 0.0033286 | 0.0033522 | 0.0033641 | 0.0033641 | 0.0033522 | 0.0033286 | 0.0032936 | 0.0032474 | 0.0031906 | 0.0031238 | 0.0030475 | 0.0029627 | 0.0028701 | 0.0027706 | 0.0026651 | 0.0025546 | 0.00244 | 0.0023224 | 0.0022027 | 0.0020817 | 0.0019605 | 0.0018398 | 0.0017205 | 0.0016033 | 0.0014887 | 0.0013775 | 0.0012701 | 0.001167 | 0.0010684 | 0.00097477 | 0.00088618 | 0.0008028 | 0.0007247 | 0.0006519 | 0.00058434 | 0.00052194 | 0.00046456 | 0.00041204 | 0.00036416 | 0.00032071 | 0.00028146 | 0.00024613 | 0.00021448 | 0.00018625 | 0.00016116 | 0.00013896 | 0.00011939 | 0.00010222 | 8.721e-05 | 7.4142e-05 | 6.281e-05 | 5.3023e-05 | 4.4603e-05 | 3.7388e-05
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 77.62% | 758.0887 | 1061.9113 | 1032.8557 | 1009.7632 | 989.952 | 910 | [102 empty] | 4.4603e-05 | 5.3023e-05 | 6.281e-05 | 7.4142e-05 | 8.721e-05 | 0.00010222 | 0.00011939 | 0.00013896 | 0.00016116 | 0.00018625 | 0.00021448 | 0.00024613 | 0.00028146 | 0.00032071 | 0.00036416 | 0.00041204 | 0.00046456 | 0.00052194 | 0.00058434 | 0.0006519 | 0.0007247 | 0.0008028 | 0.00088618 | 0.00097477 | 0.0010684 | 0.001167 | 0.0012701 | 0.0013775 | 0.0014887 | 0.0016033 | 0.0017205 | 0.0018398 | 0.0019605 | 0.0020817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0022027 | 0.0023224 | 0.00244 | 0.0025546 | 0.0026651 | 0.0027706 | 0.0028701 | 0.0029627 | 0.0030475 | 0.0031238 | 0.0031906 | 0.0032474 | 0.0032936 | 0.0033286 | 0.0033522 | 0.0033641 | 0.0033641 | 0.0033522 | 0.0033286 | 0.0032936 | 0.0032474 | 0.0031906 | 0.0031238 | 0.0030475 | 0.0029627 | 0.0028701 | 0.0027706 | 0.0026651 | 0.0025546 | 0.00244 | 0.0023224 | 0.0022027 | 0.0020817 | 0.0019605 | 0.0018398 | 0.0017205 | 0.0016033 | 0.0014887 | 0.0013775 | 0.0012701 | 0.001167 | 0.0010684 | 0.00097477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 0.8 | confidence | [117 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00088618 | 0.0008028 | 0.0007247 | 0.0006519 | 0.00058434 | 0.00052194 | 0.00046456 | 0.00041204 | 0.00036416 | 0.00032071 | 0.00028146 | 0.00024613 | 0.00021448 | 0.00018625 | 0.00016116 | 0.00013896 | 0.00011939 | 0.00010222 | 8.721e-05 | 7.4142e-05 | 6.281e-05 | 5.3023e-05 | 4.4603e-05 | 3.7388e-05
|  | The lowerbound threshold is | 758.0887 | [118 empty] | 4.4603e-05 | 5.3023e-05 | 6.281e-05 | 7.4142e-05 | 8.721e-05 | 0.00010222 | 0.00011939 | 0.00013896 | 0.00016116 | 0.00018625 | 0.00021448 | 0.00024613 | 0.00028146 | 0.00032071 | 0.00036416 | 0.00041204 | 0.00046456 | 0.00052194 | 0.00058434 | 0.0006519 | 0.0007247 | 0.0008028 | 0.00088618 | 0.00097477 | 0.0010684 | 0.001167 | 0.0012701 | 0.0013775 | 0.0014887 | 0.0016033 | 0.0017205 | 0.0018398 | 0.0019605 | 0.0020817 | 0.0022027 | 0.0023224 | 0.00244 | 0.0025546 | 0.0026651 | 0.0027706 | 0.0028701 | 0.0029627 | 0.0030475 | 0.0031238 | 0.0031906 | 0.0032474 | 0.0032936 | 0.0033286 | 0.0033522 | 0.0033641 | 0.0033641 | 0.0033522 | 0.0033286 | 0.0032936 | 0.0032474 | 0.0031906 | 0.0031238 | 0.0030475 | 0.0029627 | 0.0028701 | 0.0027706 | 0.0026651 | 0.0025546 | 0.00244 | 0.0023224 | 0.0022027 | 0.0020817 | 0.0019605 | 0.0018398 | 0.0017205 | 0.0016033 | 0.0014887 | 0.0013775 | 0.0012701 | 0.001167 | 0.0010684 | 0.00097477 | 0.00088618 | 0.0008028 | 0.0007247 | 0.0006519 | 0.00058434 | 0.00052194 | 0.00046456 | 0.00041204 | 0.00036416 | 0.00032071 | 0.00028146 | 0.00024613 | 0.00021448 | 0.00018625 | 0.00016116 | 0.00013896 | 0.00011939 | 0.00010222 | 8.721e-05 | 7.4142e-05 | 6.281e-05 | 5.3023e-05 | 4.4603e-05 | 3.7388e-05
|  | and the upperbound threshold is | 1061.9113
|  | Between a lowerbound value of | 800 |  | Miss the pie
|  | and an upperbound value of | 1100 |  | chart? Press
|  | the range probability is | 0.76881 |  | CTRL and 6
|  | The lowerbound area covers | 0.17671 |  | to show the
|  | and the upperbound area covers | 0.054481 |  | pie chart
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Note: NORM.DIST and NORM.INV functions use the mean (i.e., the PERT expected value) which impliies probabilistic symmetry.
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on M2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on N2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: Use a simple heuristic to quickly create MINIMUM point-estimates. Do this by selecting a percentage in cell B2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and reducing it by the percentage value specified in cell B2. If you want, overwrite any cell formula in column B to manually enter a non-calculated, minimum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell B2, you can do that in the Vlookups worksheet).
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: Use a simple heuristic to quickly create MAXIMUM point-estimates. Do this by selecting a percentage in cell D2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column C and increasing it by the percentage value specified in cell D2. If you want, overwrite any cell formula in column D to manually enter a non-calculated, maximum value for a particular three-point estimate. (If you need to modify the dropdown choices in cell D2, you can do that in the Vlookups worksheet).
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on O3: You can choose different probabilities by entering a value between 1% and 99%.
Note on A13: Need more than just 10 rows to enter your estimates? Rows 14 through 103 are hidden. Unhide these rows to display 90 more rows like rows 4 through 13.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.

## SPERT® Normal (3-Point entry)
| Statistical PERT® (SPERT®) Normal Edition 3-Point Entry | [10 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[12 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium confidence |  |  | 36 | 1296 | 150 | 71.07% | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 148.8784 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 1.633e-05 | 2.1987e-05 | 2.9399e-05 | 3.9037e-05 | 5.1477e-05 | 6.7411e-05 | 8.7667e-05 | 0.00011322 | 0.00014521 | 0.00018495 | 0.00023393 | 0.00029384 | 0.00036654 | 0.00045406 | 0.00055858 | 0.00068241 | 0.00082792 | 0.00099751 | 0.0011935 | 0.0014182 | 0.0016734 | 0.001961 | 0.002282 | 0.0026372 | 0.0030267 | 0.0034496 | 0.0039043 | 0.0043885 | 0.0048986 | 0.0054301 | 0.0059776 | 0.0065348 | 0.0070944 | 0.0076487 | 0.0081893 | 0.0087074 | 0.0091942 | 0.009641 | 0.01004 | 0.010382 | 0.010662 | 0.010874 | 0.011014 | 0.011077 | 0.011065 | 0.010975 | 0.010811 | 0.010576 | 0.010275 | 0.0099125 | 0.009497 | 0.0090359 | 0.0085377 | 0.0080112 | 0.0074651 | 0.0069081 | 0.0063484 | 0.0057937 | 0.0052508 | 0.0047259 | 0.004224 | 0.0037493 | 0.0033049 | 0.0028931 | 0.002515 | 0.0021712 | 0.0018614 | 0.0015848 | 0.00134 | 0.0011251 | 0.00093816 | 0.00077686 | 0.00063884 | 0.00052171 | 0.00042311 | 0.00034076 | 0.00027255 | 0.00021648 | 0.00017075 | 0.00013375 | 0.00010405 | 8.0378e-05 | 6.1664e-05 | 4.6979e-05 | 3.5544e-05 | 2.6706e-05 | 1.9927e-05 | 1.4766e-05 | 1.0865e-05 | 7.9401e-06 | 5.7622e-06 | 4.1528e-06 | 2.9722e-06 | 2.1125e-06 | 1.491e-06 | 1.0451e-06 | 7.2752e-07 | 5.0292e-07 | 3.4525e-07 | 2.3537e-07 | 1.5935e-07
2 | 60 | 120 | 240 | 1 | 0.5 | 130 | High confidence |  |  | 20.4853 | 419.6468 | 150 | 83.55% | 103.7471 | 156.2529 | 151.2316 | 147.2408 | 143.8171 | 140.7425 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5037e-11 | 8.7797e-11 | 2.1534e-10 | 5.1695e-10 | 1.2147e-09 | 2.7936e-09 | 6.2885e-09 | 1.3855e-08 | 2.9879e-08 | 6.3069e-08 | 1.303e-07 | 2.6349e-07 | 5.215e-07 | 1.0103e-06 | 1.9157e-06 | 3.5553e-06 | 6.4583e-06 | 1.1483e-05 | 1.9983e-05 | 3.4038e-05 | 5.6748e-05 | 9.2603e-05 | 0.00014791 | 0.00023122 | 0.0003538 | 0.00052988 | 0.00077674 | 0.0011145 | 0.0015651 | 0.0021513 | 0.0028943 | 0.0038113 | 0.0049124 | 0.0061972 | 0.0076522 | 0.0092483 | 0.01094 | 0.012667 | 0.014355 | 0.015923 | 0.017287 | 0.01837 | 0.019107 | 0.019451 | 0.019382 | 0.018903 | 0.018045 | 0.01686 | 0.015419 | 0.013801 | 0.012092 | 0.010369 | 0.008703 | 0.0071497 | 0.0057491 | 0.0045247 | 0.0034855 | 0.002628 | 0.0019395 | 0.0014009 | 0.00099046 | 0.0006854 | 0.00046423 | 0.00030776 | 0.0001997 | 0.00012683 | 7.8844e-05 | 4.7972e-05 | 2.8569e-05 | 1.6653e-05 | 9.5011e-06 | 5.3056e-06 | 2.8999e-06 | 1.5514e-06 | 8.1236e-07 | 4.1635e-07 | 2.0886e-07 | 1.0255e-07 | 4.9284e-08 | 2.3182e-08 | 1.0673e-08 | 4.8097e-09 | 2.1214e-09 | 9.1585e-10 | 3.87e-10 | 1.6006e-10 | 6.4793e-11 | 2.5672e-11 | 9.9562e-12 | 3.7792e-12 | 1.4041e-12 | 5.106e-13 | 1.8174e-13 | 6.3315e-14 | 2.159e-14 | 7.2056e-15 | 2.3539e-15 | 7.5263e-16 | 2.3554e-16 | 7.215e-17 | 2.1632e-17
3 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-high confidence |  |  | 28.2426 | 797.6468 | 150 | 76.06% | 93.8056 | 166.1944 | 159.2716 | 153.7696 | 149.0494 | 144.8105 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5419e-07 | 5.7429e-07 | 9.2071e-07 | 1.4595e-06 | 2.2877e-06 | 3.5457e-06 | 5.4336e-06 | 8.2335e-06 | 1.2336e-05 | 1.8275e-05 | 2.677e-05 | 3.8775e-05 | 5.5531e-05 | 7.8637e-05 | 0.00011011 | 0.00015244 | 0.00020869 | 0.00028248 | 0.00037807 | 0.00050034 | 0.00065472 | 0.00084712 | 0.0010838 | 0.0013709 | 0.0017148 | 0.0021208 | 0.0025935 | 0.0031359 | 0.0037493 | 0.0044324 | 0.0051812 | 0.0059885 | 0.0068439 | 0.0077337 | 0.0086412 | 0.0095468 | 0.010429 | 0.011265 | 0.012031 | 0.012706 | 0.013267 | 0.013698 | 0.013985 | 0.014117 | 0.01409 | 0.013906 | 0.01357 | 0.013094 | 0.012492 | 0.011785 | 0.010993 | 0.010139 | 0.0092464 | 0.0083379 | 0.0074342 | 0.0065542 | 0.0057134 | 0.0049247 | 0.0041972 | 0.003537 | 0.0029473 | 0.0024283 | 0.0019782 | 0.0015935 | 0.0012692 | 0.00099957 | 0.00077838 | 0.00059933 | 0.0004563 | 0.0003435 | 0.00025568 | 0.00018818 | 0.00013695 | 9.8545e-05 | 7.0115e-05 | 4.9327e-05 | 3.4313e-05 | 2.3601e-05 | 1.6051e-05 | 1.0794e-05 | 7.1773e-06 | 4.7189e-06 | 3.0677e-06 | 1.9719e-06 | 1.2533e-06 | 7.8765e-07 | 4.8945e-07 | 3.0073e-07 | 1.8271e-07 | 1.0976e-07 | 6.5193e-08 | 3.8289e-08 | 2.2235e-08 | 1.2768e-08 | 7.2492e-09 | 4.0697e-09 | 2.2591e-09 | 1.24e-09 | 6.7294e-10 | 3.6112e-10 | 1.9161e-10
4 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium confidence |  |  | 36 | 1296 | 150 | 71.07% | 83.8641 | 176.1359 | 167.3116 | 160.2984 | 154.2816 | 148.8784 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 1.633e-05 | 2.1987e-05 | 2.9399e-05 | 3.9037e-05 | 5.1477e-05 | 6.7411e-05 | 8.7667e-05 | 0.00011322 | 0.00014521 | 0.00018495 | 0.00023393 | 0.00029384 | 0.00036654 | 0.00045406 | 0.00055858 | 0.00068241 | 0.00082792 | 0.00099751 | 0.0011935 | 0.0014182 | 0.0016734 | 0.001961 | 0.002282 | 0.0026372 | 0.0030267 | 0.0034496 | 0.0039043 | 0.0043885 | 0.0048986 | 0.0054301 | 0.0059776 | 0.0065348 | 0.0070944 | 0.0076487 | 0.0081893 | 0.0087074 | 0.0091942 | 0.009641 | 0.01004 | 0.010382 | 0.010662 | 0.010874 | 0.011014 | 0.011077 | 0.011065 | 0.010975 | 0.010811 | 0.010576 | 0.010275 | 0.0099125 | 0.009497 | 0.0090359 | 0.0085377 | 0.0080112 | 0.0074651 | 0.0069081 | 0.0063484 | 0.0057937 | 0.0052508 | 0.0047259 | 0.004224 | 0.0037493 | 0.0033049 | 0.0028931 | 0.002515 | 0.0021712 | 0.0018614 | 0.0015848 | 0.00134 | 0.0011251 | 0.00093816 | 0.00077686 | 0.00063884 | 0.00052171 | 0.00042311 | 0.00034076 | 0.00027255 | 0.00021648 | 0.00017075 | 0.00013375 | 0.00010405 | 8.0378e-05 | 6.1664e-05 | 4.6979e-05 | 3.5544e-05 | 2.6706e-05 | 1.9927e-05 | 1.4766e-05 | 1.0865e-05 | 7.9401e-06 | 5.7622e-06 | 4.1528e-06 | 2.9722e-06 | 2.1125e-06 | 1.491e-06 | 1.0451e-06 | 7.2752e-07 | 5.0292e-07 | 3.4525e-07 | 2.3537e-07 | 1.5935e-07
5 | 60 | 120 | 240 | 1 | 0.5 | 130 | Medium-low confidence |  |  | 48.3721 | 2339.8615 | 150 | 66.04% | 68.0086 | 191.9914 | 180.1345 | 170.711 | 162.6265 | 155.3664 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00022281 | 0.00026272 | 0.00030858 | 0.00036106 | 0.00042084 | 0.00048864 | 0.00056518 | 0.0006512 | 0.00074744 | 0.0008546 | 0.00097338 | 0.0011044 | 0.0012483 | 0.0014054 | 0.0015763 | 0.0017612 | 0.0019602 | 0.0021733 | 0.0024004 | 0.002641 | 0.0028945 | 0.0031602 | 0.0034371 | 0.0037239 | 0.0040191 | 0.004321 | 0.0046278 | 0.0049373 | 0.0052474 | 0.0055555 | 0.0058591 | 0.0061556 | 0.0064422 | 0.0067163 | 0.0069752 | 0.0072163 | 0.007437 | 0.0076351 | 0.0078083 | 0.0079548 | 0.008073 | 0.0081615 | 0.0082192 | 0.0082456 | 0.0082403 | 0.0082034 | 0.0081353 | 0.0080368 | 0.0079091 | 0.0077534 | 0.0075717 | 0.0073658 | 0.0071381 | 0.0068908 | 0.0066265 | 0.0063479 | 0.0060577 | 0.0057585 | 0.0054532 | 0.0051441 | 0.004834 | 0.0045251 | 0.0042197 | 0.0039198 | 0.0036273 | 0.0033436 | 0.0030704 | 0.0028086 | 0.0025593 | 0.0023232 | 0.0021007 | 0.0018923 | 0.001698 | 0.0015178 | 0.0013515 | 0.0011988 | 0.0010593 | 0.00093245 | 0.00081762 | 0.00071418 | 0.00062143 | 0.00053865 | 0.00046511 | 0.00040006 | 0.00034279 | 0.00029259 | 0.00024878 | 0.00021072 | 0.0001778 | 0.00014945 | 0.00012513 | 0.00010437 | 8.6719e-05 | 7.1777e-05 | 5.9181e-05 | 4.8608e-05 | 3.9771e-05 | 3.2416e-05 | 2.6319e-05 | 2.1287e-05 | 1.7151e-05
6 | 60 | 120 | 240 | 1 | 0.5 | 130 | Low confidence |  |  | 60.7442 | 3689.8615 | 150 | 62.9% | 52.1531 | 207.8469 | 192.9573 | 181.1236 | 170.9714 | 161.8543 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.00066504 | 0.00073828 | 0.00081758 | 0.00090321 | 0.00099536 | 0.0010943 | 0.0012 | 0.0013128 | 0.0014327 | 0.0015598 | 0.001694 | 0.0018352 | 0.0019834 | 0.0021383 | 0.0022997 | 0.0024673 | 0.0026406 | 0.0028192 | 0.0030025 | 0.00319 | 0.003381 | 0.0035746 | 0.0037701 | 0.0039667 | 0.0041633 | 0.004359 | 0.0045528 | 0.0047436 | 0.0049304 | 0.005112 | 0.0052874 | 0.0054556 | 0.0056153 | 0.0057657 | 0.0059056 | 0.0060343 | 0.0061507 | 0.006254 | 0.0063437 | 0.0064189 | 0.0064792 | 0.0065241 | 0.0065534 | 0.0065667 | 0.006564 | 0.0065454 | 0.0065109 | 0.0064608 | 0.0063954 | 0.0063154 | 0.0062211 | 0.0061133 | 0.0059927 | 0.0058602 | 0.0057167 | 0.0055631 | 0.0054004 | 0.0052297 | 0.0050521 | 0.0048686 | 0.0046804 | 0.0044884 | 0.0042939 | 0.0040978 | 0.0039011 | 0.0037048 | 0.0035098 | 0.003317 | 0.0031271 | 0.0029409 | 0.0027591 | 0.0025822 | 0.0024108 | 0.0022452 | 0.0020859 | 0.0019332 | 0.0017874 | 0.0016485 | 0.0015167 | 0.001392 | 0.0012745 | 0.001164 | 0.0010605 | 0.00096391 | 0.00087395 | 0.00079046 | 0.0007132 | 0.00064193 | 0.00057637 | 0.00051624 | 0.00046127 | 0.00041114 | 0.00036557 | 0.00032425 | 0.00028691 | 0.00025325 | 0.00022299 | 0.00019587 | 0.00017163 | 0.00015002 | 0.00013081
7 | 60 | 120 | 240 | 1 | 0.5 | 130 | Guesstimate |  |  | 73.1163 | 5346 | 150 | 60.78% | 36.2976 | 223.7024 | 205.7802 | 191.5363 | 179.3162 | 168.3422 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 0.0011232 | 0.0012071 | 0.0012952 | 0.0013874 | 0.0014836 | 0.0015839 | 0.001688 | 0.001796 | 0.0019077 | 0.0020229 | 0.0021415 | 0.0022632 | 0.0023878 | 0.002515 | 0.0026445 | 0.002776 | 0.0029092 | 0.0030436 | 0.0031789 | 0.0033147 | 0.0034504 | 0.0035856 | 0.0037198 | 0.0038526 | 0.0039834 | 0.0041117 | 0.004237 | 0.0043588 | 0.0044766 | 0.0045898 | 0.0046979 | 0.0048005 | 0.0048971 | 0.0049872 | 0.0050705 | 0.0051465 | 0.0052148 | 0.0052751 | 0.0053272 | 0.0053707 | 0.0054055 | 0.0054313 | 0.0054481 | 0.0054558 | 0.0054542 | 0.0054435 | 0.0054237 | 0.0053949 | 0.0053572 | 0.0053108 | 0.0052559 | 0.0051929 | 0.005122 | 0.0050435 | 0.0049579 | 0.0048656 | 0.004767 | 0.0046625 | 0.0045526 | 0.0044378 | 0.0043187 | 0.0041956 | 0.0040693 | 0.0039401 | 0.0038085 | 0.0036752 | 0.0035406 | 0.0034052 | 0.0032694 | 0.0031338 | 0.0029987 | 0.0028647 | 0.002732 | 0.0026011 | 0.0024723 | 0.0023459 | 0.0022223 | 0.0021016 | 0.0019841 | 0.00187 | 0.0017596 | 0.0016529 | 0.00155 | 0.0014511 | 0.0013562 | 0.0012654 | 0.0011787 | 0.0010961 | 0.0010175 | 0.00094303 | 0.00087251 | 0.00080591 | 0.00074314 | 0.0006841 | 0.0006287 | 0.00057681 | 0.00052831 | 0.00048308 | 0.00044098 | 0.00040187 | 0.00036561
8 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
11 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [121 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 420 | 840 | 1680 |  |  | 910 |  |  |  | 123.2275 | 15185.0166 | 1050 | 87.2% | 521.7404 | 1298.2596 | 1223.9985 | 1164.9781 | 1114.3438 | 1068.8727 | 540.3175 | 547.6379 | 554.9584 | 562.2788 | 569.5993 | 576.9197 | 584.2402 | 591.5606 | 598.8811 | 606.2015 | 613.522 | 620.8424 | 628.1628 | 635.4833 | 642.8037 | 650.1242 | 657.4446 | 664.7651 | 672.0855 | 679.406 | 686.7264 | 694.0469 | 701.3673 | 708.6877 | 716.0082 | 723.3286 | 730.6491 | 737.9695 | 745.29 | 752.6104 | 759.9309 | 767.2513 | 774.5718 | 781.8922 | 789.2126 | 796.5331 | 803.8535 | 811.174 | 818.4944 | 825.8149 | 833.1353 | 840.4558 | 847.7762 | 855.0967 | 862.4171 | 869.7375 | 877.058 | 884.3784 | 891.6989 | 899.0193 | 906.3398 | 913.6602 | 920.9807 | 928.3011 | 935.6216 | 942.942 | 950.2625 | 957.5829 | 964.9033 | 972.2238 | 979.5442 | 986.8647 | 994.1851 | 1001.5056 | 1008.826 | 1016.1465 | 1023.4669 | 1030.7874 | 1038.1078 | 1045.4282 | 1052.7487 | 1060.0691 | 1067.3896 | 1074.71 | 1082.0305 | 1089.3509 | 1096.6714 | 1103.9918 | 1111.3123 | 1118.6327 | 1125.9531 | 1133.2736 | 1140.594 | 1147.9145 | 1155.2349 | 1162.5554 | 1169.8758 | 1177.1963 | 1184.5167 | 1191.8372 | 1199.1576 | 1206.478 | 1213.7985 | 1221.1189 | 1228.4394 | 1235.7598 | 1243.0803 | 1250.4007 | 1257.7212 | 1265.0416 | 1272.3621 | 1279.6825 | 4.2905e-05 | 5.1005e-05 | 6.042e-05 | 7.132e-05 | 8.3891e-05 | 9.8329e-05 | 0.00011485 | 0.00013367 | 0.00015502 | 0.00017916 | 0.00020632 | 0.00023676 | 0.00027074 | 0.00030851 | 0.0003503 | 0.00039635 | 0.00044688 | 0.00050208 | 0.0005621 | 0.00062709 | 0.00069712 | 0.00077224 | 0.00085245 | 0.00093767 | 0.0010278 | 0.0011226 | 0.0012218 | 0.0013251 | 0.0014321 | 0.0015422 | 0.001655 | 0.0017698 | 0.0018859 | 0.0020025 | 0.0021188 | 0.002234 | 0.0023471 | 0.0024573 | 0.0025636 | 0.0026651 | 0.0027608 | 0.0028499 | 0.0029315 | 0.0030049 | 0.0030692 | 0.0031238 | 0.0031682 | 0.0032019 | 0.0032246 | 0.003236 | 0.003236 | 0.0032246 | 0.0032019 | 0.0031682 | 0.0031238 | 0.0030692 | 0.0030049 | 0.0029315 | 0.0028499 | 0.0027608 | 0.0026651 | 0.0025636 | 0.0024573 | 0.0023471 | 0.002234 | 0.0021188 | 0.0020025 | 0.0018859 | 0.0017698 | 0.001655 | 0.0015422 | 0.0014321 | 0.0013251 | 0.0012218 | 0.0011226 | 0.0010278 | 0.00093767 | 0.00085245 | 0.00077224 | 0.00069712 | 0.00062709 | 0.0005621 | 0.00050208 | 0.00044688 | 0.00039635 | 0.0003503 | 0.00030851 | 0.00027074 | 0.00023676 | 0.00020632 | 0.00017916 | 0.00015502 | 0.00013367 | 0.00011485 | 9.8329e-05 | 8.3891e-05 | 7.132e-05 | 6.042e-05 | 5.1005e-05 | 4.2905e-05 | 3.5965e-05
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 76.74% | 752.0776 | 1067.9224 | 1037.7171 | 1013.7109 | 993.1157 | 974.6206 | [102 empty] | 4.2905e-05 | 5.1005e-05 | 6.042e-05 | 7.132e-05 | 8.3891e-05 | 9.8329e-05 | 0.00011485 | 0.00013367 | 0.00015502 | 0.00017916 | 0.00020632 | 0.00023676 | 0.00027074 | 0.00030851 | 0.0003503 | 0.00039635 | 0.00044688 | 0.00050208 | 0.0005621 | 0.00062709 | 0.00069712 | 0.00077224 | 0.00085245 | 0.00093767 | 0.0010278 | 0.0011226 | 0.0012218 | 0.0013251 | 0.0014321 | 0.0015422 | 0.001655 | 0.0017698 | 0.0018859 | 0.0020025 | 0.0021188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[122 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002234 | 0.0023471 | 0.0024573 | 0.0025636 | 0.0026651 | 0.0027608 | 0.0028499 | 0.0029315 | 0.0030049 | 0.0030692 | 0.0031238 | 0.0031682 | 0.0032019 | 0.0032246 | 0.003236 | 0.003236 | 0.0032246 | 0.0032019 | 0.0031682 | 0.0031238 | 0.0030692 | 0.0030049 | 0.0029315 | 0.0028499 | 0.0027608 | 0.0026651 | 0.0025636 | 0.0024573 | 0.0023471 | 0.002234 | 0.0021188 | 0.0020025 | 0.0018859 | 0.0017698 | 0.001655 | 0.0015422 | 0.0014321 | 0.0013251 | 0.0012218 | 0.0011226 | 0.0010278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With | 0.8 | confidence | [117 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00093767 | 0.00085245 | 0.00077224 | 0.00069712 | 0.00062709 | 0.0005621 | 0.00050208 | 0.00044688 | 0.00039635 | 0.0003503 | 0.00030851 | 0.00027074 | 0.00023676 | 0.00020632 | 0.00017916 | 0.00015502 | 0.00013367 | 0.00011485 | 9.8329e-05 | 8.3891e-05 | 7.132e-05 | 6.042e-05 | 5.1005e-05 | 4.2905e-05 | 3.5965e-05
|  | The lowerbound threshold is | 752.0776 | [118 empty] | 4.2905e-05 | 5.1005e-05 | 6.042e-05 | 7.132e-05 | 8.3891e-05 | 9.8329e-05 | 0.00011485 | 0.00013367 | 0.00015502 | 0.00017916 | 0.00020632 | 0.00023676 | 0.00027074 | 0.00030851 | 0.0003503 | 0.00039635 | 0.00044688 | 0.00050208 | 0.0005621 | 0.00062709 | 0.00069712 | 0.00077224 | 0.00085245 | 0.00093767 | 0.0010278 | 0.0011226 | 0.0012218 | 0.0013251 | 0.0014321 | 0.0015422 | 0.001655 | 0.0017698 | 0.0018859 | 0.0020025 | 0.0021188 | 0.002234 | 0.0023471 | 0.0024573 | 0.0025636 | 0.0026651 | 0.0027608 | 0.0028499 | 0.0029315 | 0.0030049 | 0.0030692 | 0.0031238 | 0.0031682 | 0.0032019 | 0.0032246 | 0.003236 | 0.003236 | 0.0032246 | 0.0032019 | 0.0031682 | 0.0031238 | 0.0030692 | 0.0030049 | 0.0029315 | 0.0028499 | 0.0027608 | 0.0026651 | 0.0025636 | 0.0024573 | 0.0023471 | 0.002234 | 0.0021188 | 0.0020025 | 0.0018859 | 0.0017698 | 0.001655 | 0.0015422 | 0.0014321 | 0.0013251 | 0.0012218 | 0.0011226 | 0.0010278 | 0.00093767 | 0.00085245 | 0.00077224 | 0.00069712 | 0.00062709 | 0.0005621 | 0.00050208 | 0.00044688 | 0.00039635 | 0.0003503 | 0.00030851 | 0.00027074 | 0.00023676 | 0.00020632 | 0.00017916 | 0.00015502 | 0.00013367 | 0.00011485 | 9.8329e-05 | 8.3891e-05 | 7.132e-05 | 6.042e-05 | 5.1005e-05 | 4.2905e-05 | 3.5965e-05
|  | and the upperbound threshold is | 1067.9224
|  | Between a lowerbound value of | 800 |  | Miss the pie
|  | and an upperbound value of | 1100 |  | chart? Press
|  | the range probability is | 0.75243 |  | CTRL and 6
|  | The lowerbound area covers | 0.18602 |  | to show the
|  | and the upperbound area covers | 0.061553 |  | pie chart
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Note: NORM.DIST and NORM.INV functions use the mean (i.e., the PERT expected value) which impliies probabilistic symmetry.
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on M2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on N2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on O3: You can choose different probabilities by entering a value between 1% and 99%.
Note on A13: Need more than just 10 rows to enter your estimates? Rows 14 through 103 are hidden. Unhide these rows to display 90 more rows like rows 4 through 13.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell D108, and/or choose the confidence lower and upperbound thresholds in cells D112 and D113.

## SPERT® Normal (Mixed entry)
| Statistical PERT® (SPERT®) Normal Edition Mixed entry | [14 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
|  |  | -0.5 | < Heuristics > | 1 | [10 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Min % | Min point | Minimum | Most Likely | Maximum | Max point | Max % |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns Y through HS are hidden; they are used to create Sparklines and the bell-curve ball chart
1 |  |  | 60 | 120 | 240 |  |  | 1 | 0.5 | 130 | Near certainty |  |  | 12.7279 | 162 | 150 | 94.19% | 113.6885 | 146.3115 | 143.1916 | 140.7121 | 138.5849 | 136.6745 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 6.9685e-25 | 7.5266e-24 | 7.6901e-23 | 7.4325e-22 | 6.7954e-21 | 5.8771e-20 | 4.8082e-19 | 3.7212e-18 | 2.7243e-17 | 1.8866e-16 | 1.236e-15 | 7.6593e-15 | 4.49e-14 | 2.4899e-13 | 1.3061e-12 | 6.4812e-12 | 3.0423e-11 | 1.3509e-10 | 5.6743e-10 | 2.2547e-09 | 8.4746e-09 | 3.0132e-08 | 1.0135e-07 | 3.2245e-07 | 9.705e-07 | 2.7631e-06 | 7.4417e-06 | 1.8959e-05 | 4.5691e-05 | 0.00010417 | 0.00022464 | 0.00045827 | 0.00088437 | 0.0016144 | 0.0027878 | 0.004554 | 0.0070371 | 0.010286 | 0.014223 | 0.018605 | 0.02302 | 0.026945 | 0.029834 | 0.031247 | 0.030959 | 0.029016 | 0.025726 | 0.021576 | 0.017117 | 0.012846 | 0.0091198 | 0.0061245 | 0.0038907 | 0.0023381 | 0.0013291 | 0.00071473 | 0.00036357 | 0.00017495 | 7.9636e-05 | 3.4291e-05 | 1.3967e-05 | 5.3818e-06 | 1.9616e-06 | 6.7634e-07 | 2.206e-07 | 6.8061e-08 | 1.9864e-08 | 5.4843e-09 | 1.4323e-09 | 3.5386e-10 | 8.2698e-11 | 1.8282e-11 | 3.8233e-12 | 7.5635e-13 | 1.4154e-13 | 2.5056e-14 | 4.1957e-15 | 6.6463e-16 | 9.9592e-17 | 1.4117e-17 | 1.8929e-18 | 2.401e-19 | 2.8809e-20 | 3.2699e-21 | 3.5109e-22 | 3.5659e-23 | 3.426e-24 | 3.1138e-25 | 2.6771e-26 | 2.1772e-27 | 1.675e-28 | 1.219e-29 | 8.392e-31 | 5.4651e-32 | 3.3667e-33 | 1.9619e-34 | 1.0815e-35 | 5.6397e-37 | 2.7819e-38 | 1.2981e-39 | 5.73e-41
2 |  |  | 60 | 120 | 240 |  |  | 1 | 0.5 | 130 | High confidence |  |  | 20.4853 | 419.6468 | 150 | 83.55% | 103.7471 | 156.2529 | 151.2316 | 147.2408 | 143.8171 | 140.7425 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5037e-11 | 8.7797e-11 | 2.1534e-10 | 5.1695e-10 | 1.2147e-09 | 2.7936e-09 | 6.2885e-09 | 1.3855e-08 | 2.9879e-08 | 6.3069e-08 | 1.303e-07 | 2.6349e-07 | 5.215e-07 | 1.0103e-06 | 1.9157e-06 | 3.5553e-06 | 6.4583e-06 | 1.1483e-05 | 1.9983e-05 | 3.4038e-05 | 5.6748e-05 | 9.2603e-05 | 0.00014791 | 0.00023122 | 0.0003538 | 0.00052988 | 0.00077674 | 0.0011145 | 0.0015651 | 0.0021513 | 0.0028943 | 0.0038113 | 0.0049124 | 0.0061972 | 0.0076522 | 0.0092483 | 0.01094 | 0.012667 | 0.014355 | 0.015923 | 0.017287 | 0.01837 | 0.019107 | 0.019451 | 0.019382 | 0.018903 | 0.018045 | 0.01686 | 0.015419 | 0.013801 | 0.012092 | 0.010369 | 0.008703 | 0.0071497 | 0.0057491 | 0.0045247 | 0.0034855 | 0.002628 | 0.0019395 | 0.0014009 | 0.00099046 | 0.0006854 | 0.00046423 | 0.00030776 | 0.0001997 | 0.00012683 | 7.8844e-05 | 4.7972e-05 | 2.8569e-05 | 1.6653e-05 | 9.5011e-06 | 5.3056e-06 | 2.8999e-06 | 1.5514e-06 | 8.1236e-07 | 4.1635e-07 | 2.0886e-07 | 1.0255e-07 | 4.9284e-08 | 2.3182e-08 | 1.0673e-08 | 4.8097e-09 | 2.1214e-09 | 9.1585e-10 | 3.87e-10 | 1.6006e-10 | 6.4793e-11 | 2.5672e-11 | 9.9562e-12 | 3.7792e-12 | 1.4041e-12 | 5.106e-13 | 1.8174e-13 | 6.3315e-14 | 2.159e-14 | 7.2056e-15 | 2.3539e-15 | 7.5263e-16 | 2.3554e-16 | 7.215e-17 | 2.1632e-17
3 |  |  | 60 | 120 | 240 |  |  | 1 | 0.5 | 130 | Medium-high confidence |  |  | 28.2426 | 797.6468 | 150 | 76.06% | 93.8056 | 166.1944 | 159.2716 | 153.7696 | 149.0494 | 144.8105 | 3 | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 207 | 210 | 213 | 216 | 219 | 222 | 225 | 228 | 231 | 234 | 237 | 240 | 243 | 246 | 249 | 252 | 255 | 258 | 261 | 264 | 267 | 270 | 273 | 276 | 279 | 282 | 285 | 288 | 291 | 294 | 297 | 300 | 3.5419e-07 | 5.7429e-07 | 9.2071e-07 | 1.4595e-06 | 2.2877e-06 | 3.5457e-06 | 5.4336e-06 | 8.2335e-06 | 1.2336e-05 | 1.8275e-05 | 2.677e-05 | 3.8775e-05 | 5.5531e-05 | 7.8637e-05 | 0.00011011 | 0.00015244 | 0.00020869 | 0.00028248 | 0.00037807 | 0.00050034 | 0.00065472 | 0.00084712 | 0.0010838 | 0.0013709 | 0.0017148 | 0.0021208 | 0.0025935 | 0.0031359 | 0.0037493 | 0.0044324 | 0.0051812 | 0.0059885 | 0.0068439 | 0.0077337 | 0.0086412 | 0.0095468 | 0.010429 | 0.011265 | 0.012031 | 0.012706 | 0.013267 | 0.013698 | 0.013985 | 0.014117 | 0.01409 | 0.013906 | 0.01357 | 0.013094 | 0.012492 | 0.011785 | 0.010993 | 0.010139 | 0.0092464 | 0.0083379 | 0.0074342 | 0.0065542 | 0.0057134 | 0.0049247 | 0.0041972 | 0.003537 | 0.0029473 | 0.0024283 | 0.0019782 | 0.0015935 | 0.0012692 | 0.00099957 | 0.00077838 | 0.00059933 | 0.0004563 | 0.0003435 | 0.00025568 | 0.00018818 | 0.00013695 | 9.8545e-05 | 7.0115e-05 | 4.9327e-05 | 3.4313e-05 | 2.3601e-05 | 1.6051e-05 | 1.0794e-05 | 7.1773e-06 | 4.7189e-06 | 3.0677e-06 | 1.9719e-06 | 1.2533e-06 | 7.8765e-07 | 4.8945e-07 | 3.0073e-07 | 1.8271e-07 | 1.0976e-07 | 6.5193e-08 | 3.8289e-08 | 2.2235e-08 | 1.2768e-08 | 7.2492e-09 | 4.0697e-09 | 2.2591e-09 | 1.24e-09 | 6.7294e-10 | 3.6112e-10 | 1.9161e-10
4 | -0.1 |  | 108 | 120 | 144 |  | 0.2 | 1 | 0.5 | 122 | Medium confidence |  |  | 7.2 | 51.84 | 150 | 99.99% | 112.7728 | 131.2272 | 129.4623 | 128.0597 | 126.8563 | 125.7757 | 0.6 | 96 | 96.6 | 97.2 | 97.8 | 98.4 | 99 | 99.6 | 100.2 | 100.8 | 101.4 | 102 | 102.6 | 103.2 | 103.8 | 104.4 | 105 | 105.6 | 106.2 | 106.8 | 107.4 | 108 | 108.6 | 109.2 | 109.8 | 110.4 | 111 | 111.6 | 112.2 | 112.8 | 113.4 | 114 | 114.6 | 115.2 | 115.8 | 116.4 | 117 | 117.6 | 118.2 | 118.8 | 119.4 | 120 | 120.6 | 121.2 | 121.8 | 122.4 | 123 | 123.6 | 124.2 | 124.8 | 125.4 | 126 | 126.6 | 127.2 | 127.8 | 128.4 | 129 | 129.6 | 130.2 | 130.8 | 131.4 | 132 | 132.6 | 133.2 | 133.8 | 134.4 | 135 | 135.6 | 136.2 | 136.8 | 137.4 | 138 | 138.6 | 139.2 | 139.8 | 140.4 | 141 | 141.6 | 142.2 | 142.8 | 143.4 | 144 | 144.6 | 145.2 | 145.8 | 146.4 | 147 | 147.6 | 148.2 | 148.8 | 149.4 | 150 | 150.6 | 151.2 | 151.8 | 152.4 | 153 | 153.6 | 154.2 | 154.8 | 155.4 | 156 | 8.1649e-05 | 0.00010993 | 0.00014699 | 0.00019519 | 0.00025739 | 0.00033706 | 0.00043834 | 0.0005661 | 0.00072605 | 0.00092474 | 0.0011697 | 0.0014692 | 0.0018327 | 0.0022703 | 0.0027929 | 0.003412 | 0.0041396 | 0.0049875 | 0.0059676 | 0.0070908 | 0.0083671 | 0.0098048 | 0.01141 | 0.013186 | 0.015133 | 0.017248 | 0.019522 | 0.021942 | 0.024493 | 0.02715 | 0.029888 | 0.032674 | 0.035472 | 0.038244 | 0.040947 | 0.043537 | 0.045971 | 0.048205 | 0.050198 | 0.051911 | 0.053312 | 0.054371 | 0.055068 | 0.055387 | 0.055323 | 0.054877 | 0.054057 | 0.052882 | 0.051373 | 0.049563 | 0.047485 | 0.04518 | 0.042689 | 0.040056 | 0.037325 | 0.03454 | 0.031742 | 0.028968 | 0.026254 | 0.02363 | 0.02112 | 0.018747 | 0.016525 | 0.014465 | 0.012575 | 0.010856 | 0.0093072 | 0.0079241 | 0.0066998 | 0.0056255 | 0.0046908 | 0.0038843 | 0.0031942 | 0.0026085 | 0.0021155 | 0.0017038 | 0.0013627 | 0.0010824 | 0.00085376 | 0.00066877 | 0.00052024 | 0.00040189 | 0.00030832 | 0.0002349 | 0.00017772 | 0.00013353 | 9.9634e-05 | 7.3828e-05 | 5.4327e-05 | 3.9701e-05 | 2.8811e-05 | 2.0764e-05 | 1.4861e-05 | 1.0562e-05 | 7.4552e-06 | 5.2257e-06 | 3.6376e-06 | 2.5146e-06 | 1.7262e-06 | 1.1769e-06 | 7.9676e-07
5 | -0.25 |  | 90 | 120 | 160 | 160 |  | 1 | 0.75 | 121.6667 | Medium-low confidence |  |  | 18.8114 | 353.8679 | 150 | 93.4% | 97.5589 | 145.7744 | 141.1634 | 137.4987 | 134.3547 | 131.5314 | 1.1667 | 66.6667 | 67.8333 | 69 | 70.1667 | 71.3333 | 72.5 | 73.6667 | 74.8333 | 76 | 77.1667 | 78.3333 | 79.5 | 80.6667 | 81.8333 | 83 | 84.1667 | 85.3333 | 86.5 | 87.6667 | 88.8333 | 90 | 91.1667 | 92.3333 | 93.5 | 94.6667 | 95.8333 | 97 | 98.1667 | 99.3333 | 100.5 | 101.6667 | 102.8333 | 104 | 105.1667 | 106.3333 | 107.5 | 108.6667 | 109.8333 | 111 | 112.1667 | 113.3333 | 114.5 | 115.6667 | 116.8333 | 118 | 119.1667 | 120.3333 | 121.5 | 122.6667 | 123.8333 | 125 | 126.1667 | 127.3333 | 128.5 | 129.6667 | 130.8333 | 132 | 133.1667 | 134.3333 | 135.5 | 136.6667 | 137.8333 | 139 | 140.1667 | 141.3333 | 142.5 | 143.6667 | 144.8333 | 146 | 147.1667 | 148.3333 | 149.5 | 150.6667 | 151.8333 | 153 | 154.1667 | 155.3333 | 156.5 | 157.6667 | 158.8333 | 160 | 161.1667 | 162.3333 | 163.5 | 164.6667 | 165.8333 | 167 | 168.1667 | 169.3333 | 170.5 | 171.6667 | 172.8333 | 174 | 175.1667 | 176.3333 | 177.5 | 178.6667 | 179.8333 | 181 | 182.1667 | 183.3333 | 0.00029528 | 0.0003533 | 0.00042111 | 0.00049999 | 0.00059138 | 0.00069679 | 0.00081783 | 0.00095622 | 0.0011137 | 0.0012922 | 0.0014935 | 0.0017196 | 0.0019723 | 0.0022534 | 0.0025647 | 0.0029078 | 0.0032841 | 0.0036949 | 0.0041412 | 0.0046235 | 0.0051422 | 0.0056971 | 0.0062876 | 0.0069128 | 0.0075709 | 0.0082598 | 0.0089769 | 0.0097187 | 0.010481 | 0.011261 | 0.012051 | 0.012848 | 0.013645 | 0.014435 | 0.015213 | 0.015971 | 0.016703 | 0.017401 | 0.018058 | 0.018668 | 0.019225 | 0.019723 | 0.020156 | 0.020519 | 0.020808 | 0.021021 | 0.021154 | 0.021207 | 0.021178 | 0.021067 | 0.020877 | 0.020609 | 0.020267 | 0.019853 | 0.019374 | 0.018833 | 0.018238 | 0.017593 | 0.016906 | 0.016183 | 0.015432 | 0.014659 | 0.013872 | 0.013076 | 0.012279 | 0.011486 | 0.010703 | 0.0099347 | 0.0091864 | 0.008462 | 0.0077647 | 0.0070975 | 0.0064628 | 0.0058622 | 0.005297 | 0.004768 | 0.0042753 | 0.0038188 | 0.0033979 | 0.0030118 | 0.0026594 | 0.0023392 | 0.0020496 | 0.001789 | 0.0015555 | 0.0013473 | 0.0011625 | 0.00099919 | 0.00085553 | 0.00072971 | 0.00062 | 0.00052477 | 0.00044245 | 0.00037162 | 0.00031093 | 0.00025915 | 0.00021517 | 0.00017796 | 0.00014662 | 0.00012034 | 9.8391e-05
6 |  | 40 | 40 | 120 | 200 | 200 |  | 1 | 1 | 120 | Low confidence |  |  | 53.9949 | 2915.4461 | 150 | 71.08% | 50.8028 | 189.1972 | 175.9621 | 165.4432 | 156.419 | 148.3149 | 2.6667 | -13.3333 | -10.6667 | -8 | -5.3333 | -2.6667 | 2.6645e-15 | 2.6667 | 5.3333 | 8 | 10.6667 | 13.3333 | 16 | 18.6667 | 21.3333 | 24 | 26.6667 | 29.3333 | 32 | 34.6667 | 37.3333 | 40 | 42.6667 | 45.3333 | 48 | 50.6667 | 53.3333 | 56 | 58.6667 | 61.3333 | 64 | 66.6667 | 69.3333 | 72 | 74.6667 | 77.3333 | 80 | 82.6667 | 85.3333 | 88 | 90.6667 | 93.3333 | 96 | 98.6667 | 101.3333 | 104 | 106.6667 | 109.3333 | 112 | 114.6667 | 117.3333 | 120 | 122.6667 | 125.3333 | 128 | 130.6667 | 133.3333 | 136 | 138.6667 | 141.3333 | 144 | 146.6667 | 149.3333 | 152 | 154.6667 | 157.3333 | 160 | 162.6667 | 165.3333 | 168 | 170.6667 | 173.3333 | 176 | 178.6667 | 181.3333 | 184 | 186.6667 | 189.3333 | 192 | 194.6667 | 197.3333 | 200 | 202.6667 | 205.3333 | 208 | 210.6667 | 213.3333 | 216 | 218.6667 | 221.3333 | 224 | 226.6667 | 229.3333 | 232 | 234.6667 | 237.3333 | 240 | 242.6667 | 245.3333 | 248 | 250.6667 | 253.3333 | 0.0003503 | 0.00039525 | 0.00044489 | 0.00049954 | 0.00055953 | 0.0006252 | 0.00069688 | 0.00077489 | 0.00085953 | 0.00095109 | 0.0010498 | 0.001156 | 0.0012698 | 0.0013915 | 0.001521 | 0.0016586 | 0.0018042 | 0.0019578 | 0.0021193 | 0.0022886 | 0.0024653 | 0.0026493 | 0.00284 | 0.003037 | 0.0032398 | 0.0034477 | 0.00366 | 0.0038759 | 0.0040946 | 0.004315 | 0.0045363 | 0.0047572 | 0.0049768 | 0.0051939 | 0.0054071 | 0.0056155 | 0.0058176 | 0.0060124 | 0.0061985 | 0.0063749 | 0.0065402 | 0.0066935 | 0.0068338 | 0.0069599 | 0.0070712 | 0.0071667 | 0.0072457 | 0.0073079 | 0.0073526 | 0.0073795 | 0.0073885 | 0.0073795 | 0.0073526 | 0.0073079 | 0.0072457 | 0.0071667 | 0.0070712 | 0.0069599 | 0.0068338 | 0.0066935 | 0.0065402 | 0.0063749 | 0.0061985 | 0.0060124 | 0.0058176 | 0.0056155 | 0.0054071 | 0.0051939 | 0.0049768 | 0.0047572 | 0.0045363 | 0.004315 | 0.0040946 | 0.0038759 | 0.00366 | 0.0034477 | 0.0032398 | 0.003037 | 0.00284 | 0.0026493 | 0.0024653 | 0.0022886 | 0.0021193 | 0.0019578 | 0.0018042 | 0.0016586 | 0.001521 | 0.0013915 | 0.0012698 | 0.001156 | 0.0010498 | 0.00095109 | 0.00085953 | 0.00077489 | 0.00069688 | 0.0006252 | 0.00055953 | 0.00049954 | 0.00044489 | 0.00039525 | 0.0003503
7 |  | 80 | 80 | 120 | 210 |  | 0.75 | 1 | 0.44444 | 128.3333 | Guesstimate |  |  | 52.8062 | 2788.5 | 150 | 65.92% | 60.6594 | 196.0073 | 183.0635 | 172.7762 | 163.9506 | 156.025 | 2.1667 | 36.6667 | 38.8333 | 41 | 43.1667 | 45.3333 | 47.5 | 49.6667 | 51.8333 | 54 | 56.1667 | 58.3333 | 60.5 | 62.6667 | 64.8333 | 67 | 69.1667 | 71.3333 | 73.5 | 75.6667 | 77.8333 | 80 | 82.1667 | 84.3333 | 86.5 | 88.6667 | 90.8333 | 93 | 95.1667 | 97.3333 | 99.5 | 101.6667 | 103.8333 | 106 | 108.1667 | 110.3333 | 112.5 | 114.6667 | 116.8333 | 119 | 121.1667 | 123.3333 | 125.5 | 127.6667 | 129.8333 | 132 | 134.1667 | 136.3333 | 138.5 | 140.6667 | 142.8333 | 145 | 147.1667 | 149.3333 | 151.5 | 153.6667 | 155.8333 | 158 | 160.1667 | 162.3333 | 164.5 | 166.6667 | 168.8333 | 171 | 173.1667 | 175.3333 | 177.5 | 179.6667 | 181.8333 | 184 | 186.1667 | 188.3333 | 190.5 | 192.6667 | 194.8333 | 197 | 199.1667 | 201.3333 | 203.5 | 205.6667 | 207.8333 | 210 | 212.1667 | 214.3333 | 216.5 | 218.6667 | 220.8333 | 223 | 225.1667 | 227.3333 | 229.5 | 231.6667 | 233.8333 | 236 | 238.1667 | 240.3333 | 242.5 | 244.6667 | 246.8333 | 249 | 251.1667 | 253.3333 | 0.0016745 | 0.0017966 | 0.0019243 | 0.0020577 | 0.0021967 | 0.002341 | 0.0024907 | 0.0026454 | 0.0028051 | 0.0029694 | 0.003138 | 0.0033106 | 0.0034868 | 0.0036663 | 0.0038485 | 0.0040329 | 0.0042191 | 0.0044064 | 0.0045943 | 0.0047822 | 0.0049694 | 0.0051553 | 0.005339 | 0.0055201 | 0.0056977 | 0.0058711 | 0.0060396 | 0.0062024 | 0.006359 | 0.0065086 | 0.0066504 | 0.0067839 | 0.0069085 | 0.0070235 | 0.0071284 | 0.0072227 | 0.007306 | 0.0073778 | 0.0074377 | 0.0074856 | 0.007521 | 0.007544 | 0.0075542 | 0.0075518 | 0.0075366 | 0.0075089 | 0.0074686 | 0.0074161 | 0.0073516 | 0.0072753 | 0.0071878 | 0.0070893 | 0.0069804 | 0.0068617 | 0.0067336 | 0.0065968 | 0.0064519 | 0.0062996 | 0.0061405 | 0.0059754 | 0.0058049 | 0.0056298 | 0.0054508 | 0.0052686 | 0.005084 | 0.0048976 | 0.00471 | 0.004522 | 0.0043343 | 0.0041473 | 0.0039617 | 0.0037781 | 0.0035969 | 0.0034186 | 0.0032438 | 0.0030726 | 0.0029056 | 0.0027431 | 0.0025853 | 0.0024325 | 0.0022849 | 0.0021426 | 0.0020058 | 0.0018745 | 0.0017489 | 0.001629 | 0.0015148 | 0.0014062 | 0.0013032 | 0.0012057 | 0.0011136 | 0.0010268 | 0.00094519 | 0.0008686 | 0.00079688 | 0.00072985 | 0.00066733 | 0.00060915 | 0.0005551 | 0.00050499 | 0.00045864
8 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
11 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
12 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
13 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
14 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
15 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
17 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
18 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
23 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
24 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
25 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
26 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
27 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
28 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
29 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
30 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
31 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
32 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
33 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
34 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
35 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
36 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
37 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
38 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
39 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
40 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
41 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
42 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
43 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
44 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
45 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
46 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
47 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
48 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
49 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
50 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
51 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
52 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
53 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
54 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
55 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
56 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
57 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
58 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
59 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
60 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
61 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
62 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
63 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
64 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
65 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
66 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
67 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
68 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
69 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
70 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
71 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
72 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
73 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
74 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
75 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
76 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
77 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
78 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
79 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
80 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
81 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
82 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
83 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
84 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
85 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
86 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
87 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
88 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
89 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
90 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
91 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
92 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
93 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
94 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
95 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
96 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
97 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
98 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
99 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
100 | [125 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 498 | 840 | 1434 |  |  |  |  | 882 |  |  |  | 86.5387 | 7488.9476 | 1050 | 97.39% | 633.0351 | 1130.9649 | 1083.3462 | 1045.5004 | 1013.032 | 983.8744 | 622.3839 | 627.5248 | 632.6657 | 637.8066 | 642.9475 | 648.0884 | 653.2294 | 658.3703 | 663.5112 | 668.6521 | 673.793 | 678.9339 | 684.0748 | 689.2158 | 694.3567 | 699.4976 | 704.6385 | 709.7794 | 714.9203 | 720.0612 | 725.2021 | 730.3431 | 735.484 | 740.6249 | 745.7658 | 750.9067 | 756.0476 | 761.1885 | 766.3295 | 771.4704 | 776.6113 | 781.7522 | 786.8931 | 792.034 | 797.1749 | 802.3158 | 807.4568 | 812.5977 | 817.7386 | 822.8795 | 828.0204 | 833.1613 | 838.3022 | 843.4432 | 848.5841 | 853.725 | 858.8659 | 864.0068 | 869.1477 | 874.2886 | 879.4295 | 884.5705 | 889.7114 | 894.8523 | 899.9932 | 905.1341 | 910.275 | 915.4159 | 920.5568 | 925.6978 | 930.8387 | 935.9796 | 941.1205 | 946.2614 | 951.4023 | 956.5432 | 961.6842 | 966.8251 | 971.966 | 977.1069 | 982.2478 | 987.3887 | 992.5296 | 997.6705 | 1002.8115 | 1007.9524 | 1013.0933 | 1018.2342 | 1023.3751 | 1028.516 | 1033.6569 | 1038.7979 | 1043.9388 | 1049.0797 | 1054.2206 | 1059.3615 | 1064.5024 | 1069.6433 | 1074.7842 | 1079.9252 | 1085.0661 | 1090.207 | 1095.3479 | 1100.4888 | 1105.6297 | 1110.7706 | 1115.9116 | 1121.0525 | 1126.1934 | 1131.3343 | 1136.4752 | 1141.6161 | 6.1095e-05 | 7.2629e-05 | 8.6035e-05 | 0.00010156 | 0.00011946 | 0.00014002 | 0.00016354 | 0.00019034 | 0.00022075 | 0.00025511 | 0.00029379 | 0.00033714 | 0.00038552 | 0.0004393 | 0.00049881 | 0.00056439 | 0.00063634 | 0.00071494 | 0.00080041 | 0.00089294 | 0.00099267 | 0.0010996 | 0.0012138 | 0.0013352 | 0.0014635 | 0.0015985 | 0.0017398 | 0.0018869 | 0.0020392 | 0.0021961 | 0.0023567 | 0.0025201 | 0.0026854 | 0.0028515 | 0.0030171 | 0.0031811 | 0.0033422 | 0.0034991 | 0.0036505 | 0.003795 | 0.0039313 | 0.0040582 | 0.0041744 | 0.0042788 | 0.0043704 | 0.0044482 | 0.0045114 | 0.0045594 | 0.0045917 | 0.004608 | 0.004608 | 0.0045917 | 0.0045594 | 0.0045114 | 0.0044482 | 0.0043704 | 0.0042788 | 0.0041744 | 0.0040582 | 0.0039313 | 0.003795 | 0.0036505 | 0.0034991 | 0.0033422 | 0.0031811 | 0.0030171 | 0.0028515 | 0.0026854 | 0.0025201 | 0.0023567 | 0.0021961 | 0.0020392 | 0.0018869 | 0.0017398 | 0.0015985 | 0.0014635 | 0.0013352 | 0.0012138 | 0.0010996 | 0.00099267 | 0.00089294 | 0.00080041 | 0.00071494 | 0.00063634 | 0.00056439 | 0.00049881 | 0.0004393 | 0.00038552 | 0.00033714 | 0.00029379 | 0.00025511 | 0.00022075 | 0.00019034 | 0.00016354 | 0.00014002 | 0.00011946 | 0.00010156 | 8.6035e-05 | 7.2629e-05 | 6.1095e-05 | 5.1212e-05
|  |  | Do not show currency formatting | [9 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 91.36% | 771.0962 | 992.9038 | 971.6916 | 954.8328 | 940.3695 | 927.3809 | [102 empty] | 6.1095e-05 | 7.2629e-05 | 8.6035e-05 | 0.00010156 | 0.00011946 | 0.00014002 | 0.00016354 | 0.00019034 | 0.00022075 | 0.00025511 | 0.00029379 | 0.00033714 | 0.00038552 | 0.0004393 | 0.00049881 | 0.00056439 | 0.00063634 | 0.00071494 | 0.00080041 | 0.00089294 | 0.00099267 | 0.0010996 | 0.0012138 | 0.0013352 | 0.0014635 | 0.0015985 | 0.0017398 | 0.0018869 | 0.0020392 | 0.0021961 | 0.0023567 | 0.0025201 | 0.0026854 | 0.0028515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[126 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0030171 | 0.0031811 | 0.0033422 | 0.0034991 | 0.0036505 | 0.003795 | 0.0039313 | 0.0040582 | 0.0041744 | 0.0042788 | 0.0043704 | 0.0044482 | 0.0045114 | 0.0045594 | 0.0045917 | 0.004608 | 0.004608 | 0.0045917 | 0.0045594 | 0.0045114 | 0.0044482 | 0.0043704 | 0.0042788 | 0.0041744 | 0.0040582 | 0.0039313 | 0.003795 | 0.0036505 | 0.0034991 | 0.0033422 | 0.0031811 | 0.0030171 | 0.0028515 | 0.0026854 | 0.0025201 | 0.0023567 | 0.0021961 | 0.0020392 | 0.0018869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | With | 0.8 | confidence | [119 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0017398 | 0.0015985 | 0.0014635 | 0.0013352 | 0.0012138 | 0.0010996 | 0.00099267 | 0.00089294 | 0.00080041 | 0.00071494 | 0.00063634 | 0.00056439 | 0.00049881 | 0.0004393 | 0.00038552 | 0.00033714 | 0.00029379 | 0.00025511 | 0.00022075 | 0.00019034 | 0.00016354 | 0.00014002 | 0.00011946 | 0.00010156 | 8.6035e-05 | 7.2629e-05 | 6.1095e-05 | 5.1212e-05
|  |  |  | The lowerbound threshold is | 771.0962 | [120 empty] | 6.1095e-05 | 7.2629e-05 | 8.6035e-05 | 0.00010156 | 0.00011946 | 0.00014002 | 0.00016354 | 0.00019034 | 0.00022075 | 0.00025511 | 0.00029379 | 0.00033714 | 0.00038552 | 0.0004393 | 0.00049881 | 0.00056439 | 0.00063634 | 0.00071494 | 0.00080041 | 0.00089294 | 0.00099267 | 0.0010996 | 0.0012138 | 0.0013352 | 0.0014635 | 0.0015985 | 0.0017398 | 0.0018869 | 0.0020392 | 0.0021961 | 0.0023567 | 0.0025201 | 0.0026854 | 0.0028515 | 0.0030171 | 0.0031811 | 0.0033422 | 0.0034991 | 0.0036505 | 0.003795 | 0.0039313 | 0.0040582 | 0.0041744 | 0.0042788 | 0.0043704 | 0.0044482 | 0.0045114 | 0.0045594 | 0.0045917 | 0.004608 | 0.004608 | 0.0045917 | 0.0045594 | 0.0045114 | 0.0044482 | 0.0043704 | 0.0042788 | 0.0041744 | 0.0040582 | 0.0039313 | 0.003795 | 0.0036505 | 0.0034991 | 0.0033422 | 0.0031811 | 0.0030171 | 0.0028515 | 0.0026854 | 0.0025201 | 0.0023567 | 0.0021961 | 0.0020392 | 0.0018869 | 0.0017398 | 0.0015985 | 0.0014635 | 0.0013352 | 0.0012138 | 0.0010996 | 0.00099267 | 0.00089294 | 0.00080041 | 0.00071494 | 0.00063634 | 0.00056439 | 0.00049881 | 0.0004393 | 0.00038552 | 0.00033714 | 0.00029379 | 0.00025511 | 0.00022075 | 0.00019034 | 0.00016354 | 0.00014002 | 0.00011946 | 0.00010156 | 8.6035e-05 | 7.2629e-05 | 6.1095e-05 | 5.1212e-05
|  |  |  | and the upperbound threshold is | 992.9038
|  |  |  | Between a lowerbound value of | 800 |  | Miss the pie
|  |  |  | and an upperbound value of | 1000 |  | chart? Press
|  |  |  | the range probability is | 0.74197 |  | CTRL and 6
|  |  |  | The lowerbound area covers | 0.17168 |  | to show the
|  |  |  | and the upperbound area covers | 0.086354 |  | pie chart
To use this template:
1) Create a 3-point estimate under the Minimum, Most Likely, and Maximum columns
2) Render a subjective judgment about how likely the Most Likely outcome is, under the Most Likely Confidence column
3) Examine the SPERT probabilistic estimates for various confidence levels
Note: NORM.DIST and NORM.INV functions use the mean (i.e., the PERT expected value) which impliies probabilistic symmetry.
Optionally:
Enter any desired estimate under the Planning Estimate column to find the SPERT probability for the planning estimate
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on Q2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on R2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: Optionally, choose a minimum point-estimate for a single uncertainty by selecting a dropdown value in this column for any row. The percentage you choose will reduce the row's Most Likely point-estimate, and it will override the minimum point-estimate calculated by the heuristic in cell D2.
Note on C3: Optionally, manually enter a minimum point-estimate for a single uncertainty by entering a specific value in this column for any row. The value you enter will override the row's calculated, mininum point-estimate using percentage adjustments.
Note on D3: Use a simple heuristic to quickly create MINIMUM point-estimates for all rows. Do this by selecting a percentage in cell D2. Minimum point-estimates are automatically created for you by taking the Most Likely point-estimate in column E and reducing it by the percentage value specified in cell D2. Optionally, choose a row-speciific heuristic by selecting a percentage in column B, or enter a specific minimum point-estimate in column C. (If you need to modify the dropdown choices in cell D2 or column B, you can do that in the Vlookups worksheet).
Note on E3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on F3: Use a simple heuristic to quickly create MAXIMUM point-estimates for all rows. Do this by selecting a percentage in cell F2. Maximum point-estimates are automatically created for you by taking the Most Likely point-estimate in column E and increasing it by the percentage value specified in cell F2. Optionally, choose a row-speciific heuristic by selecting a percentage in column H, or enter a specific minimum point-estimate in column G. (If you need to modify the dropdown choices in cell F2 or column H, you can do that in the Vlookups worksheet).
Note on G3: Optionally, manually enter a maximum point-estimate for a single uncertainty by entering a specific value in this column for any row. The value you enter will override the row's calculated, maximum point-estimate using percentage adjustments.
Note on H3: Optionally, choose a maximum point-estimate for a single uncertainty by selecting a dropdown value in this column for any row. The percentage you choose will increase the row's Most Likely point-estimate, and it will override the maximum point-estimate calculated by the heuristic in cell F2.
Note on I3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on J3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on K3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on L3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on M3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on O3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on S3: You can choose different probabilities by entering a value between 1% and 99%.
Note on A13: Need more than just 10 rows to enter your estimates? Rows 14 through 103 are hidden. Unhide these rows to display 90 more rows like rows 4 through 13.
After you finish entering your estimates above, use this area to calculate the probability of all uncertainties together. This is especially useful for creating a forecast for an entire project, for example.
Choose the confidence you want for the confidence interval in cell F108, and/or choose the confidence lower and upperbound thresholds in cells F112 and F113.

## SPERT® Normal Charts
| Statistical PERT® (SPERT®) Normal Edition Normal Distribution Charts | [10 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[12 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 180 | 1 | 1 | 120 | Medium confidence |  |  | 24 | 576 | 150 | 89.44% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856 | 2 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104 | 106 | 108 | 110 | 112 | 114 | 116 | 118 | 120 | 122 | 124 | 126 | 128 | 130 | 132 | 134 | 136 | 138 | 140 | 142 | 144 | 146 | 148 | 150 | 152 | 154 | 156 | 158 | 160 | 162 | 164 | 166 | 168 | 170 | 172 | 174 | 176 | 178 | 180 | 182 | 184 | 186 | 188 | 190 | 192 | 194 | 196 | 198 | 200 | 202 | 204 | 206 | 208 | 210 | 212 | 214 | 216 | 218 | 220 | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
| 60 | 120 | 180 |  |  | 120 |  |  | 24 |  | 576 | 150 | 89.44% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  | 1000 | 100% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
[122 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | With a confidence interval of | 0.8 | [118 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | the lowerbound threshold is | 89.2428 | [118 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | and the upperbound threshold is | 150.7572 | [118 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | Between a lowerbound value of | 89 |  | Miss the pie
|  | and an upperbound value of | 151 |  | chart? Press
|  | the range probability is | 0.80353 |  | CTRL and 6
|  | The lowerbound area covers | 0.098236 |  | to show the
|  | and the upperbound area covers | 0.098236 |  | pie chart
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on M2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on N2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on O3: You can choose different probabilities by entering a value between 1% and 99%.

## SPERT® MC Simulation
| Statistical PERT® (SPERT®) Normal Edition Monte Carlo Simulation | [12 empty] | Show Left-Side Area |  | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
[14 empty] | Planning Estimate | SPERT Probability | SPERT Probabilistic Estimates | [5 empty] | This section is only to build Line Sparklines to show the bell-shaped curve for each row, and the summary bell-curve chart.
ID | Minimum | Most Likely | Maximum |  |  | PERT Mean | Most Likely Confidence | Curve | Your SD | SPERT SD | SPERT Var | Rand() | Trial Outcome |  |  | 0.1 | 0.9 | 0.85 | 0.8 | 0.75 | 0.7 | x-axis increments (magenta shows the increment, the next 101 columns are the x-axis values for the Line Sparkline column and summary bell-curve chart) | [101 empty] | These are the y-axis values with which the bell-shaped curve is built (used only for the Line SparkLine column) | [100 empty] | ← Columns U through HO are hidden; they are used to create Sparklines and the bell-curve bar chart
1 | 60 | 120 | 180 | 1 | 1 | 120 | Medium confidence |  |  | 24 | 576 | 0.74536 | 135.8392 | 100 | 20.23% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856 | 2 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94 | 96 | 98 | 100 | 102 | 104 | 106 | 108 | 110 | 112 | 114 | 116 | 118 | 120 | 122 | 124 | 126 | 128 | 130 | 132 | 134 | 136 | 138 | 140 | 142 | 144 | 146 | 148 | 150 | 152 | 154 | 156 | 158 | 160 | 162 | 164 | 166 | 168 | 170 | 172 | 174 | 176 | 178 | 180 | 182 | 184 | 186 | 188 | 190 | 192 | 194 | 196 | 198 | 200 | 202 | 204 | 206 | 208 | 210 | 212 | 214 | 216 | 218 | 220 | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
| 60 | 120 | 180 |  |  | 120 |  |  | 24 |  | 576 |  |  | 100 | 20.23% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
| Do not show currency formatting | [7 empty] | Whole project or portfolio planning estimate |  |  |  |  | 1000 | 100% | 89.2428 | 150.7572 | 144.8744 | 140.1989 | 136.1878 | 132.5856
[124 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | SPERT Monte Carlo Simulation Results | [107 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Press F9 to re-simulate 10,000 trials | [14 empty] | 9.91% | 89.82% | 84.78% | 79.85% | 74.52% | 69.33% | [102 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
[124 empty] | 2.8235e-06 | 3.9817e-06 | 5.5763e-06 | 7.7553e-06 | 1.0711e-05 | 1.4691e-05 | 2.0011e-05 | 2.7069e-05 | 3.6362e-05 | 4.8507e-05 | 6.4262e-05 | 8.4544e-05 | 0.00011046 | 0.00014332 | 0.00018466 | 0.00023629 | 0.00030025 | 0.0003789 | 0.00047483 | 0.00059094 | 0.00073035 | 0.00089639 | 0.0010926 | 0.0013225 | 0.0015897 | 0.0018977 | 0.0022496 | 0.0026484 | 0.0030963 | 0.0035949 | 0.0041449 | 0.0047459 | 0.0053966 | 0.0060939 | 0.0068338 | 0.0076104 | 0.0084166 | 0.0092438 | 0.010082 | 0.01092 | 0.011746 | 0.012547 | 0.01331 | 0.014022 | 0.014669 | 0.015241 | 0.015724 | 0.016111 | 0.016393 | 0.016565 | 0.016623 | 0.016565 | 0.016393 | 0.016111 | 0.015724 | 0.015241 | 0.014669 | 0.014022 | 0.01331 | 0.012547 | 0.011746 | 0.01092 | 0.010082 | 0.0092438 | 0.0084166 | 0.0076104 | 0.0068338 | 0.0060939 | 0.0053966 | 0.0047459 | 0.0041449 | 0.0035949 | 0.0030963 | 0.0026484 | 0.0022496 | 0.0018977 | 0.0015897 | 0.0013225 | 0.0010926 | 0.00089639 | 0.00073035 | 0.00059094 | 0.00047483 | 0.0003789 | 0.00030025 | 0.00023629 | 0.00018466 | 0.00014332 | 0.00011046 | 8.4544e-05 | 6.4262e-05 | 4.8507e-05 | 3.6362e-05 | 2.7069e-05 | 2.0011e-05 | 1.4691e-05 | 1.0711e-05 | 7.7553e-06 | 5.5763e-06 | 3.9817e-06 | 2.8235e-06
|  | Planning Estimate | 100
|  | SPERT Simulated Probability | 20.45%
|  | Minimum | 34.8571
|  | Maximum | 225.0149
|  | Mean | 120.0563
|  | With a confidence interval of | 0.8
|  | the lowerbound threshold is | 89.2428
|  | and the upperbound threshold is | 150.7572
|  | Between a lowerbound value of | 89
|  | and an upperbound value of | 151
|  | the range probability is | 0.80353
|  | The lowerbound area covers | 0.098236
|  | and the upperbound area covers | 0.098236
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Trial | Result
135.8392
1 | 114.8673
2 | 108.0338
3 | 95.1501
4 | 150.967
5 | 150.475
6 | 146.0533
7 | 132.9112
8 | 74.9854
9 | 112.3278
10 | 114.0442
11 | 106.456
12 | 124.7167
13 | 141.2511
14 | 92.7313
15 | 123.2488
16 | 116.1717
17 | 116.9634
18 | 99.1284
19 | 117.2611
20 | 162.4389
21 | 126.8659
22 | 118.3308
23 | 142.0276
24 | 109.11
25 | 86.2117
26 | 108.5298
27 | 119.8176
28 | 89.4244
29 | 160.755
30 | 83.2119
31 | 106.3588
32 | 96.6046
33 | 159.0084
34 | 169.0724
35 | 119.7144
36 | 144.158
37 | 105.429
38 | 80.7774
39 | 135.6378
40 | 89.3225
41 | 118.518
42 | 127.5032
43 | 109.4366
44 | 80.9848
45 | 125.2997
46 | 85.5823
47 | 83.0616
48 | 45.0557
49 | 111.9197
50 | 121.0842
51 | 125.5793
52 | 89.3489
53 | 118.1275
54 | 154.311
55 | 92.6031
56 | 77.5984
57 | 134.8849
58 | 147.4785
59 | 132.5717
60 | 164.7239
61 | 105.5277
62 | 115.0891
63 | 104.581
64 | 84.316
65 | 95.1822
66 | 108.4504
67 | 83.7861
68 | 112.5078
69 | 96.7308
70 | 150.2045
71 | 111.1733
72 | 136.4143
73 | 137.1984
74 | 114.4623
75 | 65.8193
76 | 128.6476
77 | 144.2117
78 | 125.9829
79 | 103.3895
80 | 127.7397
81 | 119.6238
82 | 119.0673
83 | 129.0639
84 | 116.8005
85 | 136.3002
86 | 121.6425
87 | 128.0582
88 | 90.4455
89 | 94.8234
90 | 129.0177
91 | 117.767
92 | 99.6211
93 | 105.3133
94 | 78.4238
95 | 100.2516
96 | 84.5994
97 | 88.8817
98 | 127.7051
99 | 121.9447
100 | 123.4344
101 | 115.938
102 | 88.5589
103 | 119.1716
104 | 120.2905
105 | 96.1431
106 | 131.4421
107 | 120.4282
108 | 104.607
109 | 126.8121
110 | 80.9505
111 | 145.6469
112 | 124.6281
113 | 116.2724
114 | 118.4451
115 | 164.6431
116 | 95.8801
117 | 115.9455
118 | 139.5752
119 | 138.5875
120 | 61.8536
121 | 100.3148
122 | 120.9003
123 | 98.6319
124 | 138.05
125 | 123.3076
126 | 118.7275
127 | 116.6254
128 | 107.98
129 | 124.5717
130 | 120.7528
131 | 122.8232
132 | 160.6527
133 | 92.2583
134 | 134.0992
135 | 109.8344
136 | 140.1158
137 | 136.8071
138 | 131.2291
139 | 128.2943
140 | 94.9273
141 | 139.3034
142 | 113.1041
143 | 131.293
144 | 96.2944
145 | 83.6823
146 | 122.1493
147 | 62.2818
148 | 69.7635
149 | 88.9008
150 | 92.8606
151 | 88.6414
152 | 80.8358
153 | 93.2018
154 | 142.1235
155 | 100.0845
156 | 116.0889
157 | 123.2184
158 | 125.0485
159 | 141.9412
160 | 94.2286
161 | 122.1473
162 | 112.405
163 | 119.0672
164 | 94.7715
165 | 149.9984
166 | 129.325
167 | 117.3893
168 | 112.7522
169 | 107.1932
170 | 149.6708
171 | 93.598
172 | 128.2449
173 | 139.1326
174 | 106.7383
175 | 157.3825
176 | 83.5659
177 | 149.6762
178 | 118.8337
179 | 140.5186
180 | 113.711
181 | 104.072
182 | 89.3332
183 | 118.422
184 | 137.0212
185 | 90.6097
186 | 90.408
187 | 97.6999
188 | 123.2566
189 | 97.7295
190 | 123.5796
191 | 118.0782
192 | 122.2415
193 | 126.8553
194 | 132.1773
195 | 118.0521
196 | 103.9625
197 | 109.6787
198 | 97.9288
199 | 115.3819
200 | 159.0113
201 | 136.4082
202 | 152.2471
203 | 101.1513
204 | 103.1865
205 | 122.1025
206 | 110.1777
207 | 106.4535
208 | 117.9162
209 | 139.7755
210 | 90.798
211 | 123.2796
212 | 156.949
213 | 112.2716
214 | 119.1658
215 | 132.2012
216 | 130.8536
217 | 109.6094
218 | 119.7923
219 | 104.9836
220 | 86.198
221 | 108.3652
222 | 119.809
223 | 110.6873
224 | 155.5725
225 | 158.7744
226 | 107.3884
227 | 112.9019
228 | 71.4276
229 | 121.0598
230 | 99.5385
231 | 87.7235
232 | 90.9571
233 | 123.0697
234 | 167.4982
235 | 85.1622
236 | 113.5146
237 | 127.6151
238 | 166.1139
239 | 116.4014
240 | 115.9478
241 | 162.5492
242 | 96.9008
243 | 92.3556
244 | 138.4738
245 | 147.0245
246 | 143.7834
247 | 112.0427
248 | 171.7547
249 | 180.3393
250 | 95.83
251 | 146.4018
252 | 127.4319
253 | 83.505
254 | 116.335
255 | 93.8503
256 | 120.3943
257 | 82.3063
258 | 178.6034
259 | 119.2922
260 | 95.1387
261 | 127.0237
262 | 111.0533
263 | 111.9207
264 | 180.9293
265 | 153.4413
266 | 171.9927
267 | 92.1927
268 | 116.9601
269 | 160.9864
270 | 122.7622
271 | 118.3473
272 | 115.5735
273 | 138.0188
274 | 53.1514
275 | 96.4449
276 | 125.7461
277 | 95.6748
278 | 91.2937
279 | 113.4203
280 | 85.0625
281 | 143.6492
282 | 102.6928
283 | 122.8628
284 | 149.7617
285 | 91.7222
286 | 110.214
287 | 99.0852
288 | 158.8925
289 | 145.4695
290 | 92.835
291 | 129.7089
292 | 122.3019
293 | 101.7256
294 | 142.0797
295 | 87.9141
296 | 139.8292
297 | 101.8083
298 | 100.4169
299 | 147.8443
300 | 112.1406
301 | 102.5491
302 | 142.7534
303 | 146.0249
304 | 135.4303
305 | 126.2359
306 | 119.2488
307 | 102.882
308 | 111.8587
309 | 84.7722
310 | 115.7771
311 | 137.7326
312 | 145.7169
313 | 145.5051
314 | 101.9871
315 | 102.9985
316 | 121.7152
317 | 148.0111
318 | 112.0441
319 | 109.1481
320 | 135.702
321 | 86.5368
322 | 106.7055
323 | 146.8638
324 | 149.9645
325 | 143.0773
326 | 112.3043
327 | 117.9484
328 | 107.5292
329 | 91.4845
330 | 97.5357
331 | 139.8812
332 | 118.2326
333 | 86.4581
334 | 168.9196
335 | 131.0098
336 | 142.7536
337 | 125.5286
338 | 140.7571
339 | 157.69
340 | 102.6038
341 | 113.6362
342 | 121.9835
343 | 108.6345
344 | 124.6025
345 | 97.396
346 | 118.0832
347 | 121.3791
348 | 133.8109
349 | 90.4206
350 | 134.5889
351 | 133.6316
352 | 121.3589
353 | 93.2167
354 | 110.7691
355 | 120.2476
356 | 105.6427
357 | 135.0767
358 | 100.759
359 | 87.1383
360 | 125.4036
361 | 94.252
362 | 134.019
363 | 104.2857
364 | 74.0051
365 | 123.2201
366 | 86.5403
367 | 102.2907
368 | 123.8186
369 | 129.9991
370 | 124.9279
371 | 126.3194
372 | 120.8186
373 | 130.5317
374 | 136.2591
375 | 172.133
376 | 105.3034
377 | 134.3896
378 | 146.004
379 | 79.5979
380 | 155.5968
381 | 142.122
382 | 139.5808
383 | 124.0276
384 | 135.352
385 | 171.7244
386 | 101.7082
387 | 94.3191
388 | 140.9359
389 | 79.9749
390 | 105.4207
391 | 122.8497
392 | 107.4954
393 | 98.1244
394 | 115.5376
395 | 103.9366
396 | 78.7281
397 | 97.4169
398 | 97.1255
399 | 81.77
400 | 120.6496
401 | 161.3215
402 | 102.1835
403 | 126.9963
404 | 121.3595
405 | 153.746
406 | 138.3441
407 | 98.1849
408 | 141.9691
409 | 126.5858
410 | 87.927
411 | 111.9095
412 | 140.5209
413 | 122.7037
414 | 153.0448
415 | 53.0032
416 | 117.709
417 | 157.3662
418 | 134.7785
419 | 155.597
420 | 120.4906
421 | 150.6615
422 | 142.8746
423 | 90.2137
424 | 136.7014
425 | 104.1166
426 | 127.0007
427 | 110.1594
428 | 122.0102
429 | 121.0682
430 | 127.3931
431 | 116.6787
432 | 134.6503
433 | 95.979
434 | 124.805
435 | 148.8979
436 | 133.2145
437 | 134.7915
438 | 167.4907
439 | 123.3839
440 | 131.2447
441 | 99.4217
442 | 128.9109
443 | 144.1118
444 | 130.9812
445 | 155.2968
446 | 99.5334
447 | 126.0902
448 | 110.1626
449 | 165.3441
450 | 88.1416
451 | 130.6414
452 | 77.5688
453 | 125.9324
454 | 116.9191
455 | 96.7686
456 | 130.5191
457 | 108.2702
458 | 129.4177
459 | 107.295
460 | 103.0322
461 | 141.6418
462 | 117.4156
463 | 94.7602
464 | 119.237
465 | 131.4578
466 | 116.649
467 | 101.7426
468 | 140.1311
469 | 114.5363
470 | 93.454
471 | 131.2535
472 | 103.1982
473 | 78.7249
474 | 79.5572
475 | 96.2627
476 | 102.1281
477 | 151.6483
478 | 126.6042
479 | 113.4221
480 | 77.7482
481 | 107.6252
482 | 123.0887
483 | 108.1697
484 | 105.2225
485 | 150.8276
486 | 151.8962
487 | 102.4582
488 | 133.6074
489 | 195.2277
490 | 87.9264
491 | 111.2477
492 | 128.9356
493 | 135.8653
494 | 130.9582
495 | 116.8182
496 | 136.8028
497 | 106.9669
498 | 143.7148
499 | 118.0375
500 | 141.6599
501 | 142.2406
502 | 140.6808
503 | 100.0983
504 | 114.6545
505 | 105.7248
506 | 85.7469
507 | 99.6144
508 | 112.2726
509 | 109.5904
510 | 141.8896
511 | 134.6908
512 | 132.3336
513 | 130.6639
514 | 86.4197
515 | 118.5771
516 | 104.9129
517 | 139.5219
518 | 104.979
519 | 95.9689
520 | 85.7775
521 | 81.6957
522 | 146.2064
523 | 120.0429
524 | 82.8702
525 | 69.1456
526 | 91.3409
527 | 148.8217
528 | 122.8465
529 | 98.4082
530 | 141.9219
531 | 138.1555
532 | 110.6602
533 | 133.1461
534 | 160.9791
535 | 98.4973
536 | 151.3926
537 | 112.7984
538 | 102.7893
539 | 124.6277
540 | 108.5705
541 | 110.5832
542 | 131.7419
543 | 125.172
544 | 138.7793
545 | 102.0617
546 | 159.3218
547 | 92.2322
548 | 112.5537
549 | 111.9498
550 | 143.0256
551 | 129.9919
552 | 85.8407
553 | 168.1821
554 | 103.0573
555 | 129.7955
556 | 128.3912
557 | 104.2995
558 | 103.7085
559 | 111.8316
560 | 133.6397
561 | 124.422
562 | 171.2015
563 | 107.7458
564 | 127.4718
565 | 61.7676
566 | 137.8101
567 | 119.2543
568 | 142.9326
569 | 154.0277
570 | 100.6781
571 | 101.3199
572 | 129.2108
573 | 127.8086
574 | 137.2771
575 | 132.7889
576 | 95.3739
577 | 147.31
578 | 157.7917
579 | 83.7998
580 | 104.5414
581 | 125.5644
582 | 119.2411
583 | 133.7779
584 | 153.3906
585 | 107.7852
586 | 90.3198
587 | 122.2168
588 | 105.6708
589 | 167.6031
590 | 138.8418
591 | 114.6282
592 | 142.6293
593 | 85.8644
594 | 88.3515
595 | 137.162
596 | 111.3966
597 | 156.487
598 | 107.6297
599 | 151.1836
600 | 136.6148
601 | 140.6925
602 | 103.2044
603 | 122.8568
604 | 141.5192
605 | 128.9342
606 | 129.1013
607 | 121.3535
608 | 109.4994
609 | 113.0367
610 | 106.5168
611 | 133.0698
612 | 110.2745
613 | 118.7828
614 | 134.6793
615 | 104.6715
616 | 136.0875
617 | 136.0508
618 | 152.3483
619 | 125.1011
620 | 125.3832
621 | 135.0049
622 | 134.0342
623 | 118.0428
624 | 158.6451
625 | 85.9003
626 | 102.6062
627 | 150.1302
628 | 77.2648
629 | 107.3233
630 | 107.6267
631 | 101.1097
632 | 114.2482
633 | 82.8921
634 | 119.5108
635 | 137.6676
636 | 190.2932
637 | 109.9142
638 | 128.8979
639 | 150.7558
640 | 104.2549
641 | 115.4813
642 | 160.6763
643 | 116.4281
644 | 101.992
645 | 144.2762
646 | 103.0113
647 | 138.5082
648 | 99.581
649 | 122.7696
650 | 94.6358
651 | 146.1739
652 | 133.3053
653 | 134.1863
654 | 97.6456
655 | 109.9027
656 | 104.0792
657 | 120.5397
658 | 91.869
659 | 107.1892
660 | 105.288
661 | 75.916
662 | 111.0229
663 | 114.1815
664 | 97.9174
665 | 129.3847
666 | 127.4899
667 | 121.8532
668 | 118.4603
669 | 138.0407
670 | 123.615
671 | 109.5114
672 | 118.9846
673 | 143.1075
674 | 121.9376
675 | 127.9617
676 | 125.3572
677 | 113.2411
678 | 107.2072
679 | 123.5466
680 | 111.0123
681 | 122.6037
682 | 101.5287
683 | 154.4241
684 | 66.8729
685 | 146.5157
686 | 103.981
687 | 129.6854
688 | 149.5821
689 | 169.8957
690 | 123.343
691 | 117.4404
692 | 117.7125
693 | 105.9217
694 | 97.7257
695 | 131.5884
696 | 86.0211
697 | 115.8954
698 | 157.6863
699 | 119.0533
700 | 151.2957
701 | 108.1953
702 | 97.8358
703 | 75.2489
704 | 99.6027
705 | 145.7428
706 | 159.0899
707 | 134.5409
708 | 93.4956
709 | 147.921
710 | 169.1533
711 | 116.271
712 | 149.0373
713 | 112.8341
714 | 124.3397
715 | 96.7593
716 | 100.1017
717 | 145.6645
718 | 142.0482
719 | 88.6424
720 | 109.9358
721 | 98.7184
722 | 162.5106
723 | 113.738
724 | 75.8643
725 | 154.798
726 | 128.1588
727 | 84.6335
728 | 97.7129
729 | 127.1646
730 | 158.8042
731 | 117.5971
732 | 122.6759
733 | 121.6177
734 | 95.9723
735 | 168.1145
736 | 138.0604
737 | 133.0569
738 | 119.1263
739 | 144.5742
740 | 135.5649
741 | 107.1766
742 | 109.3721
743 | 153.3094
744 | 153.9859
745 | 132.4772
746 | 150.6253
747 | 112.3258
748 | 143.2074
749 | 123.2895
750 | 150.8088
751 | 103.737
752 | 100.0022
753 | 154.7712
754 | 126.9941
755 | 130.5649
756 | 140.9763
757 | 159.5908
758 | 116.823
759 | 113.3809
760 | 119.1089
761 | 155.269
762 | 120.9035
763 | 145.5141
764 | 124.8725
765 | 116.1867
766 | 114.1876
767 | 105.8524
768 | 124.8646
769 | 109.8904
770 | 129.7777
771 | 149.5804
772 | 123.4978
773 | 103.5854
774 | 113.0016
775 | 136.0982
776 | 126.4925
777 | 130.9601
778 | 96.6064
779 | 96.0785
780 | 104.8842
781 | 119.9206
782 | 112.4179
783 | 103.6419
784 | 89.2783
785 | 88.2666
786 | 121.2816
787 | 114.0182
788 | 103.8525
789 | 136.9983
790 | 136.1661
791 | 106.5256
792 | 167.3803
793 | 154.263
794 | 161.8671
795 | 139.8777
796 | 71.5227
797 | 131.1853
798 | 110.1908
799 | 111.0536
800 | 155.9103
801 | 151.5391
802 | 142.5915
803 | 165.1314
804 | 68.9253
805 | 143.6315
806 | 112.8629
807 | 90.2342
808 | 96.8937
809 | 137.4038
810 | 107.2689
811 | 165.762
812 | 110.7026
813 | 118.2583
814 | 120.0929
815 | 102.6771
816 | 152.4569
817 | 103.9419
818 | 102.8626
819 | 130.675
820 | 89.2621
821 | 101.5156
822 | 128.2984
823 | 126.0656
824 | 147.2355
825 | 102.4999
826 | 125.0418
827 | 93.9366
828 | 102.2092
829 | 155.6547
830 | 146.7768
831 | 163.658
832 | 120.9518
833 | 104.5679
834 | 158.356
835 | 131.1645
836 | 123.9249
837 | 110.3848
838 | 96.3561
839 | 144.2402
840 | 101.0708
841 | 117.4511
842 | 122.8435
843 | 131.9357
844 | 109.6475
845 | 120.62
846 | 140.2733
847 | 128.2202
848 | 101.8841
849 | 91.0794
850 | 119.3711
851 | 96.6862
852 | 105.1884
853 | 76.0487
854 | 125.5883
855 | 124.385
856 | 152.1416
857 | 126.4172
858 | 139.7617
859 | 124.1548
860 | 114.0211
861 | 120.6562
862 | 133.2333
863 | 87.3963
864 | 166.8597
865 | 156.8089
866 | 112.3672
867 | 141.2584
868 | 99.4721
869 | 92.7586
870 | 103.4636
871 | 163.9286
872 | 93.0342
873 | 95.6741
874 | 139.626
875 | 124.5858
876 | 124.553
877 | 148.1626
878 | 143.6396
879 | 150.1118
880 | 153.0867
881 | 147.9524
882 | 121.1668
883 | 149.4995
884 | 71.3668
885 | 148.2323
886 | 138.5224
887 | 131.8479
888 | 134.1831
889 | 106.6067
890 | 140.709
891 | 94.6253
892 | 121.326
893 | 170.4945
894 | 144.7407
895 | 154.285
896 | 130.4621
897 | 76.8398
898 | 89.8668
899 | 159.8694
900 | 122.7456
901 | 116.5383
902 | 83.195
903 | 141.028
904 | 146.7989
905 | 143.9795
906 | 118.6385
907 | 118.8976
908 | 150.1577
909 | 128.1858
910 | 108.9694
911 | 107.4436
912 | 169.2453
913 | 97.2312
914 | 118.4425
915 | 128.6621
916 | 125.8698
917 | 142.6805
918 | 172.9193
919 | 105.857
920 | 111.7429
921 | 136.8423
922 | 100.3952
923 | 122.1884
924 | 113.8349
925 | 96.8774
926 | 98.2432
927 | 130.6093
928 | 123.8261
929 | 105.9772
930 | 119.2267
931 | 102.3407
932 | 103.988
933 | 165.9456
934 | 139.2282
935 | 89.3232
936 | 82.659
937 | 119.6452
938 | 74.9268
939 | 142.8809
940 | 156.8533
941 | 159.8843
942 | 126.3488
943 | 132.1828
944 | 167.6488
945 | 101.773
946 | 124.0465
947 | 109.7409
948 | 109.8011
949 | 129.5881
950 | 128.8072
951 | 132.3632
952 | 117.1492
953 | 144.5025
954 | 125.7924
955 | 117.1514
956 | 143.5395
957 | 100.3495
958 | 126.4355
959 | 165.9762
960 | 114.0235
961 | 121.1983
962 | 102.2894
963 | 115.9718
964 | 145.4211
965 | 116.5046
966 | 115.2732
967 | 95.7865
968 | 101.9535
969 | 152.6608
970 | 108.9264
971 | 106.2243
972 | 126.722
973 | 110.0473
974 | 76.1135
975 | 132.9504
976 | 104.8278
977 | 117.7747
978 | 96.7651
979 | 131.3067
980 | 98.2466
981 | 136.3187
982 | 109.7285
983 | 129.2567
984 | 151.5492
985 | 118.3727
986 | 135.2693
987 | 115.9196
988 | 143.1545
989 | 128.6439
990 | 162.0163
991 | 146.3222
992 | 102.726
993 | 152.1724
994 | 138.6396
995 | 123.7524
996 | 125.4841
997 | 76.6482
998 | 109.6014
999 | 109.6886
1000 | 102.5371
1001 | 126.2486
1002 | 133.7772
1003 | 159.6581
1004 | 147.6964
1005 | 144.8656
1006 | 78.7538
1007 | 111.6815
1008 | 137.5978
1009 | 70.7276
1010 | 115.6937
1011 | 111.2791
1012 | 108.1556
1013 | 144.2063
1014 | 125.3678
1015 | 148.6998
1016 | 98.1652
1017 | 125.443
1018 | 135.673
1019 | 90.369
1020 | 74.5419
1021 | 62.1778
1022 | 121.4078
1023 | 129.3518
1024 | 89.8348
1025 | 135.358
1026 | 99.7375
1027 | 103.9496
1028 | 154.3393
1029 | 71.4889
1030 | 107.2067
1031 | 88.1445
1032 | 157.4719
1033 | 92.8695
1034 | 95.371
1035 | 106.7808
1036 | 119.1331
1037 | 167.0703
1038 | 92.4339
1039 | 107.6087
1040 | 109.3101
1041 | 102.2969
1042 | 109.8807
1043 | 123.0276
1044 | 118.3125
1045 | 138.4944
1046 | 94.0124
1047 | 97.4243
1048 | 115.5273
1049 | 111.8466
1050 | 116.3941
1051 | 82.3916
1052 | 108.5592
1053 | 153.0534
1054 | 141.7397
1055 | 125.3386
1056 | 90.2289
1057 | 114.0206
1058 | 172.7936
1059 | 73.7242
1060 | 125.1571
1061 | 123.2447
1062 | 118.91
1063 | 106.2282
1064 | 124.529
1065 | 102.3486
1066 | 141.9494
1067 | 121.4646
1068 | 133.5064
1069 | 128.4681
1070 | 128.9142
1071 | 97.5252
1072 | 119.7748
1073 | 190.0987
1074 | 133.7251
1075 | 127.9995
1076 | 106.7435
1077 | 79.7634
1078 | 148.9671
1079 | 117.0687
1080 | 120.9811
1081 | 109.0115
1082 | 118.6488
1083 | 155.7389
1084 | 91.9957
1085 | 140.2449
1086 | 104.5244
1087 | 139.4448
1088 | 102.1309
1089 | 102.9361
1090 | 132.946
1091 | 121.8681
1092 | 175.813
1093 | 146.2243
1094 | 110.9607
1095 | 157.3924
1096 | 104.9419
1097 | 161.4555
1098 | 159.2371
1099 | 84.2
1100 | 125.5491
1101 | 164.1544
1102 | 146.1036
1103 | 128.9245
1104 | 140.7067
1105 | 115.6833
1106 | 143.8673
1107 | 95.0743
1108 | 108.8594
1109 | 122.8211
1110 | 79.5755
1111 | 142.4457
1112 | 127.6775
1113 | 124.5201
1114 | 93.6317
1115 | 104.5533
1116 | 94.9958
1117 | 119.4241
1118 | 90.0929
1119 | 108.7492
1120 | 124.5919
1121 | 172.0581
1122 | 126.1223
1123 | 136.3703
1124 | 123.4415
1125 | 100.8665
1126 | 136.187
1127 | 127.2553
1128 | 80.9392
1129 | 143.1505
1130 | 92.2057
1131 | 121.2819
1132 | 94.0074
1133 | 153.8128
1134 | 104.8419
1135 | 117.7703
1136 | 97.9442
1137 | 125.8446
1138 | 107.0173
1139 | 96.8191
1140 | 112.0978
1141 | 103.0171
1142 | 111.0636
1143 | 139.8394
1144 | 84.6552
1145 | 132.1798
1146 | 112.3612
1147 | 132.0977
1148 | 139.6729
1149 | 161.5983
1150 | 116.8647
1151 | 128.1692
1152 | 103.5516
1153 | 124.8927
1154 | 147.2663
1155 | 106.1519
1156 | 162.9222
1157 | 153.1469
1158 | 55.1874
1159 | 89.3458
1160 | 137.5846
1161 | 141.3936
1162 | 155.5843
1163 | 95.6462
1164 | 122.3591
1165 | 119.4261
1166 | 134.6511
1167 | 94.7683
1168 | 116.4266
1169 | 153.5061
1170 | 129.5546
1171 | 124.9217
1172 | 105.3846
1173 | 75.1419
1174 | 129.3621
1175 | 104.0478
1176 | 113.5301
1177 | 92.4451
1178 | 107.4899
1179 | 92.3436
1180 | 107.6539
1181 | 86.3337
1182 | 127.3883
1183 | 102.2408
1184 | 151.8821
1185 | 126.1221
1186 | 127.3917
1187 | 119.1227
1188 | 145.0036
1189 | 101.0806
1190 | 87.2964
1191 | 89.4691
1192 | 85.4719
1193 | 81.2759
1194 | 124.2553
1195 | 124.2659
1196 | 162.9828
1197 | 139.0368
1198 | 149.9701
1199 | 136.971
1200 | 92.3955
1201 | 74.4877
1202 | 104.2851
1203 | 126.6825
1204 | 119.9306
1205 | 99.3464
1206 | 151.4492
1207 | 108.4029
1208 | 125.7114
1209 | 111.2181
1210 | 123.6092
1211 | 158.2078
1212 | 108.4006
1213 | 139.393
1214 | 153.1368
1215 | 78.2508
1216 | 132.6532
1217 | 94.932
1218 | 129.5761
1219 | 138.2537
1220 | 93.8393
1221 | 89.4855
1222 | 98.3647
1223 | 146.3103
1224 | 104.7809
1225 | 83.626
1226 | 120.8527
1227 | 112.3464
1228 | 97.4718
1229 | 144.3552
1230 | 114.8348
1231 | 124.7096
1232 | 132.1666
1233 | 101.5394
1234 | 112.598
1235 | 129.5213
1236 | 125.8861
1237 | 94.4195
1238 | 143.9136
1239 | 150.4857
1240 | 163.4519
1241 | 122.5397
1242 | 146.0737
1243 | 120.2383
1244 | 143.757
1245 | 126.4422
1246 | 137.6854
1247 | 76.9064
1248 | 132.0207
1249 | 100.8558
1250 | 140.7245
1251 | 111.7995
1252 | 95.8852
1253 | 109.0346
1254 | 90.0132
1255 | 120.9636
1256 | 126.5962
1257 | 120.2281
1258 | 128.1933
1259 | 105.7734
1260 | 96.2663
1261 | 79.7589
1262 | 100.5899
1263 | 102.1821
1264 | 128.6695
1265 | 140.8574
1266 | 116.9512
1267 | 114.9468
1268 | 99.958
1269 | 134.448
1270 | 140.2758
1271 | 161.5943
1272 | 119.9435
1273 | 92.642
1274 | 107.5338
1275 | 100.1531
1276 | 112.5904
1277 | 140.3031
1278 | 116.551
1279 | 123.4843
1280 | 136.1757
1281 | 128.8052
1282 | 97.1749
1283 | 132.1189
1284 | 107.7864
1285 | 92.8493
1286 | 78.9459
1287 | 161.0801
1288 | 150.9234
1289 | 136.8273
1290 | 145.7931
1291 | 150.249
1292 | 117.8775
1293 | 118.4964
1294 | 153.5196
1295 | 134.6485
1296 | 146.667
1297 | 128.0363
1298 | 98.0466
1299 | 115.7926
1300 | 132.4227
1301 | 107.6267
1302 | 115.7374
1303 | 133.3466
1304 | 136.9901
1305 | 114.4557
1306 | 93.8074
1307 | 108.4655
1308 | 142.2563
1309 | 135.6595
1310 | 72.6427
1311 | 130.0728
1312 | 98.6266
1313 | 144.5009
1314 | 167.2796
1315 | 113.1792
1316 | 130.8904
1317 | 107.7429
1318 | 107.7426
1319 | 107.1514
1320 | 123.6225
1321 | 96.5737
1322 | 113.7278
1323 | 103.4323
1324 | 116.9198
1325 | 91.2755
1326 | 86.8528
1327 | 73.6478
1328 | 115.7442
1329 | 116.2989
1330 | 104.6897
1331 | 157.266
1332 | 104.4181
1333 | 151.9756
1334 | 91.6382
1335 | 148.8355
1336 | 172.6378
1337 | 106.6866
1338 | 122.694
1339 | 141.2791
1340 | 132.3336
1341 | 110.2263
1342 | 125.9408
1343 | 142.5405
1344 | 141.1192
1345 | 122.5117
1346 | 95.5765
1347 | 116.2978
1348 | 96.6927
1349 | 106.8093
1350 | 129.6328
1351 | 158.4872
1352 | 125.4657
1353 | 96.3604
1354 | 119.6287
1355 | 153.5194
1356 | 110.0188
1357 | 103.3251
1358 | 106.5119
1359 | 118.3504
1360 | 136.0129
1361 | 125.906
1362 | 133.4647
1363 | 165.5701
1364 | 102.0156
1365 | 112.8257
1366 | 145.1099
1367 | 99.1373
1368 | 120.9766
1369 | 138.3441
1370 | 108.92
1371 | 67.8152
1372 | 173.314
1373 | 117.9131
1374 | 155.7009
1375 | 124.5543
1376 | 156.2812
1377 | 115.2373
1378 | 121.3993
1379 | 135.0507
1380 | 106.963
1381 | 152.1681
1382 | 123.6995
1383 | 112.6105
1384 | 143.2981
1385 | 95.2062
1386 | 138.5507
1387 | 136.4895
1388 | 127.2636
1389 | 116.7675
1390 | 143.2017
1391 | 89.3121
1392 | 154.3722
1393 | 124.7069
1394 | 133.053
1395 | 126.4328
1396 | 172.995
1397 | 144.5357
1398 | 102.1851
1399 | 118.7282
1400 | 149.1601
1401 | 78.9122
1402 | 96.4731
1403 | 89.733
1404 | 133.4615
1405 | 123.1876
1406 | 108.3796
1407 | 77.185
1408 | 102.3737
1409 | 132.2966
1410 | 124.0994
1411 | 77.3627
1412 | 136.7375
1413 | 158.1386
1414 | 143.1114
1415 | 96.3486
1416 | 126.303
1417 | 151.8942
1418 | 132.9872
1419 | 113.0216
1420 | 158.5791
1421 | 138.2871
1422 | 112.2337
1423 | 111.6657
1424 | 85.2134
1425 | 121.1828
1426 | 142.3758
1427 | 125.6149
1428 | 143.0934
1429 | 138.3931
1430 | 120.1664
1431 | 109.6995
1432 | 159.1985
1433 | 122.0653
1434 | 95.9945
1435 | 117.7302
1436 | 128.729
1437 | 113.7258
1438 | 134.5665
1439 | 105.948
1440 | 124.1095
1441 | 98.3134
1442 | 96.5102
1443 | 138.9252
1444 | 118.165
1445 | 115.6682
1446 | 143.8985
1447 | 139.3026
1448 | 117.9253
1449 | 106.5703
1450 | 80.7226
1451 | 147.5899
1452 | 90.181
1453 | 100.921
1454 | 100.3456
1455 | 171.0521
1456 | 120.294
1457 | 134.8022
1458 | 103.994
1459 | 150.2773
1460 | 110.2666
1461 | 87.1517
1462 | 103.101
1463 | 109.8776
1464 | 121.1212
1465 | 133.7132
1466 | 89.5782
1467 | 136.3677
1468 | 136.0661
1469 | 94.7411
1470 | 124.2903
1471 | 120.5725
1472 | 108.4385
1473 | 135.3414
1474 | 144.8617
1475 | 158.6855
1476 | 113.2072
1477 | 114.5891
1478 | 123.3445
1479 | 133.7142
1480 | 102.1437
1481 | 78.4837
1482 | 152.3533
1483 | 102.9403
1484 | 115.6278
1485 | 99.1431
1486 | 178.9922
1487 | 104.3933
1488 | 110.7592
1489 | 136.6165
1490 | 85.085
1491 | 147.5466
1492 | 127.6406
1493 | 88.596
1494 | 99.3242
1495 | 104.0735
1496 | 90.1488
1497 | 99.9458
1498 | 160.4537
1499 | 105.1519
1500 | 145.0585
1501 | 78.3484
1502 | 124.1959
1503 | 76.1543
1504 | 152.8627
1505 | 78.9174
1506 | 142.0152
1507 | 126.3819
1508 | 124.3632
1509 | 152.063
1510 | 125.8841
1511 | 112.8174
1512 | 116.4944
1513 | 67.5486
1514 | 134.409
1515 | 103.9968
1516 | 106.4437
1517 | 96.3621
1518 | 97.1761
1519 | 130.7737
1520 | 85.9978
1521 | 86.7894
1522 | 134.5945
1523 | 91.7451
1524 | 89.731
1525 | 100.8612
1526 | 130.8085
1527 | 96.7663
1528 | 121.7343
1529 | 113.5218
1530 | 141.6778
1531 | 137.9791
1532 | 112.1337
1533 | 106.6142
1534 | 103.833
1535 | 98.6496
1536 | 115.539
1537 | 124.8276
1538 | 130.1449
1539 | 92.7214
1540 | 153.3363
1541 | 59.9783
1542 | 113.7702
1543 | 163.3276
1544 | 111.5239
1545 | 121.3054
1546 | 136.2214
1547 | 88.2857
1548 | 126.7305
1549 | 91.4478
1550 | 132.7171
1551 | 170.0972
1552 | 109.9364
1553 | 92.5356
1554 | 158.9941
1555 | 108.9144
1556 | 134.202
1557 | 108.6567
1558 | 101.6602
1559 | 106.4965
1560 | 66.4492
1561 | 82.7867
1562 | 115.6173
1563 | 145.8535
1564 | 119.8993
1565 | 101.018
1566 | 154.2461
1567 | 125.837
1568 | 133.8133
1569 | 95.7817
1570 | 133.872
1571 | 97.9407
1572 | 92.7173
1573 | 179.3499
1574 | 123.1256
1575 | 136.3983
1576 | 130.3513
1577 | 151.3489
1578 | 94.7642
1579 | 100.0731
1580 | 138.0602
1581 | 93.636
1582 | 93.8663
1583 | 78.1217
1584 | 115.3164
1585 | 125.819
1586 | 105.4938
1587 | 126.4675
1588 | 99.4667
1589 | 106.156
1590 | 152.166
1591 | 147.1548
1592 | 105.816
1593 | 105.6667
1594 | 155.0866
1595 | 133.2216
1596 | 83.874
1597 | 145.0075
1598 | 177.2185
1599 | 112.9746
1600 | 113.5951
1601 | 131.9924
1602 | 110.181
1603 | 103.6894
1604 | 115.5187
1605 | 109.7035
1606 | 64.7652
1607 | 121.4179
1608 | 63.0864
1609 | 147.4327
1610 | 91.9281
1611 | 167.7754
1612 | 140.7458
1613 | 149.5972
1614 | 150.3974
1615 | 117.8356
1616 | 47.3762
1617 | 123.1889
1618 | 113.8477
1619 | 106.4
1620 | 122.4471
1621 | 127.8695
1622 | 154.4641
1623 | 56.2759
1624 | 121.98
1625 | 119.0362
1626 | 159.7825
1627 | 115.2427
1628 | 130.0985
1629 | 105.2863
1630 | 113.0981
1631 | 109.1827
1632 | 100.1147
1633 | 124.6574
1634 | 114.2461
1635 | 125.5333
1636 | 125.0377
1637 | 108.7127
1638 | 125.6816
1639 | 125.173
1640 | 90.0588
1641 | 160.6138
1642 | 109.4159
1643 | 127.9419
1644 | 125.3558
1645 | 163.9473
1646 | 133.3499
1647 | 128.5635
1648 | 110.3866
1649 | 157.0893
1650 | 109.0397
1651 | 132.3314
1652 | 137.1582
1653 | 136.6409
1654 | 145.535
1655 | 87.1076
1656 | 141.1215
1657 | 148.0124
1658 | 109.3379
1659 | 127.4614
1660 | 89.1538
1661 | 125.2667
1662 | 112.0499
1663 | 146.8384
1664 | 148.0241
1665 | 83.3012
1666 | 137.6761
1667 | 88.6828
1668 | 77.7321
1669 | 74.7313
1670 | 103.472
1671 | 97.6853
1672 | 170.4719
1673 | 137.1704
1674 | 132.638
1675 | 112.4281
1676 | 110.509
1677 | 68.7147
1678 | 149.7199
1679 | 137.9741
1680 | 62.4398
1681 | 125.6123
1682 | 121.6649
1683 | 128.7695
1684 | 144.0175
1685 | 114.9703
1686 | 97.5228
1687 | 78.0943
1688 | 91.9827
1689 | 114.4342
1690 | 115.3569
1691 | 109.4028
1692 | 120.4048
1693 | 87.7758
1694 | 121.4206
1695 | 117.945
1696 | 113.13
1697 | 134.1795
1698 | 70.9627
1699 | 92.8818
1700 | 122.8453
1701 | 129.507
1702 | 141.41
1703 | 131.8528
1704 | 105.6997
1705 | 117.8188
1706 | 100.8487
1707 | 173.3206
1708 | 97.7195
1709 | 91.6284
1710 | 112.2619
1711 | 106.1283
1712 | 134.423
1713 | 138.8902
1714 | 141.8454
1715 | 120.7878
1716 | 146.7145
1717 | 113.9527
1718 | 106.6136
1719 | 135.7224
1720 | 121.3947
1721 | 102.8556
1722 | 101.8321
1723 | 172.2696
1724 | 119.2707
1725 | 122.4329
1726 | 80.7799
1727 | 88.6595
1728 | 107.8983
1729 | 127.598
1730 | 143.4879
1731 | 106.9478
1732 | 92.8434
1733 | 105.6685
1734 | 130.957
1735 | 120.9238
1736 | 139.4988
1737 | 99.818
1738 | 124.7134
1739 | 108.7977
1740 | 117.1154
1741 | 134.3187
1742 | 100.4317
1743 | 135.37
1744 | 149.2369
1745 | 145.5831
1746 | 77.3641
1747 | 149.4899
1748 | 87.1159
1749 | 111.1475
1750 | 162.6839
1751 | 127.5739
1752 | 107.1736
1753 | 141.253
1754 | 87.1613
1755 | 103.3494
1756 | 80.6297
1757 | 81.1875
1758 | 142.9515
1759 | 139.2494
1760 | 102.907
1761 | 131.7904
1762 | 147.9279
1763 | 109.2016
1764 | 149.0128
1765 | 82.7826
1766 | 79.9801
1767 | 126.6294
1768 | 114.2448
1769 | 73.4151
1770 | 121.8431
1771 | 94.8403
1772 | 145.7101
1773 | 135.5693
1774 | 93.0327
1775 | 104.4081
1776 | 150.148
1777 | 121.61
1778 | 131.922
1779 | 152.8085
1780 | 131.3364
1781 | 72.0091
1782 | 103.9026
1783 | 146.0688
1784 | 118.4916
1785 | 109.7366
1786 | 106.7815
1787 | 136.3293
1788 | 112.7263
1789 | 162.6171
1790 | 105.383
1791 | 79.188
1792 | 97.7704
1793 | 105.5446
1794 | 116.4455
1795 | 127.7877
1796 | 94.6986
1797 | 137.8373
1798 | 102.6434
1799 | 121.4875
1800 | 130.1847
1801 | 98.7566
1802 | 134.9843
1803 | 110.4324
1804 | 118.8727
1805 | 112.6202
1806 | 81.8621
1807 | 149.0998
1808 | 103.8617
1809 | 105.1503
1810 | 107.9045
1811 | 90.2202
1812 | 115.9771
1813 | 108.1977
1814 | 86.6947
1815 | 159.1951
1816 | 95.8197
1817 | 149.6832
1818 | 105.3752
1819 | 158.5558
1820 | 131.3338
1821 | 90.6228
1822 | 106.8837
1823 | 85.9336
1824 | 111.2346
1825 | 112.6045
1826 | 128.1111
1827 | 144.7027
1828 | 144.2287
1829 | 127.0129
1830 | 158.4403
1831 | 107.1813
1832 | 100.1436
1833 | 172.5681
1834 | 148.0322
1835 | 97.5782
1836 | 107.4272
1837 | 111.3168
1838 | 104.663
1839 | 68.7593
1840 | 157.8335
1841 | 88.7614
1842 | 150.7418
1843 | 73.0584
1844 | 110.8934
1845 | 98.209
1846 | 103.6088
1847 | 146.9578
1848 | 109.2196
1849 | 114.6331
1850 | 126.858
1851 | 88.8279
1852 | 141.9015
1853 | 104.6596
1854 | 137.1662
1855 | 123.7663
1856 | 70.7896
1857 | 117.7972
1858 | 112.4966
1859 | 116.4713
1860 | 111.5377
1861 | 125.6383
1862 | 95.0248
1863 | 78.7181
1864 | 147.5097
1865 | 107.2401
1866 | 78.4637
1867 | 124.6825
1868 | 105.1341
1869 | 101.7343
1870 | 130.5374
1871 | 116.758
1872 | 103.6428
1873 | 118.6541
1874 | 91.6289
1875 | 86.4229
1876 | 88.7908
1877 | 99.1018
1878 | 100.0105
1879 | 128.078
1880 | 102.2695
1881 | 165.5859
1882 | 126.8908
1883 | 118.7845
1884 | 136.1437
1885 | 163.6763
1886 | 110.6215
1887 | 111.4122
1888 | 123.6667
1889 | 127.1559
1890 | 101.5668
1891 | 128.7157
1892 | 69.3103
1893 | 158.6008
1894 | 152.6027
1895 | 143.1111
1896 | 149.668
1897 | 117.9553
1898 | 91.692
1899 | 116.2996
1900 | 102.5326
1901 | 100.0723
1902 | 100.5293
1903 | 128.0661
1904 | 119.7841
1905 | 127.5379
1906 | 123.0201
1907 | 149.5329
1908 | 119.1786
1909 | 111.3243
1910 | 141.7845
1911 | 90.2855
1912 | 111.7248
1913 | 107.7598
1914 | 127.4414
1915 | 100.821
1916 | 92.4276
1917 | 136.4742
1918 | 160.0804
1919 | 119.4427
1920 | 147.8422
1921 | 172.8044
1922 | 80.6901
1923 | 154.4563
1924 | 105.466
1925 | 89.4213
1926 | 113.8466
1927 | 129.5989
1928 | 119.2419
1929 | 118.9514
1930 | 95.8345
1931 | 158.9085
1932 | 167.3064
1933 | 97.1854
1934 | 119.3398
1935 | 88.9806
1936 | 88.4987
1937 | 119.3495
1938 | 119.3595
1939 | 139.9687
1940 | 66.3135
1941 | 106.9524
1942 | 142.444
1943 | 101.5437
1944 | 117.6006
1945 | 92.1559
1946 | 115.7111
1947 | 153.4783
1948 | 90.7779
1949 | 109.4985
1950 | 123.7123
1951 | 82.3052
1952 | 70.797
1953 | 130.0602
1954 | 130.028
1955 | 118.7706
1956 | 146.634
1957 | 111.2544
1958 | 96.3165
1959 | 158.0149
1960 | 131.2591
1961 | 100.8534
1962 | 137.2028
1963 | 149.6986
1964 | 114.7054
1965 | 125.1873
1966 | 120.1264
1967 | 107.6731
1968 | 148.7728
1969 | 91.7179
1970 | 169.1876
1971 | 113.9253
1972 | 65.4747
1973 | 134.7153
1974 | 147.7802
1975 | 71.4568
1976 | 88.008
1977 | 117.8572
1978 | 158.1738
1979 | 165.7438
1980 | 112.8081
1981 | 142.3605
1982 | 115.8979
1983 | 120.673
1984 | 128.9141
1985 | 107.0316
1986 | 136.553
1987 | 150.5524
1988 | 85.7525
1989 | 125.6905
1990 | 83.1757
1991 | 151.9001
1992 | 140.0466
1993 | 88.1028
1994 | 123.6872
1995 | 125.1578
1996 | 106.8039
1997 | 97.8315
1998 | 118.9545
1999 | 134.7584
2000 | 130.3091
2001 | 118.9861
2002 | 119.3508
2003 | 142.3228
2004 | 145.7989
2005 | 148.3482
2006 | 94.5567
2007 | 141.7556
2008 | 115.4211
2009 | 144.4583
2010 | 156.7254
2011 | 156.4363
2012 | 106.3262
2013 | 123.0258
2014 | 116.4538
2015 | 127.1184
2016 | 151.4031
2017 | 100.9095
2018 | 86.6784
2019 | 83.0255
2020 | 101.1701
2021 | 104.3887
2022 | 87.3872
2023 | 102.7102
2024 | 85.3244
2025 | 121.8654
2026 | 142.8419
2027 | 126.424
2028 | 150.6211
2029 | 101.6646
2030 | 143.0698
2031 | 119.4968
2032 | 131.5059
2033 | 130.3669
2034 | 76.8406
2035 | 109.0623
2036 | 129.8845
2037 | 145.0953
2038 | 135.9126
2039 | 117.3856
2040 | 126.5403
2041 | 116.7424
2042 | 107.0134
2043 | 154.8484
2044 | 122.2608
2045 | 99.5078
2046 | 173.3785
2047 | 138.8502
2048 | 143.2947
2049 | 141.388
2050 | 107.3111
2051 | 98.1387
2052 | 154.6578
2053 | 137.7497
2054 | 212.395
2055 | 63.1267
2056 | 126.9688
2057 | 122.898
2058 | 127.911
2059 | 98.2298
2060 | 98.5765
2061 | 123.1344
2062 | 121.1848
2063 | 101.4203
2064 | 110.342
2065 | 97.5306
2066 | 122.0918
2067 | 90.8456
2068 | 135.5668
2069 | 101.8287
2070 | 89.8819
2071 | 62.1804
2072 | 143.2565
2073 | 119.1448
2074 | 86.6133
2075 | 87.076
2076 | 129.8466
2077 | 153.2692
2078 | 103.3589
2079 | 122.4091
2080 | 123.6398
2081 | 86.4197
2082 | 135.031
2083 | 130.7478
2084 | 111.7466
2085 | 129.2981
2086 | 144.0768
2087 | 122.3025
2088 | 132.5579
2089 | 83.1038
2090 | 117.8524
2091 | 114.7824
2092 | 140.6686
2093 | 125.5787
2094 | 117.0254
2095 | 112.6709
2096 | 124.6234
2097 | 133.6021
2098 | 170.438
2099 | 127.9369
2100 | 113.2479
2101 | 131.9089
2102 | 117.2145
2103 | 126.4332
2104 | 139.0214
2105 | 135.93
2106 | 137.7222
2107 | 84.835
2108 | 131.5663
2109 | 146.7605
2110 | 133.895
2111 | 138.9041
2112 | 152.3547
2113 | 84.5221
2114 | 141.053
2115 | 136.8188
2116 | 145.0584
2117 | 118.4154
2118 | 83.0944
2119 | 159.4009
2120 | 136.6068
2121 | 135.2442
2122 | 129.1509
2123 | 173.831
2124 | 125.4488
2125 | 115.0308
2126 | 118.2902
2127 | 129.2555
2128 | 70.3188
2129 | 71.8731
2130 | 159.0317
2131 | 157.8911
2132 | 162.9181
2133 | 152.9315
2134 | 132.1136
2135 | 116.9928
2136 | 150.9149
2137 | 105.0749
2138 | 160.0489
2139 | 146.6227
2140 | 128.9271
2141 | 143.7535
2142 | 112.7764
2143 | 90.5184
2144 | 124.395
2145 | 124.1957
2146 | 102.6058
2147 | 95.0484
2148 | 121.9798
2149 | 99.3779
2150 | 85.2111
2151 | 111.5846
2152 | 125.3565
2153 | 87.261
2154 | 136.9866
2155 | 113.0884
2156 | 167.0172
2157 | 93.0595
2158 | 105.1813
2159 | 117.5228
2160 | 83.6716
2161 | 116.8251
2162 | 112.6615
2163 | 140.6074
2164 | 157.5485
2165 | 115.8438
2166 | 139.0643
2167 | 119.4034
2168 | 136.6413
2169 | 137.5164
2170 | 127.4319
2171 | 124.161
2172 | 129.0161
2173 | 105.4993
2174 | 108.7642
2175 | 118.0957
2176 | 116.6172
2177 | 160.3445
2178 | 86.9325
2179 | 99.1744
2180 | 133.3369
2181 | 131.359
2182 | 127.3461
2183 | 116.4903
2184 | 97.7903
2185 | 93.583
2186 | 111.2081
2187 | 151.9568
2188 | 116.4769
2189 | 70.4235
2190 | 115.228
2191 | 85.9658
2192 | 139.3879
2193 | 129.3743
2194 | 119.4577
2195 | 125.3587
2196 | 140.097
2197 | 131.8712
2198 | 102.5258
2199 | 126.1621
2200 | 123.7221
2201 | 113.6018
2202 | 98.4212
2203 | 78.4223
2204 | 127.5434
2205 | 120.5322
2206 | 147.6238
2207 | 121.6808
2208 | 127.2034
2209 | 124.6323
2210 | 88.9251
2211 | 105.326
2212 | 95.2665
2213 | 145.2246
2214 | 124.0459
2215 | 139.1902
2216 | 76.3763
2217 | 94.4847
2218 | 142.0939
2219 | 108.1135
2220 | 107.602
2221 | 137.4018
2222 | 101.8806
2223 | 121.835
2224 | 153.7792
2225 | 139.6166
2226 | 123.0039
2227 | 81.9547
2228 | 161.9891
2229 | 98.353
2230 | 157.6431
2231 | 94.059
2232 | 94.7803
2233 | 123.1992
2234 | 133.2993
2235 | 157.4831
2236 | 130.2255
2237 | 121.5403
2238 | 136.3678
2239 | 92.2295
2240 | 66.2566
2241 | 131.1016
2242 | 109.0535
2243 | 158.3345
2244 | 111.6837
2245 | 109.2527
2246 | 125.9796
2247 | 151.9253
2248 | 109.9569
2249 | 97.6118
2250 | 144.4684
2251 | 84.3362
2252 | 41.6332
2253 | 106.3142
2254 | 145.3711
2255 | 142.5595
2256 | 129.9705
2257 | 137.3985
2258 | 103.0972
2259 | 111.224
2260 | 137.9833
2261 | 87.992
2262 | 121.5703
2263 | 115.0563
2264 | 128.6593
2265 | 120.2367
2266 | 136.7938
2267 | 146.3479
2268 | 126.405
2269 | 120.8758
2270 | 139.8805
2271 | 78.2203
2272 | 131.591
2273 | 116.9683
2274 | 152.6188
2275 | 153.7968
2276 | 127.2151
2277 | 125.2621
2278 | 154.5817
2279 | 79.1827
2280 | 89.5358
2281 | 127.8065
2282 | 167.492
2283 | 50.0502
2284 | 141.4039
2285 | 110.9733
2286 | 124.4458
2287 | 168.7765
2288 | 102.5176
2289 | 118.4223
2290 | 113.6062
2291 | 109.5953
2292 | 125.4258
2293 | 156.5381
2294 | 145.2995
2295 | 120.7675
2296 | 107.5886
2297 | 79.9126
2298 | 103.8546
2299 | 94.0381
2300 | 77.9563
2301 | 142.4235
2302 | 134.6345
2303 | 115.1058
2304 | 84.6857
2305 | 129.2374
2306 | 131.1649
2307 | 146.9487
2308 | 155.2065
2309 | 113.7469
2310 | 112.9721
2311 | 123.2511
2312 | 123.8933
2313 | 87.9336
2314 | 106.8859
2315 | 146.4565
2316 | 129.8704
2317 | 126.1622
2318 | 151.2549
2319 | 124.7745
2320 | 76.3598
2321 | 165.4803
2322 | 136.9116
2323 | 100.3121
2324 | 135.8916
2325 | 132.3521
2326 | 131.8459
2327 | 136.8027
2328 | 130.8876
2329 | 112.0942
2330 | 131.9067
2331 | 101.5002
2332 | 114.5522
2333 | 148.7759
2334 | 143.2025
2335 | 152.4939
2336 | 130.2783
2337 | 153.886
2338 | 155.8122
2339 | 98.5034
2340 | 119.8691
2341 | 99.3781
2342 | 122.3622
2343 | 143.126
2344 | 84.1228
2345 | 106.3996
2346 | 83.9507
2347 | 141.8367
2348 | 136.9282
2349 | 138.0624
2350 | 142.7267
2351 | 111.8862
2352 | 131.7907
2353 | 132.9172
2354 | 148.3723
2355 | 103.6552
2356 | 85.3395
2357 | 120.7614
2358 | 161.8075
2359 | 114.5422
2360 | 102.5671
2361 | 66.8159
2362 | 118.8209
2363 | 104.9411
2364 | 81.6121
2365 | 152.8127
2366 | 95.8075
2367 | 112.5029
2368 | 124.3611
2369 | 116.065
2370 | 152.6958
2371 | 130.417
2372 | 117.0606
2373 | 153.1329
2374 | 139.6829
2375 | 131.956
2376 | 102.1455
2377 | 110.7178
2378 | 72.4398
2379 | 109.5468
2380 | 112.1404
2381 | 144.749
2382 | 96.5079
2383 | 70.6113
2384 | 85.7558
2385 | 130.6629
2386 | 127.8594
2387 | 150.7418
2388 | 102.0766
2389 | 86.6867
2390 | 96.9913
2391 | 131.3445
2392 | 139.0581
2393 | 105.6817
2394 | 140.5081
2395 | 112.5081
2396 | 114.9358
2397 | 106.8619
2398 | 112.1915
2399 | 117.6764
2400 | 127.2429
2401 | 89.4415
2402 | 97.5344
2403 | 144.7586
2404 | 82.3393
2405 | 150.8169
2406 | 118.8284
2407 | 101.9686
2408 | 110.8799
2409 | 129.4795
2410 | 114.7535
2411 | 133.16
2412 | 80.1638
2413 | 102.9483
2414 | 131.6034
2415 | 155.107
2416 | 151.9788
2417 | 121.8628
2418 | 142.8319
2419 | 145.4273
2420 | 96.0187
2421 | 136.1444
2422 | 148.1016
2423 | 133.6268
2424 | 138.4591
2425 | 81.2985
2426 | 137.7918
2427 | 164.8711
2428 | 104.2693
2429 | 133.1734
2430 | 136.7887
2431 | 75.333
2432 | 169.8112
2433 | 129.1678
2434 | 120.4574
2435 | 159.9745
2436 | 115.2228
2437 | 117.8262
2438 | 122.5328
2439 | 90.8938
2440 | 116.2277
2441 | 130.5773
2442 | 118.8683
2443 | 106.0575
2444 | 111.2977
2445 | 125.6045
2446 | 135.9708
2447 | 102.8162
2448 | 125.1792
2449 | 116.3289
2450 | 133.5171
2451 | 151.3416
2452 | 139.3542
2453 | 122.6559
2454 | 138.7589
2455 | 103.6994
2456 | 127.3745
2457 | 140.8949
2458 | 96.8709
2459 | 135.3917
2460 | 133.7606
2461 | 89.3454
2462 | 113.4766
2463 | 115.391
2464 | 136.0484
2465 | 135.3297
2466 | 101.3713
2467 | 114.5158
2468 | 82.5273
2469 | 127.3509
2470 | 137.749
2471 | 80.1544
2472 | 123.8681
2473 | 145.4631
2474 | 118.1352
2475 | 125.0472
2476 | 96.484
2477 | 122.8328
2478 | 77.1225
2479 | 100.3527
2480 | 101.2107
2481 | 119.3795
2482 | 143.8787
2483 | 95.3129
2484 | 129.701
2485 | 107.93
2486 | 94.2733
2487 | 89.2246
2488 | 133.5203
2489 | 152.7358
2490 | 121.131
2491 | 117.7936
2492 | 57.3783
2493 | 107.8899
2494 | 129.9636
2495 | 155.3317
2496 | 113.4812
2497 | 158.1999
2498 | 139.0613
2499 | 90.2355
2500 | 135.1775
2501 | 146.0906
2502 | 137.7271
2503 | 106.8143
2504 | 61.5103
2505 | 122.5312
2506 | 113.883
2507 | 135.0096
2508 | 136.0023
2509 | 126.698
2510 | 118.6661
2511 | 99.242
2512 | 137.8394
2513 | 111.4127
2514 | 95.1615
2515 | 164.7062
2516 | 124.9891
2517 | 119.9303
2518 | 71.9965
2519 | 83.0393
2520 | 132.7362
2521 | 165.7264
2522 | 111.977
2523 | 92.3151
2524 | 96.1356
2525 | 114.3083
2526 | 75.2932
2527 | 156.8576
2528 | 110.6449
2529 | 144.2988
2530 | 111.6377
2531 | 107.1243
2532 | 125.5403
2533 | 88.6879
2534 | 113.4789
2535 | 157.9183
2536 | 99.7444
2537 | 142.3544
2538 | 99.2342
2539 | 122.8113
2540 | 93.8415
2541 | 113.7609
2542 | 102.6396
2543 | 109.1538
2544 | 143.6381
2545 | 178.9439
2546 | 128.0955
2547 | 167.0225
2548 | 126.1283
2549 | 104.7469
2550 | 117.3143
2551 | 120.0577
2552 | 145.4095
2553 | 104.7755
2554 | 143.8027
2555 | 148.802
2556 | 81.3152
2557 | 103.4643
2558 | 147.4146
2559 | 136.0003
2560 | 63.5134
2561 | 147.5077
2562 | 152.451
2563 | 125.6331
2564 | 132.2188
2565 | 152.4391
2566 | 136.5676
2567 | 135.5991
2568 | 86.5682
2569 | 116.0945
2570 | 91.8706
2571 | 123.4537
2572 | 103.2691
2573 | 112.7591
2574 | 122.2654
2575 | 150.4875
2576 | 121.3592
2577 | 124.9969
2578 | 156.0149
2579 | 132.8834
2580 | 124.5772
2581 | 171.3267
2582 | 149.564
2583 | 133.4964
2584 | 121.7082
2585 | 174.0421
2586 | 127.9716
2587 | 130.5884
2588 | 98.0909
2589 | 156.9256
2590 | 70.1419
2591 | 137.8972
2592 | 124.1717
2593 | 117.572
2594 | 120.1205
2595 | 108.1153
2596 | 101.5123
2597 | 120.9399
2598 | 116.5576
2599 | 137.5479
2600 | 118.1521
2601 | 98.7888
2602 | 96.9736
2603 | 111.3301
2604 | 111.1703
2605 | 123.1554
2606 | 132.4985
2607 | 123.0943
2608 | 123.9759
2609 | 119.6134
2610 | 159.5587
2611 | 144.4639
2612 | 119.6382
2613 | 97.5465
2614 | 103.3231
2615 | 150.6278
2616 | 115.3351
2617 | 116.424
2618 | 119.8645
2619 | 110.9806
2620 | 106.8476
2621 | 131.179
2622 | 91.4563
2623 | 137.0903
2624 | 94.3098
2625 | 95.7781
2626 | 83.2096
2627 | 113.7042
2628 | 154.7277
2629 | 126.8825
2630 | 104.0707
2631 | 115.4045
2632 | 128.9698
2633 | 165.5453
2634 | 152.2206
2635 | 80.8084
2636 | 150.4533
2637 | 89.6372
2638 | 94.3834
2639 | 119.3149
2640 | 159.8175
2641 | 165.9189
2642 | 127.5722
2643 | 96.5871
2644 | 112.7042
2645 | 109.0664
2646 | 135.3019
2647 | 96.5617
2648 | 114.411
2649 | 120.6659
2650 | 94.6674
2651 | 96.9656
2652 | 108.0622
2653 | 99.8698
2654 | 94.5771
2655 | 148.8565
2656 | 83.6471
2657 | 96.714
2658 | 129.088
2659 | 100.5978
2660 | 83.6026
2661 | 113.3707
2662 | 72.6092
2663 | 133.4539
2664 | 109.012
2665 | 86.9551
2666 | 138.2806
2667 | 124.2456
2668 | 108.7611
2669 | 142.153
2670 | 127.1552
2671 | 124.2968
2672 | 112.9856
2673 | 108.1106
2674 | 115.7782
2675 | 137.4865
2676 | 90.5444
2677 | 113.9919
2678 | 109.2264
2679 | 105.6062
2680 | 127.3935
2681 | 100.287
2682 | 143.5879
2683 | 131.196
2684 | 154.7424
2685 | 140.4937
2686 | 84.2431
2687 | 101.0038
2688 | 144.562
2689 | 114.0608
2690 | 110.9108
2691 | 104.3527
2692 | 100.6345
2693 | 34.8571
2694 | 128.8832
2695 | 71.0787
2696 | 120.0311
2697 | 124.4337
2698 | 93.9384
2699 | 134.5558
2700 | 134.5267
2701 | 110.4635
2702 | 110.0545
2703 | 109.3525
2704 | 137.6552
2705 | 81.4358
2706 | 145.2957
2707 | 156.6987
2708 | 141.1456
2709 | 115.4055
2710 | 85.6063
2711 | 61.1666
2712 | 125.4538
2713 | 139.009
2714 | 137.1483
2715 | 167.3795
2716 | 120.4826
2717 | 134.7809
2718 | 88.3772
2719 | 155.2742
2720 | 89.0667
2721 | 81.0739
2722 | 193.8934
2723 | 133.9664
2724 | 165.5735
2725 | 154.5295
2726 | 88.0423
2727 | 96.9252
2728 | 153.1369
2729 | 98.1696
2730 | 113.3689
2731 | 129.7896
2732 | 137.8154
2733 | 142.7164
2734 | 74.9982
2735 | 97.6544
2736 | 131.4464
2737 | 142.423
2738 | 97.4547
2739 | 100.318
2740 | 121.0111
2741 | 126.6544
2742 | 104.6507
2743 | 111.4197
2744 | 118.7134
2745 | 94.8113
2746 | 91.3436
2747 | 75.85
2748 | 108.8023
2749 | 121.0448
2750 | 159.8221
2751 | 136.2045
2752 | 122.7454
2753 | 104.344
2754 | 125.4553
2755 | 131.8052
2756 | 126.089
2757 | 122.0442
2758 | 113.4249
2759 | 121.1672
2760 | 63.6752
2761 | 66.9976
2762 | 132.7107
2763 | 98.9992
2764 | 131.1693
2765 | 115.0111
2766 | 125.8988
2767 | 137.5236
2768 | 78.4518
2769 | 110.2704
2770 | 60.9905
2771 | 94.6632
2772 | 136.0501
2773 | 142.2062
2774 | 115.6963
2775 | 122.722
2776 | 114.5582
2777 | 94.2728
2778 | 147.793
2779 | 110.6097
2780 | 127.264
2781 | 110.1693
2782 | 111.8185
2783 | 62.2557
2784 | 128.4594
2785 | 143.5032
2786 | 171.1396
2787 | 115.7871
2788 | 95.4655
2789 | 74.363
2790 | 104.3526
2791 | 128.6114
2792 | 130.0232
2793 | 133.2095
2794 | 82.9784
2795 | 154.1826
2796 | 124.9979
2797 | 130.0942
2798 | 68.1626
2799 | 117.5577
2800 | 131.5505
2801 | 116.3698
2802 | 108.9505
2803 | 108.8955
2804 | 97.5957
2805 | 122.8722
2806 | 123.5536
2807 | 157.8868
2808 | 140.3184
2809 | 86.2345
2810 | 112.6002
2811 | 112.4301
2812 | 137.4508
2813 | 151.558
2814 | 132.6891
2815 | 92.0518
2816 | 176.5721
2817 | 87.5905
2818 | 145.3161
2819 | 96.9444
2820 | 96.5337
2821 | 124.1313
2822 | 122.6887
2823 | 86.2674
2824 | 135.8813
2825 | 124.33
2826 | 152.1543
2827 | 150.6008
2828 | 83.322
2829 | 121.5358
2830 | 137.1974
2831 | 150.3159
2832 | 93.1342
2833 | 153.4407
2834 | 99.8831
2835 | 72.1744
2836 | 98.4085
2837 | 139.6102
2838 | 123.6172
2839 | 110.4786
2840 | 132.0659
2841 | 80.9081
2842 | 104.7649
2843 | 173.3293
2844 | 130.6333
2845 | 146.2467
2846 | 112.6712
2847 | 138.5284
2848 | 134.1172
2849 | 155.1273
2850 | 120.2162
2851 | 91.5402
2852 | 104.625
2853 | 97.2888
2854 | 124.3674
2855 | 92.8162
2856 | 131.9807
2857 | 133.5979
2858 | 157.36
2859 | 185.6689
2860 | 184.1083
2861 | 150.8826
2862 | 91.7248
2863 | 114.7661
2864 | 136.9385
2865 | 125.9318
2866 | 101.8177
2867 | 137.4345
2868 | 194.9545
2869 | 137.2363
2870 | 73.9916
2871 | 104.8994
2872 | 91.3079
2873 | 80.6754
2874 | 112.2032
2875 | 124.5499
2876 | 139.8968
2877 | 94.9656
2878 | 99.049
2879 | 152.6721
2880 | 148.3453
2881 | 113.5396
2882 | 132.7246
2883 | 117.9254
2884 | 158.4644
2885 | 97.2528
2886 | 134.2963
2887 | 113.4849
2888 | 132.2752
2889 | 115.612
2890 | 181.4635
2891 | 74.3305
2892 | 120.811
2893 | 111.6293
2894 | 107.3307
2895 | 139.3794
2896 | 110.8072
2897 | 132.2252
2898 | 93.1542
2899 | 114.8916
2900 | 138.8471
2901 | 106.8594
2902 | 124.8797
2903 | 154.6513
2904 | 117.7154
2905 | 97.7737
2906 | 131.4768
2907 | 142.2697
2908 | 132.4056
2909 | 170.657
2910 | 138.8841
2911 | 135.6361
2912 | 133.4761
2913 | 106.4018
2914 | 113.1942
2915 | 137.1275
2916 | 169.3914
2917 | 84.3853
2918 | 176.7237
2919 | 145.5505
2920 | 123.8243
2921 | 126.5982
2922 | 126.6582
2923 | 156.1203
2924 | 100.7884
2925 | 163.4506
2926 | 151.1767
2927 | 149.7555
2928 | 58.1098
2929 | 135.3166
2930 | 138.7852
2931 | 125.9751
2932 | 95.619
2933 | 132.3683
2934 | 147.4665
2935 | 92.135
2936 | 136.7939
2937 | 104.8812
2938 | 97.8171
2939 | 137.2486
2940 | 81.1192
2941 | 120.1235
2942 | 109.2376
2943 | 109.5957
2944 | 131.156
2945 | 109.3245
2946 | 109.1977
2947 | 108.8875
2948 | 134.0308
2949 | 134.6024
2950 | 135.7124
2951 | 107.3867
2952 | 129.5957
2953 | 176.3323
2954 | 117.8459
2955 | 94.6473
2956 | 143.2825
2957 | 92.9657
2958 | 145.7737
2959 | 154.5101
2960 | 133.54
2961 | 130.3985
2962 | 136.9115
2963 | 142.3764
2964 | 91.0025
2965 | 119.7191
2966 | 113.136
2967 | 102.2308
2968 | 119.488
2969 | 109.084
2970 | 107.1647
2971 | 61.5762
2972 | 166.9701
2973 | 128.644
2974 | 109.9996
2975 | 108.265
2976 | 100.9829
2977 | 63.8754
2978 | 87.115
2979 | 146.6703
2980 | 125.7965
2981 | 144.3913
2982 | 101.2721
2983 | 106.6081
2984 | 103.2513
2985 | 146.8745
2986 | 139.3364
2987 | 135.9196
2988 | 98.7007
2989 | 134.6219
2990 | 135.9122
2991 | 120.8895
2992 | 139.5879
2993 | 153.8195
2994 | 106.8443
2995 | 113.857
2996 | 114.5801
2997 | 134.5813
2998 | 112.1914
2999 | 141.8081
3000 | 159.873
3001 | 109.6257
3002 | 123.4904
3003 | 106.2187
3004 | 88.6339
3005 | 96.6134
3006 | 113.0151
3007 | 160.4864
3008 | 117.6449
3009 | 151.1894
3010 | 105.6946
3011 | 136.2105
3012 | 104.5736
3013 | 119.6195
3014 | 87.3267
3015 | 106.5533
3016 | 132.3587
3017 | 118.6413
3018 | 155.5836
3019 | 84.3673
3020 | 122.97
3021 | 129.5883
3022 | 167.2563
3023 | 130.6128
3024 | 104.8946
3025 | 116.2906
3026 | 143.7062
3027 | 77.6126
3028 | 123.1788
3029 | 111.6104
3030 | 123.2524
3031 | 132.2265
3032 | 140.828
3033 | 126.3779
3034 | 114.814
3035 | 157.2912
3036 | 134.8055
3037 | 94.5648
3038 | 115.1632
3039 | 122.3536
3040 | 142.8024
3041 | 117.1879
3042 | 99.1836
3043 | 133.094
3044 | 113.5314
3045 | 101.9878
3046 | 128.4046
3047 | 141.036
3048 | 115.5612
3049 | 160.0129
3050 | 121.6964
3051 | 101.5423
3052 | 145.1838
3053 | 108.0933
3054 | 131.6146
3055 | 122.9528
3056 | 111.6621
3057 | 133.2319
3058 | 124.9648
3059 | 65.7263
3060 | 136.9909
3061 | 135.7071
3062 | 152.9839
3063 | 122.7685
3064 | 99.1229
3065 | 127.6267
3066 | 150.487
3067 | 119.5637
3068 | 82.9061
3069 | 114.9741
3070 | 121.4771
3071 | 127.697
3072 | 135.2636
3073 | 120.4326
3074 | 142.6677
3075 | 122.5646
3076 | 108.8066
3077 | 131.9329
3078 | 145.729
3079 | 149.8594
3080 | 112.5331
3081 | 132.6842
3082 | 119.3766
3083 | 102.0075
3084 | 90.8136
3085 | 130.4353
3086 | 114.4328
3087 | 146.7143
3088 | 118.0572
3089 | 100.0539
3090 | 82.4107
3091 | 80.8982
3092 | 144.0143
3093 | 105.081
3094 | 114.5676
3095 | 139.747
3096 | 139.7493
3097 | 151.4613
3098 | 147.5691
3099 | 103.565
3100 | 91.0768
3101 | 112.7122
3102 | 124.9007
3103 | 125.2324
3104 | 92.4662
3105 | 113.2834
3106 | 106.941
3107 | 135.268
3108 | 139.7866
3109 | 184.567
3110 | 117.767
3111 | 86.2986
3112 | 126.8629
3113 | 77.6041
3114 | 164.5658
3115 | 127.6655
3116 | 76.6671
3117 | 72.4513
3118 | 119.0865
3119 | 129.4281
3120 | 109.3701
3121 | 131.0939
3122 | 102.635
3123 | 85.021
3124 | 130.1095
3125 | 130.4377
3126 | 139.3195
3127 | 153.5095
3128 | 145.8142
3129 | 145.2649
3130 | 136.9983
3131 | 134.3284
3132 | 123.576
3133 | 96.2474
3134 | 80.4594
3135 | 82.5899
3136 | 153.0533
3137 | 120.8941
3138 | 102.1196
3139 | 82.0171
3140 | 131.4502
3141 | 121.1417
3142 | 149.009
3143 | 109.4587
3144 | 104.1608
3145 | 121.5997
3146 | 123.514
3147 | 71.3106
3148 | 113.5816
3149 | 110.7568
3150 | 138.1259
3151 | 136.8062
3152 | 117.266
3153 | 129.6712
3154 | 116.9752
3155 | 115.3156
3156 | 123.1171
3157 | 112.9534
3158 | 81.517
3159 | 151.2049
3160 | 127.8145
3161 | 106.119
3162 | 116.8969
3163 | 119.0419
3164 | 99.2821
3165 | 128.9094
3166 | 120.723
3167 | 134.3446
3168 | 92.2408
3169 | 139.2261
3170 | 152.8891
3171 | 116.1381
3172 | 84.8073
3173 | 138.6085
3174 | 79.8097
3175 | 71.8917
3176 | 131.2598
3177 | 91.8697
3178 | 96.985
3179 | 139.1562
3180 | 117.0657
3181 | 111.6864
3182 | 136.6944
3183 | 150.1353
3184 | 114.2358
3185 | 60.8776
3186 | 114.7748
3187 | 97.7271
3188 | 150.0997
3189 | 102.3891
3190 | 117.2931
3191 | 122.5556
3192 | 133.1072
3193 | 131.7369
3194 | 118.3738
3195 | 106.8276
3196 | 143.3097
3197 | 102.853
3198 | 148.548
3199 | 124.0616
3200 | 114.3854
3201 | 154.746
3202 | 134.7152
3203 | 64.8856
3204 | 161.7306
3205 | 114.4975
3206 | 116.4571
3207 | 134.898
3208 | 139.6727
3209 | 151.6657
3210 | 140.4262
3211 | 136.007
3212 | 106.647
3213 | 154.5871
3214 | 98.8541
3215 | 108.706
3216 | 138.8645
3217 | 68.4503
3218 | 116.6428
3219 | 121.926
3220 | 68.0687
3221 | 120.0885
3222 | 127.8867
3223 | 154.8247
3224 | 70.9774
3225 | 135.6891
3226 | 100.2314
3227 | 126.2515
3228 | 167.3273
3229 | 117.689
3230 | 110.2199
3231 | 111.8685
3232 | 136.4398
3233 | 129.4664
3234 | 112.5663
3235 | 168.7194
3236 | 108.1749
3237 | 134.1703
3238 | 144.2494
3239 | 121.5892
3240 | 96.0831
3241 | 79.9607
3242 | 146.7656
3243 | 151.2007
3244 | 104.2079
3245 | 117.7039
3246 | 121.9366
3247 | 93.8399
3248 | 125.6567
3249 | 114.4341
3250 | 146.3315
3251 | 77.2121
3252 | 103.4253
3253 | 100.0585
3254 | 134.8801
3255 | 155.1113
3256 | 141.6139
3257 | 126.9927
3258 | 115.5513
3259 | 126.0888
3260 | 93.4715
3261 | 135.793
3262 | 89.0708
3263 | 147.8209
3264 | 110.6945
3265 | 96.9
3266 | 130.6306
3267 | 117.8321
3268 | 96.0307
3269 | 134.4893
3270 | 129.2222
3271 | 163.9286
3272 | 125.3192
3273 | 64.4574
3274 | 112.0862
3275 | 128.0066
3276 | 140.1287
3277 | 170.3711
3278 | 131.0647
3279 | 101.3564
3280 | 126.4243
3281 | 148.3406
3282 | 165.4421
3283 | 139.104
3284 | 125.7378
3285 | 104.2316
3286 | 83.6154
3287 | 68.5093
3288 | 181.5311
3289 | 58.1208
3290 | 134.4795
3291 | 106.652
3292 | 143.2429
3293 | 122.9935
3294 | 130.2893
3295 | 134.2633
3296 | 125.2126
3297 | 92.1821
3298 | 127.8682
3299 | 155.3851
3300 | 168.8191
3301 | 148.7767
3302 | 112.5029
3303 | 163.1401
3304 | 108.1403
3305 | 93.0907
3306 | 85.6402
3307 | 149.9042
3308 | 130.5558
3309 | 155.8874
3310 | 150.3045
3311 | 105.6914
3312 | 123.8917
3313 | 98.0628
3314 | 114.5004
3315 | 114.2741
3316 | 130.2949
3317 | 132.758
3318 | 123.7761
3319 | 102.3031
3320 | 97.7981
3321 | 123.2147
3322 | 96.6238
3323 | 132.2872
3324 | 138.3733
3325 | 94.5184
3326 | 100.4155
3327 | 97.212
3328 | 78.2107
3329 | 95.5855
3330 | 104.3744
3331 | 126.5916
3332 | 141.9825
3333 | 126.9106
3334 | 142.9569
3335 | 131.4983
3336 | 78.917
3337 | 174.9679
3338 | 116.2311
3339 | 94.0542
3340 | 80.5072
3341 | 65.8503
3342 | 133.5353
3343 | 102.9887
3344 | 154.0632
3345 | 140.8618
3346 | 109.5302
3347 | 127.4068
3348 | 114.6414
3349 | 112.6693
3350 | 134.9785
3351 | 109.4907
3352 | 114.5485
3353 | 94.7426
3354 | 104.8093
3355 | 132.1129
3356 | 112.5465
3357 | 144.737
3358 | 166.6348
3359 | 88.5484
3360 | 117.3284
3361 | 122.9833
3362 | 148.012
3363 | 97.2958
3364 | 150.8941
3365 | 120.9407
3366 | 163.8461
3367 | 106.2404
3368 | 102.4645
3369 | 157.3477
3370 | 73.6535
3371 | 118.0256
3372 | 88.3229
3373 | 151.931
3374 | 89.9474
3375 | 97.1931
3376 | 93.8273
3377 | 57.5735
3378 | 91.7002
3379 | 120.8856
3380 | 91.7358
3381 | 103.7132
3382 | 134.4359
3383 | 128.2651
3384 | 119.7369
3385 | 66.4291
3386 | 96.88
3387 | 97.0724
3388 | 109.755
3389 | 144.8606
3390 | 157.7797
3391 | 110.0229
3392 | 119.1667
3393 | 89.5024
3394 | 84.7007
3395 | 157.5303
3396 | 127.5898
3397 | 108.9337
3398 | 98.9482
3399 | 122.6723
3400 | 115.3852
3401 | 135.9337
3402 | 103.1589
3403 | 178.1527
3404 | 123.4737
3405 | 106.2196
3406 | 110.3975
3407 | 114.7044
3408 | 109.4614
3409 | 154.3997
3410 | 103.6795
3411 | 101.6194
3412 | 138.779
3413 | 108.0193
3414 | 146.553
3415 | 77.0559
3416 | 110.9255
3417 | 112.0189
3418 | 143.4416
3419 | 156.8976
3420 | 108.3664
3421 | 140.7895
3422 | 155.2649
3423 | 107.7438
3424 | 163.8759
3425 | 115.4542
3426 | 178.06
3427 | 112.2198
3428 | 158.7905
3429 | 91.527
3430 | 78.7472
3431 | 106.7108
3432 | 84.4482
3433 | 91.1165
3434 | 117.9205
3435 | 136.0556
3436 | 124.6896
3437 | 95.2665
3438 | 137.1981
3439 | 118.4752
3440 | 76.2733
3441 | 104.2053
3442 | 85.4209
3443 | 102.254
3444 | 73.6242
3445 | 78.5886
3446 | 92.3741
3447 | 85.9006
3448 | 157.9599
3449 | 100.6408
3450 | 109.8267
3451 | 81.8353
3452 | 140.6706
3453 | 128.7864
3454 | 65.0871
3455 | 91.4372
3456 | 140.5829
3457 | 107.4648
3458 | 134.8134
3459 | 154.138
3460 | 137.3673
3461 | 121.5751
3462 | 120.145
3463 | 110.0842
3464 | 105.1622
3465 | 127.6279
3466 | 123.9863
3467 | 111.83
3468 | 94.7412
3469 | 132.0052
3470 | 140.3796
3471 | 134.3883
3472 | 111.2169
3473 | 151.1308
3474 | 100.3016
3475 | 127.4418
3476 | 162.8861
3477 | 91.3038
3478 | 129.9603
3479 | 142.2189
3480 | 138.2376
3481 | 149.7422
3482 | 129.6463
3483 | 121.6993
3484 | 164.7143
3485 | 138.8948
3486 | 173.6599
3487 | 129.1726
3488 | 66.8305
3489 | 107.6241
3490 | 75.1948
3491 | 131.7834
3492 | 122.254
3493 | 129.0214
3494 | 148.1116
3495 | 118.2621
3496 | 135.0474
3497 | 110.6888
3498 | 110.3155
3499 | 141.3647
3500 | 101.7419
3501 | 127.1369
3502 | 117.9182
3503 | 142.3825
3504 | 94.4362
3505 | 122.9773
3506 | 111.4333
3507 | 123.9569
3508 | 136.9443
3509 | 110.5969
3510 | 139.1193
3511 | 132.9801
3512 | 133.0234
3513 | 75.2008
3514 | 112.4842
3515 | 125.8114
3516 | 100.9436
3517 | 158.3744
3518 | 151.5222
3519 | 145.0805
3520 | 110.0516
3521 | 110.6477
3522 | 120.0026
3523 | 128.8245
3524 | 114.8797
3525 | 89.0419
3526 | 116.6877
3527 | 134.7792
3528 | 144.8981
3529 | 135.1483
3530 | 86.7201
3531 | 136.4897
3532 | 125.2707
3533 | 125.8449
3534 | 150.012
3535 | 161.0471
3536 | 156.2693
3537 | 152.712
3538 | 130.6243
3539 | 103.3615
3540 | 177.8039
3541 | 167.1342
3542 | 156.6397
3543 | 118.848
3544 | 180.2382
3545 | 125.4875
3546 | 116.978
3547 | 129.3625
3548 | 144.1249
3549 | 69.7047
3550 | 136.743
3551 | 94.3766
3552 | 123.4624
3553 | 123.6756
3554 | 101.4003
3555 | 72.8862
3556 | 149.9214
3557 | 100.1393
3558 | 151.1253
3559 | 105.0154
3560 | 121.2494
3561 | 157.1726
3562 | 150.7287
3563 | 106.9258
3564 | 66.6418
3565 | 112.6431
3566 | 83.7466
3567 | 139.8743
3568 | 137.6473
3569 | 89.1005
3570 | 88.0261
3571 | 99.8516
3572 | 136.4838
3573 | 147.4792
3574 | 172.9823
3575 | 113.5958
3576 | 101.973
3577 | 67.5913
3578 | 65.2826
3579 | 119.325
3580 | 139.5705
3581 | 136.7582
3582 | 89.6609
3583 | 65.9494
3584 | 148.1089
3585 | 122.6688
3586 | 134.7049
3587 | 107.1549
3588 | 146.893
3589 | 117.8487
3590 | 89.1427
3591 | 131.5272
3592 | 110.04
3593 | 85.1212
3594 | 111.0396
3595 | 149.4706
3596 | 101.5887
3597 | 75.0275
3598 | 143.4808
3599 | 143.1712
3600 | 148.8502
3601 | 165.8627
3602 | 135.9116
3603 | 97.4914
3604 | 115.6815
3605 | 108.2155
3606 | 119.6827
3607 | 91.2152
3608 | 149.1216
3609 | 114.9715
3610 | 96.3103
3611 | 148.3058
3612 | 133.1469
3613 | 103.5558
3614 | 144.7351
3615 | 153.8988
3616 | 106.6402
3617 | 97.174
3618 | 124.1182
3619 | 179.0335
3620 | 136.4254
3621 | 131.703
3622 | 119.6686
3623 | 152.1434
3624 | 117.5902
3625 | 121.9799
3626 | 106.158
3627 | 98.2741
3628 | 92.4263
3629 | 84.4922
3630 | 89.3935
3631 | 134.5436
3632 | 97.0788
3633 | 102.0883
3634 | 120.8713
3635 | 109.4466
3636 | 118.714
3637 | 97.4415
3638 | 115.3923
3639 | 134.0041
3640 | 82.6544
3641 | 159.3706
3642 | 137.4764
3643 | 136.2688
3644 | 100.1794
3645 | 95.2562
3646 | 155.5724
3647 | 109.8557
3648 | 171.1256
3649 | 149.107
3650 | 135.5009
3651 | 92.9708
3652 | 131.7251
3653 | 141.2336
3654 | 140.756
3655 | 136.281
3656 | 137.1808
3657 | 113.1125
3658 | 125.1798
3659 | 130.1419
3660 | 121.9047
3661 | 117.8086
3662 | 98.3248
3663 | 135.3515
3664 | 141.2249
3665 | 134.6621
3666 | 140.5458
3667 | 97.1371
3668 | 128.7185
3669 | 114.4641
3670 | 116.4886
3671 | 133.8311
3672 | 100.5887
3673 | 93.5743
3674 | 112.9966
3675 | 80.1662
3676 | 122.1747
3677 | 136.9922
3678 | 131.6955
3679 | 109.7218
3680 | 116.7091
3681 | 107.0484
3682 | 133.6737
3683 | 100.9591
3684 | 159.8824
3685 | 125.4319
3686 | 148.3687
3687 | 87.5223
3688 | 157.5531
3689 | 148.9353
3690 | 112.5057
3691 | 117.0435
3692 | 105.1655
3693 | 174.8645
3694 | 98.8295
3695 | 89.3973
3696 | 104.0698
3697 | 144.5832
3698 | 69.4463
3699 | 64.756
3700 | 110.5633
3701 | 128.3155
3702 | 133.1328
3703 | 129.6628
3704 | 94.3136
3705 | 149.5642
3706 | 87.9608
3707 | 93.1178
3708 | 103.7372
3709 | 99.5897
3710 | 130.9736
3711 | 128.533
3712 | 102.1504
3713 | 107.1351
3714 | 126.7968
3715 | 119.0491
3716 | 129.7441
3717 | 104.3474
3718 | 113.3332
3719 | 135.033
3720 | 116.4752
3721 | 152.0175
3722 | 67.283
3723 | 119.6775
3724 | 107.3139
3725 | 91.7572
3726 | 85.409
3727 | 123.2997
3728 | 138.6494
3729 | 120.8413
3730 | 160.6935
3731 | 141.0265
3732 | 177.523
3733 | 127.2634
3734 | 106.756
3735 | 118.6376
3736 | 113.3486
3737 | 138.8536
3738 | 117.0883
3739 | 143.2148
3740 | 120.7914
3741 | 73.9722
3742 | 138.7567
3743 | 106.3677
3744 | 127.355
3745 | 107.4068
3746 | 118.3916
3747 | 106.1144
3748 | 151.7411
3749 | 133.894
3750 | 113.0166
3751 | 111.3761
3752 | 88.1952
3753 | 110.0346
3754 | 126.7751
3755 | 128.3132
3756 | 113.978
3757 | 158.4562
3758 | 101.3268
3759 | 168.5863
3760 | 85.0552
3761 | 153.3604
3762 | 116.252
3763 | 119.3814
3764 | 129.3046
3765 | 126.9373
3766 | 129.6516
3767 | 121.4146
3768 | 139.2742
3769 | 123.6186
3770 | 91.8824
3771 | 108.1753
3772 | 121.8484
3773 | 168.9097
3774 | 138.7718
3775 | 109.9081
3776 | 129.6094
3777 | 149.3671
3778 | 89.969
3779 | 126.0971
3780 | 129.1529
3781 | 115.5827
3782 | 92.9258
3783 | 87.9058
3784 | 178.8868
3785 | 170.1533
3786 | 95.2053
3787 | 101.0124
3788 | 83.8076
3789 | 134.4283
3790 | 109.7679
3791 | 101.5122
3792 | 129.1242
3793 | 122.4579
3794 | 104.6904
3795 | 170.7606
3796 | 117.5013
3797 | 111.5705
3798 | 139.7293
3799 | 155.0844
3800 | 115.6025
3801 | 122.2017
3802 | 131.6222
3803 | 98.8695
3804 | 130.3813
3805 | 116.4433
3806 | 146.7598
3807 | 103.2653
3808 | 94.182
3809 | 161.8778
3810 | 132.4564
3811 | 124.4366
3812 | 105.4449
3813 | 118.7556
3814 | 77.4905
3815 | 109.8948
3816 | 65.7497
3817 | 136.5441
3818 | 93.2365
3819 | 122.6035
3820 | 144.6822
3821 | 103.0809
3822 | 156.8455
3823 | 69.2395
3824 | 138.559
3825 | 59.4326
3826 | 137.969
3827 | 113.362
3828 | 87.2704
3829 | 121.9391
3830 | 122.8666
3831 | 165.5715
3832 | 126.6412
3833 | 146.2191
3834 | 182.3418
3835 | 137.7237
3836 | 136.4375
3837 | 89.0129
3838 | 129.4604
3839 | 133.6984
3840 | 127.9675
3841 | 120.3559
3842 | 96.5333
3843 | 110.549
3844 | 95.1934
3845 | 150.76
3846 | 159.5626
3847 | 113.2246
3848 | 115.9716
3849 | 130.1393
3850 | 144.494
3851 | 105.5544
3852 | 137.2079
3853 | 91.8178
3854 | 99.8416
3855 | 125.8246
3856 | 90.3223
3857 | 102.879
3858 | 113.5624
3859 | 140.051
3860 | 126.684
3861 | 160.0495
3862 | 141.2162
3863 | 90.7502
3864 | 129.6366
3865 | 151.7992
3866 | 119.1837
3867 | 91.4234
3868 | 95.4837
3869 | 129.5058
3870 | 120.4901
3871 | 151.257
3872 | 153.5427
3873 | 141.3452
3874 | 106.3086
3875 | 109.0348
3876 | 159.734
3877 | 139.2221
3878 | 140.2409
3879 | 98.4669
3880 | 105.1132
3881 | 81.71
3882 | 137.8225
3883 | 138.9661
3884 | 124.4037
3885 | 125.3922
3886 | 90.2109
3887 | 167.4175
3888 | 82.4028
3889 | 120.7648
3890 | 134.7975
3891 | 100.4058
3892 | 113.3103
3893 | 138.6375
3894 | 91.2787
3895 | 124.6194
3896 | 81.1672
3897 | 138.6651
3898 | 86.8347
3899 | 134.2272
3900 | 139.7554
3901 | 131.2709
3902 | 97.0616
3903 | 120.4721
3904 | 140.2029
3905 | 95.5923
3906 | 95.7754
3907 | 109.8048
3908 | 83.5449
3909 | 144.9339
3910 | 112.901
3911 | 76.2577
3912 | 105.2505
3913 | 120.8083
3914 | 106.8137
3915 | 94.3825
3916 | 110.285
3917 | 89.2108
3918 | 113.5835
3919 | 134.817
3920 | 83.9843
3921 | 126.3968
3922 | 103.3067
3923 | 118.0109
3924 | 124.1916
3925 | 114.87
3926 | 93.1147
3927 | 92.3251
3928 | 61.1363
3929 | 128.8322
3930 | 133.4018
3931 | 146.2504
3932 | 117.7393
3933 | 149.6121
3934 | 139.007
3935 | 117.7156
3936 | 103.3132
3937 | 134.882
3938 | 156.5446
3939 | 111.1988
3940 | 147.0649
3941 | 134.7393
3942 | 102.2475
3943 | 115.5919
3944 | 146.2574
3945 | 134.0282
3946 | 86.6677
3947 | 139.207
3948 | 159.5724
3949 | 103.3616
3950 | 159.2271
3951 | 153.2794
3952 | 131.562
3953 | 105.8051
3954 | 109.6043
3955 | 136.8672
3956 | 135.363
3957 | 105.8311
3958 | 105.5993
3959 | 118.0958
3960 | 150.2159
3961 | 100.5037
3962 | 107.1608
3963 | 129.9161
3964 | 88.7271
3965 | 122.3087
3966 | 92.2506
3967 | 118.8529
3968 | 159.0902
3969 | 118.7963
3970 | 95.7433
3971 | 125.9933
3972 | 104.5257
3973 | 105.1643
3974 | 116.9739
3975 | 143.2434
3976 | 99.1975
3977 | 82.7989
3978 | 130.7105
3979 | 149.0121
3980 | 117.8376
3981 | 134.7173
3982 | 125.778
3983 | 113.7644
3984 | 138.3929
3985 | 122.5932
3986 | 130.7578
3987 | 96.2776
3988 | 124.01
3989 | 104.2705
3990 | 103.53
3991 | 135.8924
3992 | 129.9879
3993 | 114.8331
3994 | 111.551
3995 | 143.5033
3996 | 133.5193
3997 | 74.8049
3998 | 108.6929
3999 | 140.7806
4000 | 134.3578
4001 | 101.3482
4002 | 148.0084
4003 | 119.4494
4004 | 82.388
4005 | 120.6008
4006 | 135.7612
4007 | 89.8509
4008 | 122.4797
4009 | 138.0927
4010 | 124.1069
4011 | 128.5365
4012 | 90.3815
4013 | 110.173
4014 | 107.0756
4015 | 132.8328
4016 | 188.9725
4017 | 121.6302
4018 | 152.4052
4019 | 120.6928
4020 | 110.5313
4021 | 131.0756
4022 | 118.767
4023 | 83.8353
4024 | 82.9095
4025 | 152.2289
4026 | 107.5955
4027 | 119.9902
4028 | 116.9815
4029 | 112.2896
4030 | 115.6746
4031 | 134.2802
4032 | 119.3227
4033 | 120.4118
4034 | 84.5691
4035 | 101.5324
4036 | 132.78
4037 | 147.3016
4038 | 117.9474
4039 | 136.6902
4040 | 110.2591
4041 | 110.2014
4042 | 130.0785
4043 | 60.135
4044 | 142.0551
4045 | 162.0438
4046 | 105.1569
4047 | 144.2603
4048 | 123.079
4049 | 121.9447
4050 | 135.7043
4051 | 149.822
4052 | 100.2109
4053 | 113.6109
4054 | 115.9982
4055 | 107.9482
4056 | 117.8887
4057 | 158.9888
4058 | 62.6941
4059 | 139.4851
4060 | 123.807
4061 | 131.1282
4062 | 154.9998
4063 | 118.9574
4064 | 93.5933
4065 | 86.246
4066 | 140.7574
4067 | 98.3101
4068 | 153.5936
4069 | 92.4856
4070 | 109.9173
4071 | 124.7239
4072 | 120.36
4073 | 122.7043
4074 | 102.1662
4075 | 87.0277
4076 | 126.316
4077 | 116.6492
4078 | 95.6667
4079 | 105.1029
4080 | 144.6954
4081 | 225.0149
4082 | 154.2451
4083 | 148.1313
4084 | 122.7134
4085 | 156.3165
4086 | 127.7529
4087 | 90.3965
4088 | 128.59
4089 | 128.6524
4090 | 95.618
4091 | 123.822
4092 | 141.8418
4093 | 113.6703
4094 | 113.366
4095 | 110.9539
4096 | 126.2855
4097 | 167.718
4098 | 106.6173
4099 | 134.2079
4100 | 106.6506
4101 | 101.4349
4102 | 116.7801
4103 | 114.1869
4104 | 106.4788
4105 | 110.8619
4106 | 126.7329
4107 | 120.802
4108 | 126.4886
4109 | 137.1853
4110 | 112.7018
4111 | 42.1555
4112 | 101.4066
4113 | 136.3858
4114 | 134.2995
4115 | 88.5925
4116 | 140.3112
4117 | 106.7598
4118 | 115.4872
4119 | 142.8616
4120 | 101.184
4121 | 99.2115
4122 | 126.8135
4123 | 129.8085
4124 | 104.2085
4125 | 124.2938
4126 | 104.9549
4127 | 109.3414
4128 | 174.4205
4129 | 92.5722
4130 | 116.5182
4131 | 83.6484
4132 | 101.1887
4133 | 80.9048
4134 | 141.8575
4135 | 136.382
4136 | 109.3262
4137 | 125.4129
4138 | 68.4873
4139 | 135.8277
4140 | 100.8765
4141 | 112.9133
4142 | 127.4814
4143 | 148.4525
4144 | 95.3002
4145 | 112.9564
4146 | 91.7276
4147 | 126.2022
4148 | 104.9368
4149 | 93.9878
4150 | 123.7612
4151 | 152.229
4152 | 104.8432
4153 | 143.5459
4154 | 113.3145
4155 | 88.3414
4156 | 98.8585
4157 | 126.8325
4158 | 138.7613
4159 | 99.9503
4160 | 105.3968
4161 | 139.3238
4162 | 117.0149
4163 | 139.8882
4164 | 71.4368
4165 | 107.6591
4166 | 137.1079
4167 | 80.103
4168 | 71.7507
4169 | 143.8878
4170 | 174.1939
4171 | 86.532
4172 | 90.2908
4173 | 121.3148
4174 | 102.0951
4175 | 123.6654
4176 | 87.9135
4177 | 133.5519
4178 | 145.1658
4179 | 115.4267
4180 | 96.9827
4181 | 138.4133
4182 | 88.5442
4183 | 158.6994
4184 | 146.9059
4185 | 152.8297
4186 | 159.5278
4187 | 137.2463
4188 | 125.6891
4189 | 124.9068
4190 | 104.2039
4191 | 146.9737
4192 | 108.6176
4193 | 132.577
4194 | 100.6549
4195 | 117.1931
4196 | 127.0553
4197 | 66.832
4198 | 77.5556
4199 | 108.9188
4200 | 106.1013
4201 | 162.6522
4202 | 135.0473
4203 | 128.1824
4204 | 123.849
4205 | 98.0281
4206 | 88.2132
4207 | 111.7838
4208 | 106.496
4209 | 136.5449
4210 | 145.8406
4211 | 140.0936
4212 | 117.8151
4213 | 138.8071
4214 | 159.6012
4215 | 128.5636
4216 | 127.2198
4217 | 97.459
4218 | 116.1286
4219 | 107.7855
4220 | 105.1136
4221 | 121.8318
4222 | 116.6479
4223 | 81.2388
4224 | 140.4922
4225 | 124.2459
4226 | 116.1468
4227 | 141.2236
4228 | 92.6497
4229 | 136.0962
4230 | 93.3608
4231 | 133.9271
4232 | 105.0681
4233 | 100.5993
4234 | 143.339
4235 | 106.142
4236 | 144.4679
4237 | 148.765
4238 | 128.4154
4239 | 135.1779
4240 | 60.7088
4241 | 107.9195
4242 | 118.3803
4243 | 90.9682
4244 | 112.0169
4245 | 139.5441
4246 | 146.0419
4247 | 80.3812
4248 | 88.0242
4249 | 126.8537
4250 | 139.3418
4251 | 116.5091
4252 | 94.0125
4253 | 106.5099
4254 | 124.4855
4255 | 92.2764
4256 | 109.7178
4257 | 117.3368
4258 | 113.1587
4259 | 89.7867
4260 | 124.4326
4261 | 113.0785
4262 | 103.8936
4263 | 113.9398
4264 | 53.0622
4265 | 129.8529
4266 | 117.3348
4267 | 156.2396
4268 | 139.1311
4269 | 138.4666
4270 | 127.0597
4271 | 103.8899
4272 | 94.2841
4273 | 107.5884
4274 | 134.889
4275 | 145.8052
4276 | 133.8109
4277 | 118.9839
4278 | 101.2017
4279 | 124.4675
4280 | 87.5476
4281 | 90.7764
4282 | 101.4559
4283 | 126.47
4284 | 115.7258
4285 | 137.6371
4286 | 79.3133
4287 | 102.5309
4288 | 119.1388
4289 | 138.7227
4290 | 143.2642
4291 | 93.4067
4292 | 123.2957
4293 | 77.3585
4294 | 114.8256
4295 | 131.9978
4296 | 161.3791
4297 | 145.345
4298 | 139.6434
4299 | 140.0041
4300 | 132.4603
4301 | 116.448
4302 | 99.3364
4303 | 126.4298
4304 | 120.8961
4305 | 116.715
4306 | 136.8345
4307 | 133.1261
4308 | 119.4527
4309 | 124.5045
4310 | 131.6357
4311 | 72.8223
4312 | 151.4312
4313 | 56.1813
4314 | 121.8166
4315 | 82.6907
4316 | 100.3015
4317 | 145.2082
4318 | 167.8175
4319 | 36.6884
4320 | 133.6296
4321 | 123.5585
4322 | 139.7873
4323 | 118.6238
4324 | 124.8123
4325 | 116.0324
4326 | 170.3581
4327 | 110.065
4328 | 156.2556
4329 | 174.4803
4330 | 95.2476
4331 | 126.5764
4332 | 109.2581
4333 | 119.05
4334 | 109.5374
4335 | 110.2034
4336 | 157.4557
4337 | 156.1017
4338 | 100.6199
4339 | 152.025
4340 | 67.3389
4341 | 123.9652
4342 | 122.7731
4343 | 142.8074
4344 | 109.6758
4345 | 89.7628
4346 | 159.7377
4347 | 89.8338
4348 | 134.1966
4349 | 134.0821
4350 | 133.0259
4351 | 112.3941
4352 | 141.0371
4353 | 113.5163
4354 | 73.8064
4355 | 138.8537
4356 | 93.7158
4357 | 152.8065
4358 | 150.4611
4359 | 71.336
4360 | 100.987
4361 | 136.1531
4362 | 137.0754
4363 | 138.9431
4364 | 170.6347
4365 | 150.5014
4366 | 85.5531
4367 | 169.0678
4368 | 107.6822
4369 | 104.8308
4370 | 143.2352
4371 | 173.5764
4372 | 102.1293
4373 | 117.1812
4374 | 87.1972
4375 | 106.109
4376 | 135.909
4377 | 157.394
4378 | 137.9336
4379 | 129.2285
4380 | 134.7226
4381 | 99.728
4382 | 105.806
4383 | 136.9914
4384 | 142.9861
4385 | 128.881
4386 | 127.8798
4387 | 133.7071
4388 | 72.9965
4389 | 109.9775
4390 | 101.4203
4391 | 110.2683
4392 | 132.6421
4393 | 93.6219
4394 | 137.7902
4395 | 136.7658
4396 | 105.3846
4397 | 97.4421
4398 | 164.5105
4399 | 164.3813
4400 | 136.0536
4401 | 118.0024
4402 | 83.6284
4403 | 94.3976
4404 | 135.2241
4405 | 126.1837
4406 | 134.7593
4407 | 66.7877
4408 | 104.7275
4409 | 141.5353
4410 | 117.6849
4411 | 130.8529
4412 | 120.7047
4413 | 183.4487
4414 | 154.7338
4415 | 106.3717
4416 | 111.3645
4417 | 99.1926
4418 | 80.2477
4419 | 152.1868
4420 | 136.0795
4421 | 118.6452
4422 | 111.7736
4423 | 127.5129
4424 | 113.0519
4425 | 106.5663
4426 | 175.4474
4427 | 86.3231
4428 | 112.8444
4429 | 91.5906
4430 | 114.1514
4431 | 122.2825
4432 | 121.2996
4433 | 108.0803
4434 | 99.2658
4435 | 163.6048
4436 | 155.2535
4437 | 146.6962
4438 | 138.1705
4439 | 96.4182
4440 | 90.8054
4441 | 77.986
4442 | 117.101
4443 | 123.6154
4444 | 100.0961
4445 | 117.7748
4446 | 141.5618
4447 | 95.6422
4448 | 139.5755
4449 | 190.8037
4450 | 136.7947
4451 | 132.7467
4452 | 145.4865
4453 | 126.2467
4454 | 175.3822
4455 | 124.337
4456 | 119.0867
4457 | 134.9744
4458 | 103.5466
4459 | 129.4708
4460 | 120.0654
4461 | 147.8112
4462 | 112.0725
4463 | 134.6685
4464 | 111.5074
4465 | 95.8218
4466 | 112.4366
4467 | 129.0032
4468 | 136.6017
4469 | 119.9618
4470 | 137.0959
4471 | 133.1356
4472 | 134.814
4473 | 168.4239
4474 | 102.443
4475 | 92.9481
4476 | 161.9751
4477 | 82.6058
4478 | 159.8405
4479 | 110.6347
4480 | 124.0381
4481 | 120.9082
4482 | 175.7031
4483 | 134.8726
4484 | 111.372
4485 | 135.568
4486 | 74.8368
4487 | 114.6708
4488 | 151.0014
4489 | 113.6655
4490 | 118.3255
4491 | 70.9453
4492 | 146.4534
4493 | 96.4586
4494 | 108.7293
4495 | 135.6205
4496 | 122.8111
4497 | 63.5505
4498 | 120.5455
4499 | 140.7983
4500 | 114.9808
4501 | 158.6625
4502 | 142.1545
4503 | 89.8368
4504 | 186.5792
4505 | 139.8354
4506 | 116.5264
4507 | 166.1339
4508 | 87.7808
4509 | 104.2853
4510 | 114.7771
4511 | 92.0249
4512 | 134.7746
4513 | 109.3483
4514 | 113.8785
4515 | 137.6611
4516 | 81.6017
4517 | 132.3494
4518 | 113.6285
4519 | 125.2072
4520 | 148.0915
4521 | 128.7389
4522 | 168.5388
4523 | 93.1352
4524 | 136.9091
4525 | 162.9193
4526 | 105.5562
4527 | 130.6611
4528 | 153.4514
4529 | 122.4272
4530 | 108.2108
4531 | 153.3866
4532 | 190.9252
4533 | 133.9534
4534 | 163.3575
4535 | 123.3514
4536 | 126.6857
4537 | 90.8642
4538 | 140.5105
4539 | 165.0828
4540 | 95.2712
4541 | 129.4128
4542 | 119.8184
4543 | 124.7479
4544 | 125.6961
4545 | 117.8368
4546 | 144.5425
4547 | 107.4207
4548 | 121.4044
4549 | 107.5352
4550 | 127.4304
4551 | 128.7101
4552 | 134.185
4553 | 118.5827
4554 | 120.877
4555 | 163.2702
4556 | 174.8703
4557 | 125.5874
4558 | 135.6286
4559 | 111.3046
4560 | 121.4905
4561 | 122.9607
4562 | 106.0864
4563 | 115.3389
4564 | 103.4849
4565 | 133.4739
4566 | 75.1888
4567 | 73.5334
4568 | 107.1333
4569 | 132.1175
4570 | 85.1995
4571 | 135.5278
4572 | 88.839
4573 | 137.6722
4574 | 116.3408
4575 | 118.9884
4576 | 101.9839
4577 | 90.7545
4578 | 100.9486
4579 | 108.7403
4580 | 92.0563
4581 | 141.2256
4582 | 135.6408
4583 | 94.6035
4584 | 87.3163
4585 | 94.852
4586 | 133.4376
4587 | 130.7027
4588 | 162.1566
4589 | 143.4432
4590 | 103.7922
4591 | 150.6708
4592 | 117.9272
4593 | 130.57
4594 | 100.9011
4595 | 111.7675
4596 | 121.6178
4597 | 125.4379
4598 | 100.8713
4599 | 94.9155
4600 | 114.6652
4601 | 121.3294
4602 | 132.1688
4603 | 50.5472
4604 | 137.9338
4605 | 102.368
4606 | 114.8982
4607 | 83.3719
4608 | 116.1649
4609 | 114.747
4610 | 94.6032
4611 | 160.5276
4612 | 132.1008
4613 | 152.9747
4614 | 133.2311
4615 | 76.717
4616 | 92.0314
4617 | 73.82
4618 | 124.0785
4619 | 79.6183
4620 | 108.2122
4621 | 129.5462
4622 | 96.4428
4623 | 106.2044
4624 | 124.436
4625 | 125.2418
4626 | 143.3724
4627 | 102.334
4628 | 101.9684
4629 | 118.0346
4630 | 135.7773
4631 | 136.0813
4632 | 53.8291
4633 | 101.4204
4634 | 145.587
4635 | 156.6886
4636 | 175.8704
4637 | 98.391
4638 | 166.9581
4639 | 134.4624
4640 | 106.221
4641 | 111.319
4642 | 112.5243
4643 | 114.8868
4644 | 150.8013
4645 | 120.7164
4646 | 140.9148
4647 | 104.9732
4648 | 128.4411
4649 | 107.7105
4650 | 112.9704
4651 | 155.8506
4652 | 144.9923
4653 | 112.8537
4654 | 133.5639
4655 | 153.9124
4656 | 89.54
4657 | 122.6328
4658 | 104.8659
4659 | 86.1535
4660 | 112.214
4661 | 124.6776
4662 | 110.4752
4663 | 114.547
4664 | 152.9609
4665 | 115.7585
4666 | 139.5999
4667 | 83.6162
4668 | 141.3528
4669 | 135.0141
4670 | 101.6714
4671 | 132.4497
4672 | 127.0375
4673 | 130.4739
4674 | 86.8752
4675 | 117.8503
4676 | 95.5559
4677 | 119.1584
4678 | 120.0098
4679 | 74.9044
4680 | 135.6945
4681 | 120.499
4682 | 165.5267
4683 | 104.4821
4684 | 141.1654
4685 | 109.9843
4686 | 134.3568
4687 | 161.3069
4688 | 112.7374
4689 | 175.7445
4690 | 141.4596
4691 | 150.1878
4692 | 105.9948
4693 | 90.3403
4694 | 130.9303
4695 | 142.7684
4696 | 60.2985
4697 | 106.324
4698 | 141.9594
4699 | 127.6683
4700 | 108.4642
4701 | 137.8431
4702 | 65.3982
4703 | 94.3362
4704 | 153.7024
4705 | 130.7335
4706 | 94.6924
4707 | 107.0704
4708 | 91.2351
4709 | 95.1959
4710 | 145.1518
4711 | 158.4478
4712 | 135.2128
4713 | 153.1305
4714 | 113.4335
4715 | 116.3482
4716 | 82.3331
4717 | 91.5134
4718 | 122.6606
4719 | 141.845
4720 | 116.8526
4721 | 114.6595
4722 | 103.7923
4723 | 91.5463
4724 | 81.9511
4725 | 118.4157
4726 | 135.8177
4727 | 136.3919
4728 | 185.3326
4729 | 113.3735
4730 | 113.357
4731 | 131.9615
4732 | 118.1057
4733 | 111.6241
4734 | 55.3038
4735 | 156.5029
4736 | 141.0383
4737 | 149.8256
4738 | 112.548
4739 | 101.5863
4740 | 117.5719
4741 | 71.4078
4742 | 95.8042
4743 | 110.3334
4744 | 133.6513
4745 | 104.6706
4746 | 122.0882
4747 | 143.539
4748 | 118.8003
4749 | 121.8957
4750 | 123.3278
4751 | 133.5048
4752 | 123.7221
4753 | 109.8979
4754 | 103.6443
4755 | 176.4959
4756 | 105.7156
4757 | 124.2178
4758 | 104.072
4759 | 100.8181
4760 | 113.9863
4761 | 137.6838
4762 | 127.0849
4763 | 133.9062
4764 | 137.3909
4765 | 137.4604
4766 | 98.7026
4767 | 87.3261
4768 | 86.929
4769 | 121.5649
4770 | 132.1872
4771 | 142.4311
4772 | 129.67
4773 | 174.0328
4774 | 128.2287
4775 | 109.594
4776 | 124.9764
4777 | 100.3837
4778 | 129.699
4779 | 118.929
4780 | 86.9501
4781 | 116.156
4782 | 105.8139
4783 | 79.8782
4784 | 71.2115
4785 | 142.7832
4786 | 138.2794
4787 | 124.1659
4788 | 157.9357
4789 | 148.4992
4790 | 86.621
4791 | 107.3306
4792 | 148.4233
4793 | 123.0083
4794 | 144.7687
4795 | 189.8478
4796 | 86.5536
4797 | 141.8085
4798 | 143.0449
4799 | 161.2877
4800 | 149.0628
4801 | 100.0581
4802 | 117.8704
4803 | 102.5465
4804 | 123.7774
4805 | 92.9379
4806 | 99.7819
4807 | 125.837
4808 | 123.5874
4809 | 143.9989
4810 | 103.9772
4811 | 145.3657
4812 | 132.3341
4813 | 90.6181
4814 | 112.9607
4815 | 120.6883
4816 | 132.4131
4817 | 136.7375
4818 | 137.2645
4819 | 144.6342
4820 | 80.8089
4821 | 104.113
4822 | 113.4507
4823 | 182.1802
4824 | 104.1721
4825 | 136.8727
4826 | 115.1102
4827 | 105.7632
4828 | 150.4102
4829 | 116.0955
4830 | 145.3321
4831 | 133.2485
4832 | 99.5774
4833 | 97.5093
4834 | 167.5098
4835 | 87.5723
4836 | 148.5881
4837 | 150.4297
4838 | 112.1186
4839 | 156.2925
4840 | 99.2361
4841 | 93.5423
4842 | 154.8053
4843 | 140.1208
4844 | 113.5222
4845 | 89.4499
4846 | 152.7853
4847 | 121.9332
4848 | 104.8127
4849 | 130.0798
4850 | 136.9842
4851 | 72.2069
4852 | 95.1363
4853 | 111.5859
4854 | 148.2895
4855 | 47.4346
4856 | 95.4911
4857 | 93.7347
4858 | 131.3004
4859 | 167.49
4860 | 111.9669
4861 | 134.146
4862 | 124.5538
4863 | 117.9859
4864 | 163.4585
4865 | 174.3144
4866 | 143.3595
4867 | 92.023
4868 | 99.0078
4869 | 187.4837
4870 | 125.4855
4871 | 109.4891
4872 | 119.7327
4873 | 137.03
4874 | 97.9075
4875 | 104.8486
4876 | 80.2179
4877 | 116.1377
4878 | 102.3536
4879 | 104.0365
4880 | 152.0902
4881 | 147.6055
4882 | 117.7791
4883 | 104.0806
4884 | 156.3192
4885 | 98.2551
4886 | 106.7668
4887 | 102.7139
4888 | 105.7797
4889 | 95.2418
4890 | 110.9751
4891 | 136.8757
4892 | 130.5824
4893 | 149.3802
4894 | 121.3193
4895 | 121.3068
4896 | 109.1816
4897 | 91.1137
4898 | 168.9271
4899 | 85.6598
4900 | 43.6763
4901 | 130.6996
4902 | 148.3123
4903 | 165.3009
4904 | 93.4793
4905 | 125.0125
4906 | 145.1157
4907 | 137.2264
4908 | 70.4288
4909 | 151.5716
4910 | 111.3311
4911 | 100.4739
4912 | 137.4713
4913 | 125.1095
4914 | 120.5903
4915 | 132.8819
4916 | 125.2898
4917 | 146.9053
4918 | 107.9834
4919 | 93.7527
4920 | 124.7194
4921 | 108.1005
4922 | 148.0524
4923 | 152.271
4924 | 125.8268
4925 | 106.1581
4926 | 85.5115
4927 | 104.0976
4928 | 82.559
4929 | 120.571
4930 | 123.3684
4931 | 116.0601
4932 | 94.9397
4933 | 64.2887
4934 | 160.4411
4935 | 115.0399
4936 | 162.0043
4937 | 91.09
4938 | 67.052
4939 | 136.9745
4940 | 89.5472
4941 | 136.5843
4942 | 112.9211
4943 | 83.6959
4944 | 146.8495
4945 | 116.9331
4946 | 115.7888
4947 | 118.2801
4948 | 175.4334
4949 | 120.9066
4950 | 104.1946
4951 | 96.2792
4952 | 137.6869
4953 | 103.4366
4954 | 98.9132
4955 | 87.6912
4956 | 102.9616
4957 | 123.4518
4958 | 119.5597
4959 | 131.1257
4960 | 142.0822
4961 | 96.2601
4962 | 109.9409
4963 | 131.8337
4964 | 132.9824
4965 | 157.7872
4966 | 78.4983
4967 | 104.6203
4968 | 106.6642
4969 | 122.3074
4970 | 128.0488
4971 | 141.4236
4972 | 143.074
4973 | 124.7961
4974 | 144.8205
4975 | 105.6523
4976 | 171.4593
4977 | 140.7249
4978 | 124.1273
4979 | 189.0479
4980 | 133.3037
4981 | 99.4974
4982 | 71.0063
4983 | 140.3029
4984 | 106.8623
4985 | 176.9949
4986 | 81.6848
4987 | 81.3597
4988 | 155.1921
4989 | 133.0495
4990 | 110.2435
4991 | 106.3739
4992 | 112.2594
4993 | 91.3672
4994 | 112.7721
4995 | 136.3178
4996 | 146.7228
4997 | 110.0829
4998 | 130.0709
4999 | 126.9213
5000 | 98.4479
5001 | 108.2321
5002 | 98.1385
5003 | 102.5079
5004 | 75.2896
5005 | 175.7656
5006 | 172.0543
5007 | 114.6376
5008 | 153.0197
5009 | 142.0763
5010 | 129.9236
5011 | 144.1726
5012 | 153.7589
5013 | 106.454
5014 | 137.5387
5015 | 109.917
5016 | 83.0549
5017 | 100.8188
5018 | 130.1167
5019 | 132.046
5020 | 132.8128
5021 | 118.0432
5022 | 142.9215
5023 | 174.8589
5024 | 80.7995
5025 | 107.2946
5026 | 142.1087
5027 | 79.8723
5028 | 98.5021
5029 | 80.4603
5030 | 98.7003
5031 | 137.3032
5032 | 134.0189
5033 | 102.0985
5034 | 120.4505
5035 | 174.7103
5036 | 135.0247
5037 | 102.8999
5038 | 78.7323
5039 | 110.9044
5040 | 162.5706
5041 | 108.9008
5042 | 139.8904
5043 | 136.4628
5044 | 82.6247
5045 | 133.7413
5046 | 121.555
5047 | 110.0207
5048 | 115.4777
5049 | 62.474
5050 | 107.6029
5051 | 122.3284
5052 | 151.1104
5053 | 147.7729
5054 | 129.4634
5055 | 111.518
5056 | 101.3611
5057 | 123.5809
5058 | 111.5861
5059 | 93.2927
5060 | 101.6502
5061 | 80.9428
5062 | 89.1884
5063 | 164.6684
5064 | 142.5061
5065 | 130.0142
5066 | 106.8163
5067 | 108.0352
5068 | 135.4828
5069 | 123.7645
5070 | 124.7202
5071 | 152.6951
5072 | 97.26
5073 | 128.485
5074 | 112.5802
5075 | 99.9286
5076 | 92.737
5077 | 116.4647
5078 | 173.5061
5079 | 176.4647
5080 | 100.4054
5081 | 110.5949
5082 | 132.7155
5083 | 112.7763
5084 | 131.1514
5085 | 123.271
5086 | 114.7161
5087 | 117.2242
5088 | 128.3804
5089 | 180.5881
5090 | 117.8905
5091 | 116.374
5092 | 104.0442
5093 | 130.3162
5094 | 77.9677
5095 | 131.941
5096 | 66.1744
5097 | 82.5866
5098 | 157.299
5099 | 130.2625
5100 | 118.5019
5101 | 127.1316
5102 | 117.5138
5103 | 132.8942
5104 | 115.6192
5105 | 123.774
5106 | 116.35
5107 | 82.9504
5108 | 115.4286
5109 | 106.3588
5110 | 122.0911
5111 | 115.233
5112 | 110.1252
5113 | 139.1041
5114 | 111.1632
5115 | 119.4813
5116 | 89.7631
5117 | 164.1831
5118 | 134.5968
5119 | 117.1736
5120 | 128.7098
5121 | 102.0055
5122 | 130.321
5123 | 96.8027
5124 | 156.3625
5125 | 142.434
5126 | 109.8136
5127 | 115.3782
5128 | 112.2606
5129 | 145.2015
5130 | 101.018
5131 | 154.9023
5132 | 105.5844
5133 | 67.5339
5134 | 173.2629
5135 | 114.2848
5136 | 75.1008
5137 | 128.3148
5138 | 107.4622
5139 | 99.7041
5140 | 101.5866
5141 | 110.7204
5142 | 123.9481
5143 | 94.5307
5144 | 85.1493
5145 | 117.1718
5146 | 132.5925
5147 | 134.8032
5148 | 153.9916
5149 | 96.9097
5150 | 101.8369
5151 | 123.263
5152 | 146.0954
5153 | 109.4415
5154 | 103.1411
5155 | 143.7952
5156 | 156.1616
5157 | 90.6835
5158 | 139.6826
5159 | 112.9706
5160 | 100.7182
5161 | 89.3327
5162 | 115.2912
5163 | 123.0585
5164 | 158.6159
5165 | 153.1033
5166 | 108.5101
5167 | 120.3803
5168 | 110.5759
5169 | 124.1489
5170 | 167.184
5171 | 140.5848
5172 | 92.7556
5173 | 99.6264
5174 | 123.8685
5175 | 107.9718
5176 | 109.8546
5177 | 133.0192
5178 | 99.146
5179 | 122.4592
5180 | 108.1452
5181 | 117.3667
5182 | 89.3089
5183 | 153.6335
5184 | 162.1083
5185 | 125.9563
5186 | 125.6199
5187 | 141.6851
5188 | 145.2654
5189 | 141.9826
5190 | 94.5737
5191 | 120.7219
5192 | 104.124
5193 | 135.7482
5194 | 169.7596
5195 | 61.9382
5196 | 100.132
5197 | 94.797
5198 | 126.5673
5199 | 100.8896
5200 | 132.5025
5201 | 109.5759
5202 | 177.3179
5203 | 164.4066
5204 | 151.0771
5205 | 116.3639
5206 | 138.0379
5207 | 97.4013
5208 | 88.8505
5209 | 59.9988
5210 | 76.5231
5211 | 119.9738
5212 | 119.9794
5213 | 145.707
5214 | 91.8276
5215 | 142.0116
5216 | 106.8758
5217 | 161.4477
5218 | 86.5277
5219 | 146.7283
5220 | 95.1543
5221 | 115.7149
5222 | 102.6156
5223 | 87.5855
5224 | 99.8186
5225 | 98.8828
5226 | 152.8849
5227 | 102.9634
5228 | 173.6618
5229 | 122.4068
5230 | 146.6569
5231 | 146.5704
5232 | 129.3813
5233 | 130.6144
5234 | 89.0587
5235 | 108.5824
5236 | 91.027
5237 | 118.3347
5238 | 164.4167
5239 | 78.975
5240 | 132.7404
5241 | 81.5911
5242 | 124.6534
5243 | 85.6495
5244 | 124.1206
5245 | 157.1563
5246 | 134.3567
5247 | 147.5482
5248 | 136.7187
5249 | 145.3928
5250 | 153.4945
5251 | 87.7184
5252 | 113.9576
5253 | 157.0089
5254 | 85.0374
5255 | 93.1651
5256 | 120.0253
5257 | 115.5317
5258 | 92.7164
5259 | 99.6864
5260 | 108.7724
5261 | 155.6343
5262 | 131.4461
5263 | 159.5674
5264 | 118.6886
5265 | 104.8945
5266 | 137.5653
5267 | 114.1345
5268 | 125.2947
5269 | 132.2058
5270 | 89.2807
5271 | 117.8606
5272 | 132.1204
5273 | 163.2641
5274 | 95.8496
5275 | 95.9457
5276 | 150.5752
5277 | 127.0198
5278 | 120.3306
5279 | 121.5325
5280 | 92.1862
5281 | 94.9305
5282 | 105.5474
5283 | 136.4654
5284 | 140.4458
5285 | 131.1066
5286 | 99.2699
5287 | 148.3412
5288 | 113.5013
5289 | 107.5831
5290 | 146.3187
5291 | 113.9779
5292 | 92.1578
5293 | 152.5268
5294 | 94.9902
5295 | 121.8235
5296 | 74.7792
5297 | 111.085
5298 | 140.0276
5299 | 119.2279
5300 | 172.6726
5301 | 103.4983
5302 | 74.321
5303 | 121.7851
5304 | 103.0518
5305 | 99.7958
5306 | 105.321
5307 | 154.4054
5308 | 151.4127
5309 | 148.2545
5310 | 109.2563
5311 | 120.3493
5312 | 89.7612
5313 | 146.0071
5314 | 149.9306
5315 | 162.3143
5316 | 83.9555
5317 | 146.9171
5318 | 113.2252
5319 | 134.5282
5320 | 149.286
5321 | 110.9152
5322 | 112.792
5323 | 112.8371
5324 | 94.3292
5325 | 104.997
5326 | 125.3167
5327 | 134.246
5328 | 88.0674
5329 | 155.7651
5330 | 137.8636
5331 | 157.0307
5332 | 127.1755
5333 | 125.8414
5334 | 129.9495
5335 | 128.387
5336 | 113.6487
5337 | 115.6935
5338 | 131.8787
5339 | 125.0086
5340 | 171.5547
5341 | 123.2296
5342 | 168.5786
5343 | 118.2381
5344 | 97.572
5345 | 142.8547
5346 | 107.639
5347 | 88.3145
5348 | 122.4146
5349 | 141.9154
5350 | 136.0047
5351 | 141.933
5352 | 117.8282
5353 | 112.5839
5354 | 88.4853
5355 | 139.2114
5356 | 131.7212
5357 | 168.1305
5358 | 97.7368
5359 | 121.1153
5360 | 112.6588
5361 | 106.8633
5362 | 128.2508
5363 | 89.2178
5364 | 137.3256
5365 | 108.675
5366 | 167.1831
5367 | 98.3189
5368 | 118.1634
5369 | 138.4518
5370 | 145.9779
5371 | 156.1462
5372 | 150.9372
5373 | 70.7997
5374 | 100.9044
5375 | 114.2612
5376 | 96.5358
5377 | 164.0367
5378 | 110.2992
5379 | 157.7243
5380 | 147.9046
5381 | 121.2751
5382 | 93.4862
5383 | 152.1747
5384 | 150.3908
5385 | 95.3967
5386 | 149.8944
5387 | 146.4266
5388 | 120.1501
5389 | 161.6588
5390 | 128.8846
5391 | 126.5568
5392 | 89.6117
5393 | 86.1044
5394 | 133.3725
5395 | 116.1844
5396 | 98.3786
5397 | 131.6513
5398 | 128.2431
5399 | 127.913
5400 | 122.5829
5401 | 106.4468
5402 | 150.0999
5403 | 119.0881
5404 | 107.9354
5405 | 56.7167
5406 | 149.4695
5407 | 128.2388
5408 | 121.3657
5409 | 111.3073
5410 | 142.6498
5411 | 82.5401
5412 | 81.1211
5413 | 146.9284
5414 | 110.8966
5415 | 110.1323
5416 | 108.3388
5417 | 167.7747
5418 | 61.3046
5419 | 139.3894
5420 | 148.5777
5421 | 139.518
5422 | 129.7198
5423 | 102.1556
5424 | 112.3109
5425 | 194.937
5426 | 154.6032
5427 | 132.3606
5428 | 114.1822
5429 | 67.1713
5430 | 74.6398
5431 | 114.6525
5432 | 156.6076
5433 | 111.995
5434 | 151.9845
5435 | 99.0154
5436 | 103.8371
5437 | 140.7294
5438 | 108.0996
5439 | 85.2888
5440 | 147.2195
5441 | 123.2096
5442 | 89.4509
5443 | 169.594
5444 | 100.399
5445 | 136.8157
5446 | 101.6874
5447 | 162.7943
5448 | 133.9665
5449 | 134.8421
5450 | 150.1009
5451 | 146.0868
5452 | 121.2792
5453 | 126.6382
5454 | 153.1845
5455 | 97.9595
5456 | 88.4792
5457 | 132.8123
5458 | 136.9951
5459 | 135.2784
5460 | 148.2269
5461 | 151.2072
5462 | 92.1273
5463 | 102.0464
5464 | 85.4468
5465 | 100.9586
5466 | 154.3121
5467 | 90.6679
5468 | 149.081
5469 | 104.9182
5470 | 78.822
5471 | 110.5929
5472 | 91.6736
5473 | 139.064
5474 | 109.7857
5475 | 92.149
5476 | 123.5023
5477 | 75.0848
5478 | 74.762
5479 | 106.7505
5480 | 141.5991
5481 | 137.8092
5482 | 129.4752
5483 | 98.7068
5484 | 84.981
5485 | 98.6994
5486 | 136.5654
5487 | 119.9239
5488 | 136.8505
5489 | 116.3322
5490 | 104.4733
5491 | 159.4708
5492 | 119.6529
5493 | 146.1971
5494 | 100.7047
5495 | 130.5414
5496 | 89.3524
5497 | 112.6295
5498 | 143.8806
5499 | 125.6177
5500 | 101.8851
5501 | 107.0308
5502 | 105.7178
5503 | 110.1096
5504 | 82.5719
5505 | 108.3109
5506 | 152.4562
5507 | 128.4788
5508 | 84.0044
5509 | 126.924
5510 | 109.842
5511 | 130.3288
5512 | 100.8403
5513 | 119.3882
5514 | 97.2274
5515 | 82.632
5516 | 86.6476
5517 | 93.0447
5518 | 150.9225
5519 | 113.5355
5520 | 135.2307
5521 | 119.0913
5522 | 161.0705
5523 | 144.1019
5524 | 146.0487
5525 | 131.3383
5526 | 106.2965
5527 | 123.2464
5528 | 140.0005
5529 | 139.7257
5530 | 120.9538
5531 | 108.0818
5532 | 115.3658
5533 | 125.7212
5534 | 123.4034
5535 | 136.2092
5536 | 128.3329
5537 | 119.8019
5538 | 81.2441
5539 | 124.9275
5540 | 116.1108
5541 | 103.2052
5542 | 135.7179
5543 | 142.592
5544 | 120.3357
5545 | 100.2158
5546 | 108.8327
5547 | 157.9746
5548 | 133.5327
5549 | 147.3887
5550 | 138.2387
5551 | 98.2135
5552 | 92.3403
5553 | 83.8422
5554 | 99.1662
5555 | 115.4047
5556 | 162.122
5557 | 128.1
5558 | 101.6295
5559 | 101.9249
5560 | 109.5792
5561 | 133.006
5562 | 122.8848
5563 | 112.5195
5564 | 123.7375
5565 | 86.1583
5566 | 141.9248
5567 | 94.663
5568 | 138.6727
5569 | 89.3909
5570 | 105.168
5571 | 145.1175
5572 | 155.2806
5573 | 127.0188
5574 | 120.787
5575 | 109.169
5576 | 65.4421
5577 | 117.4046
5578 | 116.6247
5579 | 122.1446
5580 | 84.9622
5581 | 113.1963
5582 | 151.2909
5583 | 76.6772
5584 | 140.5545
5585 | 117.2259
5586 | 186.5525
5587 | 148.7259
5588 | 130.1053
5589 | 79.3898
5590 | 118.1139
5591 | 108.4005
5592 | 121.5353
5593 | 128.8898
5594 | 123.1363
5595 | 132.2862
5596 | 105.6186
5597 | 113.0185
5598 | 109.7299
5599 | 114.6712
5600 | 121.3992
5601 | 110.0546
5602 | 80.2275
5603 | 94.3439
5604 | 136.2259
5605 | 68.445
5606 | 139.7007
5607 | 122.969
5608 | 182.121
5609 | 123.3175
5610 | 129.8649
5611 | 100.9976
5612 | 101.1333
5613 | 87.2902
5614 | 134.1463
5615 | 88.2748
5616 | 118.7953
5617 | 108.5914
5618 | 128.217
5619 | 111.502
5620 | 134.607
5621 | 77.4916
5622 | 94.6922
5623 | 78.6794
5624 | 106.419
5625 | 94.6885
5626 | 138.865
5627 | 88.8104
5628 | 124.3308
5629 | 106.1597
5630 | 106.6495
5631 | 154.2558
5632 | 96.2644
5633 | 114.4705
5634 | 98.0049
5635 | 138.7374
5636 | 101.0251
5637 | 174.5322
5638 | 116.5608
5639 | 149.2581
5640 | 141.096
5641 | 109.6237
5642 | 114.514
5643 | 98.3922
5644 | 72.3929
5645 | 112.951
5646 | 134.0603
5647 | 144.2341
5648 | 130.6372
5649 | 157.226
5650 | 103.1838
5651 | 73.7523
5652 | 77.0729
5653 | 145.7626
5654 | 121.921
5655 | 130.8132
5656 | 116.6499
5657 | 92.1783
5658 | 119.7049
5659 | 142.7294
5660 | 101.4575
5661 | 126.5537
5662 | 78.423
5663 | 115.4864
5664 | 102.1785
5665 | 113.3634
5666 | 114.4516
5667 | 77.0489
5668 | 129.9154
5669 | 129.9293
5670 | 116.2692
5671 | 104.3672
5672 | 133.9902
5673 | 142.0533
5674 | 117.0359
5675 | 129.7328
5676 | 121.2996
5677 | 132.7216
5678 | 106.9503
5679 | 89.4232
5680 | 115.9045
5681 | 104.5049
5682 | 151.8543
5683 | 140.956
5684 | 127.4869
5685 | 131.9015
5686 | 115.0052
5687 | 112.9475
5688 | 160.2673
5689 | 108.4512
5690 | 118.5986
5691 | 132.9993
5692 | 95.3583
5693 | 117.6297
5694 | 129.4119
5695 | 145.3487
5696 | 85.8653
5697 | 105.7886
5698 | 109.3015
5699 | 106.7468
5700 | 104.5286
5701 | 117.2292
5702 | 171.6155
5703 | 76.538
5704 | 117.2203
5705 | 95.8016
5706 | 130.0985
5707 | 112.6879
5708 | 151.8693
5709 | 124.4284
5710 | 157.256
5711 | 132.592
5712 | 133.7588
5713 | 154.3544
5714 | 140.5206
5715 | 101.1912
5716 | 107.1797
5717 | 116.7454
5718 | 171.1224
5719 | 125.8005
5720 | 148.7282
5721 | 78.9047
5722 | 98.3025
5723 | 133.3958
5724 | 114.2469
5725 | 98.7326
5726 | 105.8284
5727 | 130.7541
5728 | 120.8888
5729 | 110.0148
5730 | 124.15
5731 | 133.8754
5732 | 118.7926
5733 | 135.4935
5734 | 144.7781
5735 | 144.5559
5736 | 101.9349
5737 | 164.7662
5738 | 120.6383
5739 | 145.4177
5740 | 135.1041
5741 | 146.2923
5742 | 60.3956
5743 | 133.6489
5744 | 137.2091
5745 | 142.0594
5746 | 113.8444
5747 | 134.4642
5748 | 124.7575
5749 | 120.9998
5750 | 103.3315
5751 | 132.3788
5752 | 92.8524
5753 | 70.9413
5754 | 130.733
5755 | 119.2105
5756 | 124.1546
5757 | 134.6851
5758 | 117.332
5759 | 152.396
5760 | 107.6852
5761 | 118.4218
5762 | 89.9602
5763 | 108.5175
5764 | 92.7541
5765 | 107.9279
5766 | 144.8759
5767 | 147.418
5768 | 116.6226
5769 | 81.4216
5770 | 151.3611
5771 | 111.0223
5772 | 119.1484
5773 | 125.334
5774 | 145.1231
5775 | 129.2129
5776 | 168.8642
5777 | 168.9696
5778 | 122.8637
5779 | 153.592
5780 | 160.5589
5781 | 92.0098
5782 | 122.3794
5783 | 102.4775
5784 | 114.773
5785 | 131.7824
5786 | 126.6686
5787 | 121.0607
5788 | 122.2391
5789 | 116.5882
5790 | 135.1226
5791 | 135.0857
5792 | 136.8064
5793 | 146.7246
5794 | 141.1794
5795 | 131.2027
5796 | 124.0117
5797 | 105.3496
5798 | 150.2384
5799 | 81.9935
5800 | 133.065
5801 | 110.4897
5802 | 136.9846
5803 | 135.6355
5804 | 134.9903
5805 | 151.7
5806 | 129.5549
5807 | 94.1271
5808 | 96.237
5809 | 117.5823
5810 | 103.2938
5811 | 129.2175
5812 | 104.7603
5813 | 125.2977
5814 | 98.1493
5815 | 122.3007
5816 | 140.8737
5817 | 147.5449
5818 | 117.3885
5819 | 140.5067
5820 | 139.2638
5821 | 147.8465
5822 | 61.7943
5823 | 99.4635
5824 | 88.6013
5825 | 133.1257
5826 | 132.412
5827 | 151.9766
5828 | 139.8611
5829 | 136.7265
5830 | 133.0508
5831 | 104.165
5832 | 101.6466
5833 | 115.838
5834 | 119.0903
5835 | 92.0073
5836 | 98.0159
5837 | 108.3889
5838 | 149.2985
5839 | 117.2132
5840 | 121.7015
5841 | 137.4975
5842 | 116.9659
5843 | 94.2522
5844 | 122.4701
5845 | 181.4648
5846 | 80.553
5847 | 128.4101
5848 | 102.4258
5849 | 112.5637
5850 | 165.3064
5851 | 98.7462
5852 | 140.0953
5853 | 130.9779
5854 | 105.7357
5855 | 114.9567
5856 | 95.0584
5857 | 120.7355
5858 | 91.8289
5859 | 163.5907
5860 | 132.4406
5861 | 90.421
5862 | 124.3567
5863 | 97.1487
5864 | 119.4911
5865 | 153.5264
5866 | 96.3744
5867 | 146.9421
5868 | 62.6886
5869 | 94.9113
5870 | 127.5873
5871 | 96.6079
5872 | 139.8204
5873 | 129.292
5874 | 99.7723
5875 | 86.3922
5876 | 121.4102
5877 | 96.6528
5878 | 149.943
5879 | 146.3334
5880 | 138.4131
5881 | 126.4162
5882 | 117.9849
5883 | 153.4895
5884 | 165.4856
5885 | 132.6703
5886 | 137.3599
5887 | 144.0339
5888 | 95.5778
5889 | 109.7017
5890 | 135.449
5891 | 156.3709
5892 | 133.7916
5893 | 167.4274
5894 | 127.362
5895 | 103.882
5896 | 116.4434
5897 | 128.2032
5898 | 91.5125
5899 | 84.6734
5900 | 119.0686
5901 | 118.9315
5902 | 95.6635
5903 | 118.7136
5904 | 106.5951
5905 | 115.119
5906 | 145.9697
5907 | 78.2444
5908 | 113.6906
5909 | 112.0819
5910 | 102.3556
5911 | 82.0717
5912 | 142.6303
5913 | 89.4661
5914 | 103.3928
5915 | 114.0761
5916 | 110.1343
5917 | 136.7372
5918 | 120.7479
5919 | 132.5122
5920 | 129.4471
5921 | 82.6302
5922 | 144.5797
5923 | 119.3325
5924 | 118.0184
5925 | 90.9949
5926 | 126.7526
5927 | 128.8986
5928 | 85.0242
5929 | 150.3065
5930 | 120.3843
5931 | 134.3117
5932 | 85.4023
5933 | 91.8146
5934 | 114.7556
5935 | 136.6722
5936 | 148.8308
5937 | 107.4063
5938 | 72.7169
5939 | 127.7468
5940 | 141.037
5941 | 90.1333
5942 | 141.6821
5943 | 162.0515
5944 | 127.0148
5945 | 154.5864
5946 | 88.4386
5947 | 123.1514
5948 | 97.1925
5949 | 86.4161
5950 | 105.7412
5951 | 129.2895
5952 | 170.7998
5953 | 159.4108
5954 | 160.6445
5955 | 108.9499
5956 | 94.4894
5957 | 125.1897
5958 | 79.9761
5959 | 129.6353
5960 | 166.234
5961 | 138.2801
5962 | 145.8644
5963 | 142.7955
5964 | 92.6101
5965 | 139.833
5966 | 127.7361
5967 | 114.7851
5968 | 139.015
5969 | 114.0098
5970 | 116.8306
5971 | 149.5951
5972 | 128.8566
5973 | 132.6874
5974 | 112.7836
5975 | 125.2336
5976 | 125.2895
5977 | 138.9473
5978 | 138.8711
5979 | 107.5767
5980 | 142.9881
5981 | 128.7503
5982 | 123.9063
5983 | 129.2651
5984 | 145.3422
5985 | 111.7714
5986 | 119.525
5987 | 81.9875
5988 | 126.8878
5989 | 124.6974
5990 | 127.363
5991 | 83.3549
5992 | 134.4874
5993 | 144.4662
5994 | 143.1387
5995 | 82.3013
5996 | 83.9179
5997 | 119.3758
5998 | 140.2522
5999 | 105.7022
6000 | 118.7128
6001 | 131.6641
6002 | 124.0609
6003 | 140.7962
6004 | 127.2616
6005 | 80.2414
6006 | 99.9824
6007 | 105.0408
6008 | 98.387
6009 | 142.1512
6010 | 90.5687
6011 | 87.4179
6012 | 116.5112
6013 | 133.5055
6014 | 65.8623
6015 | 157.1388
6016 | 118.0113
6017 | 90.3325
6018 | 139.5286
6019 | 83.1141
6020 | 122.6065
6021 | 98.988
6022 | 136.9489
6023 | 108.8077
6024 | 69.1151
6025 | 110.0514
6026 | 113.1973
6027 | 130.6759
6028 | 135.0097
6029 | 95.854
6030 | 108.1544
6031 | 104.0258
6032 | 149.2894
6033 | 105.9786
6034 | 133.4751
6035 | 121.5066
6036 | 140.9484
6037 | 105.1557
6038 | 145.7952
6039 | 133.6875
6040 | 101.9053
6041 | 138.5904
6042 | 96.3394
6043 | 129.5252
6044 | 127.9788
6045 | 122.4037
6046 | 99.6337
6047 | 107.7132
6048 | 166.8198
6049 | 139.8493
6050 | 140.324
6051 | 112.7318
6052 | 120.4284
6053 | 110.7001
6054 | 126.8878
6055 | 96.8822
6056 | 81.5979
6057 | 102.6907
6058 | 125.4303
6059 | 154.311
6060 | 145.041
6061 | 113.7646
6062 | 110.3026
6063 | 107.527
6064 | 133.5402
6065 | 102.2775
6066 | 92.5712
6067 | 87.6174
6068 | 155.166
6069 | 130.1307
6070 | 127.1268
6071 | 111.9169
6072 | 100.4227
6073 | 103.2901
6074 | 102.0973
6075 | 136.4764
6076 | 97.1138
6077 | 123.4382
6078 | 105.2737
6079 | 89.1808
6080 | 144.8049
6081 | 85.2992
6082 | 118.8033
6083 | 136.3095
6084 | 141.9234
6085 | 145.2573
6086 | 126.1392
6087 | 107.6785
6088 | 113.0275
6089 | 105.4254
6090 | 129.8198
6091 | 111.9938
6092 | 97.2479
6093 | 84.5711
6094 | 128.2342
6095 | 112.0779
6096 | 116.8516
6097 | 122.2307
6098 | 108.6911
6099 | 129.1233
6100 | 101.1918
6101 | 115.8339
6102 | 101.2893
6103 | 127.1951
6104 | 114.5932
6105 | 94.7087
6106 | 132.1899
6107 | 87.6216
6108 | 109.3374
6109 | 130.0926
6110 | 79.9252
6111 | 151.8152
6112 | 100.9281
6113 | 134.8833
6114 | 142.0485
6115 | 134.4165
6116 | 129.8154
6117 | 131.3521
6118 | 154.2979
6119 | 131.8463
6120 | 102.2242
6121 | 134.9747
6122 | 83.3544
6123 | 126.1549
6124 | 142.4262
6125 | 115.904
6126 | 154.1652
6127 | 101.3574
6128 | 114.7033
6129 | 107.5071
6130 | 133.5867
6131 | 110.1773
6132 | 137.0052
6133 | 136.8767
6134 | 66.8775
6135 | 153.058
6136 | 139.0263
6137 | 144.034
6138 | 160.7816
6139 | 151.0973
6140 | 101.3698
6141 | 132.4174
6142 | 126.0394
6143 | 128.1213
6144 | 136.9227
6145 | 139.9823
6146 | 114.0388
6147 | 82.2449
6148 | 83.7953
6149 | 165.0747
6150 | 73.6734
6151 | 127.5233
6152 | 120.5786
6153 | 124.4387
6154 | 148.1132
6155 | 145.4628
6156 | 140.1414
6157 | 109.8791
6158 | 128.1142
6159 | 119.5652
6160 | 96.9995
6161 | 116.8162
6162 | 98.8683
6163 | 97.0066
6164 | 115.5304
6165 | 101.8532
6166 | 154.5778
6167 | 194.4926
6168 | 125.1527
6169 | 193.7215
6170 | 128.5761
6171 | 112.5928
6172 | 122.4745
6173 | 109.225
6174 | 155.7696
6175 | 115.1687
6176 | 110.358
6177 | 134.1746
6178 | 139.0015
6179 | 83.4069
6180 | 121.4821
6181 | 93.1076
6182 | 125.5707
6183 | 143.6438
6184 | 120.6243
6185 | 123.0589
6186 | 158.2796
6187 | 89.9721
6188 | 109.9293
6189 | 116.8686
6190 | 159.2954
6191 | 118.1038
6192 | 119.2907
6193 | 124.5074
6194 | 96.6189
6195 | 127.8359
6196 | 117.6827
6197 | 156.3782
6198 | 103.5687
6199 | 129.6566
6200 | 98.7882
6201 | 94.9598
6202 | 80.1028
6203 | 98.5552
6204 | 102.3562
6205 | 154.5447
6206 | 100.1846
6207 | 145.8494
6208 | 128.9911
6209 | 94.3859
6210 | 97.3694
6211 | 126.3578
6212 | 137.0606
6213 | 136.5814
6214 | 149.1275
6215 | 109.6554
6216 | 150.7854
6217 | 135.613
6218 | 130.3691
6219 | 128.5562
6220 | 106.1705
6221 | 128.862
6222 | 136.802
6223 | 134.2133
6224 | 158.1681
6225 | 140.4063
6226 | 141.0173
6227 | 99.6988
6228 | 115.4131
6229 | 126.7852
6230 | 110.0824
6231 | 111.2763
6232 | 124.6072
6233 | 158.5075
6234 | 72.3756
6235 | 107.6871
6236 | 134.9093
6237 | 96.2819
6238 | 80.7851
6239 | 125.1523
6240 | 113.8857
6241 | 103.6565
6242 | 163.2772
6243 | 118.29
6244 | 91.7127
6245 | 93.6662
6246 | 141.9023
6247 | 164.1068
6248 | 107.421
6249 | 127.1075
6250 | 127.2863
6251 | 139.0615
6252 | 148.6575
6253 | 85.5814
6254 | 169.3123
6255 | 74.0046
6256 | 137.9737
6257 | 110.1654
6258 | 151.8406
6259 | 131.1849
6260 | 116.0763
6261 | 139.0648
6262 | 128.5011
6263 | 111.8183
6264 | 79.9558
6265 | 176.4284
6266 | 107.2351
6267 | 143.26
6268 | 122.7815
6269 | 121.906
6270 | 163.8083
6271 | 138.1235
6272 | 122.2199
6273 | 92.6388
6274 | 110.4618
6275 | 120.728
6276 | 112.0754
6277 | 101.0884
6278 | 147.8738
6279 | 126.214
6280 | 97.7335
6281 | 133.4175
6282 | 133.3099
6283 | 172.2948
6284 | 82.2084
6285 | 152.8258
6286 | 142.251
6287 | 160.5694
6288 | 75.7097
6289 | 99.4067
6290 | 83.4402
6291 | 130.3821
6292 | 119.8958
6293 | 118.5659
6294 | 124.3353
6295 | 90.1262
6296 | 128.7405
6297 | 121.893
6298 | 80.5017
6299 | 113.6937
6300 | 104.5698
6301 | 175.0083
6302 | 102.3996
6303 | 96.251
6304 | 76.0456
6305 | 165.4407
6306 | 104.1717
6307 | 116.9447
6308 | 145.1584
6309 | 129.1844
6310 | 132.1056
6311 | 106.2406
6312 | 103.5519
6313 | 116.1875
6314 | 152.1021
6315 | 94.8326
6316 | 123.5939
6317 | 98.7576
6318 | 111.543
6319 | 90.7664
6320 | 136.1684
6321 | 107.4954
6322 | 71.1888
6323 | 106.587
6324 | 115.4647
6325 | 85.0829
6326 | 156.7237
6327 | 93.0614
6328 | 138.2518
6329 | 100.655
6330 | 83.5367
6331 | 134.7589
6332 | 161.282
6333 | 130.7968
6334 | 107.0253
6335 | 131.9091
6336 | 89.2912
6337 | 141.3583
6338 | 110.4118
6339 | 96.8805
6340 | 154.4333
6341 | 89.5617
6342 | 124.5275
6343 | 81.3103
6344 | 69.563
6345 | 125.1837
6346 | 130.9571
6347 | 103.7652
6348 | 160.0428
6349 | 150.3063
6350 | 139.6961
6351 | 103.7745
6352 | 104.3392
6353 | 146.3015
6354 | 105.993
6355 | 76.4185
6356 | 74.6584
6357 | 172.4783
6358 | 148.8736
6359 | 86.5399
6360 | 115.8922
6361 | 112.1691
6362 | 128.0743
6363 | 110.7892
6364 | 98.4433
6365 | 115.6287
6366 | 163.3114
6367 | 182.6838
6368 | 123.7717
6369 | 100.0932
6370 | 99.7999
6371 | 112.4621
6372 | 141.1195
6373 | 100.301
6374 | 102.2307
6375 | 160.1447
6376 | 85.508
6377 | 129.9209
6378 | 147.4934
6379 | 100.9863
6380 | 103.4519
6381 | 85.5488
6382 | 131.0095
6383 | 120.2821
6384 | 120.5468
6385 | 96.3908
6386 | 98.7795
6387 | 101.7585
6388 | 137.6908
6389 | 111.0485
6390 | 131.4667
6391 | 147.0223
6392 | 101.709
6393 | 129.872
6394 | 125.6542
6395 | 125.0308
6396 | 112.4102
6397 | 144.7977
6398 | 75.0513
6399 | 128.5993
6400 | 90.8434
6401 | 130.7982
6402 | 112.2037
6403 | 110.4446
6404 | 102.9722
6405 | 94.4324
6406 | 116.569
6407 | 140.2292
6408 | 123.8425
6409 | 103.3362
6410 | 137.9589
6411 | 151.6578
6412 | 107.7169
6413 | 111.9205
6414 | 101.51
6415 | 121.6364
6416 | 125.3166
6417 | 136.0029
6418 | 106.6431
6419 | 116.937
6420 | 135.9594
6421 | 138.0238
6422 | 100.9621
6423 | 118.4038
6424 | 107.06
6425 | 100.2551
6426 | 118.841
6427 | 116.5193
6428 | 163.0604
6429 | 103.1283
6430 | 157.9284
6431 | 99.5025
6432 | 160.3585
6433 | 173.3069
6434 | 97.9994
6435 | 118.5458
6436 | 103.6101
6437 | 107.288
6438 | 152.4097
6439 | 134.4547
6440 | 151.9095
6441 | 97.6893
6442 | 77.7026
6443 | 116.2316
6444 | 117.2113
6445 | 109.3768
6446 | 116.4627
6447 | 114.11
6448 | 164.6018
6449 | 113.1885
6450 | 106.8107
6451 | 128.2451
6452 | 127.6869
6453 | 109.4744
6454 | 104.3254
6455 | 160.6498
6456 | 126.7951
6457 | 119.8181
6458 | 121.4427
6459 | 99.2522
6460 | 101.0395
6461 | 109.7941
6462 | 127.011
6463 | 85.8564
6464 | 146.0645
6465 | 84.1012
6466 | 110.0858
6467 | 111.0237
6468 | 112.1487
6469 | 148.12
6470 | 139.729
6471 | 111.8418
6472 | 107.5105
6473 | 138.0441
6474 | 122.1917
6475 | 85.6429
6476 | 106.4137
6477 | 138.2986
6478 | 147.9803
6479 | 135.4043
6480 | 105.5378
6481 | 128.8823
6482 | 150.4043
6483 | 127.9781
6484 | 129.6143
6485 | 146.3145
6486 | 126.6192
6487 | 115.1459
6488 | 105.5983
6489 | 117.4485
6490 | 112.9525
6491 | 124.5712
6492 | 132.2218
6493 | 104.5701
6494 | 111.3113
6495 | 126.7352
6496 | 124.8035
6497 | 116.8157
6498 | 166.4456
6499 | 139.5861
6500 | 154.2727
6501 | 112.068
6502 | 144.028
6503 | 81.5756
6504 | 90.2745
6505 | 164.2477
6506 | 75.5611
6507 | 99.3049
6508 | 124.7107
6509 | 134.0981
6510 | 137.5323
6511 | 131.3068
6512 | 51.8159
6513 | 125.0611
6514 | 118.0633
6515 | 143.1553
6516 | 148.5542
6517 | 123.4906
6518 | 99.9355
6519 | 144.7021
6520 | 134.0822
6521 | 103.4145
6522 | 88.0282
6523 | 103.5599
6524 | 125.6442
6525 | 90.9589
6526 | 121.5781
6527 | 143.4539
6528 | 95.246
6529 | 106.0662
6530 | 136.8261
6531 | 162.3837
6532 | 138.2413
6533 | 102.8031
6534 | 96.3404
6535 | 108.721
6536 | 104.9868
6537 | 155.4073
6538 | 112.1356
6539 | 80.8423
6540 | 139.6048
6541 | 120.0858
6542 | 97.4833
6543 | 151.3
6544 | 108.5451
6545 | 148.4839
6546 | 154.2499
6547 | 128.7158
6548 | 82.6658
6549 | 117.8472
6550 | 123.6384
6551 | 99.6512
6552 | 109.0002
6553 | 137.033
6554 | 81.0334
6555 | 186.1095
6556 | 144.8574
6557 | 113.4476
6558 | 101.471
6559 | 87.5938
6560 | 119.2348
6561 | 99.6867
6562 | 96.934
6563 | 72.5092
6564 | 130.8374
6565 | 103.7633
6566 | 111.9003
6567 | 146.5295
6568 | 129.3471
6569 | 79.9917
6570 | 105.553
6571 | 73.5797
6572 | 148.9405
6573 | 108.4683
6574 | 124.5685
6575 | 126.8535
6576 | 131.4208
6577 | 77.4802
6578 | 129.3471
6579 | 158.9238
6580 | 124.8569
6581 | 134.2098
6582 | 75.0121
6583 | 122.4536
6584 | 77.1044
6585 | 124.8562
6586 | 117.8224
6587 | 50.207
6588 | 107.9836
6589 | 129.4988
6590 | 138.6765
6591 | 125.797
6592 | 103.8855
6593 | 132.1186
6594 | 103.4516
6595 | 115.522
6596 | 116.8915
6597 | 113.6855
6598 | 138.2289
6599 | 82.3454
6600 | 85.6413
6601 | 118.7317
6602 | 142.0964
6603 | 145.7406
6604 | 129.1441
6605 | 91.4276
6606 | 113.0026
6607 | 78.6831
6608 | 121.156
6609 | 104.8628
6610 | 182.3613
6611 | 135.8847
6612 | 122.7399
6613 | 123.81
6614 | 119.0112
6615 | 102.6825
6616 | 92.9812
6617 | 112.2919
6618 | 110.867
6619 | 79.1231
6620 | 97.1978
6621 | 86.9365
6622 | 118.9968
6623 | 59.7069
6624 | 108.4445
6625 | 125.3194
6626 | 110.5678
6627 | 110.2574
6628 | 128.728
6629 | 107.2833
6630 | 122.4213
6631 | 109.0839
6632 | 110.7438
6633 | 97.1635
6634 | 109.934
6635 | 154.2998
6636 | 105.1791
6637 | 117.6448
6638 | 85.495
6639 | 177.2351
6640 | 151.7878
6641 | 116.803
6642 | 147.1517
6643 | 158.9098
6644 | 138.3885
6645 | 128.7065
6646 | 124.2093
6647 | 161.2931
6648 | 132.034
6649 | 116.3745
6650 | 127.9229
6651 | 123.1897
6652 | 130.0759
6653 | 113.2751
6654 | 112.0704
6655 | 122.6849
6656 | 106.5429
6657 | 155.3924
6658 | 134.0867
6659 | 148.9538
6660 | 122.1054
6661 | 160.9347
6662 | 106.5574
6663 | 95.6725
6664 | 108.9797
6665 | 107.4163
6666 | 113.0722
6667 | 117.0521
6668 | 92.924
6669 | 100.7773
6670 | 92.1589
6671 | 156.4669
6672 | 97.8475
6673 | 74.7103
6674 | 114.4691
6675 | 130.582
6676 | 166.2726
6677 | 89.8538
6678 | 120.9458
6679 | 139.5177
6680 | 144.8149
6681 | 118.8954
6682 | 89.8048
6683 | 122.9501
6684 | 148.2176
6685 | 140.6525
6686 | 129.7974
6687 | 88.3684
6688 | 179.7094
6689 | 117.8145
6690 | 138.7162
6691 | 122.6568
6692 | 115.0585
6693 | 116.6466
6694 | 150.6274
6695 | 117.7775
6696 | 121.5082
6697 | 135.4257
6698 | 122.5869
6699 | 113.3093
6700 | 71.6193
6701 | 176.795
6702 | 139.5214
6703 | 140.9808
6704 | 73.5872
6705 | 143.2153
6706 | 59.0205
6707 | 112.0037
6708 | 109.9443
6709 | 121.8983
6710 | 116.2047
6711 | 118.3323
6712 | 82.9212
6713 | 125.1216
6714 | 120.8714
6715 | 100.5151
6716 | 126.7465
6717 | 148.8827
6718 | 81.5959
6719 | 101.4252
6720 | 102.0224
6721 | 122.5585
6722 | 72.6981
6723 | 118.3397
6724 | 104.1486
6725 | 99.2916
6726 | 166.7306
6727 | 129.9082
6728 | 121.5279
6729 | 120.587
6730 | 108.2756
6731 | 129.0277
6732 | 98.2935
6733 | 116.9436
6734 | 117.4744
6735 | 156.6462
6736 | 105.2816
6737 | 73.0695
6738 | 105.4239
6739 | 103.4088
6740 | 110.2929
6741 | 115.0771
6742 | 74.2113
6743 | 105.2496
6744 | 141.9941
6745 | 114.4152
6746 | 162.9104
6747 | 141.3635
6748 | 97.6821
6749 | 109.2423
6750 | 123.108
6751 | 82.9409
6752 | 126.6726
6753 | 122.5264
6754 | 131.4999
6755 | 115.3751
6756 | 124.5466
6757 | 114.5454
6758 | 75.7976
6759 | 113.0486
6760 | 140.0905
6761 | 112.6086
6762 | 153.2513
6763 | 107.7066
6764 | 136.1413
6765 | 79.7303
6766 | 161.4533
6767 | 111.8036
6768 | 123.4515
6769 | 102.5719
6770 | 128.0171
6771 | 88.683
6772 | 99.4423
6773 | 140.0268
6774 | 149.5438
6775 | 77.1753
6776 | 64.6436
6777 | 126.1546
6778 | 135.7463
6779 | 99.457
6780 | 126.9306
6781 | 120.7943
6782 | 130.2476
6783 | 148.7366
6784 | 128.9126
6785 | 132.8617
6786 | 130.9789
6787 | 169.8688
6788 | 129.1344
6789 | 129.922
6790 | 158.6998
6791 | 119.9422
6792 | 94.3176
6793 | 77.5707
6794 | 99.4121
6795 | 106.9291
6796 | 58.884
6797 | 119.8695
6798 | 61.5375
6799 | 157.5562
6800 | 106.0483
6801 | 126.4149
6802 | 115.7964
6803 | 107.4684
6804 | 134.3562
6805 | 136.8857
6806 | 150.0329
6807 | 131.1486
6808 | 133.6456
6809 | 114.1142
6810 | 142.4506
6811 | 86.8733
6812 | 105.48
6813 | 105.0579
6814 | 124.6118
6815 | 134.3172
6816 | 162.2196
6817 | 111.6031
6818 | 166.3369
6819 | 139.6401
6820 | 106.6824
6821 | 64.387
6822 | 134.4365
6823 | 78.1716
6824 | 116.2569
6825 | 144.1925
6826 | 111.2622
6827 | 135.1499
6828 | 143.1785
6829 | 115.0273
6830 | 121.8463
6831 | 64.1789
6832 | 87.5197
6833 | 123.4133
6834 | 68.521
6835 | 124.1761
6836 | 156.4274
6837 | 109.6032
6838 | 93.0407
6839 | 105.0956
6840 | 125.7996
6841 | 116.4715
6842 | 114.0263
6843 | 134.0861
6844 | 127.2148
6845 | 117.0972
6846 | 67.9365
6847 | 139.6013
6848 | 105.7626
6849 | 105.8457
6850 | 140.0519
6851 | 128.6556
6852 | 123.1884
6853 | 117.2646
6854 | 104.2646
6855 | 139.1045
6856 | 99.1082
6857 | 111.7184
6858 | 122.5662
6859 | 130.4447
6860 | 124.8198
6861 | 143.5544
6862 | 117.0748
6863 | 130.9596
6864 | 88.7295
6865 | 95.7462
6866 | 100.7437
6867 | 119.4098
6868 | 100.8102
6869 | 107.0299
6870 | 161.7578
6871 | 88.7552
6872 | 103.7627
6873 | 132.8706
6874 | 130.5772
6875 | 130.8644
6876 | 127.0829
6877 | 119.3185
6878 | 119.4424
6879 | 136.3601
6880 | 147.7786
6881 | 55.7267
6882 | 64.6665
6883 | 112.9637
6884 | 146.7456
6885 | 161.6809
6886 | 107.2141
6887 | 122.4344
6888 | 140.3428
6889 | 140.4075
6890 | 151.7162
6891 | 120.418
6892 | 105.1661
6893 | 103.8736
6894 | 140.2215
6895 | 152.1446
6896 | 91.5222
6897 | 141.8829
6898 | 149.5223
6899 | 100.053
6900 | 110.7736
6901 | 120.6422
6902 | 132.7062
6903 | 118.1358
6904 | 141.4229
6905 | 77.9154
6906 | 80.3886
6907 | 152.1544
6908 | 135.5599
6909 | 92.3543
6910 | 134.7114
6911 | 136.7061
6912 | 80.8819
6913 | 92.9015
6914 | 147.97
6915 | 133.842
6916 | 67.6951
6917 | 141.6298
6918 | 136.8067
6919 | 149.5325
6920 | 160.0702
6921 | 142.1644
6922 | 102.3973
6923 | 109.1916
6924 | 101.2266
6925 | 74.8782
6926 | 119.4505
6927 | 121.5528
6928 | 113.5536
6929 | 171.3512
6930 | 107.8472
6931 | 78.7205
6932 | 122.1987
6933 | 113.3542
6934 | 154.3166
6935 | 76.9668
6936 | 142.9757
6937 | 109.9169
6938 | 129.2571
6939 | 98.3
6940 | 116.9651
6941 | 150.9865
6942 | 95.6778
6943 | 91.6194
6944 | 111.3644
6945 | 123.3773
6946 | 122.6439
6947 | 133.3013
6948 | 88.5865
6949 | 112.2566
6950 | 144.4075
6951 | 123.4944
6952 | 142.8926
6953 | 111.0181
6954 | 141.9399
6955 | 147.4223
6956 | 116.9114
6957 | 112.6122
6958 | 115.0924
6959 | 57.913
6960 | 130.4733
6961 | 162.9832
6962 | 172.223
6963 | 117.8808
6964 | 106.9121
6965 | 61.656
6966 | 100.5854
6967 | 134.4018
6968 | 121.321
6969 | 127.3057
6970 | 83.4187
6971 | 88.5649
6972 | 92.7814
6973 | 123.9864
6974 | 146.1646
6975 | 92.2943
6976 | 76.0507
6977 | 143.5973
6978 | 87.1766
6979 | 110.7452
6980 | 118.6321
6981 | 139.9831
6982 | 133.2375
6983 | 91.9373
6984 | 112.1718
6985 | 99.1181
6986 | 133.1202
6987 | 135.7169
6988 | 152.2287
6989 | 121.9262
6990 | 139.8932
6991 | 133.1892
6992 | 108.7819
6993 | 94.339
6994 | 146.3475
6995 | 124.7091
6996 | 153.9277
6997 | 107.5179
6998 | 141.765
6999 | 71.2936
7000 | 111.1987
7001 | 94.3886
7002 | 126.9968
7003 | 113.3859
7004 | 76.7819
7005 | 114.8741
7006 | 131.2102
7007 | 146.6646
7008 | 94.8281
7009 | 144.6677
7010 | 115.3827
7011 | 120.594
7012 | 133.9998
7013 | 121.7492
7014 | 106.3511
7015 | 75.0082
7016 | 135.9095
7017 | 106.2341
7018 | 112.6009
7019 | 176.9087
7020 | 108.5321
7021 | 123.3572
7022 | 79.5928
7023 | 116.9952
7024 | 101.6296
7025 | 115.2142
7026 | 86.0502
7027 | 101.8134
7028 | 138.1096
7029 | 129.8492
7030 | 144.475
7031 | 122.3144
7032 | 77.1088
7033 | 149.0423
7034 | 156.4825
7035 | 92.9517
7036 | 67.6249
7037 | 98.802
7038 | 135.0617
7039 | 89.5575
7040 | 122.2909
7041 | 107.9062
7042 | 109.0536
7043 | 138.3927
7044 | 85.3118
7045 | 128.7965
7046 | 93.892
7047 | 128.0332
7048 | 112.8049
7049 | 110.6934
7050 | 90.8696
7051 | 129.5586
7052 | 105.0761
7053 | 168.3166
7054 | 162.8466
7055 | 150.6645
7056 | 149.9095
7057 | 145.324
7058 | 120.5012
7059 | 99.6409
7060 | 109.2913
7061 | 137.657
7062 | 104.2571
7063 | 107.6945
7064 | 94.6726
7065 | 77.6029
7066 | 81.9644
7067 | 79.8209
7068 | 85.0325
7069 | 146.3747
7070 | 142.8168
7071 | 141.7425
7072 | 152.7459
7073 | 142.5895
7074 | 157.9645
7075 | 119.4899
7076 | 96.4644
7077 | 142.4091
7078 | 162.9166
7079 | 115.543
7080 | 150.1259
7081 | 139.8673
7082 | 100.9418
7083 | 124.7256
7084 | 102.9446
7085 | 108.4085
7086 | 155.5556
7087 | 133.6286
7088 | 121.2852
7089 | 160.7946
7090 | 85.0631
7091 | 124.4702
7092 | 107.5778
7093 | 151.4327
7094 | 105.4945
7095 | 126.5836
7096 | 68.114
7097 | 90.6137
7098 | 102.7083
7099 | 134.6823
7100 | 137.8314
7101 | 68.5318
7102 | 124.8196
7103 | 135.5499
7104 | 127.3423
7105 | 147.4954
7106 | 102.8333
7107 | 137.1907
7108 | 109.6055
7109 | 95.45
7110 | 128.1198
7111 | 129.9166
7112 | 112.824
7113 | 104.7536
7114 | 100.0816
7115 | 152.3487
7116 | 131.1954
7117 | 119.199
7118 | 120.0121
7119 | 104.817
7120 | 138.0673
7121 | 124.0819
7122 | 141.2466
7123 | 151.9545
7124 | 163.9939
7125 | 114.9501
7126 | 131.3762
7127 | 159.9045
7128 | 139.1575
7129 | 132.3248
7130 | 100.685
7131 | 119.2339
7132 | 112.5293
7133 | 113.6056
7134 | 110.3738
7135 | 100.6801
7136 | 106.0684
7137 | 150.1067
7138 | 110.5344
7139 | 100.9546
7140 | 147.9498
7141 | 104.1108
7142 | 114.2745
7143 | 113.1705
7144 | 119.7769
7145 | 138.7575
7146 | 129.726
7147 | 104.6492
7148 | 57.8285
7149 | 135.4647
7150 | 120.3268
7151 | 108.8339
7152 | 125.3647
7153 | 92.148
7154 | 87.4605
7155 | 116.5793
7156 | 134.7947
7157 | 110.569
7158 | 112.8316
7159 | 128.6019
7160 | 140.5222
7161 | 117.5138
7162 | 121.5656
7163 | 131.5116
7164 | 98.7193
7165 | 111.1332
7166 | 129.3052
7167 | 145.6281
7168 | 145.7798
7169 | 116.2934
7170 | 123.1535
7171 | 117.0824
7172 | 107.2733
7173 | 152.3258
7174 | 102.9872
7175 | 170.5428
7176 | 176.7309
7177 | 138.1234
7178 | 152.7917
7179 | 158.1013
7180 | 97.4866
7181 | 121.991
7182 | 105.1851
7183 | 101.8552
7184 | 104.573
7185 | 170.1745
7186 | 152.6195
7187 | 143.627
7188 | 107.6592
7189 | 104.2711
7190 | 87.2662
7191 | 155.0598
7192 | 120.5126
7193 | 98.7072
7194 | 133.4485
7195 | 123.1993
7196 | 111.9575
7197 | 82.4025
7198 | 128.748
7199 | 130.4511
7200 | 137.0737
7201 | 115.092
7202 | 122.2405
7203 | 77.2333
7204 | 119.2947
7205 | 138.7893
7206 | 98.7843
7207 | 142.3373
7208 | 141.0735
7209 | 96.2389
7210 | 124.5044
7211 | 61.6239
7212 | 152.4909
7213 | 120.575
7214 | 159.7343
7215 | 160.3128
7216 | 125.6759
7217 | 115.9592
7218 | 126.849
7219 | 135.3566
7220 | 171.1294
7221 | 96.5041
7222 | 116.8513
7223 | 88.6285
7224 | 74.5335
7225 | 126.4932
7226 | 150.9595
7227 | 148.3524
7228 | 102.479
7229 | 117.875
7230 | 131.5154
7231 | 142.4966
7232 | 93.6723
7233 | 105.3736
7234 | 87.0941
7235 | 153.4741
7236 | 91.6278
7237 | 113.3946
7238 | 159.8196
7239 | 114.3066
7240 | 128.6567
7241 | 117.1648
7242 | 103.4721
7243 | 87.2042
7244 | 96.0975
7245 | 121.6782
7246 | 149.3775
7247 | 93.8337
7248 | 86.6811
7249 | 164.5103
7250 | 154.3452
7251 | 130.4184
7252 | 84.384
7253 | 138.1826
7254 | 156.7455
7255 | 83.6557
7256 | 130.4773
7257 | 95.651
7258 | 101.8094
7259 | 76.5742
7260 | 141.6625
7261 | 147.3587
7262 | 136.6596
7263 | 96.2133
7264 | 114.9743
7265 | 143.6151
7266 | 96.6117
7267 | 124.4826
7268 | 127.1621
7269 | 94.6483
7270 | 94.3061
7271 | 111.837
7272 | 116.9009
7273 | 120.778
7274 | 86.8615
7275 | 147.3075
7276 | 125.1072
7277 | 109.8256
7278 | 99.6998
7279 | 141.0391
7280 | 115.9666
7281 | 107.9642
7282 | 137.6566
7283 | 104.3926
7284 | 107.4976
7285 | 86.218
7286 | 143.6005
7287 | 107.9149
7288 | 101.1802
7289 | 150.1901
7290 | 133.202
7291 | 139.9685
7292 | 138.9114
7293 | 78.7764
7294 | 120.5071
7295 | 72.6752
7296 | 123.2142
7297 | 118.525
7298 | 97.2883
7299 | 135.6973
7300 | 89.7012
7301 | 99.5257
7302 | 160.1327
7303 | 144.5083
7304 | 116.162
7305 | 118.8226
7306 | 108.417
7307 | 129.8594
7308 | 123.2891
7309 | 137.2314
7310 | 68.2171
7311 | 116.561
7312 | 107.1233
7313 | 120.7301
7314 | 153.8038
7315 | 137.9303
7316 | 111.2331
7317 | 100.0518
7318 | 122.3522
7319 | 141.757
7320 | 126.2931
7321 | 88.0485
7322 | 101.2341
7323 | 103.1575
7324 | 166.4708
7325 | 165.4967
7326 | 136.8825
7327 | 119.9376
7328 | 100.8545
7329 | 112.4282
7330 | 97.9122
7331 | 123.5674
7332 | 154.6183
7333 | 146.5084
7334 | 116.451
7335 | 123.5755
7336 | 135.4852
7337 | 165.0868
7338 | 94.7124
7339 | 123.1076
7340 | 111.5222
7341 | 126.8353
7342 | 138.4387
7343 | 106.0235
7344 | 100.3566
7345 | 130.3316
7346 | 129.9088
7347 | 128.6448
7348 | 121.7282
7349 | 133.2772
7350 | 117.53
7351 | 114.3491
7352 | 139.749
7353 | 99.9344
7354 | 125.2405
7355 | 126.8328
7356 | 115.8789
7357 | 126.1071
7358 | 126.1696
7359 | 167.7806
7360 | 99.8844
7361 | 101.6806
7362 | 124.0462
7363 | 140.3437
7364 | 108.285
7365 | 146.0381
7366 | 115.216
7367 | 96.4968
7368 | 112.6727
7369 | 137.9039
7370 | 96.6177
7371 | 149.7822
7372 | 114.5833
7373 | 137.4866
7374 | 130.1685
7375 | 101.8645
7376 | 116.7015
7377 | 128.4566
7378 | 80.8098
7379 | 106.7538
7380 | 148.1912
7381 | 104.2247
7382 | 148.3053
7383 | 121.1604
7384 | 110.7719
7385 | 123.6117
7386 | 130.0293
7387 | 92.9718
7388 | 138.5176
7389 | 113.7499
7390 | 129.5081
7391 | 158.206
7392 | 141.3613
7393 | 86.9913
7394 | 135.6629
7395 | 156.7485
7396 | 90.0422
7397 | 77.1124
7398 | 113.0371
7399 | 129.5029
7400 | 132.1275
7401 | 123.1872
7402 | 140.4282
7403 | 116.0701
7404 | 64.4285
7405 | 80.1597
7406 | 123.9835
7407 | 128.5212
7408 | 113.1756
7409 | 115.9685
7410 | 93.171
7411 | 112.363
7412 | 104.5038
7413 | 155.5263
7414 | 171.6317
7415 | 150.8155
7416 | 142.2198
7417 | 129.1182
7418 | 171.65
7419 | 82.8758
7420 | 127.4905
7421 | 110.0706
7422 | 114.5691
7423 | 101.1635
7424 | 153.2504
7425 | 115.2742
7426 | 123.1296
7427 | 145.2004
7428 | 82.6634
7429 | 71.6663
7430 | 115.0242
7431 | 132.2185
7432 | 130.7611
7433 | 131.8306
7434 | 152.9185
7435 | 110.1876
7436 | 97.0761
7437 | 106.9076
7438 | 79.4235
7439 | 160.3047
7440 | 144.9534
7441 | 115.868
7442 | 122.8105
7443 | 121.026
7444 | 152.3206
7445 | 133.7173
7446 | 108.4723
7447 | 130.8706
7448 | 124.3511
7449 | 170.886
7450 | 80.9814
7451 | 142.9681
7452 | 102.0546
7453 | 136.7569
7454 | 106.1644
7455 | 126.2278
7456 | 103.9716
7457 | 99.3226
7458 | 117.1562
7459 | 130.4233
7460 | 145.1146
7461 | 105.9635
7462 | 131.2924
7463 | 75.5765
7464 | 104.3092
7465 | 98.5759
7466 | 159.5461
7467 | 119.8475
7468 | 122.4121
7469 | 118.0328
7470 | 138.2464
7471 | 134.4097
7472 | 125.7004
7473 | 107.6999
7474 | 73.3536
7475 | 104.8333
7476 | 134.4064
7477 | 81.8831
7478 | 142.293
7479 | 74.6851
7480 | 107.4355
7481 | 90.4072
7482 | 107.4365
7483 | 82.4164
7484 | 85.2559
7485 | 124.1686
7486 | 129.3507
7487 | 104.6756
7488 | 121.6596
7489 | 79.4669
7490 | 125.226
7491 | 137.4148
7492 | 129.3145
7493 | 139.881
7494 | 110.0585
7495 | 112.4191
7496 | 133.0266
7497 | 118.0193
7498 | 92.1016
7499 | 171.5975
7500 | 132.5671
7501 | 144.486
7502 | 150.5768
7503 | 114.5656
7504 | 133.1835
7505 | 137.5787
7506 | 98.4451
7507 | 83.1249
7508 | 97.9863
7509 | 90.6076
7510 | 118.8935
7511 | 116.4947
7512 | 124.9911
7513 | 127.9335
7514 | 123.0888
7515 | 93.6569
7516 | 110.0471
7517 | 97.2441
7518 | 167.5529
7519 | 127.0558
7520 | 134.6406
7521 | 115.6592
7522 | 125.4044
7523 | 124.7307
7524 | 111.6856
7525 | 116.0698
7526 | 119.2786
7527 | 79.8408
7528 | 136.465
7529 | 102.4614
7530 | 120.6851
7531 | 104.4301
7532 | 126.5144
7533 | 141.5015
7534 | 78.3089
7535 | 150.2022
7536 | 119.6503
7537 | 86.4388
7538 | 128.4288
7539 | 136.2508
7540 | 131.242
7541 | 128.3678
7542 | 124.7839
7543 | 126.9846
7544 | 99.7501
7545 | 133.1951
7546 | 91.41
7547 | 116.7394
7548 | 101.0105
7549 | 96.6528
7550 | 111.4172
7551 | 118.665
7552 | 143.218
7553 | 125.6775
7554 | 58.9733
7555 | 60.5163
7556 | 87.9271
7557 | 122.2294
7558 | 107.4503
7559 | 131.6648
7560 | 123.666
7561 | 118.9996
7562 | 121.6897
7563 | 101.525
7564 | 108.5313
7565 | 120.7967
7566 | 98.8816
7567 | 102.7274
7568 | 92.2324
7569 | 143.2445
7570 | 158.3161
7571 | 110.7157
7572 | 130.3489
7573 | 112.2656
7574 | 158.2235
7575 | 88.7425
7576 | 165.2853
7577 | 126.6405
7578 | 112.3862
7579 | 114.8578
7580 | 84.3264
7581 | 133.1246
7582 | 131.1762
7583 | 129.0834
7584 | 135.9004
7585 | 148.2303
7586 | 127.6568
7587 | 154.6069
7588 | 133.2666
7589 | 125.2011
7590 | 130.5119
7591 | 138.3534
7592 | 145.7718
7593 | 136.6534
7594 | 145.6014
7595 | 123.1974
7596 | 98.3852
7597 | 100.2239
7598 | 118.6409
7599 | 49.6549
7600 | 135.4968
7601 | 158.3381
7602 | 92.261
7603 | 99.3263
7604 | 127.0423
7605 | 115.0864
7606 | 142.5039
7607 | 129.8088
7608 | 137.2456
7609 | 152.8534
7610 | 113.001
7611 | 136.5593
7612 | 108.2392
7613 | 138.1612
7614 | 119.1452
7615 | 67.411
7616 | 133.4912
7617 | 115.3892
7618 | 91.5593
7619 | 114.2811
7620 | 149.589
7621 | 164.7389
7622 | 99.03
7623 | 125.5682
7624 | 119.5698
7625 | 129.5432
7626 | 121.4551
7627 | 114.4031
7628 | 119.2868
7629 | 139.7469
7630 | 132.5142
7631 | 91.0286
7632 | 126.1289
7633 | 136.4546
7634 | 148.6957
7635 | 126.1344
7636 | 132.951
7637 | 114.8077
7638 | 104.5097
7639 | 128.7683
7640 | 104.5948
7641 | 101.9031
7642 | 109.1875
7643 | 95.2355
7644 | 150.8027
7645 | 123.3375
7646 | 140.2002
7647 | 82.6309
7648 | 142.375
7649 | 120.7747
7650 | 104.8622
7651 | 108.7817
7652 | 119.4463
7653 | 105.7674
7654 | 131.9278
7655 | 116.1235
7656 | 139.1656
7657 | 92.362
7658 | 57.5824
7659 | 117.6134
7660 | 62.1457
7661 | 96.6445
7662 | 121.1439
7663 | 133.4721
7664 | 123.726
7665 | 135.0196
7666 | 98.4305
7667 | 141.2676
7668 | 93.3228
7669 | 121.0835
7670 | 148.9144
7671 | 145.8632
7672 | 134.1938
7673 | 103.3982
7674 | 159.659
7675 | 119.3369
7676 | 106.7694
7677 | 112.7139
7678 | 78.5672
7679 | 99.5648
7680 | 133.5749
7681 | 116.9365
7682 | 145.4572
7683 | 100.0683
7684 | 94.7915
7685 | 94.3466
7686 | 109.6054
7687 | 137.2787
7688 | 149.8322
7689 | 117.3383
7690 | 102.8577
7691 | 80.7019
7692 | 110.2756
7693 | 136.0849
7694 | 103.5535
7695 | 138.1726
7696 | 123.7851
7697 | 108.8724
7698 | 98.1879
7699 | 129.4815
7700 | 97.8313
7701 | 95.5567
7702 | 128.6695
7703 | 155.8679
7704 | 141.243
7705 | 71.7053
7706 | 68.5393
7707 | 121.7988
7708 | 128.1926
7709 | 113.7926
7710 | 117.7547
7711 | 93.3964
7712 | 97.8669
7713 | 131.4532
7714 | 91.9342
7715 | 94.7643
7716 | 129.954
7717 | 129.4131
7718 | 161.8413
7719 | 115.4951
7720 | 99.9572
7721 | 144.5499
7722 | 133.2582
7723 | 125.544
7724 | 127.5957
7725 | 142.2767
7726 | 119.8121
7727 | 157.3057
7728 | 128.0392
7729 | 127.3976
7730 | 139.0149
7731 | 101.5621
7732 | 135.1508
7733 | 119.9433
7734 | 114.1459
7735 | 140.6963
7736 | 132.8455
7737 | 84.7504
7738 | 95.3148
7739 | 121.6714
7740 | 123.8994
7741 | 119.9524
7742 | 116.8779
7743 | 88.3881
7744 | 118.3771
7745 | 106.1539
7746 | 101.9805
7747 | 143.9711
7748 | 112.8584
7749 | 94.1687
7750 | 120.9948
7751 | 145.8698
7752 | 120.6105
7753 | 116.2178
7754 | 116.5036
7755 | 150.6598
7756 | 158.452
7757 | 121.3334
7758 | 100.607
7759 | 79.8697
7760 | 136.7813
7761 | 65.8154
7762 | 109.5346
7763 | 78.7329
7764 | 86.1985
7765 | 126.7568
7766 | 181.7814
7767 | 150.2465
7768 | 156.3017
7769 | 95.5813
7770 | 118.4377
7771 | 95.7109
7772 | 103.9279
7773 | 125.5686
7774 | 106.3119
7775 | 83.6541
7776 | 132.8256
7777 | 88.9651
7778 | 126.1227
7779 | 143.8128
7780 | 138.3967
7781 | 89.2063
7782 | 64.9195
7783 | 124.9057
7784 | 140.4251
7785 | 167.5999
7786 | 142.3089
7787 | 145.3279
7788 | 121.4277
7789 | 116.4625
7790 | 76.0564
7791 | 83.9594
7792 | 110.8294
7793 | 131.7129
7794 | 176.6895
7795 | 133.501
7796 | 126.4988
7797 | 143.7911
7798 | 122.6242
7799 | 146.5772
7800 | 138.132
7801 | 129.3555
7802 | 125.1827
7803 | 173.8128
7804 | 121.2791
7805 | 141.3477
7806 | 88.2771
7807 | 79.0284
7808 | 87.858
7809 | 132.2214
7810 | 138.983
7811 | 97.2033
7812 | 98.3317
7813 | 97.3156
7814 | 140.1615
7815 | 121.0295
7816 | 82.6014
7817 | 147.7548
7818 | 114.8298
7819 | 162.586
7820 | 137.4462
7821 | 94.3449
7822 | 140.2853
7823 | 109.3019
7824 | 103.2037
7825 | 124.2737
7826 | 114.2278
7827 | 86.7812
7828 | 108.6609
7829 | 134.6822
7830 | 105.647
7831 | 112.2251
7832 | 112.8042
7833 | 168.195
7834 | 107.918
7835 | 131.8184
7836 | 143.439
7837 | 109.9012
7838 | 108.7253
7839 | 144.889
7840 | 101.125
7841 | 150.9735
7842 | 118.7366
7843 | 147.7346
7844 | 115.5919
7845 | 152.4434
7846 | 70.132
7847 | 125.2873
7848 | 168.0703
7849 | 163.2895
7850 | 96.5119
7851 | 112.9145
7852 | 107.1293
7853 | 136.4288
7854 | 96.109
7855 | 154.5748
7856 | 113.9723
7857 | 121.79
7858 | 132.8573
7859 | 111.6677
7860 | 103.7284
7861 | 97.5231
7862 | 81.2754
7863 | 141.6172
7864 | 119.918
7865 | 101.8706
7866 | 146.9155
7867 | 166.1548
7868 | 132.4164
7869 | 125.3735
7870 | 100.3253
7871 | 103.416
7872 | 145.5265
7873 | 110.8795
7874 | 121.0486
7875 | 115.0066
7876 | 159.0054
7877 | 93.388
7878 | 105.2416
7879 | 134.3546
7880 | 120.8552
7881 | 117.6915
7882 | 112.2809
7883 | 112.9733
7884 | 153.6351
7885 | 129.2304
7886 | 145.3235
7887 | 105.1505
7888 | 112.51
7889 | 123.1575
7890 | 150.7711
7891 | 133.4698
7892 | 107.7861
7893 | 143.814
7894 | 91.46
7895 | 106.2682
7896 | 88.2686
7897 | 110.0524
7898 | 147.3094
7899 | 140.5816
7900 | 120.9217
7901 | 121.6494
7902 | 134.3187
7903 | 74.0653
7904 | 155.6935
7905 | 134.6823
7906 | 143.2718
7907 | 101.8927
7908 | 113.4228
7909 | 159.3906
7910 | 149.2007
7911 | 120.3332
7912 | 81.7013
7913 | 140.4978
7914 | 141.909
7915 | 117.2264
7916 | 88.7243
7917 | 91.3305
7918 | 106.4184
7919 | 144.275
7920 | 138.2397
7921 | 132.7177
7922 | 90.4372
7923 | 132.2921
7924 | 149.3343
7925 | 155.6462
7926 | 82.2491
7927 | 93.1367
7928 | 83.3281
7929 | 152.5038
7930 | 102.7303
7931 | 103.325
7932 | 82.281
7933 | 83.9609
7934 | 105.6198
7935 | 146.9267
7936 | 127.0898
7937 | 68.1162
7938 | 116.4721
7939 | 116.2872
7940 | 111.5741
7941 | 112.9683
7942 | 173.5546
7943 | 154.8333
7944 | 102.391
7945 | 118.5425
7946 | 100.0591
7947 | 132.9773
7948 | 145.8434
7949 | 153.6009
7950 | 114.1131
7951 | 152.6424
7952 | 141.5373
7953 | 99.5477
7954 | 89.0055
7955 | 100.4308
7956 | 122.8582
7957 | 156.0233
7958 | 93.9516
7959 | 143.7454
7960 | 82.3591
7961 | 112.5374
7962 | 98.2518
7963 | 105.7125
7964 | 152.9785
7965 | 88.9952
7966 | 146.1479
7967 | 144.664
7968 | 153.0439
7969 | 119.7916
7970 | 71.5828
7971 | 128.6006
7972 | 123.0322
7973 | 119.1075
7974 | 122.6182
7975 | 110.2253
7976 | 116.0327
7977 | 100.3996
7978 | 107.8127
7979 | 95.8842
7980 | 121.613
7981 | 116.3312
7982 | 140.677
7983 | 106.1005
7984 | 128.9725
7985 | 74.4843
7986 | 150.6482
7987 | 163.2875
7988 | 144.6399
7989 | 78.6133
7990 | 159.3086
7991 | 95.2793
7992 | 114.613
7993 | 113.0184
7994 | 155.3689
7995 | 114.9148
7996 | 155.1957
7997 | 140.6242
7998 | 89.7089
7999 | 124.828
8000 | 113.4325
8001 | 121.3652
8002 | 144.7489
8003 | 136.6992
8004 | 95.1345
8005 | 106.5247
8006 | 122.8079
8007 | 114.7329
8008 | 135.4325
8009 | 123.1704
8010 | 126.0737
8011 | 82.6409
8012 | 99.0026
8013 | 161.5998
8014 | 92.3061
8015 | 110.6657
8016 | 141.747
8017 | 147.1846
8018 | 92.4389
8019 | 134.7405
8020 | 104.2152
8021 | 124.7017
8022 | 108.4219
8023 | 120.5453
8024 | 92.7948
8025 | 93.1091
8026 | 126.8236
8027 | 133.0741
8028 | 102.097
8029 | 148.0567
8030 | 85.1069
8031 | 148.2572
8032 | 159.3277
8033 | 105.5593
8034 | 108.2359
8035 | 132.4802
8036 | 141.0689
8037 | 137.6632
8038 | 159.117
8039 | 125.2018
8040 | 77.8422
8041 | 98.1011
8042 | 159.3194
8043 | 144.1023
8044 | 146.0691
8045 | 132.1013
8046 | 166.8664
8047 | 114.6836
8048 | 70.6297
8049 | 158.1571
8050 | 144.4299
8051 | 130.4668
8052 | 106.4663
8053 | 91.3683
8054 | 125.8051
8055 | 104.0468
8056 | 91.0563
8057 | 94.0272
8058 | 110.3685
8059 | 109.2074
8060 | 114.2461
8061 | 141.9494
8062 | 135.7717
8063 | 107.97
8064 | 111.174
8065 | 121.8532
8066 | 140.9521
8067 | 99.9763
8068 | 118.9982
8069 | 90.2407
8070 | 77.6751
8071 | 118.6065
8072 | 121.1735
8073 | 92.733
8074 | 156.586
8075 | 125.8929
8076 | 101.8333
8077 | 148.8221
8078 | 126.728
8079 | 130.9589
8080 | 94.5161
8081 | 129.2745
8082 | 113.6721
8083 | 88.9628
8084 | 95.8078
8085 | 148.4433
8086 | 109.6678
8087 | 97.7588
8088 | 137.9746
8089 | 120.2184
8090 | 134.1516
8091 | 141.6621
8092 | 100.8054
8093 | 100.1981
8094 | 133.695
8095 | 111.0743
8096 | 80.4931
8097 | 110.5132
8098 | 82.2335
8099 | 113.171
8100 | 112.8687
8101 | 106.2828
8102 | 166.3047
8103 | 104.7574
8104 | 100.3202
8105 | 109.3188
8106 | 125.9183
8107 | 99.0068
8108 | 116.5702
8109 | 108.2479
8110 | 143.1797
8111 | 106.8845
8112 | 117.8592
8113 | 97.7764
8114 | 101.972
8115 | 135.3503
8116 | 116.8189
8117 | 97.3303
8118 | 129.7096
8119 | 122.5318
8120 | 79.1196
8121 | 161.2361
8122 | 90.8621
8123 | 131.849
8124 | 130.0108
8125 | 113.7812
8126 | 131.7546
8127 | 136.1197
8128 | 183.1111
8129 | 145.7291
8130 | 157.7656
8131 | 129.9981
8132 | 91.316
8133 | 127.3323
8134 | 105.2142
8135 | 123.5065
8136 | 77.2782
8137 | 98.7452
8138 | 140.7938
8139 | 124.3998
8140 | 99.1516
8141 | 74.729
8142 | 127.1226
8143 | 114.9703
8144 | 131.307
8145 | 92.2141
8146 | 90.2666
8147 | 120.1934
8148 | 77.6812
8149 | 133.9838
8150 | 114.8381
8151 | 113.0418
8152 | 158.7278
8153 | 104.4779
8154 | 115.6909
8155 | 160.5743
8156 | 111.1309
8157 | 154.0416
8158 | 155.276
8159 | 124.0163
8160 | 146.2311
8161 | 117.7268
8162 | 96.6708
8163 | 157.183
8164 | 122.5558
8165 | 97.1338
8166 | 132.0022
8167 | 125.9291
8168 | 97.7375
8169 | 116.454
8170 | 84.3001
8171 | 100.4034
8172 | 124.6416
8173 | 163.0006
8174 | 82.225
8175 | 128.5081
8176 | 95.1478
8177 | 85.108
8178 | 119.8117
8179 | 132.1569
8180 | 83.4518
8181 | 118.5148
8182 | 123.7113
8183 | 149.9406
8184 | 107.946
8185 | 91.7527
8186 | 91.6754
8187 | 123.4846
8188 | 121.6997
8189 | 126.5687
8190 | 125.7815
8191 | 144.4838
8192 | 135.0281
8193 | 99.4465
8194 | 81.2275
8195 | 169.4672
8196 | 156.1392
8197 | 120.2812
8198 | 75.8837
8199 | 148.9651
8200 | 116.2711
8201 | 134.4266
8202 | 89.8874
8203 | 96.2763
8204 | 118.0566
8205 | 137.7544
8206 | 116.6726
8207 | 104.1151
8208 | 93.2996
8209 | 92.8748
8210 | 97.2662
8211 | 79.5062
8212 | 163.7267
8213 | 129.597
8214 | 95.9826
8215 | 100.771
8216 | 101.9032
8217 | 96.2836
8218 | 139.9057
8219 | 118.1846
8220 | 99.395
8221 | 109.0594
8222 | 93.3276
8223 | 182.0586
8224 | 95.7092
8225 | 96.3764
8226 | 101.671
8227 | 140.9461
8228 | 117.511
8229 | 126.6663
8230 | 89.0355
8231 | 125.7897
8232 | 138.6821
8233 | 130.6415
8234 | 100.4826
8235 | 84.3078
8236 | 108.3402
8237 | 110.5885
8238 | 120.0018
8239 | 100.4755
8240 | 121.8525
8241 | 156.896
8242 | 122.3067
8243 | 96.9594
8244 | 114.5276
8245 | 111.8145
8246 | 113.1708
8247 | 70.7254
8248 | 102.1184
8249 | 138.6094
8250 | 107.181
8251 | 107.2029
8252 | 130.6239
8253 | 134.2661
8254 | 115.2811
8255 | 85.4471
8256 | 94.1934
8257 | 114.4811
8258 | 104.4504
8259 | 169.9202
8260 | 123.8945
8261 | 125.554
8262 | 147.7187
8263 | 149.3646
8264 | 120.2241
8265 | 124.2531
8266 | 113.4994
8267 | 140.7364
8268 | 102.1963
8269 | 101.3284
8270 | 129.7088
8271 | 123.9164
8272 | 125.0069
8273 | 119.9462
8274 | 101.9639
8275 | 106.9543
8276 | 88.5148
8277 | 107.9054
8278 | 96.8685
8279 | 133.0663
8280 | 156.0183
8281 | 154.1441
8282 | 145.6379
8283 | 101.1663
8284 | 150.5976
8285 | 116.9285
8286 | 136.656
8287 | 118.2436
8288 | 135.2291
8289 | 165.0621
8290 | 141.6734
8291 | 167.725
8292 | 148.3262
8293 | 138.4817
8294 | 121.9739
8295 | 89.6844
8296 | 105.6499
8297 | 166.4532
8298 | 154.5689
8299 | 133.768
8300 | 126.853
8301 | 125.493
8302 | 128.7813
8303 | 122.7161
8304 | 132.4131
8305 | 140.4788
8306 | 130.178
8307 | 141.6437
8308 | 145.0642
8309 | 120.2216
8310 | 134.8328
8311 | 159.1828
8312 | 130.4565
8313 | 114.2255
8314 | 104.3162
8315 | 116.5667
8316 | 123.072
8317 | 129.383
8318 | 115.2393
8319 | 140.1572
8320 | 133.6446
8321 | 154.4434
8322 | 137.868
8323 | 156.4332
8324 | 133.8177
8325 | 85.0212
8326 | 141.4285
8327 | 114.4276
8328 | 96.1962
8329 | 91.3646
8330 | 106.0324
8331 | 122.8453
8332 | 127.6665
8333 | 106.472
8334 | 150.3924
8335 | 129.4999
8336 | 137.3149
8337 | 101.249
8338 | 123.7946
8339 | 103.4669
8340 | 111.9433
8341 | 130.4795
8342 | 147.2591
8343 | 112.1173
8344 | 122.1219
8345 | 152.3272
8346 | 131.0743
8347 | 137.1322
8348 | 125.3252
8349 | 124.8054
8350 | 115.6547
8351 | 145.8288
8352 | 102.5215
8353 | 141.8819
8354 | 125.089
8355 | 167.358
8356 | 130.3385
8357 | 166.4955
8358 | 120.4932
8359 | 93.6955
8360 | 96.2518
8361 | 146.0068
8362 | 130.864
8363 | 149.2623
8364 | 87.3739
8365 | 141.8243
8366 | 119.4468
8367 | 131.1095
8368 | 142.5988
8369 | 91.3928
8370 | 83.0267
8371 | 96.8671
8372 | 98.2334
8373 | 98.1201
8374 | 112.2474
8375 | 105.0417
8376 | 174.7496
8377 | 125.1987
8378 | 125.731
8379 | 103.4315
8380 | 116.5052
8381 | 137.8296
8382 | 148.2782
8383 | 100.7217
8384 | 139.3531
8385 | 102.5232
8386 | 136.4007
8387 | 171.8497
8388 | 156.9176
8389 | 118.387
8390 | 96.1542
8391 | 119.5389
8392 | 134.0389
8393 | 142.5685
8394 | 137.3378
8395 | 137.8712
8396 | 97.486
8397 | 141.5136
8398 | 83.9638
8399 | 147.6474
8400 | 135.1627
8401 | 116.6769
8402 | 122.1754
8403 | 140.4967
8404 | 131.7941
8405 | 124.1739
8406 | 144.9341
8407 | 125.2346
8408 | 117.6792
8409 | 110.6179
8410 | 128.0915
8411 | 133.0665
8412 | 143.8348
8413 | 107.5733
8414 | 163.922
8415 | 86.8222
8416 | 102.0194
8417 | 79.1608
8418 | 141.2089
8419 | 97.6256
8420 | 124.1133
8421 | 134.6469
8422 | 107.8519
8423 | 103.5952
8424 | 165.4599
8425 | 125.4009
8426 | 102.5671
8427 | 147.7931
8428 | 121.2847
8429 | 140.2557
8430 | 132.2817
8431 | 127.0302
8432 | 73.8365
8433 | 81.1824
8434 | 96.3211
8435 | 146.0266
8436 | 127.5545
8437 | 123.8222
8438 | 121.7358
8439 | 147.558
8440 | 122.3762
8441 | 137.8127
8442 | 128.3373
8443 | 118.7044
8444 | 109.7824
8445 | 139.7236
8446 | 148.4803
8447 | 107.324
8448 | 139.7252
8449 | 104.6322
8450 | 99.3436
8451 | 62.3353
8452 | 124.2972
8453 | 80.2324
8454 | 91.1767
8455 | 161.9309
8456 | 118.9434
8457 | 121.9916
8458 | 98.8082
8459 | 151.0388
8460 | 90.3182
8461 | 128.3193
8462 | 188.9111
8463 | 89.829
8464 | 108.3862
8465 | 121.1759
8466 | 106.0395
8467 | 161.7075
8468 | 144.9357
8469 | 101.2176
8470 | 151.5026
8471 | 124.1746
8472 | 129.3703
8473 | 110.9809
8474 | 110.3938
8475 | 108.5387
8476 | 125.3984
8477 | 114.7517
8478 | 138.5461
8479 | 132.4526
8480 | 132.158
8481 | 141.9291
8482 | 142.3392
8483 | 98.5567
8484 | 155.4787
8485 | 96.4772
8486 | 140.9774
8487 | 142.4552
8488 | 120.9738
8489 | 158.1059
8490 | 130.7564
8491 | 89.0118
8492 | 135.8303
8493 | 147.5361
8494 | 124.4315
8495 | 99.0788
8496 | 71.6534
8497 | 169.2627
8498 | 72.8778
8499 | 122.4676
8500 | 98.497
8501 | 130.0538
8502 | 90.442
8503 | 83.8244
8504 | 136.9677
8505 | 119.89
8506 | 98.734
8507 | 126.9617
8508 | 130.0687
8509 | 116.7651
8510 | 160.5742
8511 | 142.7096
8512 | 131.0171
8513 | 170.5841
8514 | 110.5046
8515 | 97.2887
8516 | 141.5889
8517 | 107.6929
8518 | 116.4932
8519 | 80.6589
8520 | 123.4093
8521 | 120.1957
8522 | 149.0754
8523 | 110.883
8524 | 145.4556
8525 | 82.0229
8526 | 105.8261
8527 | 72.272
8528 | 143.7679
8529 | 90.0554
8530 | 116.0524
8531 | 95.045
8532 | 114.4281
8533 | 142.5745
8534 | 94.4454
8535 | 116.7384
8536 | 106.523
8537 | 144.1515
8538 | 64.4948
8539 | 121.9964
8540 | 143.2718
8541 | 105.0009
8542 | 75.5497
8543 | 71.6833
8544 | 149.6178
8545 | 99.3844
8546 | 94.6287
8547 | 149.4584
8548 | 93.8153
8549 | 151.6907
8550 | 104.4068
8551 | 142.2248
8552 | 110.0123
8553 | 76.5724
8554 | 137.9818
8555 | 81.0239
8556 | 136.5717
8557 | 140.2098
8558 | 134.5157
8559 | 117.7323
8560 | 172.1923
8561 | 97.9071
8562 | 133.8377
8563 | 110.7009
8564 | 114.7283
8565 | 99.9887
8566 | 112.704
8567 | 166.254
8568 | 160.5076
8569 | 146.3029
8570 | 133.4834
8571 | 124.6654
8572 | 104.5313
8573 | 138.7132
8574 | 123.5858
8575 | 67.8997
8576 | 108.0226
8577 | 158.0949
8578 | 107.4435
8579 | 140.6573
8580 | 125.4875
8581 | 118.8538
8582 | 116.4051
8583 | 78.8733
8584 | 73.0048
8585 | 118.1281
8586 | 149.9848
8587 | 140.676
8588 | 98.5464
8589 | 138.9891
8590 | 103.3216
8591 | 112.1389
8592 | 164.4326
8593 | 162.6997
8594 | 125.8826
8595 | 133.837
8596 | 137.6063
8597 | 115.0961
8598 | 132.2979
8599 | 99.9448
8600 | 116.6762
8601 | 63.3336
8602 | 123.6302
8603 | 78.877
8604 | 115.3234
8605 | 155.54
8606 | 123.7512
8607 | 151.2486
8608 | 115.3643
8609 | 112.4627
8610 | 144.4802
8611 | 127.3511
8612 | 104.165
8613 | 110.8557
8614 | 79.8109
8615 | 92.8534
8616 | 149.5617
8617 | 102.63
8618 | 99.4733
8619 | 133.1918
8620 | 130.41
8621 | 112.8418
8622 | 123.2678
8623 | 119.7945
8624 | 118.2112
8625 | 139.1436
8626 | 150.1507
8627 | 134.7826
8628 | 90.528
8629 | 112.1476
8630 | 140.1881
8631 | 134.2161
8632 | 121.2783
8633 | 118.5142
8634 | 107.5424
8635 | 111.7323
8636 | 107.5019
8637 | 148.4078
8638 | 154.4864
8639 | 126.9998
8640 | 115.6435
8641 | 123.8203
8642 | 145.0946
8643 | 129.1558
8644 | 111.248
8645 | 123.4858
8646 | 79.4306
8647 | 151.467
8648 | 105.4708
8649 | 107.3441
8650 | 129.5752
8651 | 114.7083
8652 | 103.5779
8653 | 142.0103
8654 | 114.6686
8655 | 111.1968
8656 | 129.2994
8657 | 155.4775
8658 | 133.1524
8659 | 122.4208
8660 | 93.5518
8661 | 135.2291
8662 | 98.2592
8663 | 143.4873
8664 | 170.0145
8665 | 121.6557
8666 | 137.5753
8667 | 139.0965
8668 | 166.5827
8669 | 117.9351
8670 | 88.3636
8671 | 106.6203
8672 | 96.5805
8673 | 102.6332
8674 | 119.5231
8675 | 87.4755
8676 | 131.1622
8677 | 128.4484
8678 | 146.2522
8679 | 111.9608
8680 | 121.6993
8681 | 113.8874
8682 | 126.9147
8683 | 156.914
8684 | 88.734
8685 | 108.8445
8686 | 108.1202
8687 | 149.3907
8688 | 120.2542
8689 | 118.2667
8690 | 116.4072
8691 | 118.4931
8692 | 130.879
8693 | 126.9756
8694 | 146.8845
8695 | 141.5362
8696 | 103.0283
8697 | 145.0012
8698 | 117.8358
8699 | 102.7762
8700 | 110.0424
8701 | 109.6725
8702 | 140.1752
8703 | 126.3116
8704 | 159.8146
8705 | 143.6124
8706 | 122.6522
8707 | 74.9562
8708 | 137.8497
8709 | 147.4235
8710 | 85.758
8711 | 77.1909
8712 | 137.451
8713 | 131.6492
8714 | 135.306
8715 | 156.5031
8716 | 111.6679
8717 | 118.8749
8718 | 115.1259
8719 | 139.3604
8720 | 147.6814
8721 | 122.0241
8722 | 153.5621
8723 | 155.0882
8724 | 137.9466
8725 | 111.5964
8726 | 106.533
8727 | 82.8849
8728 | 165.2456
8729 | 151.0391
8730 | 97.751
8731 | 136.4068
8732 | 90.5625
8733 | 97.3463
8734 | 133.9625
8735 | 115.1109
8736 | 114.3232
8737 | 124.4815
8738 | 90.1757
8739 | 146.8029
8740 | 120.4992
8741 | 83.9362
8742 | 101.2
8743 | 139.5372
8744 | 128.566
8745 | 138.6609
8746 | 147.992
8747 | 125.1512
8748 | 91.9053
8749 | 105.2639
8750 | 149.1904
8751 | 117.3151
8752 | 133.3375
8753 | 124.6709
8754 | 139.4439
8755 | 65.2374
8756 | 104.36
8757 | 139.9864
8758 | 149.6742
8759 | 144.3043
8760 | 130.9154
8761 | 130.0107
8762 | 94.6662
8763 | 114.8887
8764 | 108.7069
8765 | 121.5743
8766 | 160.2319
8767 | 114.253
8768 | 132.0828
8769 | 90.4722
8770 | 130.7696
8771 | 115.2737
8772 | 120.2805
8773 | 121.8931
8774 | 116.8912
8775 | 123.1935
8776 | 104.0569
8777 | 104.4524
8778 | 89.2054
8779 | 117.4523
8780 | 137.013
8781 | 120.3869
8782 | 63.5396
8783 | 124.7956
8784 | 111.9545
8785 | 136.788
8786 | 87.6301
8787 | 152.5704
8788 | 129.9729
8789 | 86.7807
8790 | 159.3028
8791 | 103.1395
8792 | 118.2884
8793 | 118.8882
8794 | 128.9555
8795 | 133.2069
8796 | 113.9459
8797 | 95.6715
8798 | 129.456
8799 | 105.1313
8800 | 114.5099
8801 | 153.5643
8802 | 107.1687
8803 | 112.1658
8804 | 119.5602
8805 | 136.9288
8806 | 156.3292
8807 | 117.3078
8808 | 116.2363
8809 | 107.6348
8810 | 100.3264
8811 | 124.4965
8812 | 144.2102
8813 | 105.3021
8814 | 94.4206
8815 | 151.5578
8816 | 96.9697
8817 | 142.7471
8818 | 118.1981
8819 | 145.0959
8820 | 160.8735
8821 | 109.3935
8822 | 135.0221
8823 | 116.8721
8824 | 131.987
8825 | 81.9056
8826 | 103.3635
8827 | 94.7441
8828 | 128.9076
8829 | 115.8065
8830 | 172.3796
8831 | 137.9788
8832 | 116.0128
8833 | 161.9816
8834 | 96.8308
8835 | 164.0105
8836 | 85.9712
8837 | 128.4679
8838 | 126.3998
8839 | 111.0988
8840 | 102.9779
8841 | 116.572
8842 | 93.5264
8843 | 120.5936
8844 | 113.5055
8845 | 101.802
8846 | 104.2062
8847 | 107.0917
8848 | 159.471
8849 | 127.0698
8850 | 73.9524
8851 | 179.9961
8852 | 104.4897
8853 | 117.006
8854 | 133.2929
8855 | 107.1532
8856 | 175.3951
8857 | 121.1532
8858 | 83.7008
8859 | 119.4795
8860 | 155.3119
8861 | 151.9485
8862 | 76.2446
8863 | 97.5056
8864 | 132.8176
8865 | 117.6335
8866 | 121.6495
8867 | 102.2181
8868 | 121.8842
8869 | 97.382
8870 | 132.6818
8871 | 95.5648
8872 | 111.2012
8873 | 105.5191
8874 | 123.5026
8875 | 137.4078
8876 | 152.3585
8877 | 89.9845
8878 | 110.9657
8879 | 127.7948
8880 | 130.5805
8881 | 90.699
8882 | 70.4486
8883 | 75.9132
8884 | 115.9402
8885 | 120.7083
8886 | 136.4941
8887 | 108.6944
8888 | 103.7773
8889 | 79.682
8890 | 82.0814
8891 | 79.3151
8892 | 90.8539
8893 | 88.6754
8894 | 125.6231
8895 | 98.8645
8896 | 112.6206
8897 | 119.3192
8898 | 91.0061
8899 | 157.8629
8900 | 108.7919
8901 | 135.9351
8902 | 91.9567
8903 | 91.0607
8904 | 86.2767
8905 | 122.1248
8906 | 105.3813
8907 | 126.0877
8908 | 151.4404
8909 | 117.6014
8910 | 130.0151
8911 | 156.7375
8912 | 147.2208
8913 | 127.7183
8914 | 105.6526
8915 | 111.5295
8916 | 96.7453
8917 | 73.0666
8918 | 138.3264
8919 | 130.5644
8920 | 91.5628
8921 | 117.5412
8922 | 80.7769
8923 | 69.26
8924 | 129.7112
8925 | 119.7587
8926 | 113.6939
8927 | 122.9365
8928 | 118.8901
8929 | 136.6501
8930 | 110.844
8931 | 134.8189
8932 | 86.2133
8933 | 135.5236
8934 | 157.4466
8935 | 104.8921
8936 | 129.3341
8937 | 120.6187
8938 | 166.3686
8939 | 108.1538
8940 | 106.726
8941 | 119.5801
8942 | 50.6616
8943 | 102.3352
8944 | 140.2966
8945 | 128.9306
8946 | 117.1982
8947 | 98.8143
8948 | 131.5027
8949 | 111.8657
8950 | 126.5427
8951 | 109.7314
8952 | 145.6877
8953 | 114.7237
8954 | 148.02
8955 | 148.1719
8956 | 131.283
8957 | 113.4687
8958 | 121.849
8959 | 83.3338
8960 | 130.1418
8961 | 85.8449
8962 | 108.3022
8963 | 153.4555
8964 | 122.4849
8965 | 127.276
8966 | 145.6904
8967 | 119.3279
8968 | 90.3061
8969 | 114.8406
8970 | 122.27
8971 | 152.1071
8972 | 128.4096
8973 | 100.1562
8974 | 119.7064
8975 | 93.388
8976 | 104.6333
8977 | 98.491
8978 | 121.5103
8979 | 106.5371
8980 | 130.9573
8981 | 95.1863
8982 | 111.6277
8983 | 146.5532
8984 | 126.1117
8985 | 132.5558
8986 | 128.7741
8987 | 101.4214
8988 | 126.1665
8989 | 141.9985
8990 | 121.1524
8991 | 135.9143
8992 | 96.8161
8993 | 125.1922
8994 | 119.3097
8995 | 140.8883
8996 | 99.8557
8997 | 95.1829
8998 | 107.4862
8999 | 142.9487
9000 | 115.3159
9001 | 103.6283
9002 | 125.0798
9003 | 132.5283
9004 | 121.5337
9005 | 143.7359
9006 | 91.1868
9007 | 163.9747
9008 | 116.442
9009 | 120.3761
9010 | 125.2131
9011 | 140.5101
9012 | 101.4719
9013 | 122.3106
9014 | 123.8577
9015 | 141.1717
9016 | 152.562
9017 | 124.0648
9018 | 134.4981
9019 | 142.6821
9020 | 100.0271
9021 | 131.374
9022 | 125.9128
9023 | 131.42
9024 | 127.1386
9025 | 107.9298
9026 | 94.0965
9027 | 127.5265
9028 | 98.7634
9029 | 145.0716
9030 | 117.2012
9031 | 143.8677
9032 | 101.8731
9033 | 124.9948
9034 | 153.4676
9035 | 118.5791
9036 | 83.6444
9037 | 112.9555
9038 | 99.7809
9039 | 132.3468
9040 | 113.907
9041 | 143.5652
9042 | 135.0272
9043 | 136.9259
9044 | 110.1111
9045 | 125.1994
9046 | 146.2852
9047 | 161.8698
9048 | 125.2092
9049 | 111.1247
9050 | 89.7055
9051 | 157.3319
9052 | 89.8312
9053 | 106.5317
9054 | 131.6564
9055 | 86.656
9056 | 88.686
9057 | 134.32
9058 | 99.3918
9059 | 104.592
9060 | 135.2709
9061 | 185.9515
9062 | 117.7724
9063 | 90.5201
9064 | 90.5811
9065 | 135.691
9066 | 111.2715
9067 | 75.5074
9068 | 133.6433
9069 | 111.5012
9070 | 146.4267
9071 | 142.805
9072 | 140.2716
9073 | 116.1232
9074 | 126.2522
9075 | 125.1906
9076 | 77.1591
9077 | 131.4207
9078 | 105.8264
9079 | 155.6841
9080 | 98.3151
9081 | 86.4219
9082 | 137.3309
9083 | 93.2828
9084 | 159.3688
9085 | 64.2931
9086 | 142.9291
9087 | 121.7753
9088 | 82.1439
9089 | 109.8513
9090 | 108.9449
9091 | 94.3655
9092 | 127.1439
9093 | 130.5019
9094 | 141.3719
9095 | 99.2688
9096 | 133.0666
9097 | 110.5526
9098 | 168.2468
9099 | 105.2106
9100 | 128.308
9101 | 111.6886
9102 | 172.7629
9103 | 145.9813
9104 | 85.8596
9105 | 122.8381
9106 | 103.2911
9107 | 78.3698
9108 | 110.179
9109 | 65.4166
9110 | 133.9511
9111 | 134.1183
9112 | 108.5649
9113 | 136.9526
9114 | 130.2568
9115 | 130.5721
9116 | 149.3853
9117 | 159.5591
9118 | 124.1891
9119 | 147.7947
9120 | 149.7991
9121 | 133.812
9122 | 135.0964
9123 | 72.3327
9124 | 152.2994
9125 | 144.6435
9126 | 137.684
9127 | 119.5824
9128 | 112.6017
9129 | 150.1247
9130 | 111.767
9131 | 89.4
9132 | 98.5547
9133 | 100.887
9134 | 131.2178
9135 | 118.7439
9136 | 116.3157
9137 | 101.5842
9138 | 110.3757
9139 | 121.52
9140 | 127.3568
9141 | 129.45
9142 | 132.5002
9143 | 167.3608
9144 | 92.0601
9145 | 139.7559
9146 | 142.5478
9147 | 116.0601
9148 | 94.4916
9149 | 122.2046
9150 | 162.6971
9151 | 90.3691
9152 | 130.6774
9153 | 97.3503
9154 | 98.4322
9155 | 144.4403
9156 | 137.8038
9157 | 121.5169
9158 | 160.1098
9159 | 124.8743
9160 | 135.915
9161 | 105.0482
9162 | 60.3965
9163 | 73.7678
9164 | 96.2961
9165 | 72.875
9166 | 152.9895
9167 | 84.2597
9168 | 98.635
9169 | 122.0224
9170 | 157.4925
9171 | 132.122
9172 | 102.9142
9173 | 118.634
9174 | 118.7381
9175 | 93.1491
9176 | 107.3287
9177 | 109.6372
9178 | 80.0876
9179 | 107.7395
9180 | 140.3192
9181 | 141.0485
9182 | 106.5618
9183 | 80.4644
9184 | 144.367
9185 | 148.5808
9186 | 119.4939
9187 | 131.1857
9188 | 133.8898
9189 | 126.4515
9190 | 153.5878
9191 | 123.5475
9192 | 126.2508
9193 | 151.5692
9194 | 148.3616
9195 | 118.1109
9196 | 129.4978
9197 | 106.0891
9198 | 112.6449
9199 | 162.7085
9200 | 110.9245
9201 | 120.3975
9202 | 122.2984
9203 | 98.4143
9204 | 145.2749
9205 | 151.0159
9206 | 134.1501
9207 | 163.4418
9208 | 176.4924
9209 | 92.5105
9210 | 116.6575
9211 | 79.2391
9212 | 130.181
9213 | 130.9525
9214 | 125.6028
9215 | 144.7314
9216 | 149.3802
9217 | 92.5641
9218 | 122.446
9219 | 149.2585
9220 | 98.6007
9221 | 100.5968
9222 | 174.7801
9223 | 133.9561
9224 | 125.2849
9225 | 69.9159
9226 | 162.1026
9227 | 101.2198
9228 | 112.5381
9229 | 102.9224
9230 | 87.4054
9231 | 129.4727
9232 | 129.6699
9233 | 122.3604
9234 | 114.6537
9235 | 96.6952
9236 | 91.3406
9237 | 118.5835
9238 | 140.2717
9239 | 171.5051
9240 | 125.1767
9241 | 169.366
9242 | 184.2554
9243 | 111.0039
9244 | 80.3118
9245 | 168.5105
9246 | 94.0508
9247 | 122.4726
9248 | 155.887
9249 | 122.7529
9250 | 76.5382
9251 | 158.6474
9252 | 114.6361
9253 | 114.5393
9254 | 147.265
9255 | 104.0008
9256 | 113.7419
9257 | 82.2396
9258 | 136.1298
9259 | 123.4284
9260 | 104.5995
9261 | 143.7487
9262 | 91.5931
9263 | 133.3283
9264 | 96.206
9265 | 153.7958
9266 | 133.4801
9267 | 114.9647
9268 | 97.2853
9269 | 95.2841
9270 | 155.692
9271 | 75.8043
9272 | 93.2783
9273 | 126.3301
9274 | 115.0712
9275 | 148.2773
9276 | 125.9994
9277 | 98.1508
9278 | 134.1199
9279 | 125.8163
9280 | 108.2517
9281 | 99.2018
9282 | 119.9144
9283 | 116.8452
9284 | 115.4248
9285 | 121.2733
9286 | 131.1279
9287 | 111.5914
9288 | 129.1644
9289 | 77.0647
9290 | 122.6737
9291 | 76.8804
9292 | 90.8478
9293 | 153.8335
9294 | 109.2002
9295 | 135.4783
9296 | 100.6644
9297 | 115.3436
9298 | 119.5246
9299 | 135.697
9300 | 143.4839
9301 | 126.5671
9302 | 107.3837
9303 | 106.5958
9304 | 95.1478
9305 | 93.3344
9306 | 170.7675
9307 | 64.8495
9308 | 152.3336
9309 | 55.9366
9310 | 95.9516
9311 | 126.3265
9312 | 126.2249
9313 | 117.5062
9314 | 97.4332
9315 | 133.7868
9316 | 139.681
9317 | 137.191
9318 | 93.4463
9319 | 102.0659
9320 | 77.3135
9321 | 114.1414
9322 | 72.5412
9323 | 149.6752
9324 | 84.531
9325 | 104.678
9326 | 141.6941
9327 | 173.19
9328 | 105.4375
9329 | 131.0399
9330 | 108.5448
9331 | 103.4427
9332 | 90.783
9333 | 147.9146
9334 | 113.9821
9335 | 108.4244
9336 | 112.637
9337 | 101.4893
9338 | 135.467
9339 | 97.6587
9340 | 108.3871
9341 | 150.779
9342 | 131.1153
9343 | 164.3199
9344 | 99.9489
9345 | 106.1834
9346 | 145.4506
9347 | 169.2249
9348 | 106.8236
9349 | 134.0403
9350 | 146.4694
9351 | 91.7245
9352 | 106.0566
9353 | 138.7673
9354 | 113.2497
9355 | 114.9969
9356 | 119.8835
9357 | 132.9522
9358 | 118.8943
9359 | 171.3042
9360 | 84.4973
9361 | 136.3001
9362 | 142.1055
9363 | 117.802
9364 | 114.7027
9365 | 113.6746
9366 | 113.5484
9367 | 124.1796
9368 | 114.4986
9369 | 77.3799
9370 | 129.7852
9371 | 125.1496
9372 | 87.2032
9373 | 115.9847
9374 | 114.0304
9375 | 114.4951
9376 | 57.5144
9377 | 120.8693
9378 | 126.6466
9379 | 119.1676
9380 | 106.1025
9381 | 96.9476
9382 | 82.4233
9383 | 101.2159
9384 | 134.3146
9385 | 168.2463
9386 | 72.3427
9387 | 124.064
9388 | 131.8975
9389 | 123.7694
9390 | 85.0695
9391 | 134.0093
9392 | 144.3942
9393 | 101.6369
9394 | 77.4056
9395 | 124.8991
9396 | 124.993
9397 | 126.8924
9398 | 130.8613
9399 | 136.0418
9400 | 119.6827
9401 | 107.8112
9402 | 74.6619
9403 | 112.4601
9404 | 108.6895
9405 | 150.6501
9406 | 174.7917
9407 | 124.8489
9408 | 142.0724
9409 | 120.8139
9410 | 123.9784
9411 | 126.7802
9412 | 89.6765
9413 | 86.3709
9414 | 103.5058
9415 | 138.2152
9416 | 162.029
9417 | 116.8919
9418 | 129.9538
9419 | 127.1715
9420 | 83.9597
9421 | 81.229
9422 | 107.3736
9423 | 134.7215
9424 | 94.762
9425 | 142.719
9426 | 119.3289
9427 | 147.7271
9428 | 89.2689
9429 | 122.7904
9430 | 124.7149
9431 | 93.2122
9432 | 125.6171
9433 | 124.9782
9434 | 115.2882
9435 | 101.6724
9436 | 151.2065
9437 | 154.557
9438 | 136.774
9439 | 139.3057
9440 | 116.7098
9441 | 148.8902
9442 | 142.1069
9443 | 118.5748
9444 | 146.397
9445 | 129.6203
9446 | 121.8768
9447 | 120.2506
9448 | 107.4954
9449 | 114.9961
9450 | 123.1286
9451 | 135.4167
9452 | 159.7361
9453 | 99.7294
9454 | 105.8241
9455 | 126.5102
9456 | 71.9194
9457 | 147.7796
9458 | 134.6606
9459 | 112.4591
9460 | 104.3129
9461 | 148.7973
9462 | 115.7414
9463 | 113.3994
9464 | 91.7299
9465 | 151.6533
9466 | 136.9645
9467 | 145.4532
9468 | 130.7867
9469 | 116.679
9470 | 91.6618
9471 | 132.6537
9472 | 113.7843
9473 | 143.2617
9474 | 114.06
9475 | 139.41
9476 | 108.8761
9477 | 92.1476
9478 | 121.5439
9479 | 70.0185
9480 | 78.2797
9481 | 137.1214
9482 | 153.8353
9483 | 131.7362
9484 | 119.6103
9485 | 89.6264
9486 | 136.3016
9487 | 131.3913
9488 | 139.6397
9489 | 139.9998
9490 | 140.4699
9491 | 139.4102
9492 | 162.5172
9493 | 148.3181
9494 | 120.0113
9495 | 125.1129
9496 | 120.9458
9497 | 132.9418
9498 | 132.084
9499 | 100.1431
9500 | 122.4014
9501 | 117.6201
9502 | 138.0956
9503 | 139.901
9504 | 105.4272
9505 | 95.3706
9506 | 99.3095
9507 | 71.6999
9508 | 117.2102
9509 | 121.489
9510 | 127.4436
9511 | 143.1849
9512 | 114.8712
9513 | 117.4311
9514 | 68.7415
9515 | 105.709
9516 | 149.1769
9517 | 136.1882
9518 | 141.3188
9519 | 113.2156
9520 | 133.0057
9521 | 174.1432
9522 | 97.8243
9523 | 99.8692
9524 | 126.1136
9525 | 148.2614
9526 | 93.2846
9527 | 104.2011
9528 | 96.3114
9529 | 120.8563
9530 | 94.123
9531 | 150.4268
9532 | 179.0236
9533 | 157.8678
9534 | 79.1428
9535 | 118.1738
9536 | 153.3962
9537 | 71.0378
9538 | 101.3342
9539 | 143.9521
9540 | 122.15
9541 | 68.1805
9542 | 164.4288
9543 | 121.4263
9544 | 153.0139
9545 | 100.5887
9546 | 136.5995
9547 | 122.9436
9548 | 139.9238
9549 | 127.9864
9550 | 99.8219
9551 | 138.4268
9552 | 123.9849
9553 | 147.3469
9554 | 95.5725
9555 | 104.3281
9556 | 118.4584
9557 | 133.9231
9558 | 144.0077
9559 | 141.2741
9560 | 140.5013
9561 | 175.1806
9562 | 81.786
9563 | 143.863
9564 | 90.7742
9565 | 103.7831
9566 | 102.0792
9567 | 161.3497
9568 | 119.7345
9569 | 119.4697
9570 | 119.7476
9571 | 119.8498
9572 | 136.8953
9573 | 121.4252
9574 | 149.6751
9575 | 158.0714
9576 | 147.0485
9577 | 87.0177
9578 | 129.8337
9579 | 92.3921
9580 | 136.3305
9581 | 127.1453
9582 | 145.5812
9583 | 106.6862
9584 | 110.9169
9585 | 122.4565
9586 | 85.0835
9587 | 125.3508
9588 | 129.5881
9589 | 99.82
9590 | 93.2967
9591 | 107.8749
9592 | 101.352
9593 | 120.2089
9594 | 153.9533
9595 | 169.7786
9596 | 85.4963
9597 | 97.1559
9598 | 118.3302
9599 | 166.5737
9600 | 133.3948
9601 | 131.2512
9602 | 110.942
9603 | 91.5209
9604 | 92.2018
9605 | 119.7875
9606 | 127.4144
9607 | 125.2369
9608 | 129.076
9609 | 98.1248
9610 | 123.1016
9611 | 138.7854
9612 | 102.0239
9613 | 107.0708
9614 | 157.6741
9615 | 109.5596
9616 | 99.1038
9617 | 127.3955
9618 | 124.438
9619 | 130.1291
9620 | 98.2166
9621 | 121.4851
9622 | 127.0756
9623 | 137.9211
9624 | 98.2636
9625 | 141.9284
9626 | 115.3631
9627 | 108.1297
9628 | 106.0329
9629 | 119.332
9630 | 121.9294
9631 | 90.4178
9632 | 149.3757
9633 | 146.9012
9634 | 129.1992
9635 | 112.8984
9636 | 112.683
9637 | 127.5506
9638 | 133.0695
9639 | 93.395
9640 | 99.5161
9641 | 182.1295
9642 | 89.9289
9643 | 129.0174
9644 | 80.6015
9645 | 129.9569
9646 | 92.5502
9647 | 166.1368
9648 | 108.8843
9649 | 128.0785
9650 | 93.4519
9651 | 127.9335
9652 | 101.2631
9653 | 101.0492
9654 | 135.5662
9655 | 51.9168
9656 | 131.4741
9657 | 106.0323
9658 | 132.6862
9659 | 96.9506
9660 | 90.0369
9661 | 119.2268
9662 | 168.9854
9663 | 120.1296
9664 | 119.564
9665 | 114.3617
9666 | 167.2984
9667 | 98.1729
9668 | 115.5284
9669 | 154.49
9670 | 104.7163
9671 | 102.2451
9672 | 103.9882
9673 | 94.7101
9674 | 124.5375
9675 | 107.8731
9676 | 136.2638
9677 | 112.0325
9678 | 83.7472
9679 | 117.7841
9680 | 93.1579
9681 | 117.0176
9682 | 102.6021
9683 | 120.5222
9684 | 120.5766
9685 | 112.5843
9686 | 97.0787
9687 | 120.1609
9688 | 85.861
9689 | 139.6579
9690 | 121.3832
9691 | 114.1415
9692 | 122.606
9693 | 129.7986
9694 | 135.9519
9695 | 127.3066
9696 | 84.0832
9697 | 124.2575
9698 | 89.049
9699 | 106.8581
9700 | 119.9589
9701 | 134.3173
9702 | 93.6008
9703 | 142.1575
9704 | 67.7619
9705 | 134.7026
9706 | 39.9058
9707 | 68.8875
9708 | 119.3738
9709 | 122.8505
9710 | 136.4283
9711 | 144.2581
9712 | 97.3292
9713 | 120.5552
9714 | 97.083
9715 | 118.3303
9716 | 90.1958
9717 | 124.0584
9718 | 153.92
9719 | 91.5946
9720 | 84.403
9721 | 78.6788
9722 | 104.262
9723 | 133.1983
9724 | 75.7722
9725 | 145.5169
9726 | 107.246
9727 | 144.1444
9728 | 151.8748
9729 | 131.5777
9730 | 140.7866
9731 | 103.934
9732 | 156.3175
9733 | 153.6544
9734 | 114.6298
9735 | 125.0519
9736 | 84.3155
9737 | 130.403
9738 | 110.4433
9739 | 166.4525
9740 | 123.6014
9741 | 97.2509
9742 | 126.8226
9743 | 84.6279
9744 | 108.3164
9745 | 143.9962
9746 | 122.982
9747 | 93.1265
9748 | 84.7689
9749 | 143.4709
9750 | 129.8895
9751 | 85.3986
9752 | 100.7398
9753 | 115.6002
9754 | 142.0078
9755 | 104.2126
9756 | 100.6202
9757 | 136.909
9758 | 167.7671
9759 | 117.7499
9760 | 163.4889
9761 | 154.5178
9762 | 136.7308
9763 | 138.8345
9764 | 135.6599
9765 | 81.7071
9766 | 93.651
9767 | 125.5596
9768 | 143.1614
9769 | 158.8384
9770 | 158.6731
9771 | 147.1584
9772 | 126.1381
9773 | 146.0709
9774 | 115.8887
9775 | 103.3094
9776 | 149.3607
9777 | 138.2522
9778 | 101.2743
9779 | 74.3265
9780 | 182.785
9781 | 135.6829
9782 | 90.9794
9783 | 100.5763
9784 | 126.5703
9785 | 136.9536
9786 | 141.3811
9787 | 115.29
9788 | 106.0222
9789 | 179.7065
9790 | 137.9636
9791 | 103.8512
9792 | 153.5257
9793 | 74.8528
9794 | 127.9765
9795 | 163.345
9796 | 131.5019
9797 | 130.7863
9798 | 94.9008
9799 | 122.9052
9800 | 168.0509
9801 | 115.313
9802 | 151.2896
9803 | 111.9036
9804 | 137.4915
9805 | 184.6359
9806 | 146.1218
9807 | 150.3839
9808 | 118.4086
9809 | 122.9142
9810 | 137.9015
9811 | 125.2653
9812 | 96.2293
9813 | 94.6978
9814 | 107.0744
9815 | 112.618
9816 | 119.1787
9817 | 99.1124
9818 | 77.7047
9819 | 112.7725
9820 | 134.428
9821 | 128.3904
9822 | 62.4777
9823 | 109.985
9824 | 102.7029
9825 | 134.6535
9826 | 123.7362
9827 | 93.9006
9828 | 88.8195
9829 | 101.7909
9830 | 99.0521
9831 | 111.4612
9832 | 113.5883
9833 | 123.0019
9834 | 108.8934
9835 | 90.0798
9836 | 121.1338
9837 | 106.0632
9838 | 129.5482
9839 | 120.0035
9840 | 124.3314
9841 | 155.4116
9842 | 68.7926
9843 | 95.5562
9844 | 136.074
9845 | 143.7277
9846 | 132.9258
9847 | 128.0843
9848 | 179.2493
9849 | 110.0172
9850 | 137.6338
9851 | 144.2145
9852 | 134.4191
9853 | 111.9104
9854 | 197.7924
9855 | 117.9393
9856 | 148.7963
9857 | 107.6392
9858 | 134.8226
9859 | 134.8578
9860 | 50.2404
9861 | 153.1475
9862 | 81.6656
9863 | 62.0129
9864 | 86.1039
9865 | 132.8358
9866 | 146.8103
9867 | 147.3419
9868 | 139.6943
9869 | 118.932
9870 | 139.055
9871 | 129.8688
9872 | 131.515
9873 | 148.9435
9874 | 105.8235
9875 | 132.3629
9876 | 104.0472
9877 | 123.7798
9878 | 115.3393
9879 | 81.5171
9880 | 103.4413
9881 | 126.7927
9882 | 107.8597
9883 | 84.9365
9884 | 83.5126
9885 | 82.0383
9886 | 101.3524
9887 | 129.2607
9888 | 104.6057
9889 | 98.2111
9890 | 128.4292
9891 | 116.0746
9892 | 129.1026
9893 | 51.089
9894 | 139.3105
9895 | 109.9024
9896 | 145.2505
9897 | 105.6303
9898 | 111.5428
9899 | 120.0176
9900 | 107.4099
9901 | 117.9564
9902 | 84.4808
9903 | 160.0891
9904 | 105.5033
9905 | 126.6453
9906 | 116.9538
9907 | 102.2321
9908 | 113.4338
9909 | 108.94
9910 | 140.1704
9911 | 157.8851
9912 | 106.7325
9913 | 120.8785
9914 | 112.676
9915 | 135.4919
9916 | 133.3052
9917 | 123.0721
9918 | 157.5651
9919 | 134.2242
9920 | 163.8893
9921 | 132.3
9922 | 122.0251
9923 | 88.3796
9924 | 150.1424
9925 | 118.6123
9926 | 121.0471
9927 | 117.6891
9928 | 130.5435
9929 | 112.7664
9930 | 128.1345
9931 | 127.0813
9932 | 119.5497
9933 | 132.1489
9934 | 158.2691
9935 | 120.6261
9936 | 146.8421
9937 | 128.2426
9938 | 115.5814
9939 | 113.8678
9940 | 137.8367
9941 | 102.3051
9942 | 153.8172
9943 | 108.2652
9944 | 88.6395
9945 | 104.8709
9946 | 111.5977
9947 | 94.8938
9948 | 111.6211
9949 | 142.8239
9950 | 72.7313
9951 | 134.5828
9952 | 133.1693
9953 | 116.0421
9954 | 121.8763
9955 | 98.5514
9956 | 150.8586
9957 | 108.7708
9958 | 115.8768
9959 | 99.8342
9960 | 150.5939
9961 | 122.5682
9962 | 92.8953
9963 | 139.8347
9964 | 115.2079
9965 | 107.4783
9966 | 127.6637
9967 | 124.387
9968 | 106.1883
9969 | 84.529
9970 | 121.44
9971 | 135.511
9972 | 123.3258
9973 | 151.7125
9974 | 109.8673
9975 | 136.6958
9976 | 104.0698
9977 | 154.2195
9978 | 91.7569
9979 | 117.7457
9980 | 106.18
9981 | 111.7106
9982 | 145.9889
9983 | 109.4038
9984 | 87.5565
9985 | 65.9106
9986 | 130.3303
9987 | 134.8609
9988 | 107.262
9989 | 138.0343
9990 | 118.4635
9991 | 102.5029
9992 | 152.0059
9993 | 129.0131
9994 | 88.8297
9995 | 75.9779
9996 | 159.7998
9997 | 133.0592
9998 | 92.9983
9999 | 150.6132
10000 | 94.223
Note on O2: You may optionally enter a planning estimate for each uncertainty you enter, and see its cumulative probability result in the 'SPERT Probability' column. The cumulative probability is the likelihood your planning estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. Choosing a larger planning estimate will increase the cumulative probability, and choosing a smaller planning estimate will decrease the cumulative probability.
Note on P2: The SPERT Probability shows the cumulative probability of each Planning Estimate you entered in column K. If you select 'Show Left-Side Area' in cell K1, this column shows the likelihood that your Planning Estimate will be EQUAL TO or GREATER THAN the uncertainty you are estimating. If you select 'Show Right-Side Area' in cell K1, this column shows the likelihood that the uncertainty will EXCEED your Planning Estimate in column K.
Note on B3: The Minimum point-estimate represents the smallest value that is feasible, but highly improbable.
Note on C3: The Most Likely point-estimate represents the value you believe will most likely occur for each uncertainty, although many other possible outcomes exist between the Minimum and Maximum point-estimates.
Note on D3: The Maximum point-estimate represents the largest value that is feasible, but highly improbable
Note on E3: This checks that a proper 3-point estimate was entered: Minimum value must be > 0 and < Most Likely Most Likely must be > Minimum and < Maximum Maximum must be > Most Likely
Note on F3: This checks that the task has a bell-shaped appearance (even though it may be skewed). When the range between the Minimum and Most Likely is no more than 3x greater than the range between the Maximum and Most Likely, the light is green (and vice versa). When the range between the Minimum and Most Likely is no more than 5x greater than the range between the Maximum and Most Likely, the light is yellow (and vice versa). Using the SPERT® Normal Edition may not be ideal for such a skewed uncertainty. When the range difference is more than 5x greater, the light is red. Using the SPERT® Normal Edition is not recommended for this uncertainty. Use the SPERT® Beta Edition instead.
Note on G3: The PERT Mean is calcuated using the PERT formula: (Min+(4*Most Likely)+Max)/6 On a perfectly normal distribution (no skewing), the mean will also be the Most Likely outcome (the mode) and the median (50th percentile).
Note on H3: The shape of the bell-curve is heavily influenced by how confident you believe the Most Likely outcome will occur relative to other, possible outcomes between the Minimum and Maximum point-estimates. When you are more confident in the Most Likely outcome, the bell-curve grows taller, and there is a shrinking likelihood of other occurrences near the Minimum and Maximum point-estimates. Conversely, when you are less confident in the Most Likely outcome, the bell-curve grows flatter, and there is a rising likelihood of other occurrences near the Minimum and Maximum point-estimates. (You can add to, remove, or modify the dropdown control options using the VLookups worksheet).
Note on I3: William Davis: SPERT builds an implied, bell-shaped curve to represent the risk characteristics for your uncertainty. The flatter, wider the bell-curve curve is, the more uncertain the outcomes are over the feasible region. If the bell-curve's vertical rise is steep, though, your uncertainty has much less volatility near the most likely outcome. If the bell-curve is centered, it perfectly fits a normal distribution. If the bell-curve is off-center, then a normal distribution is less fitting of your uncertainty's risk properties (but using the normal distribution may be "good enough" as long as the traffic light indicator is green or yellow.
Note on K3: The SPERT Standard Deviation (SD) is calculated using this formula: SPERT SD = (Max - Min) * RSM where RSM is the Ratio Scale Multiplier associated with the Most Likely Confidence selection in column H. RSMs are associated with Most Likely Confidence choices in the VLookups worksheet. Excel's normal distribution functions, NORM.DIST and NORM.INV use the SPERT Standard Deviation as one of the input arguments.
Note on Q3: You can choose different probabilities by entering a value between 1% and 99%.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## SPERT® Normal - Agile Forecast
Statistical PERT® (SPERT®) Normal Edition | This is an experimental worksheet for agile team forecasting |  |  |  |  | Scenario 1 | Scenario 2 | Scenario 3
| Scenario 1 | Scenario 2 | Scenario 3 |  | 1 | 16 | 16 | 16 | ← Columns Q through T are hidden; they are used to create scenario calculations and probabilities
The starting date for our next release is | 2019-04-01 |  |  |  | 2 | 16 | 16 | 16
We'll use | 2 |  |  | week sprints | 3 | 16 | 16 | 16
We'll most likely complete about | 18 |  |  | story points (or user stories or features) per sprint | 4 | 16 | 16 | 16
We have | Medium confidence |  |  | that the most likely outcome will regularly occur | 5 | 16 | 16 | 16
In a worst-case scenario, we would complete only | 10 |  |  | story points (or user stories or features) | 6 | 16 | 16 | 16
In a best-case scenario, we might possibly complete | 30 |  |  | story points (or user stories or features) | 7 | 16 | 16 | 16
Our Product Backlog or next release represents about | 200 |  |  | story points of effort (or user stories or features) | 8 | 16 | 16 | 16
We desire | 0.5 | 0.66 | 0.75 | confidence in each sprint iteration | 9 | 16 | 16 | 16
Be sure this indicator is green or yellow → | 0.66667 | 0.66667 | 0.66667 | if red, check your inputs and ensure this is a bell-shaped uncertainty | 10 | 16 | 16 | 16
So, on average, we expect each sprint will finish | 18.6667 | 18.6667 | 18.6667 | story points (or user stories or features) per sprint | 11 | 16 | 16 | 16
For this uncertainty, the SPERT standard deviation is | 4 | 4 | 4 | that is: (MAX - MIN) * SPERT RSM | 12 |  | 16 | 16
Given this, we forecast that we'll complete at least | 18.6667 | 17.0168 | 15.9687 | story points (or user stories or features) each sprint (for the confidence level expressed in cell C6) | 13 |  |  | 16
We'll need | 10.7143 | 11.7531 | 12.5245 | sprints to do all the work of the Product Backlog or the next release | 14
So, we'll need about | 22 | 24 | 26 | business weeks | 15
During this time, there is/are |  |  |  | extra days (working or non-working) | 16
In total, the number of days needed are | 154 | 168 | 182 | which includes both working + non-working days | 17
So, we will complete the Product Backlog or next release on | 2019-09-02 | 2019-09-16 | 2019-09-30 | or earlier, with | 18
| 0.65616 | 0.95837 | 0.99845 | confidence in our forecast (under all these assumptions) | 19
20
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP |  |  |  |  | 21
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com |  |  |  |  | 22
Watch a Pluralsight course on Statistical PERT® Normal Edition |  |  |  |  | 23
Watch Statistical PERT videos on YouTube |  |  |  |  | 24
Connect with or follow William W. Davis on LinkedIn |  |  |  |  | 25
Follow Statistical PERT on Twitter to learn when new updates are released |  |  |  |  | 26
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the |  |  |  |  | 27
GNU General Public License as published by the Free Software Foundation, either version 3 of the License, |  |  |  |  | 28
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify |  |  |  |  | 29
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet. |  |  |  |  | 30
On both verbatim and modified copies of this file, you must always retain the original copyright notice, |  |  |  |  | 31
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License. |  |  |  |  | 32
33
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY; |  |  |  |  | 34
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE. |  |  |  |  | 35
See the GNU General Public License for more details (https://www.gnu.org/licenses/). |  |  |  |  | 36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
[6 empty] | 13.2665 | 13.8564 | 14.4222

## SPERT® Normal - Agile Forecast2
Statistical PERT® (SPERT®) Normal Edition | This is a special worksheet for agile team forecasting |  |  |  |  | Scenario 1 | Scenario 2 | Scenario 3
| Scenario 1 | Scenario 2 | Scenario 3 |  | 1 | 16 | 16 | 16 | ← Columns Q through T are hidden; they are used to create scenario calculations and probabilities
The starting date for our next release is | 2020-06-01 |  |  |  | 2 | 16 | 16 | 16
We'll use | 2 |  |  | week sprints | 3 | 16 | 16 | 16
We'll most likely complete about | 18 |  |  | story points (or user stories or features) per sprint | 4 | 16 | 16 | 16
We have | Medium confidence |  |  | that the most likely outcome will regularly occur | 5 | 16 | 16 | 16
In a worst-case scenario, we would complete only | 10 |  |  | story points (or user stories or features) | 6 | 16 | 16 | 16
In a best-case scenario, we might possibly complete | 30 |  |  | story points (or user stories or features) | 7 | 16 | 16 | 16
Our Product Backlog or next release represents about | 200 |  |  | story points of effort (or user stories or features) | 8 | 16 | 16 | 16
We desire | 0.5 | 0.66 | 0.75 | confidence in each sprint iteration | 9 | 16 | 16 | 16
Be sure this indicator is green or yellow → | 0.66667 | 0.66667 | 0.66667 | if red, check your inputs and ensure this is a bell-shaped uncertainty | 10 | 16 | 16 | 16
So, on average, we expect each sprint will finish | 18.6667 | 18.6667 | 18.6667 | story points (or user stories or features) per sprint | 11 | 16 | 16 | 16
For this uncertainty, the SPERT standard deviation is | 4 | 4 | 4 | that is: (MAX - MIN) * SPERT RSM | 12 |  | 16 | 16
Optional: Use your own standard deviation |  |  |  | You can override SPERT's standard deviation using a calculated standard deviation derived from historical data
Given this, we forecast that we'll complete at least | 18.6667 | 17.0168 | 15.9687 | story points (or user stories or features) each sprint (for the confidence level expressed in cell C6) | 13 |  |  | 16
We'll need | 10.7143 | 11.7531 | 12.5245 | sprints to do all the work of the Product Backlog or the next release | 14
So, we'll need about | 22 | 24 | 26 | business weeks | 15
During this time, there is/are |  |  |  | extra days (working or non-working) | 16
In total, the number of days needed are | 154 | 168 | 182 | which includes both working + non-working days | 17
So, we will complete the Product Backlog or next release on | 2020-11-02 | 2020-11-16 | 2020-11-30 | or earlier, with | 18
| 0.65616 | 0.95837 | 0.99845 | confidence in our forecast (under all these assumptions) | 19
20
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP |  |  |  |  | 21
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com |  |  |  |  | 22
Watch a Pluralsight course on Statistical PERT® Normal Edition |  |  |  |  | 23
Watch Statistical PERT videos on YouTube |  |  |  |  | 24
Connect with or follow William W. Davis on LinkedIn |  |  |  |  | 25
Follow Statistical PERT on Twitter to learn when new updates are released |  |  |  |  | 26
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the |  |  |  |  | 27
GNU General Public License as published by the Free Software Foundation, either version 3 of the License, |  |  |  |  | 28
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify |  |  |  |  | 29
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet. |  |  |  |  | 30
On both verbatim and modified copies of this file, you must always retain the original copyright notice, |  |  |  |  | 31
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License. |  |  |  |  | 32
33
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY; |  |  |  |  | 34
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE. |  |  |  |  | 35
See the GNU General Public License for more details (https://www.gnu.org/licenses/). |  |  |  |  | 36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
[6 empty] | 13.2665 | 13.8564 | 14.4222

## VLookups
Statistical PERT® (SPERT®) Normal Edition VLOOKUP list of values
SPERT Most Likely Subjective Terms | RSM | Min | Most Likely | Max
Near certainty | 0.070711 | 1 | 98 | 1 |  | Dropdown values for the Most Likely Confidence selection
High confidence | 0.11381 | 3 | 94 | 3 |  | Ratio Scale Multiplier used in the SPERT Standard Deviation formula
Medium-high confidence | 0.1569 | 5 | 90 | 5 |  | Number of trials out of 100, used to create the Most Likely Confidence pie chart
Medium confidence | 0.2 | 8 | 84 | 8
Medium-low confidence | 0.26873 | 14 | 72 | 14 | Note: Changing the SPERT Most Likely Subjective Terms may cause the data validation
Low confidence | 0.33747 | 23 | 54 | 23 | to break (for the Most Likely Confidence column) due to an Excel bug. If that occurs, just
Guesstimate | 0.4062 | 33 | 34 | 33 | re-edit the data validation by re-selecting these list items.
These are the Minimum heuristic percentages used in the 'SPERT Normal (1-Point entry)' and 'SPERT Normal (Mixed entry)' worksheets to create a minimum value for a 3-point estimate. You can add to, remove, or change this list. | -0.05
-0.1
-0.15
-0.2
-0.25
-0.3
-0.35
-0.4
-0.5
-0.6
-0.7
These are the Maximum heuristic percentages used in the 'SPERT Normal (1-Point entry)' and 'SPERT Normal (Mixed entry)' worksheets to create a maximum value for a 3-point estimate. You can add to, remove, or change this list. | 0.1
0.2
0.3
0.4
0.5
0.75
1
1.25
1.5
1.75
2
Choose which side of the normal curve to display
Show Left-Side Area | FALSE | Show the likelihood that the SPERT estimates will be EQUAL TO or GREATER THAN an uncertainty
Show Right-Side Area | TRUE | Show the likelihood that an uncertainty will EXCEED the SPERT estimates below
Choose whether to show currency formatting
Show currency formatting | TRUE
Do not show currency formatting | FALSE
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Ratio Scale Modeler
Statistical PERT® (SPERT®) Normal Edition Ratio Scale Modeler
| HIGHER Confidence |  |  |  | MEDIUM Confidence |  |  |  | LOWER Confidence
|  | Standard Devation: | 8.4853 |  |  | Standard Devation: | 24 |  |  | Standard Devation: | 48.7442
|  | Ratio Scale Modifier: | 0.070711 |  |  | Ratio Scale Modifier: | 0.2 |  |  | Ratio Scale Modifier: | 0.4062
|  | Mean: | 120 |  |  | Mean: | 120 |  |  | Mean: | 120
| Minimum | Most Likely | Maximum |  | Minimum | Most Likely | Maximum |  | Minimum | Most Likely | Maximum
PERT Estimate: | 60 | 120 | 180 | PERT Estimate: | 60 | 120 | 180 | PERT Estimate: | 60 | 120 | 180
Distribution: | 1 | 98 | 1 | Distribution: | 8 | 84 | 8 | Distribution: | 33 | 34 | 33
1 | 60 | 120 | 180 | 1 | 60 | 120 | 180 | 1 | 60 | 120 | 180
2 |  | 120 |  | 2 | 60 | 120 | 180 | 2 | 60 | 120 | 180
3 |  | 120 |  | 3 | 60 | 120 | 180 | 3 | 60 | 120 | 180
4 |  | 120 |  | 4 | 60 | 120 | 180 | 4 | 60 | 120 | 180
5 |  | 120 |  | 5 | 60 | 120 | 180 | 5 | 60 | 120 | 180
6 |  | 120 |  | 6 | 60 | 120 | 180 | 6 | 60 | 120 | 180
7 |  | 120 |  | 7 | 60 | 120 | 180 | 7 | 60 | 120 | 180
8 |  | 120 |  | 8 | 60 | 120 | 180 | 8 | 60 | 120 | 180
9 |  | 120 |  | 9 |  | 120 |  | 9 | 60 | 120 | 180
10 |  | 120 |  | 10 |  | 120 |  | 10 | 60 | 120 | 180
11 |  | 120 |  | 11 |  | 120 |  | 11 | 60 | 120 | 180
12 |  | 120 |  | 12 |  | 120 |  | 12 | 60 | 120 | 180
13 |  | 120 |  | 13 |  | 120 |  | 13 | 60 | 120 | 180
14 |  | 120 |  | 14 |  | 120 |  | 14 | 60 | 120 | 180
15 |  | 120 |  | 15 |  | 120 |  | 15 | 60 | 120 | 180
16 |  | 120 |  | 16 |  | 120 |  | 16 | 60 | 120 | 180
17 |  | 120 |  | 17 |  | 120 |  | 17 | 60 | 120 | 180
18 |  | 120 |  | 18 |  | 120 |  | 18 | 60 | 120 | 180
19 |  | 120 |  | 19 |  | 120 |  | 19 | 60 | 120 | 180
20 |  | 120 |  | 20 |  | 120 |  | 20 | 60 | 120 | 180
21 |  | 120 |  | 21 |  | 120 |  | 21 | 60 | 120 | 180
22 |  | 120 |  | 22 |  | 120 |  | 22 | 60 | 120 | 180
23 |  | 120 |  | 23 |  | 120 |  | 23 | 60 | 120 | 180
24 |  | 120 |  | 24 |  | 120 |  | 24 | 60 | 120 | 180
25 |  | 120 |  | 25 |  | 120 |  | 25 | 60 | 120 | 180
26 |  | 120 |  | 26 |  | 120 |  | 26 | 60 | 120 | 180
27 |  | 120 |  | 27 |  | 120 |  | 27 | 60 | 120 | 180
28 |  | 120 |  | 28 |  | 120 |  | 28 | 60 | 120 | 180
29 |  | 120 |  | 29 |  | 120 |  | 29 | 60 | 120 | 180
30 |  | 120 |  | 30 |  | 120 |  | 30 | 60 | 120 | 180
31 |  | 120 |  | 31 |  | 120 |  | 31 | 60 | 120 | 180
32 |  | 120 |  | 32 |  | 120 |  | 32 | 60 | 120 | 180
33 |  | 120 |  | 33 |  | 120 |  | 33 | 60 | 120 | 180
34 |  | 120 |  | 34 |  | 120 |  | 34 |  | 120
35 |  | 120 |  | 35 |  | 120 |  | 35
36 |  | 120 |  | 36 |  | 120 |  | 36
37 |  | 120 |  | 37 |  | 120 |  | 37
38 |  | 120 |  | 38 |  | 120 |  | 38
39 |  | 120 |  | 39 |  | 120 |  | 39
40 |  | 120 |  | 40 |  | 120 |  | 40
41 |  | 120 |  | 41 |  | 120 |  | 41
42 |  | 120 |  | 42 |  | 120 |  | 42
43 |  | 120 |  | 43 |  | 120 |  | 43
44 |  | 120 |  | 44 |  | 120 |  | 44
45 |  | 120 |  | 45 |  | 120 |  | 45
46 |  | 120 |  | 46 |  | 120 |  | 46
47 |  | 120 |  | 47 |  | 120 |  | 47
48 |  | 120 |  | 48 |  | 120 |  | 48
49 |  | 120 |  | 49 |  | 120 |  | 49
50 |  | 120 |  | 50 |  | 120 |  | 50
51 |  | 120 |  | 51 |  | 120 |  | 51
52 |  | 120 |  | 52 |  | 120 |  | 52
53 |  | 120 |  | 53 |  | 120 |  | 53
54 |  | 120 |  | 54 |  | 120 |  | 54
55 |  | 120 |  | 55 |  | 120 |  | 55
56 |  | 120 |  | 56 |  | 120 |  | 56
57 |  | 120 |  | 57 |  | 120 |  | 57
58 |  | 120 |  | 58 |  | 120 |  | 58
59 |  | 120 |  | 59 |  | 120 |  | 59
60 |  | 120 |  | 60 |  | 120 |  | 60
61 |  | 120 |  | 61 |  | 120 |  | 61
62 |  | 120 |  | 62 |  | 120 |  | 62
63 |  | 120 |  | 63 |  | 120 |  | 63
64 |  | 120 |  | 64 |  | 120 |  | 64
65 |  | 120 |  | 65 |  | 120 |  | 65
66 |  | 120 |  | 66 |  | 120 |  | 66
67 |  | 120 |  | 67 |  | 120 |  | 67
68 |  | 120 |  | 68 |  | 120 |  | 68
69 |  | 120 |  | 69 |  | 120 |  | 69
70 |  | 120 |  | 70 |  | 120 |  | 70
71 |  | 120 |  | 71 |  | 120 |  | 71
72 |  | 120 |  | 72 |  | 120 |  | 72
73 |  | 120 |  | 73 |  | 120 |  | 73
74 |  | 120 |  | 74 |  | 120 |  | 74
75 |  | 120 |  | 75 |  | 120 |  | 75
76 |  | 120 |  | 76 |  | 120 |  | 76
77 |  | 120 |  | 77 |  | 120 |  | 77
78 |  | 120 |  | 78 |  | 120 |  | 78
79 |  | 120 |  | 79 |  | 120 |  | 79
80 |  | 120 |  | 80 |  | 120 |  | 80
81 |  | 120 |  | 81 |  | 120 |  | 81
82 |  | 120 |  | 82 |  | 120 |  | 82
83 |  | 120 |  | 83 |  | 120 |  | 83
84 |  | 120 |  | 84 |  | 120 |  | 84
85 |  | 120 |  | 85 |  |  |  | 85
86 |  | 120 |  | 86 |  |  |  | 86
87 |  | 120 |  | 87 |  |  |  | 87
88 |  | 120 |  | 88 |  |  |  | 88
89 |  | 120 |  | 89 |  |  |  | 89
90 |  | 120 |  | 90 |  |  |  | 90
91 |  | 120 |  | 91 |  |  |  | 91
92 |  | 120 |  | 92 |  |  |  | 92
93 |  | 120 |  | 93 |  |  |  | 93
94 |  | 120 |  | 94 |  |  |  | 94
95 |  | 120 |  | 95 |  |  |  | 95
96 |  | 120 |  | 96 |  |  |  | 96
97 |  | 120 |  | 97 |  |  |  | 97
98 |  | 120 |  | 98 |  |  |  | 98
99 |  |  |  | 99 |  |  |  | 99
100 |  |  |  | 100 |  |  |  | 100
Version 4c – © 2015-2019, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Follow Statistical PERT on Twitter to learn when new updates are released
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## Collabinart®
Collabinart® Experience Collaboration through Interpretive Art™
At the 2018 PMI Global Conference,
attendees experienced Collabinart®.
Collabinart is a freely-licensed
team-building and training
framework to build collaboration
skills using masterpiece artworks.
Use Collabinart at any point in a
team's journey together. Develop
team camaraderie, active listening
skills, and collaboration skills.
It's fun, free, and effective.
Visit the Collabinart website
to learn more.
The Young Shepherdess (1865)
William-Adolphe Bouguereau
San Diego Museum of Art

## Change Log
Statistical PERT® (SPERT®) Normal Edition Change Log
Date | Version | Description
2019-12-07 | 4c | Formatted titles to include tab names
2019-12-07 | 4b | Added Monte Carlo simulation to the SPERT Charts tab; renamed it SPERT MC Simulation
2019-12-07 | 4a | Added the "Your SD" standard deviation option to override the SPERT SD (standard deviation)
2019-07-12 | 3.0.3 | Format and painting title on Collabinart tab.
2019-07-09 | 3.0.2 | Format GNU GPL page, replace ™ with ® on Collabinart tab, minor formatting on Agile Forecast tab and GNU footer links (all tabs) to https
2019-06-30 | 3.0.1 | Added full GNU GPL license, updated footer language.
2019-03-10 | 3.0 | Added: Sparklines, tri-colored combo charts, Practice Forecasting and Super Simple SPERT tabs, 3-scenario agile forecasting
2018-11-17 | 2.4 | Changed the % calculation for the whole release in the "Agile Forecast" tab
2018-09-22 | 2.3 | Added a new tab "Agile Forecast" for agile team estimation/forecasting
2017-03-01 | 2.2 | Added new tab 'for Beginners' to make it easy and non-threatening to use Statistical PERT for smart people who don't love statistics :-)
2017-02-03 | 2.1 | Added new tab 'Mixed Mode' allowing manual 3-point entry and/or global or line-level heuristics
2017-01-12 | 2.0.2 | Removed the dash to read, "Statistical PERT® Normal Edition" and "SPERT® Normal Edition"
2017-01-03 | 2.0.1 | Changed '(1-point entry)' & '(3-point entry)' tabs so cells L104 and L106 only show probabilities when a planning estimate is entered
2017-01-01 | 2.0 | Added: '(1-Point entry)' tab to create 3-pt estimates with heuristics, show left/right side probabilities, enhanced formatting.
2016-10-06 | 1.4.1 | Added HTTPS to links. Renamed "SPERT Graphs…" to "SPERT Charts…"
2016-10-03 | 1.4 | Added a pie chart to 'SPERT Graphs…' worksheet and removed "Unskewed" probabilities which used the mode instead of mean
2016-09-21 | 1.3a | Changed links to HTTPS, added a SPERT logo to the Welcome tab, and changed pie chart so upperbound is red, lowerbound is green
2016-09-10 | 1.3 | Added a confidence interval probability and pie chart for all estimated tasks
2016-07-09 | 1.2 | Added traffic light indicators to check for a valid 3-point estimate and implied bell-shape of the task
2016-07-03 | 1.1 | Added new worksheet, SPERT Bell-Curve for Task Duration to show the implied, normal bell-shaped curve
2015-10-09 | 1.02 | Formatting changes for the PMI article on ProjectManagement.com; updated formulas in cols O - T.
2015-09-17 | 1.01 | Changed formulas in cells M4:M15, N4:N15 so the Most Likely value in column C is > 0 (not > 4)
2015-07-31 | 1.00 | Initial release

## GNU GPL
GNU GENERAL PUBLIC LICENSE
Version 3, 29 June 2007
Copyright (C) 2007 Free Software Foundation, Inc. <https://fsf.org/>
Everyone is permitted to copy and distribute verbatim copies
of this license document, but changing it is not allowed.
Preamble
The GNU General Public License is a free, copyleft license for
software and other kinds of works.
The licenses for most software and other practical works are designed
to take away your freedom to share and change the works. By contrast,
the GNU General Public License is intended to guarantee your freedom to
share and change all versions of a program--to make sure it remains free
software for all its users. We, the Free Software Foundation, use the
GNU General Public License for most of our software; it applies also to
any other work released this way by its authors. You can apply it to
your programs, too.
When we speak of free software, we are referring to freedom, not
price. Our General Public Licenses are designed to make sure that you
have the freedom to distribute copies of free software (and charge for
them if you wish), that you receive source code or can get it if you
want it, that you can change the software or use pieces of it in new
free programs, and that you know you can do these things.
To protect your rights, we need to prevent others from denying you
these rights or asking you to surrender the rights. Therefore, you have
certain responsibilities if you distribute copies of the software, or if
you modify it: responsibilities to respect the freedom of others.
For example, if you distribute copies of such a program, whether
gratis or for a fee, you must pass on to the recipients the same
freedoms that you received. You must make sure that they, too, receive
or can get the source code. And you must show them these terms so they
know their rights.
Developers that use the GNU GPL protect your rights with two steps:
(1) assert copyright on the software, and (2) offer you this License
giving you legal permission to copy, distribute and/or modify it.
For the developers' and authors' protection, the GPL clearly explains
that there is no warranty for this free software. For both users' and
authors' sake, the GPL requires that modified versions be marked as
changed, so that their problems will not be attributed erroneously to
authors of previous versions.
Some devices are designed to deny users access to install or run
modified versions of the software inside them, although the manufacturer
can do so. This is fundamentally incompatible with the aim of
protecting users' freedom to change the software. The systematic
pattern of such abuse occurs in the area of products for individuals to
use, which is precisely where it is most unacceptable. Therefore, we
have designed this version of the GPL to prohibit the practice for those
products. If such problems arise substantially in other domains, we
stand ready to extend this provision to those domains in future versions
of the GPL, as needed to protect the freedom of users.
Finally, every program is threatened constantly by software patents.
States should not allow patents to restrict development and use of
software on general-purpose computers, but in those that do, we wish to
avoid the special danger that patents applied to a free program could
make it effectively proprietary. To prevent this, the GPL assures that
patents cannot be used to render the program non-free.
The precise terms and conditions for copying, distribution and
modification follow.
TERMS AND CONDITIONS
0. Definitions.
"This License" refers to version 3 of the GNU General Public License.
"Copyright" also means copyright-like laws that apply to other kinds of
works, such as semiconductor masks.
"The Program" refers to any copyrightable work licensed under this
License. Each licensee is addressed as "you". "Licensees" and
"recipients" may be individuals or organizations.
To "modify" a work means to copy from or adapt all or part of the work
in a fashion requiring copyright permission, other than the making of an
exact copy. The resulting work is called a "modified version" of the
earlier work or a work "based on" the earlier work.
A "covered work" means either the unmodified Program or a work based
on the Program.
To "propagate" a work means to do anything with it that, without
permission, would make you directly or secondarily liable for
infringement under applicable copyright law, except executing it on a
computer or modifying a private copy. Propagation includes copying,
distribution (with or without modification), making available to the
public, and in some countries other activities as well.
To "convey" a work means any kind of propagation that enables other
parties to make or receive copies. Mere interaction with a user through
a computer network, with no transfer of a copy, is not conveying.
An interactive user interface displays "Appropriate Legal Notices"
to the extent that it includes a convenient and prominently visible
feature that (1) displays an appropriate copyright notice, and (2)
tells the user that there is no warranty for the work (except to the
extent that warranties are provided), that licensees may convey the
work under this License, and how to view a copy of this License. If
the interface presents a list of user commands or options, such as a
menu, a prominent item in the list meets this criterion.
1. Source Code.
The "source code" for a work means the preferred form of the work
for making modifications to it. "Object code" means any non-source
form of a work.
A "Standard Interface" means an interface that either is an official
standard defined by a recognized standards body, or, in the case of
interfaces specified for a particular programming language, one that
is widely used among developers working in that language.
The "System Libraries" of an executable work include anything, other
than the work as a whole, that (a) is included in the normal form of
packaging a Major Component, but which is not part of that Major
Component, and (b) serves only to enable use of the work with that
Major Component, or to implement a Standard Interface for which an
implementation is available to the public in source code form. A
"Major Component", in this context, means a major essential component
(kernel, window system, and so on) of the specific operating system
(if any) on which the executable work runs, or a compiler used to
produce the work, or an object code interpreter used to run it.
The "Corresponding Source" for a work in object code form means all
the source code needed to generate, install, and (for an executable
work) run the object code and to modify the work, including scripts to
control those activities. However, it does not include the work's
System Libraries, or general-purpose tools or generally available free
programs which are used unmodified in performing those activities but
which are not part of the work. For example, Corresponding Source
includes interface definition files associated with source files for
the work, and the source code for shared libraries and dynamically
linked subprograms that the work is specifically designed to require,
such as by intimate data communication or control flow between those
subprograms and other parts of the work.
The Corresponding Source need not include anything that users
can regenerate automatically from other parts of the Corresponding
Source.
The Corresponding Source for a work in source code form is that
same work.
2. Basic Permissions.
All rights granted under this License are granted for the term of
copyright on the Program, and are irrevocable provided the stated
conditions are met. This License explicitly affirms your unlimited
permission to run the unmodified Program. The output from running a
covered work is covered by this License only if the output, given its
content, constitutes a covered work. This License acknowledges your
rights of fair use or other equivalent, as provided by copyright law.
You may make, run and propagate covered works that you do not
convey, without conditions so long as your license otherwise remains
in force. You may convey covered works to others for the sole purpose
of having them make modifications exclusively for you, or provide you
with facilities for running those works, provided that you comply with
the terms of this License in conveying all material for which you do
not control copyright. Those thus making or running the covered works
for you must do so exclusively on your behalf, under your direction
and control, on terms that prohibit them from making any copies of
your copyrighted material outside their relationship with you.
Conveying under any other circumstances is permitted solely under
the conditions stated below. Sublicensing is not allowed; section 10
makes it unnecessary.
3. Protecting Users' Legal Rights From Anti-Circumvention Law.
No covered work shall be deemed part of an effective technological
measure under any applicable law fulfilling obligations under article
11 of the WIPO copyright treaty adopted on 20 December 1996, or
similar laws prohibiting or restricting circumvention of such
measures.
When you convey a covered work, you waive any legal power to forbid
circumvention of technological measures to the extent such circumvention
is effected by exercising rights under this License with respect to
the covered work, and you disclaim any intention to limit operation or
modification of the work as a means of enforcing, against the work's
users, your or third parties' legal rights to forbid circumvention of
technological measures.
4. Conveying Verbatim Copies.
You may convey verbatim copies of the Program's source code as you
receive it, in any medium, provided that you conspicuously and
appropriately publish on each copy an appropriate copyright notice;
keep intact all notices stating that this License and any
non-permissive terms added in accord with section 7 apply to the code;
keep intact all notices of the absence of any warranty; and give all
recipients a copy of this License along with the Program.
You may charge any price or no price for each copy that you convey,
and you may offer support or warranty protection for a fee.
5. Conveying Modified Source Versions.
You may convey a work based on the Program, or the modifications to
produce it from the Program, in the form of source code under the
terms of section 4, provided that you also meet all of these conditions:
a) The work must carry prominent notices stating that you modified
it, and giving a relevant date.
b) The work must carry prominent notices stating that it is
released under this License and any conditions added under section
7. This requirement modifies the requirement in section 4 to
"keep intact all notices".
c) You must license the entire work, as a whole, under this
License to anyone who comes into possession of a copy. This
License will therefore apply, along with any applicable section 7
additional terms, to the whole of the work, and all its parts,
regardless of how they are packaged. This License gives no
permission to license the work in any other way, but it does not
invalidate such permission if you have separately received it.
d) If the work has interactive user interfaces, each must display
Appropriate Legal Notices; however, if the Program has interactive
interfaces that do not display Appropriate Legal Notices, your
work need not make them do so.
A compilation of a covered work with other separate and independent
works, which are not by their nature extensions of the covered work,
and which are not combined with it such as to form a larger program,
in or on a volume of a storage or distribution medium, is called an
"aggregate" if the compilation and its resulting copyright are not
used to limit the access or legal rights of the compilation's users
beyond what the individual works permit. Inclusion of a covered work
in an aggregate does not cause this License to apply to the other
parts of the aggregate.
6. Conveying Non-Source Forms.
You may convey a covered work in object code form under the terms
of sections 4 and 5, provided that you also convey the
machine-readable Corresponding Source under the terms of this License,
in one of these ways:
a) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by the
Corresponding Source fixed on a durable physical medium
customarily used for software interchange.
b) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by a
written offer, valid for at least three years and valid for as
long as you offer spare parts or customer support for that product
model, to give anyone who possesses the object code either (1) a
copy of the Corresponding Source for all the software in the
product that is covered by this License, on a durable physical
medium customarily used for software interchange, for a price no
more than your reasonable cost of physically performing this
conveying of source, or (2) access to copy the
Corresponding Source from a network server at no charge.
c) Convey individual copies of the object code with a copy of the
written offer to provide the Corresponding Source. This
alternative is allowed only occasionally and noncommercially, and
only if you received the object code with such an offer, in accord
with subsection 6b.
d) Convey the object code by offering access from a designated
place (gratis or for a charge), and offer equivalent access to the
Corresponding Source in the same way through the same place at no
further charge. You need not require recipients to copy the
Corresponding Source along with the object code. If the place to
copy the object code is a network server, the Corresponding Source
may be on a different server (operated by you or a third party)
that supports equivalent copying facilities, provided you maintain
clear directions next to the object code saying where to find the
Corresponding Source. Regardless of what server hosts the
Corresponding Source, you remain obligated to ensure that it is
available for as long as needed to satisfy these requirements.
e) Convey the object code using peer-to-peer transmission, provided
you inform other peers where the object code and Corresponding
Source of the work are being offered to the general public at no
charge under subsection 6d.
A separable portion of the object code, whose source code is excluded
from the Corresponding Source as a System Library, need not be
included in conveying the object code work.
A "User Product" is either (1) a "consumer product", which means any
tangible personal property which is normally used for personal, family,
or household purposes, or (2) anything designed or sold for incorporation
into a dwelling. In determining whether a product is a consumer product,
doubtful cases shall be resolved in favor of coverage. For a particular
product received by a particular user, "normally used" refers to a
typical or common use of that class of product, regardless of the status
of the particular user or of the way in which the particular user
actually uses, or expects or is expected to use, the product. A product
is a consumer product regardless of whether the product has substantial
commercial, industrial or non-consumer uses, unless such uses represent
the only significant mode of use of the product.
"Installation Information" for a User Product means any methods,
procedures, authorization keys, or other information required to install
and execute modified versions of a covered work in that User Product from
a modified version of its Corresponding Source. The information must
suffice to ensure that the continued functioning of the modified object
code is in no case prevented or interfered with solely because
modification has been made.
If you convey an object code work under this section in, or with, or
specifically for use in, a User Product, and the conveying occurs as
part of a transaction in which the right of possession and use of the
User Product is transferred to the recipient in perpetuity or for a
fixed term (regardless of how the transaction is characterized), the
Corresponding Source conveyed under this section must be accompanied
by the Installation Information. But this requirement does not apply
if neither you nor any third party retains the ability to install
modified object code on the User Product (for example, the work has
been installed in ROM).
The requirement to provide Installation Information does not include a
requirement to continue to provide support service, warranty, or updates
for a work that has been modified or installed by the recipient, or for
the User Product in which it has been modified or installed. Access to a
network may be denied when the modification itself materially and
adversely affects the operation of the network or violates the rules and
protocols for communication across the network.
Corresponding Source conveyed, and Installation Information provided,
in accord with this section must be in a format that is publicly
documented (and with an implementation available to the public in
source code form), and must require no special password or key for
unpacking, reading or copying.
7. Additional Terms.
"Additional permissions" are terms that supplement the terms of this
License by making exceptions from one or more of its conditions.
Additional permissions that are applicable to the entire Program shall
be treated as though they were included in this License, to the extent
that they are valid under applicable law. If additional permissions
apply only to part of the Program, that part may be used separately
under those permissions, but the entire Program remains governed by
this License without regard to the additional permissions.
When you convey a copy of a covered work, you may at your option
remove any additional permissions from that copy, or from any part of
it. (Additional permissions may be written to require their own
removal in certain cases when you modify the work.) You may place
additional permissions on material, added by you to a covered work,
for which you have or can give appropriate copyright permission.
Notwithstanding any other provision of this License, for material you
add to a covered work, you may (if authorized by the copyright holders of
that material) supplement the terms of this License with terms:
a) Disclaiming warranty or limiting liability differently from the
terms of sections 15 and 16 of this License; or
b) Requiring preservation of specified reasonable legal notices or
author attributions in that material or in the Appropriate Legal
Notices displayed by works containing it; or
c) Prohibiting misrepresentation of the origin of that material, or
requiring that modified versions of such material be marked in
reasonable ways as different from the original version; or
d) Limiting the use for publicity purposes of names of licensors or
authors of the material; or
e) Declining to grant rights under trademark law for use of some
trade names, trademarks, or service marks; or
f) Requiring indemnification of licensors and authors of that
material by anyone who conveys the material (or modified versions of
it) with contractual assumptions of liability to the recipient, for
any liability that these contractual assumptions directly impose on
those licensors and authors.
All other non-permissive additional terms are considered "further
restrictions" within the meaning of section 10. If the Program as you
received it, or any part of it, contains a notice stating that it is
governed by this License along with a term that is a further
restriction, you may remove that term. If a license document contains
a further restriction but permits relicensing or conveying under this
License, you may add to a covered work material governed by the terms
of that license document, provided that the further restriction does
not survive such relicensing or conveying.
If you add terms to a covered work in accord with this section, you
must place, in the relevant source files, a statement of the
additional terms that apply to those files, or a notice indicating
where to find the applicable terms.
Additional terms, permissive or non-permissive, may be stated in the
form of a separately written license, or stated as exceptions;
the above requirements apply either way.
8. Termination.
You may not propagate or modify a covered work except as expressly
provided under this License. Any attempt otherwise to propagate or
modify it is void, and will automatically terminate your rights under
this License (including any patent licenses granted under the third
paragraph of section 11).
However, if you cease all violation of this License, then your
license from a particular copyright holder is reinstated (a)
provisionally, unless and until the copyright holder explicitly and
finally terminates your license, and (b) permanently, if the copyright
holder fails to notify you of the violation by some reasonable means
prior to 60 days after the cessation.
Moreover, your license from a particular copyright holder is
reinstated permanently if the copyright holder notifies you of the
violation by some reasonable means, this is the first time you have
received notice of violation of this License (for any work) from that
copyright holder, and you cure the violation prior to 30 days after
your receipt of the notice.
Termination of your rights under this section does not terminate the
licenses of parties who have received copies or rights from you under
this License. If your rights have been terminated and not permanently
reinstated, you do not qualify to receive new licenses for the same
material under section 10.
9. Acceptance Not Required for Having Copies.
You are not required to accept this License in order to receive or
run a copy of the Program. Ancillary propagation of a covered work
occurring solely as a consequence of using peer-to-peer transmission
to receive a copy likewise does not require acceptance. However,
nothing other than this License grants you permission to propagate or
modify any covered work. These actions infringe copyright if you do
not accept this License. Therefore, by modifying or propagating a
covered work, you indicate your acceptance of this License to do so.
10. Automatic Licensing of Downstream Recipients.
Each time you convey a covered work, the recipient automatically
receives a license from the original licensors, to run, modify and
propagate that work, subject to this License. You are not responsible
for enforcing compliance by third parties with this License.
An "entity transaction" is a transaction transferring control of an
organization, or substantially all assets of one, or subdividing an
organization, or merging organizations. If propagation of a covered
work results from an entity transaction, each party to that
transaction who receives a copy of the work also receives whatever
licenses to the work the party's predecessor in interest had or could
give under the previous paragraph, plus a right to possession of the
Corresponding Source of the work from the predecessor in interest, if
the predecessor has it or can get it with reasonable efforts.
You may not impose any further restrictions on the exercise of the
rights granted or affirmed under this License. For example, you may
not impose a license fee, royalty, or other charge for exercise of
rights granted under this License, and you may not initiate litigation
(including a cross-claim or counterclaim in a lawsuit) alleging that
any patent claim is infringed by making, using, selling, offering for
sale, or importing the Program or any portion of it.
11. Patents.
A "contributor" is a copyright holder who authorizes use under this
License of the Program or a work on which the Program is based. The
work thus licensed is called the contributor's "contributor version".
A contributor's "essential patent claims" are all patent claims
owned or controlled by the contributor, whether already acquired or
hereafter acquired, that would be infringed by some manner, permitted
by this License, of making, using, or selling its contributor version,
but do not include claims that would be infringed only as a
consequence of further modification of the contributor version. For
purposes of this definition, "control" includes the right to grant
patent sublicenses in a manner consistent with the requirements of
this License.
Each contributor grants you a non-exclusive, worldwide, royalty-free
patent license under the contributor's essential patent claims, to
make, use, sell, offer for sale, import and otherwise run, modify and
propagate the contents of its contributor version.
In the following three paragraphs, a "patent license" is any express
agreement or commitment, however denominated, not to enforce a patent
(such as an express permission to practice a patent or covenant not to
sue for patent infringement). To "grant" such a patent license to a
party means to make such an agreement or commitment not to enforce a
patent against the party.
If you convey a covered work, knowingly relying on a patent license,
and the Corresponding Source of the work is not available for anyone
to copy, free of charge and under the terms of this License, through a
publicly available network server or other readily accessible means,
then you must either (1) cause the Corresponding Source to be so
available, or (2) arrange to deprive yourself of the benefit of the
patent license for this particular work, or (3) arrange, in a manner
consistent with the requirements of this License, to extend the patent
license to downstream recipients. "Knowingly relying" means you have
actual knowledge that, but for the patent license, your conveying the
covered work in a country, or your recipient's use of the covered work
in a country, would infringe one or more identifiable patents in that
country that you have reason to believe are valid.
If, pursuant to or in connection with a single transaction or
arrangement, you convey, or propagate by procuring conveyance of, a
covered work, and grant a patent license to some of the parties
receiving the covered work authorizing them to use, propagate, modify
or convey a specific copy of the covered work, then the patent license
you grant is automatically extended to all recipients of the covered
work and works based on it.
A patent license is "discriminatory" if it does not include within
the scope of its coverage, prohibits the exercise of, or is
conditioned on the non-exercise of one or more of the rights that are
specifically granted under this License. You may not convey a covered
work if you are a party to an arrangement with a third party that is
in the business of distributing software, under which you make payment
to the third party based on the extent of your activity of conveying
the work, and under which the third party grants, to any of the
parties who would receive the covered work from you, a discriminatory
patent license (a) in connection with copies of the covered work
conveyed by you (or copies made from those copies), or (b) primarily
for and in connection with specific products or compilations that
contain the covered work, unless you entered into that arrangement,
or that patent license was granted, prior to 28 March 2007.
Nothing in this License shall be construed as excluding or limiting
any implied license or other defenses to infringement that may
otherwise be available to you under applicable patent law.
12. No Surrender of Others' Freedom.
If conditions are imposed on you (whether by court order, agreement or
otherwise) that contradict the conditions of this License, they do not
excuse you from the conditions of this License. If you cannot convey a
covered work so as to satisfy simultaneously your obligations under this
License and any other pertinent obligations, then as a consequence you may
not convey it at all. For example, if you agree to terms that obligate you
to collect a royalty for further conveying from those to whom you convey
the Program, the only way you could satisfy both those terms and this
License would be to refrain entirely from conveying the Program.
13. Use with the GNU Affero General Public License.
Notwithstanding any other provision of this License, you have
permission to link or combine any covered work with a work licensed
under version 3 of the GNU Affero General Public License into a single
combined work, and to convey the resulting work. The terms of this
License will continue to apply to the part which is the covered work,
but the special requirements of the GNU Affero General Public License,
section 13, concerning interaction through a network will apply to the
combination as such.
14. Revised Versions of this License.
The Free Software Foundation may publish revised and/or new versions of
the GNU General Public License from time to time. Such new versions will
be similar in spirit to the present version, but may differ in detail to
address new problems or concerns.
Each version is given a distinguishing version number. If the
Program specifies that a certain numbered version of the GNU General
Public License "or any later version" applies to it, you have the
option of following the terms and conditions either of that numbered
version or of any later version published by the Free Software
Foundation. If the Program does not specify a version number of the
GNU General Public License, you may choose any version ever published
by the Free Software Foundation.
If the Program specifies that a proxy can decide which future
versions of the GNU General Public License can be used, that proxy's
public statement of acceptance of a version permanently authorizes you
to choose that version for the Program.
Later license versions may give you additional or different
permissions. However, no additional obligations are imposed on any
author or copyright holder as a result of your choosing to follow a
later version.
15. Disclaimer of Warranty.
THERE IS NO WARRANTY FOR THE PROGRAM, TO THE EXTENT PERMITTED BY
APPLICABLE LAW. EXCEPT WHEN OTHERWISE STATED IN WRITING THE COPYRIGHT
HOLDERS AND/OR OTHER PARTIES PROVIDE THE PROGRAM "AS IS" WITHOUT WARRANTY
OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO,
THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR
PURPOSE. THE ENTIRE RISK AS TO THE QUALITY AND PERFORMANCE OF THE PROGRAM
IS WITH YOU. SHOULD THE PROGRAM PROVE DEFECTIVE, YOU ASSUME THE COST OF
ALL NECESSARY SERVICING, REPAIR OR CORRECTION.
16. Limitation of Liability.
IN NO EVENT UNLESS REQUIRED BY APPLICABLE LAW OR AGREED TO IN WRITING
WILL ANY COPYRIGHT HOLDER, OR ANY OTHER PARTY WHO MODIFIES AND/OR CONVEYS
THE PROGRAM AS PERMITTED ABOVE, BE LIABLE TO YOU FOR DAMAGES, INCLUDING ANY
GENERAL, SPECIAL, INCIDENTAL OR CONSEQUENTIAL DAMAGES ARISING OUT OF THE
USE OR INABILITY TO USE THE PROGRAM (INCLUDING BUT NOT LIMITED TO LOSS OF
DATA OR DATA BEING RENDERED INACCURATE OR LOSSES SUSTAINED BY YOU OR THIRD
PARTIES OR A FAILURE OF THE PROGRAM TO OPERATE WITH ANY OTHER PROGRAMS),
EVEN IF SUCH HOLDER OR OTHER PARTY HAS BEEN ADVISED OF THE POSSIBILITY OF
SUCH DAMAGES.
17. Interpretation of Sections 15 and 16.
If the disclaimer of warranty and limitation of liability provided
above cannot be given local legal effect according to their terms,
reviewing courts shall apply local law that most closely approximates
an absolute waiver of all civil liability in connection with the
Program, unless a warranty or assumption of liability accompanies a
copy of the Program in return for a fee.
END OF TERMS AND CONDITIONS